Annual Review - Summary Sheet

PROGRAMME TITLE: Good Governance Fund
Country/Region:	Bosnia and Herzegovina (BiH), Georgia, Moldova, Serbia and Ukraine
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Spend:	ODA: £23.62m (original: £30m)		Non-ODA: N/A
Start Date: April 2016		End Date: March 2021
Outputs					Score
Strand 1: IFI, Multi-lateral and other donor projects					A
Strand 2: Managed Fund					A

Overall output score : A [outputs met expectations]
Outcome Assessment:
Outcome Score: B [insufficient evidence to demonstrate likely contribution to outcomes]				Risk: Medium

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*
Programme Score	n/a	A	A	B
Risk Rating	n/a	Medium	Medium

*output/outcome scores

What support is the UK providing?
The Joint DFID/FCO Good Governance Fund (GGF) is a responsive, flexible, demand-led fund, providing technical assistance in support of governance and economic reform in Bosnia and Herzegovina (BiH), Georgia, Moldova, Serbia and Ukraine.[1] Established in 2015, the GGF has funding approved, through the Conflict, Stability and Security Fund (CSSF), until March 2021, and supports National Security Council (NSC)/UK Government (HMG) objectives for the region. GGF promotes reforms to improve the resilience and prosperity of GGF countries, through technical assistance supporting: liberalisation and modernisation of key growth sectors; reform of tax systems and improvements to the business environment; strengthening rule of law and democratic accountability; public finance management reform and anti-corruption; strengthening independent media and strategic communications.
[1] From April 2018 GGF is operating in Armenia and Macedonia. These new Posts are not within the scope of the current Annual Review.
Funding is provided through three channels: supporting activities by international financial institutions (IFIs), multilateral organisations and other donors; a demand-led Managed Fund, largely responding to needs identified by government counterparts; and a Strategic Support Fund (SSF), usually supporting small initiatives by local non-governmental organisations.
Summary of progress and lessons learnt/actions taken since last review
In only two years, GGF has achieved a considerable amount. It was launched at short notice, on an ambitious scale across five diverse and challenging country contexts. In these demanding circumstances some 200 projects addressing a wide range of issues have been successfully mobilised. The available data indicates that many are providing political and economic benefits, and gaining credit for the UK.
The past year has seen a helpful consolidation of GGF activities, refining the portfolio, entrenching working procedures and developing more robust quality assurance and risk management processes. All GGF countries have refreshed their theories of change, which has served to refine/reorient GGF priorities, demonstrate alignment with NSC/HMG objectives and develop thinking about the process of change in each country. Working partnerships with counterpart governments are positive in all countries, and excellent in the majority. Similarly, working relationships with implementing partners (international organisations, Price Waterhouse Cooper, which manages the Managed Fund, NGOs) are generally good, despite some local issues usually around tailoring programmes to local realities. Significant improvements have been made in risk management; these now need to be embedded throughout the life of projects.
The GGF has worked to strengthen its outcomes, outputs and performance indicators, some of which were weak during the Fund’s early period. Whilst some problems remain, greater scrutiny is now applied and these issues are being resolved progressively. Additionally, some poor performing IFI and MF projects have now ended or have been closed.
GGF staffs collectively acknowledge that some focus is now needed on improving value for money mechanisms, and on the identification of gender implications in projects. The reviewers also believe greater attention should be paid to conflict sensitivity. Monitoring and evaluation also require strengthening; an external contractor has now been appointed to address this.
The overall output score for GGF is A, indicating that outputs in the review period have met expectations. At this stage, as might be expected, evidence at outcome level is limited; consequently the overall outcome score is B, indicating insufficient evidence to demonstrate likely contribution to outcomes. An immediate priority must be to focus on the contribution of project outputs to broader reform priorities, and developing outcome indicators that adequately capture and measure this.
Summary of recommendations for the next year
- The review highlights some diversity in the performance of projects sitting under strand 1 and recommends a process of internal review for those where challenges were highlighted.
- Disruption caused by re-tendering the operation of the Managed Fund will require mitigation.
- The new monitoring, evaluation and learning contractor must develop arrangements to better capture results (especially outcome level) from IFI trust fund, Managed Fund stage II and Strategic Support Fund (SSF) projects.
- The new value for money strategy should clarify respective responsibilities of posts and the joint unit, and provide staff with practical guidance covering the full range of value for money issues.
- Posts and implementing partners should be given guidance and training to address gender issues more systematically and in depth, and given a simple conflict sensitivity screening tool.
- GGF (steering the work of the Monitoring, Evaluation and Learning provider) should give specific consideration to: defining higher-level country specific outcome indicators; implementing a more flexible approach to defining and tracking project specific outcomes; a proportionate approach to project monitoring; monitoring of contextual/environmental factors; a consistent approach to monitoring cross cutting issues (including access and influence).
- Key learning in relation to theory of change assumptions should be an integral part of discussions throughout the programme life-cycle.