# CSSF Annual Review Synthesis Paper: Lessons from the Fund’s third year
JOINT FUNDS UNIT MANAGEMENT RESPONSE

Introduction

This document is a management response for the 2017 to 2018 Conflict Stability and Security Fund (CSSF) Annual Review Synthesis Report. It summarises findings and recommendations from the report, highlighting areas of progress made over the last year and work already underway to improve programme delivery.

CSSF, Annual Reviews and Synthesis of Annual Review Evidence

The CSSF was established in April 2015. In 2017/18 the fund provided £1.2 billion of development and security support to countries at risk of conflict or instability. Its programmes deliver against National Security and UK Aid objectives, covering 10 regions and over 70 countries. More information is available in our Annual Report.

Since the outset of the CSSF, programmes have been subject to Annual Reviews (ARs), which assess a number of technical and programme management standards including financial and risk management, value for money, conflict and gender sensitivity, as well as contextual factors such as changes to the political environment. CSSF Directors and boards take the findings of ARs seriously. For example, programme teams are required to draw up plans to address AR recommendations, and actions taken are assessed at subsequent ARs. ARs are also used as crucial evidence during the annual allocations process.

Each year the Stabilisation Unit (SU) produces a report that reviews progress in the CSSF and draws together findings from the most recent ARs. This year’s report focuses on those areas highlighted by the recent Independent Commission for Aid Impact (ICAI) review of the CSSF. The Joint Funds Unit (JFU), which administers the CSSF, welcomes the report, its recognition of areas of best practice across the CSSF and its constructive recommendations on areas for improvements. The JFU hopes this paper contributes to improved learning and sharing of lessons with stakeholders and implementing partners.
Progress and Highlights

Highlights from this year’s ARs demonstrate significant progress since the 16/17 synthesis. They include:

Progress to outcomes were assessed for the first time in 2017/18 ARs. This was in line with ICAI’s recommendation to focus on assessing the higher-level changes that result from programme outputs.

A conflict sensitivity marker was developed and piloted. The marker sets standards for CSSF programmes to ensure that they are suitably informed by contextual analysis and can identify, monitor and adapt to specific conflict risks.

The use of conflict analysis to inform programme decisions increased with Joint Assessments of Conflict and Stability (JACS) carried out in 2017/18 in Central Asia, Egypt, Iraq, Nigeria, South Sudan, Sudan, Sri Lanka, Tunisia, Western Balkans, Zimbabwe and for the Middle East Peace Process Programme.

Findings from the gender audit of all Western Balkans and EECAD programmes demonstrated the positive impact of CSSF standards and practices for gender sensitivity, as well as the Joint Funds Unit (JFU) commitment to gender equality in programming for both official development assistance (ODA) and non-ODA programme spend.

Some good examples of increased coherence across HMG. The Hurricane Irma Recovery AR, for example, found that “the joint, cross-HMG structure and access that the CSSF had proved essential to allow the programme management and procurement of complex assets/services to be delivered from multiple departments to multiple locations” simultaneously.

The ARs also showed good examples of working with other donors to increase effect. For example, the efficiency of pre-deployment training and therefore the quality of AMISOM troops deployed to Somalia has increased through UK collaboration with the US.

The Training Analysis System for Evaluation and Reporting (TASER) tool was developed by the British Peace Support Team in Eastern Africa. It is based on the Kirkpatrick Model for analysing training, and complements the Political Access and Influence (PAI) tool previously developed by the East Africa Monitoring, Evaluation and Learning provider. It provides a measure of training quality, and helps to demonstrate how training has contributed to changed behaviour and operational effect.

AR Synthesis – performance analysis

Whilst the 2017/18 ARs demonstrate innovative approaches are being applied across CSSF programmes to address key issues such as risk management, conflict sensitivity, and harnessing political access and influence. The ARs also show that there is still a need to continue learning lessons, driving improvements, and setting clear standards where necessary, ensuring that adequate and consistent support is provided as required.

Overall ARs showed that the majority (over two thirds) of CSSF programmes met or were on course to meet expectations at output level. The rest of programmes moderately or partially did not meet expectations with one programme substantially not meeting expectations. At outcome level, over two fifths of programmes globally met or were on course to meet expectations. The rest of the programmes moderately or partially did not meet expectations with one programme substantially not meeting expectations.

Over a third of programmes scored lower at outcome level than output level. This is not surprising however, given the higher-level strategic change they are seeking to achieve, which requires long-term efforts to materialise.
### Programmes fall into four broad groups when output scores on multi-year programmes are analysed:
Consistently at expectation: Over a third of multi-year programmes have met expectations at output level every year in their lifetime.

Consistently below expectation: Just under a sixth of multi-year programmes have partially or moderately not met expectations two or three years in a row.

Improving: Well over a third of multi-year programmes have seen an improvement in their scores over their two or three-year lifetime and are now performing at expectation at output level.

Dropping: Six programmes have seen their scores drop from meeting expectations (A) and are now scoring below expectation (B) at output level.

The main reason given in ARs for outcome scores being below output scores was due to theories of change (TOCs) and results frameworks (RFs) needing improvement. Over three quarters of the ARs sampled highlight the need for improved TOCs and/or RFs.

AR Synthesis Recommendations and JFU Management Response

Findings from this year’s synthesis have been analysed across the portfolio and shared widely with programme teams, including as part of the Annual CSSF Global Lessons Learnt forum. Recommendations, including the JFU management response are summarised below:

Improve quality assurance of ToCs and RFs ensuring that the most high value and high-risk programmes are reviewed by technical advisers before they are signed off.

Partially Accept: The JFU already mandates that programmes must have a robust ToC and RF. The annual allocations process continues to be linked to this requirement. The newly recruited JFU Monitoring and Evaluation (M&E) adviser will ensure regional advisers are providing quality assurance for ToC and RFs and work to secure the availability of advisers where none are in place.

The JFU is developing a Global Monitoring Evaluation and Learning strategy, which, subject to approval, will be launched in spring 2019. The strategy, accompanied by significant additional resources (including through six newly recruited regional M&E advisers and a possible global contract), aims to:

Build better systems, tools and processes for results management, including ToC and RFs;

Strengthen capacity and capability of programme teams across the CSSF network to better use ToC and RFs, and;

Improve learning and knowledge management, including sharing best practice,

Enhance Capacity and Capability by commissioning a capability review of the CSSF to identify the type and number of staff required to deliver on objectives and effectively manage risk. JFU and the SU should also review their training offer to network staff.

Partially Accept: The JFU regularly reviews its global resources and requirements for technical advisory and programme management resource. The synthesis recognises that newly recruited gender and M&E advisers will help. The JFU and SU frequently assesses its training offer, and seeks and acts on feedback from course attendants to ensure staff have access to high quality programme management and thematic training. The JFU has commissioned a review to examine the breakdown of staff across the portfolio and assess capability gaps and needs, the results of which will inform the development of future training and learning plans.

Take a tougher approach on poor performance, non-compliance and coherence. The CSSF has played a catalytic role in enhancing coherence and integration across HMG on conflict, stability and security issues. However, the synthesis finds further steps could be taken which would improve this. JFU should establish a policy on how to deal with programmes consistently performing below expectation.

Do Not Accept: The annual allocations process already takes account of poor performance, resulting in the closure of programmes that did not meet CSSF standards of management. While the JFU accepts that Boards can and should take more ownership and accountability in this area, we must interrogate and learn from programmes that perform below expectation, rather than setting an arbitrary policy based on AR scores.

Strengthen monitoring, evaluation and learning. The synthesis finds that it would be helpful for programmes to develop robust approaches to assessing political access and influence and better measure the outcomes of defence engagement. It also finds there is a need to establish a central repository of lessons and evidence, and a helpdesk for programme inquiries. There would be value in moving away from a one-size-fits-all AR process to one, which is both more proportionate to the size of programmes and tailored to their specific contexts, track records and risk levels. This would enable a lighter touch review of consistently high performing programmes and a deeper assessment of programmes, which are high risk, high priority or poor performing.

Partially Accept: The JFU agrees that demonstrating PAI results more explicitly is important, but does not agree that a standardised approach to monitoring PAI will work across all parts of the portfolio. Successful pilots of new methods to measure defence engagement activities have been carried out in East Africa and Pakistan. However, the JFU does not believe that mandating the use of the PAI tool for all Defence Engagement activity while other monitoring methods are in development would be helpful.

Between DFID and the SU, a number of ‘helpdesk’ functions already exist that CSSF staff can tap into. The global Monitoring Evaluation and Learning contract will look at options for developing learning platforms and networks to promote cross-fund learning and evidence sharing.

The existing AR process provides the rigour and assurance needed for the JFU to monitor programme performance. CSSF programme management teams and reviewers are already advised to ensure ARs are proportionate to budget, risk and level of complexity of programmes. They are encouraged to look into how the process can be more efficient, including sequencing where there are multiple programmes/reviews and securing support from implementing partners.

Enhance risk management, issue risk guidance on Overseas Security and Justice Analysis (OSJAs) and commission or conduct conflict and gender sensitivity reviews/audits of their portfolio.

Partially accept: The JFU is developing risk guidance, to include pathways for risk management across programmes. The JFU will also share best practice examples of risk management across the network. The OSJA process is defined and managed by the FCO and has application far beyond the CSSF. We will continue to work with the FCO’s Human Rights and Democracy Department and the SU to ensure that their guidance meets the needs of CSSF programme managers and SROs.

An example of improving risk management has been the development of the Conflict Sensitivity Marker, which has been used to audit 20 CSSF programmes over the last year. A report has been produced summarising the audit's findings, and 14 recommendations have been put forward to strengthen conflict sensitive practice across the CSSF. Together with the SU, the JFU is driving forward implementation of recommendations with programme teams. The second wave of the conflict sensitive audit is currently underway. The JFU will also work with the SU to monitor outcomes from audits and JACS reviews, which are used across CSSF programmes.

Conflict and gender sensitivity audits are important tools for CSSF programme management, but they are not always a proportionate or appropriate tool to use in every programme across every context, not least because some programmes have already conducted detailed JACSs, or have technical advisory capacity already in place to address conflict and gender sensitivity.