Prosperity Fund Business Case

ASEAN Low Carbon Energy Programme:
Accelerating sustainable growth in ASEAN through improving green finance flows for low carbon energy, and increasing energy efficiency.

## Table of Contents

 Approved by FCO Ministers December 2018
# Glossary
ACEF	–	Asia Clean Energy Forum
ACE	–	ASEAN Centre for Energy
ADB	–	Asian Development Bank
AEC	–	ASEAN Economic Community
APD	–	Asia Pacific Directorate
ASEAN	–	The Association of South East Asian Nations established in 1967 with ten member countries namely Burma, Brunei Darussalam, Cambodia, Indonesia, Laos, Malaysia, the Philippines, Singapore, Thailand, and Vietnam.
ASEAN-5	–	Indonesia, Malaysia, the Philippines, Thailand, Vietnam
BEIS	–	Department for Business, Energy & Industrial Strategy
BHC	–	British High Commission
BRDO	–	Better Regulation Delivery Office
CCE	–	Climate Change and Energy
CCEN	–	Climate Change and Energy Network
COP	–	Conference of the Parties
DFID	–	Department for International Development
DIT	–	Department for International Trade
EDD	–	Economic Diplomacy Directorate
EE	–	Energy Efficiency
ESCO	–	Energy Services Company
ETL	–	Energy Technology List
EU	–	European Union
–	Foreign and Commonwealth Office
FDI	–	Foreign Direct Investment
FinTech	–	Financial Services Technology
FTA	–	Free Trade Agreement
FTE	–	Full Time Equivalent
GDP	–	Gross Domestic Product
GF	–	Green Finance
GFCI	–	Global Financial Centres Index
GFI	–	Green Finance Initiative
GHG	–	Greenhouse gas
GII	–	Global Innovation Index
GINI	–	income inequality index measuring the extent to which the distribution of income within an economy deviates from a perfectly equal distribution
GIZ	–	Gesellschaft für Internationale Zusammenarbeit; German Development Agency
GW	–	GigaWatt
G7	–	The Group of Seven is an informal bloc of industrialised democracies that promotes collective decision-making in issues as global economic governance, international security and energy policy. Countries in the G7 are Canada, France, Germany, Italy, Japan and the UK
G-20	–	The Group of Twenty is the central forum for international cooperation on financial and economic issues and is comprise of 19 countries plus the EU
HEPS	–	High Energy Performance Standards
HMG	–	Her Majesty’s Government
HMT	–	Her Majesty’s Treasury
ICF	–	International Climate Fund
ICMA	–	International Capital Markets Association
IEA	–	International Energy Agency
IMF	–	International Monetary Fund
INDCs	–	Intended Nationally Determined Contributions
IPR	–	Intellectual Property Rights
JFU	-	Joint Funds Unit
JICA	–	Japan International Cooperation Agency
KPIs	–	Key Performance Indicators
KWh	–	KiloWatt-hour
LC	–	Low Carbon
LNG	–	Liquefied natural gas
LSE	–	London Stock Exchange
MEPS	–	Minimum Energy Performance Standards
MtCo2e	–	Metric tons of carbon dioxide equivalent
Mtoe	–	Million tons of oil equivalent
MREL	–	Monitoring, Reporting, Evaluation and Learning
NAMA	–	Nationally Appropriate Mitigation Actions
NDCs	–	Nationally Determined Contributions
NGOs	–	Non-governmental organisation
NPV	–	Net Present Value
NSC	–	National Security Council
ODA	–	Official Development Assistance
ODA-8	–	Prosperity Fund-6 countries plus Cambodia and Laos
ODI	–	Overseas Development Institute
OECD	–	The Organisation for Economic Cooperation and Development
OGD	–	Other Government Department
OJEU	–	Official Journal of the European Union
ONS	–	Office of National Statistics
PB	–	Portfolio Board
PBR	–	Payment by Results
PF-6	–	‘Prosperity Fund 6’ are the following countries: Burma, Indonesia, Malaysia, the Philippines, Thailand, Vietnam
PFDU	–	Prosperity Fund Delivery Unit (FCO)
PPP	–	Public Private Partnership
RE	–	Renewable Energy
SDG	–	Sustainable Development Goals
SE Asia	–	South East Asia, comprising the ten nations of ASEAN listed above
Solar PV	–	Solar Photovoltaic
SoR	–	Statement of Requirements
SRO	–	Senior Responsible Officer
tCO2e	–	Tonnes of carbon dioxide equivalent
TPES	–	Total Primary Energy Supply
UKCCU	–	UK Climate Change Unit
UN	–	United Nations
UNEP	–	United Nations Environment Programme
UNESCAP	–	United Nations Economic and Social Commission for Asia and the Pacific
UNFCCC	–	United Nations Framework Convention on Climate Change
VFM	–	Value for money
WEO	–	World Economic Outlook
# Executive Summary
This document sets out the business case to deliver a four year £15m Prosperity Fund Programme in ASEAN focusing on low carbon energy. It will promote inclusive economic growth and increase global prosperity, including for the UK, through reduction of energy emissions and energy poverty and increased ease of doing business in ASEAN. This programme is expected to deliver £241m of primary benefits and £76m of secondary benefits over 10 years. Transforming energy towards more affordable, reliable and cleaner energy sources is essential to reduce poverty and to address national development strategies for health, education, rural development and gender equality.[1]
[1] ESCAP
## Rationale for Intervention
#### I. Geopolitical
1. South East Asia has a population of more than 600 million people - equivalent to the world’s 7th largest economy. It is the 4th largest exporting region in the world, a major manufacturing hub and key to global trade flows. SE Asia has experienced a decade of high economic growth that has lifted 100 million people out of poverty.[2] However, there are still 87 million people below national poverty lines in SE Asia and 38 million people who fall below the World Bank’s $1.90 poverty measure[3], of which 2/3 are women[4]. While still comparatively strong, economic growth in SE Asia has moderated in recent years[5] and economic inequality is growing. If poverty reduction gains are going to be cemented and extended, economic reforms need to be undertaken and inequality reduced. SE Asia’s continued economic growth will depend, in part, on whether it can meet the huge energy security and low carbon challenges it faces, including access to clean, affordable and reliable energy.
  [2] 2011 ASEAN Statistical Report on the Millennium Development Goals
  [3] Statistic excludes Burma for which there is no data
  [4] UN Women 2013
  [5] Average 4.6% in the region in 2015 compared to 9.4% average 2005-2007. ESCAP 96
2. SE Asia is increasingly important to the UK in both international diplomacy and trade. ASEAN is the 3rd largest non-EU export market for the UK – worth £14.2 billion in 2016 - comparing favourable to our exports to other major players (China £16.7 billion, India £6.6 billion and Brazil £3.8 billion.[6]) The Programme will mainly operate in 5 SE Asian countries: Burma, Malaysia, the Philippines, Thailand and Vietnam. Indonesia has its own proposed Indonesia Renewable Energy Programme and Indonesia Regulatory Reform Programme. However, given the City of London’s identification of Indonesia as a priority market for green finance, we have proposed including it in those interventions. These 6 countries (known for ease of reference throughout this business case as the PF6), cover 95% of SE Asia’s total population and those in poverty (both metrics) and 86% of SE Asia’s GDP.
  [6] United Kingdom Balance of Payments - The Pink Book time series dataset (July 2016)
#### II. Energy
1. The International Energy Agency (IEA) forecasts an 80% increase in ASEAN energy demand by 2040[7]. This increased demand poses major challenges to energy policy objectives in the region, including energy security, sustainable development, energy access and affordability.[8] IEA also highlights that constraints to SE Asia include insufficient energy efficiency[9] measures, poor regional energy connectivity and integration, and lack of access to electricity.
  [7] TPES (Total Primary Energy Supply) will rise from 594 Mtoe (mil tons of oil equiv) in 2013 to 1070 Mtoe in 2040
  [8] OECD South East Asia Economic Outlook 2017 p 33
  [9] There is no formal definition of energy efficiency. For the purposes of this programme we will use the Collins Dictionary definition: “a measure of how efficiently an appliance, building, organisation or country uses energy”
2. The importance of affordable, reliable and cleaner energy is recognised and enshrined in the 2030 Agenda for Sustainable Development, under SDG 7, with targets on universal access, increased renewable energy, improved energy efficiency, and enhanced international cooperation. SDG 7 is an essential catalyst to address equality, climate change, education, public health, clean water and sanitation.[10] The proposed programme will support ambitions on emissions reductions set out in the Paris Agreement on Climate Change. Prosperity Funding helped many countries in SEA develop their emissions reductions pledges (INDCs) for the Paris COP in 2015, creating strong government and private sector relationships. Host government support is strong for the proposed programming areas.
  [10] 2016 Regional Trends Report Energy Sustainable Development in Asia and the Pacific UNESCAP, intro
3. The proposed Low Carbon Energy programme supports 2 objectives of the NSC Strategy: increasing British global influence through soft power, and promoting UK prosperity via trade, including through climate change investment. Low carbon energy has been identified as a priority area for Prosperity Fund programming, and aligns well with intermediate outcomes in the Prosperity Fund’s Theory of Change:
- Investment in infrastructure and human capital
- Innovation and knowledge transfer of low carbon technologies
- Trade, financial and economic reform
- Policy and regulatory capacity
- Ease of doing business
## What will we deliver?

1. The business case proposes that we focus on: Green Finance[11] and Energy Efficiency (roughly 50/50 split), these being the 2 most readily identified as important by stakeholders in the region, and areas of significant UK expertise.
  [11] There is no agreed definition of “green finance”. For the purposes of this programme, we are guided by the World Bank definition: “the financing of investments that provide environmental benefits in the broader context of sustainable development”. Our focus will be on private finance rather than that from the international donor community.
2. The programme will provide policy support, capacity building and technical assistance to facilitate green finance flows and improve the regulatory, policy and practical conditions for energy efficiency measures. It will support 4 broad types of activity: capacity building of government, institutions and business; policy reform of energy frameworks and standards; market development by strengthening connections between project developers and investors; raising awareness of available technologies to increase the uptake of energy efficient products and services; and partnership coordination and commercial ventures within SE Asia. All components of the programme aim at improving energy security and inclusive access to clean and reliable energy sources, with direct benefits for most vulnerable population, including women, in accordance with the International Development (Gender Equality) Act 2014.
## What are the expected results?
The programme targets 5 specific outcomes:
Strengthened policy and regulatory framework for green finance and energy efficiency;
- Greater investment in low carbon technologies, including improved green finance flows;
- Energy efficiency savings;
- Ease of doing business improved; and
- Innovation and knowledge transfer of low carbon economies.
1. The main quantified primary benefit over 10 years will be the return on investing in climate change mitigation. The Carbon Trust scoping study estimated the potential investment that could be leveraged with greater uptake of renewable energy and energy efficiency measures. Investment will be leveraged directly via the development of a pipeline of bankable energy efficiency and green finance programmes. Energy efficiency investment will also be encouraged through embedding energy efficiency incentives in the regulatory framework, and capacity building activities with industry. Similarly green finance investment will be encouraged by increasing the capacity of commercial banks, the regulatory and policy framework, and developing Climate Investment Plans. There will also be an additional primary benefit as a result of a significant reduction in greenhouse gas emissions - a cumulative carbon saving of 13.9MtCO2e across the region, which has a present value £456m.[12]
  [12] This is the present value of the primary benefits, see economic appraisal.
2. The secondary benefit of the programme is increased trade, and in particular green exports from international and UK businesses to the region. The quantified UK return on increased outward green investment opportunities, and sales of energy efficient goods and services is estimated at £76 million. The actual impact could potentially be significantly higher – this programme is designed to produce permanent change with significant ongoing benefits for both development and trade. There are also significant unquantified primary benefits with strong impact on helping alleviate gender and poverty inequality, such as inclusive economic growth, job creation (including for women) and improved environmental sustainability.
3. The Green Finance programme component is expected to result in increased flows of green finance; greater public and private sector capability; and regulatory frameworks that create an enabling environment to incentivise investment in green infrastructure and encourage international trade, including from the UK. It will help to facilitate billions of investment in low carbon infrastructure. Unquantified primary benefits include: Improved environmental sustainability; avoided reliance on imported energy; improved air quality and health; jobs created as a result of increased investment in green energy; economic growth generated as a result of increased investment in green energy (indirect impact); and increased levels of institutional knowledge of green finance issues.[13]
  [13] UN Women Watch Fact Sheet 2009
4. The Energy Efficiency programme component will help establish a regulatory framework that incentivises energy efficiency, reduces emissions and encourages greater regional investment in higher performance goods, leading to an increased market for high quality goods and services, such as from the UK. Unquantified primary benefits include: cost savings to consumers due to lower energy bills; cost savings to host governments due to avoided investment in power supplies; avoided reliance on imported energy; improved air quality and health; jobs created as a result of increased investment in energy efficiency; economic growth generated as a result of increased investment in energy efficiency (indirect impact); and increased level of institutional knowledge of energy efficiency issues.
## Impact on poverty and gender equality
The programme will have an impact on poverty in the following ways:
1. Reducing carbon emissions through increased green investment and energy efficiency will help mitigate the effects of climate change. Evidence shows that the poor stand to be the most affected by climate change and will disproportionately suffer as a result, and that women are more likely than men to suffer the consequences of climate change and natural disasters. UN figures indicate that 80% of people displaced by climate change are women.[14]
  [14] Climate change 'impacts women more than men 'http://www.bbc.co.uk/news/science-environment-43294221
2. Increasing the amount of available power through green investment and savings from energy efficiency measures will increase the supply of power available, improving energy access with concomitant benefits of improved health and education
3. Supporting the transition to low carbon energy is likely to provide a cost saving to governments, businesses and households, as renewables such as solar increasingly become cheaper than fossil fuels. Money saved can be channelled to other areas such as health, education and business investment.
4. Supporting green investment will help provide a diverse and decentralised range of low carbon energy projects and industries, providing local employment
5. Increasing the transition to low carbon energy through support for green investment will speed the decline of coal, bringing significant health benefits and a reduction in air pollution-related deaths.
6. Increasing the low carbon energy options for household cooking will reduce the detrimental health and social impacts of biomass or kerosene cooking stoves.
In Asia, women account for 2/3 of the population living below the poverty line[15]. Thus all the above measures not only have a positive impact on poverty reduction, but are particularly beneficial to women.
[15] UN Women
## Why us?
The UK is well placed to help develop the regulatory framework and policy expertise around both green finance and energy efficiency, drawing on extensive expertise, consultancy, equipment and technology supply. The UK’s expertise on green finance, through the City of London, is unrivalled - it is the largest net exporter of financial services, accounting for 21% of financial exports.[16] One third of global clean energy projects from 2007 to 2012 had legal and financial advice from the UK.[17] The UK has high quality, energy efficient products and a well-developed energy efficiency market, particularly in: sustainable architecture, insulation and lighting; policy advice and design; energy management and accounting services; and innovative financing solutions (the latter forming a nice synergy with the green finance element).
[16] 2015 data from Trademap.org
[17] The size and performance of the UK low carbon economy (BIS, 2015)
## Who else?
1. The programme will be complementary to development assistance from multilaterals and other donors. The Programme’s initial market assessment of GF and EE will identify particular initiatives where we can add value.
2. The programme will complement other proposed PF programmes in the region – such as working with the Future Cities programme on energy efficiency in urban planning; and the Indonesia Renewable Energy Programme.
3. Although predominantly focused on the PF6, the programme will look across the whole of ASEAN to identify areas where ASEAN-level programming may be the most effective way to promote programme objectives.
## How will the programme be delivered?
The programme will be delivered through a lead supplier procured through the PF Framework Agreement. The supplier may deliver the full programme themselves or form a consortium to do so. Tenders will be assessed against VFM criteria including their ability to deliver inclusive growth, reduce poverty and improve gender equality. In-country project management and policy leads will engage on the ground, supported and co-ordinated by a central programme office in Singapore. The Senior Responsible Owner (SRO) and suitable governance and monitoring, reporting, evaluation and learning (MREL) structures will ensure the programme delivers value for money and is compliant with the International Development Act and the International Development (Gender Equality) amendment.

# Strategic Case

This business case investigates the opportunities to promote inclusive economic growth in SE Asia and for increasing global prosperity, including for the UK. This Prosperity Fund programme would be deploying £15m of Official Development Assistance (ODA) funds to pursue these objectives.
## South East Asia and country selection rationale
South East Asia has a population of more than 600 million people and is equivalent to the world’s 7th largest economy. It is the fourth-largest exporting region in the world, trailing only the EU, North America, and China/Hong Kong, and accounts for 7% of global exports. It is a major hub for manufacturing and well positioned in global trade flows. Developing Asia has experienced a decade of high economic growth that has lifted 1 billion people out of poverty (1990-2012)[18] and allowed the region to meet the first of the Millennium Development Goals: halving between 1990 and 2015 the proportion of people whose income is less than $1 a day. However, there are still 87 m people below national poverty lines in SE Asia and 37.9 million people who fall below the World Bank’s $1.90 poverty measure,[19] of which 2/3 are women[20]. While still comparatively strong globally (2.4% projected global growth 2016[21]), growth in SE Asia has moderated in recent years[22], productivity is levelling out and the gains of the last decade face increasing threat from the uncertain global economy, on which the SE Asia economy is highly dependent. Additionally, just as SE Asia is dependent on global growth, global growth is increasingly dependent on Developing Asia giving all players in the global economy an incentive to foster Asian growth.[23] SE Asia is increasingly important to the UK too in both international diplomacy and trade. In addition to our diplomatic co-operation on global challenges such as climate change and illicit trafficking, the UK continues to develop its defence and security partnerships with countries across the region in areas such as counter-terrorism, maritime security, and cyber security. SE Asia is the third largest non-EU export market for the UK – after the US and China – worth £14.2 billion in 2016. UK exports to SE Asia compared favourably to our exports to other major players in 2016: China £16.7 billion, India £6.6 billion and Brazil £3.8 billion.[24] SE Asia delivers 4 times more inward investment into the UK than China does but the UK is still relatively underrepresented in terms of our trade relationship with SE Asia compared with other European partners.
[18] Asian Development Outlook 2016: Asia’s Potential Growth. Asian Development Bank, page xvii
[19] Statistic excludes Burma for which there is no data
[20] UN Women, 2013
[21] Global economic prospects: A fragile recovery (World Bank Group, 2017)
[22] Average 4.6% in the region in 2015 compared to 9.4% average 2005-2007. Average 4.6% in the region in 2015 compared to 9.4% average 2005-2007. Economic and Social Survey of Asia and the Pacific 2016: Nurturing productivity for inclusive growth and sustainable development. UNESCAP, page 96
[23] Asian Development Outlook 2016: Asia’s Potential Growth. Asian Development Bank, page xvii
[24] United Kingdom Balance of Payments - The Pink Book time series dataset (July 2016)
#### Geography and History of Southeast Asia
1. SE Asia is a geo-political construct describing countries to the east of the Indian subcontinent and south of China. Its easterly border is generally taken to be the Philippine Sea and to the south, it borders Papua New Guinea and Australia. The term originated in the Second World War and there is no universally agreed list for which countries it includes. The 10 countries that are commonly agreed to be included are Brunei, Burma, Cambodia, Indonesia, Laos, Malaysia, Philippines, Singapore, Thailand and Vietnam. The Southeast Asian archipelago has been a nexus for trade since around 100BC, sitting at the cross roads of the Indian Ocean and the South China Sea.
2. The 20th century saw the countries in SE Asia embroiled in the World Wars. Subsequently, the region gained independence from Western colonisation, with the exception of Thailand, which was not colonised. Communism rose in the region too with Laos, Cambodia and Vietnam under Communist rule for part of the century. Vietnam and Laos retain Communist rule.
3. More recently, SE Asia has been characterised by high economic growth, particularly in Singapore and the “ASEAN 5”: Indonesia, Malaysia, the Philippines, Thailand and Vietnam, and by closer regional integration. Burma, Cambodia and Laos have typically grown more slowly and have remained poorer, in part due to political instability. East Timor is also considered part of SE Asia in some definitions and plans are also underway for its accession to ASEAN.
### ASEAN and the ASEAN Economic Community (AEC)
1. Alongside country-specific and multi-country analysis, the strategic case will look across ASEAN (The Association of Southeast Asian Nations). ASEAN[25] was established in 1967 with the purpose of fostering cooperation between the ten member countries of SE Asia in the economic, social, cultural, technical, educational and other fields, and in the promotion of regional peace and stability through respect for justice and the rule of law. The principle of economic growth and integration is fundamental to ASEAN. Its 2008 charter turning ASEAN into a legal entity emphasizes the centrality of ASEAN in regional co-operation and its ambition to create a single free-trade area for the region. ASEAN is a unifying force for reform in the region so it is important that PF ASEAN programme design understands and works within the ASEAN context.
  [25] In this business case, ASEAN will be used to refer specifically to the organisation rather than the region as a whole. An ASEAN intervention will only refer to working with ASEAN as an organisation, other interventions will be referred to as multi-country or regional
2. As part of ASEAN’s economic integration, the ASEAN agreed to a joint approach to economic integration – The AEC Blueprint 2025.[26] This provides strategic direction for the AEC from 2016 to 2025. Its objective is to establish a common market that extends the principles of free trade to the movement of mobile factors of production, such as labour and capital. Its vision for ASEAN is:
  [26] ASEAN Economic Community Blueprint 2025 (ASEAN Secretariat, 2015)
  1. a highly integrated and cohesive economy
  2. a competitive, innovative and dynamic region
  3. enhanced connectivity and sectoral cooperation
  4. a more resilient, inclusive people-oriented, and people-centred community
  5. a global ASEAN that is integrated with the global economy.
This approach presents a clear and structured framework for UK economic cooperation to assist in delivering the AEC blueprint. Regional integration remains a good way for the region to build economic resilience and improve growth prospects. Our interventions with clusters of ASEAN countries, and targeted work in individual countries to bring them up to a common level, can work in synergy with the AEC vision. Such supportive policies facilitate deeper co-operation and improve long-term commitments to regional integration.

### Programme country selection
The programme is designed to operate regionally within South East Asia. The regional approach has been selected because:
  1. It echoes how the region self-organises through ASEAN. This provides proven delivery pathways and links well with ASEAN’s general direction of travel on low carbon issues, such as its objectives to reduce energy intensity set out in the AEC blueprint for 2025.
  2. A regional approach will drive regional harmonisation which will improve the conditions for intra-region and international trade, improving economic growth.
  3. Many interventions can be rolled out effectively regionally rather than country by country. This represents a good value means of ach
  4. l both primary and secondary benefit.
  5. It spreads risk and the programme is able to flex, such as scaling up or down in any particular country, depending on likely success as the programme develops.
    Figure 1: The country groups for analysis and programme development
  6. The marginal cost of including a country is low because the programme is able to utilise regional programme delivery partners, and the existing Singapore Prosperity Fund hub can provide oversight. This presents good value for money.
  7. It provides opportunities for lesson learning from peers among countries in the region, where some are at different stages of development.
1. While the regional approach offers opportunities to leverage regional cooperation among countries and for economies of scale, there is a risk of fragmentation. This could result in creating a programme that is too generic to address the highest priority issues across a range of countries at very different levels of development, spreading resources too thinly to achieve meaningful impact and creating a programme that is difficult to implement and manage. We therefore sought to reduce the countries covered to the minimum number for which the benefits of a regional approach could still be realised. Of the 10 South East Asian countries[27], only 8 are eligible for ODA so Singapore and Brunei were automatically excluded.
  [27] Burma, Brunei, Cambodia, Indonesia, Laos, Malaysia, the Philippines, Singapore, Thailand, Vietnam
2. The analysis undertaken to narrow down the country focus concludes that Burma, Indonesia, Malaysia, Philippines, Thailand and Vietnam are good fits for the programme. We have termed these the ‘PF6’ for the purposes of this programme. All are populous and economically fast growing which will provide the right conditions for the Prosperity Fund to promote inclusive economic growth. All except Burma are middle-income countries with similar levels of development (along a spectrum). Burma has a high total number of people in poverty and without energy access, and high predicted economic growth, giving it strong primary benefit potential and a good chance of benefitting from low carbon energy transition in the near term as its economy grows.
3. The analysis concludes that the ASEAN Low Carbon Energy Programme should focus its efforts in PF6 countries, and seek to engage Laos and Cambodia in a light touch manner – mainly through participation in regional interventions. This will ensure that the programme maintain sufficient scale to be ambitious, while reducing the complexities of the operating environment. Both countries’ economies are growing rapidly though and they may be more suitable candidates in future years if the Fund is replenished.
4. Focusing on these 6 out of the 10 SE Asian countries still realises the benefits of the regional approach: as the table below indicates, the PF6 countries make up 94.5% of the population of South East Asia, 90.5% of its landmass, 86% of its GDP, 95.7% of its population below national poverty lines and 96% below the World Bank $1.90 poverty measure, and 91% of those without energy access.
Table 1: Comparing the PF6 to total Southeast Asia[28]
[28] World Bank Poverty and Equity database, available at: http://povertydata.worldbank.org/poverty/country/, latest available data at time of writing
Country	Population (m)	GDP (US$ bn)	People living below World Bank $1.90 measure		Population below the national poverty line		Land mass (km2)
			Percentage	Number (m)	Percentage	Number (m)
Brunei	0.4	11.4	-	-	-	-	5770
Burma	52.9	63.2	NA	NA	25.6[29]	13.8	678500
Cambodia	15.8	20	2.2	0.3	17.7	2.1	181035
Indonesia	261	932.3	8.3	21	11.3	28.9	1904556
Laos	6.8	15.8	6.7	1.1	23.2	1.6	236800
Malaysia	31.2	314.5	0.3	0.1	0.6	0.18	329750
Philippines	104.9	313.6	13.1	12.6	25.2	25.4	300000
Singapore	5.6	309.8	-	-	-	-	693
Thailand	68.9	411.8	-	-	10.5	7.4	514000
Vietnam	94.7	205.3	3.1	2.8	13.5	7.7	329560
PF6 as a % of total SE Asia figure	95.5%	86.3%	96.3% of those below $1.90 a day[30]		95.7% of those below national poverty line		90.5%
[29] ADB Basic 2017 Statistics: Economic Research and Regional Cooperation Department, April 2017
[30] Statistic excludes Burma for which there is no data

1. It is challenging to disaggregate the available evidence on SE Asia only to include the PF6 countries. As the preceding table indicates though, the PF6 account for the vast majority of SE Asia on the significant metrics. We therefore consider that using evidence and analysis under the collective term “South East Asia” provides a good representative basis of the particular 6 countries of this proposed programme. Where possible our analysis will focus specifically on the so-termed PF6 countries of this programme (Burma, Malaysia, Indonesia, the Philippines, Thailand and Vietnam). However, we will also use “South East Asia” analysis as a proxy for the PF6 countries where there is existing analysis of the region, which cannot be disaggregated into individual countries. We consider the resources incurred were we to create specific data for the PF6 grouping would be disproportionate to the additional benefit achieved.
2. Analysis of these 6 countries – the PF6 – will look at their unique features and also their similarities to identify common barriers to growth that can be tackled with a multi-country approach. However, we recognise that some country-specific issues may need addressing where, for example, their capacity or policy framework need additional steps to bring them up to the level where a multi-country approach can be adopted. There may also be benefits to working initially with 1 or 2 countries on a theme where they have particular interests or expertise, as a pilot stage before rolling out to the others. The aim will be to avoid a fragmented programme but to deliver across the countries chosen as much as possible, to ensure harmonisation as well as economies of scale and value for money.
3. The PF6 countries on which we are focused have a strong drive for regional integration under the AEC. The Prosperity Fund may have a role to play pursuing this objective, which aligns with the aims of the Prosperity Fund, goes with the grain of how ASEAN organises itself, maximises the multiplier effect and helps promote regional harmonisation. Where ASEAN-level programming is identified as the most effective way to promote inclusive economic growth, Laos and Cambodia will be invited to participate in the programmes, furthering regional integration. This would be likely to be the case, for example, if the ASEAN organisation itself is developing regional standards on low carbon issues. Work with the ASEAN secretariat[31] will include Brunei and Singapore as ASEAN members, but no programming will take place in either country and no ODA funding will be extended to them.
  [31] The ASEAN ODA coefficient is 100%
### Constraints to economic development in SE Asia

SE Asia’s strong economic growth potential provides enormous opportunities to improve the lives of its citizens and contribute to global prosperity, including for the UK. Despite this there are still substantial economic reform needs that, if left unaddressed, will constrain growth. The PF6 countries are economically, politically and socially diverse, but there are a number of common barriers to economic growth and they share a common aim to increase economic prosperity for their people. Diagnostic work revealed three key challenges in ASEAN which map well to priority Prosperity Fund themes:
- Challenging business environment (including corruption, inefficient regulatory reform and enforcement; inefficient allocation of finance and lack of access to financial services)
- Social infrastructure constraints (including unsustainable urbanisation, poor physical infrastructure, lack of capacity and capability in health provision, need for enhanced education)
- Unsustainable energy provision and increased environmental risks, including from climate change. This theme, from which the programme developed, is addressed in more detail below.
#### Unsustainable energy provision and increased environmental risks, including from climate change
##### Rising energy needs and carbon emissions
SE Asia’s continued economic growth will depend, in part, on whether it can meet its growing energy demand: “Any nation that wants to grow its economy and improve living standards must secure a robust energy supply”.[32] The International Energy Agency (IEA) forecasts that SE Asian energy demand will increase by 80% by 2040. Regional electricity demand will triple. The IEA estimates that securing the region’s energy needs will require US$2.5 trillion of cumulative investment in energy supply infrastructure to 2040 (about $100 billion per annum). This should include better regional energy connectivity and integration, and providing electricity access to the 120 million people in ASEAN currently without. UNESCAP[33] cites the main energy challenges as:
[32] Better Growth, Better Climate, Chapter 4: Energy, New Climate Economy
[33] Enhancing regional cooperation for sustainable energy in Asia and the Pacific, Note by the secretariat. UNESCAP. 5 April 2017
  - energy access
  - lack of renewable energy (and the challenges of financing it)
  - insufficient energy efficiency (Asia and the Pacific are the world’s most energy-intensive regions)[34]
    [34] Regional Cooperation For Sustainable Energy In Asia And The Pacific, UNESCAP, 2017 page v
ADB[35] cites challenges (notable overlap with ESCAP) of:
[35] Challenges for Renewable Energy in Asia and the Pacific, Anthony Maxwell, ADB presentation
- Energy access
- private sector investment (particularly given perceptions of risk)
- lack of sector planning (including weak regulatory and policy frameworks)
- lack of appropriate technology
- low capacity
- grid integration
- donor coordination
##### Greater energy diversification and efficiency needed
Diversifying SE Asia’s energy supplies, including through the enhanced uptake of low carbon energy sources, will enhance ASEAN energy security and resilience and reduce its exposure to volatile price spikes. National energy policies in SEA include ambitious plans on EE and renewables but actual progress is slow, threatening future energy shortages and encouraging the greater deployment of least cost, most polluting fossil fuel alternatives. SE Asia’s dash for coal threatens serious social and economic costs: mortality from air pollution in nearby China is already valued at ten percent of GDP. The poorest populations, small businesses and women[36] are less likely to be able to withstand economic shocks and are ostensibly the most impacted. UNESCAP considers energy efficiency in Asia as the logical first step in the energy transition. Energy efficiency measures in the region could save 35% of energy consumption over the business-as-usual case by 2035.[37] Improving energy efficiency requires countries to overcome market barriers that prevent consumers and companies from purchasing the most efficient equipment and appliances. These barriers include market failures and imperfections; consumer attention to first costs rather than life cycle costs; attitudes, behaviours and misinformation; and fiscal policies that discourage gains in energy productivity or reward inefficient energy consumption. These barriers often require government interventions to make labelling mandatory, set national and sector-wide energy efficiency targets and establish the legal frameworks necessary to implement and enforce mandates.
[36] These demographics often intersect: Women account for 2/3rd of the population living below the poverty line in Asia (UN Women), micro businesses are less likely to resist economic and global shocks.
[37] ESCAP, “Asia Pacific: Response to Climate Change”, 10 December 2015.

##### Negative impact of climate change and environmental degradation
SE Asia is one of the world’s most vulnerable regions to climate change. ADB estimates that Business-as-usual emission levels could cost SE Asia 7% of GDP a year by 2100 – twice the global average. These impacts will be felt primarily by the region’s poorest. Women are exceptionally vulnerable to extreme climate events which are forecast to rise in frequency and severity unless global emissions, particularly from the energy sector, are significantly reduced. The region’s business-as-usual doubling of energy-related carbon emissions threatens global efforts to combat climate change. Interventions to reduce the emissions-intensity of SEA’s energy future will not only protect economic growth in the region, but will also protect the poor, including poor women from the worst impacts of climate change. Mitigating and adapting to climate change is an economic imperative if poverty reduction wins are to be protected. If Southeast Asia is to deliver its climate commitments, significant investment in low carbon infrastructure will be needed - £386 billion by 2030. Action to increase energy security and low carbon energy contributes directly to achieving Sustainable Development Goal 7 (Affordable & Clean Energy). It will also reduce ill health and premature deaths, predominantly among women and young children, arising from the use by 276 million people in ASEAN of biomass for cooking.

### Impact of energy on economic development, poverty reduction and gender equality
1. “Energy is the golden thread that connects economic growth, increased social equity, and an environment that allows the world to thrive."[38] Studies have shown that energy is either the cause or the facilitator of growth and plays a fundamental part of economic growth.[39] The United Nations states “energy is an essential factor for sustainable development and poverty eradication.”[40] It is widely accepted that increases in electricity generation capacity drives poverty reduction.[41] It can boost economic growth in developing countries (by 1-2% pa).[42] DFID’s new Economic Development Strategy has an increased emphasis on energy to help meet businesses’ rising energy needs; to ensure affordable access for the poor; and to enhance environmental sustainability in energy use. G7 Energy Ministers concluded at the Rome Energy Ministerial in April 2017 that “continued investment in the energy sector, in particular in quality energy infrastructure, in upstream development, in low emissions and in low carbon technologies and in energy efficiency, remains critically important for ensuring future energy security and mitigating risks to sustainable growth of global economy.”[43]
  [38] Former UN Secretary-General Ban Ki-moon
  [39] The Human Development index is a long-standing measure tracked by UNDP, and reported on a semi-annual basis. Energy is a key component, http://hdr.undp.org/en/content/access-energy-and-human-development
  [40] United Nations, 2016. Sustainable Development Knowledge Platform. Energy for Sustainable Development. [Online] Available from: https://sustainabledevelopment.un.org/topics/energy
  [41] ISD 2013, the evidence of benefits for poor people of increased renewable electricity capacity: literature review, https://opendocs.ids.ac.uk/opendocs/bitstream/handle/123456789/2961/ER31%20Final%20Online.pdf?sequence
  [42] International Energy Agency (IEA), 2017 Gas as a Transition Fuel report.
  [43] Chair’s summary, G7 Rome Energy Ministerial Meeting 9-10 April 2017
2. A low carbon transition also has the potential to yield significant economic growth potential through potential industrial productivity gains and inducing innovation in clean technologies, with knowledge spillovers into other sectors, which are likely to drive higher GDP growth than otherwise.[44] It is well established that high quality energy infrastructure is critical to poverty reduction and inclusive growth.[45] There is strong evidence that improving access to energy improves gender equality as the burden of collecting solid fuel for energy falls disproportionately on women.[46] There is also a benefit to women when poor quality domestic sources of energy (e.g. biomass for heating, cooking and lighting) are exchanged for cleaner energy sources such as from renewables. Air pollution and fire-related accidents in the home disproportionately affect women given longer times spent in the home. Energy efficiency is a cost-effective route to provide a greater and more reliable supply of clean electricity to poor households, alleviating poverty,[47] as well as freeing up government resources for other services such as education and healthcare.
  [44] Aghion, Hepburn, Teytelboym and Zenghelis, 2014. Path-Dependency, Innovation and the Economics of Climate Change. Policy Paper. Centre for Climate Change Economics and Policy, Grantham Research Institute on Climate Change & the Environment, and New Climate Economy.
  [45] ADB 2012, Infrastructure for supporting inclusive growth and poverty reduction in Asia
  [46] Evidence on Demand: Correlation and causation between energy development and economic growth, 2014. Harvard 2015, Burden of disease from rising coal emissions in Asia, presented at International Symposium on Climate Change and Coal May 29, 2015 http://acmg.seas.harvard.edu/presentations/2015/koplitz_japan_symposium_20150529.pdf [accessed 24/11/2016]
  [47] European Commission, Energy for poverty reduction and sustainable development, http://ec.europa.eu/environment/archives/wssd/pdf/energy_poor.pdf

Low carbon energy specifically has an impact on gender equality and inclusive growth,[48] with robust evidence of positive impacts for women’s empowerment from deployment of low carbon energy technologies. Further, improvements in education are widely and consistently reported as resulting from deployment of low carbon energy generation technologies – and impacts are generally higher for girls than boys.[49] When women are educated and employed, economies grow and development outcomes are improved. Renewable energy creates opportunities for increased entrepreneurship and enterprise.[50] Many small-scale, local renewable energy enterprises are likely to attract and retain female workers.
[48] OECD 2013, Making growth green and inclusive, the case of Ethiopia
[49] ISD 2013
[50] NORDREGIO 2011, Smart, sustainable and inclusive growth

While energy is a driver for growth, as shown above, outdated and inadequate energy constrains growth. Insufficient, unreliable or costly access to power is recognised to be an important binding constraint for many emerging countries.[51] Approximately 20,000 people in SE Asia die every year from air pollution linked to coal-fired power stations, while 70,000 annually could die by 2030 if all proposed coal-fired power plant projects in the region are built,[52] and this disproportionately affects the poor. Associated annual health costs have been calculated to total US$280 billion in recent years.[53] Transforming energy towards more affordable, reliable and cleaner energy sources is essential to improve the welfare of the poor, and to address national development strategies for health, education, rural development and gender equality.[54] This is recognised and enshrined in the 2030 Agenda for Sustainable Development, under SDG 7, with targets on universal access, increased renewable energy, improved energy efficiency, and enhanced international cooperation. SDG 7 is seen as an essential catalyst for achieving other SDGs, such as those addressing equality, climate change, education, public health, clean water and sanitation.[55] Energy has a direct influence on SDG1 (End poverty in all its forms everywhere); SDG5 (Achieve gender equality and empower all women and girls); SDG 8 (Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all) and work under SDG13 (Take urgent action to combat climate change and its impacts).
[51] CDC, 2016. What are the links between power, economic growth and job creation? Available from: http://www.cdcgroup.com/Documents/Evaluations/Power%20economic%20growth%20and%20jobs.pdf Accessed 13/03/2017] p.24
[52] DBS report Green Finance Opportunities in ASEAN (Nov 2017) https://www.dbs.com/iwov-resources/images/sustainability/img/Green_Finance_Opportunities_in_ASEAN.pdf
[53] Organisation for Economic Co-operation and Development (OECD) (2014). Towards Green Growth in Southeast Asia. http://www.iau-hesd.net/sites/default/files/documents/towards_green_growth_in_southeast_asia.pdf
[54] ESCAP
[55] 2016 Regional Trends Report Energy Sustainable Development in Asia and the Pacific UNESCAP, intro
## The proposed ASEAN Low Carbon Energy Programme
1. The proposed Programme builds on the concept note approved by the Prosperity Fund Ministerial Board which outlined 4 areas of opportunity: Green Finance, Energy Efficiency, Energy Networks and Renewables. In order to avoid fragmentation and increase impact, we propose to focus on just 2 of these 4 areas: Green Finance and Energy Efficiency (roughly 50/50 split), these being the 2 most readily identified as important by stakeholders in the region, and areas of significant UK expertise.
2. The programme will provide policy support, capacity building and technical assistance to facilitate green finance flows and improve the regulatory, policy and practical conditions for energy efficiency measures. It will support 4 broad types of activity: capacity building of government, institutions and business; policy reform of energy frameworks and standards; market development by strengthening connections between project developers and investors; raising awareness of available technologies to increase the uptake of energy efficient products and services; and partnership coordination and commercial ventures within SE Asia. All components of the programme aim at improving energy security and inclusive access to clean and reliable energy sources, with direct benefits for most vulnerable population, including women, in accordance with the International Development (Gender Equality) Act 2014.
3. The proposed Low Carbon Energy programme strongly supports the NSC Strategy: in particular its objectives on increasing British global influence through soft power, promoting UK prosperity via trade, as well as the NSC targets on development. The proposed programme directly tackles one of the constraints to growth by enabling a transition toward more affordable, reliable and cleaner energy sources; and understanding of environmental risks, including those arising from climate change.

## Low carbon energy in SE Asia: the case for Prosperity Fund focus
1. Transitioning from energy and carbon-intensive growth to a low carbon pathway will require enhanced policies and measures to improve energy efficiency; a strategy for managing the phase-out of unabated coal-fired power; avoidance of new (unabated) coal; continued efforts to manage complex energy grid systems and the incorporation of climate risk into decision-making; and the implementation of measures to shift South-East Asia’s financial sector towards a system that can finance low-pollution, low-carbon, resource-efficient infrastructure at a low cost of capital.
2. ASEAN has set an aspirational target of 23% of renewables in the energy mix by 2025 and ambitious targets on energy efficiency. Each PF6 country has set its own renewable energy and energy efficiency targets as part of its energy plans or NDCs as per the Paris Agreement. ADB estimates that that half of the region’s emissions reduction through 2050 can come from low-carbon energy production and another third from energy efficiency measures, with the rest achieved by curtailing emissions from deforestation, land degradation, and other non-energy sources. But current political commitment is not sufficient to drive the necessary investments in renewables: a combination of economic and regulatory support is necessary to boost deployment of renewable energy and make the renewable energy targets effective and credible.[56] UNESCAP also notes that strengthening government and capacity, and mobilising finance and investment are 2 of the key drivers to achieve energy transformation in the region.
  [56] IRENA 2015

### Compliance with the International Development (Gender Equality) Act 2014
1. Women are more likely to suffer from climate change and natural disasters as they constitute the majority of the world’s poor (2/3rd of the population living under the poverty line in Asia are women) and their livelihood is more dependent on natural resources that are threatened by climate change. UN figures indicate that 80% of people displaced by climate change are women.[57] Catastrophic events also lower women’s life expectancy more than men – this difference increases the stronger the disaster[58]. Women face social, economic and political barriers that limit their resilience and their ability to protect themselves from extreme weather events, air pollution, food and water scarcity and economic hardship.
  [57] Climate Change ‘impacts women more than men’, BBC 2018, http://www.bbc.co.uk/news/science-environment-43294221
  [58] Neumayer, Eric and Plümper, Thomas (2007) The gendered nature of natural disasters: the impact of catastrophic events on the gender gap in life expectancy, 1981–2002. Annals of the Association of American Geographers, 97 (3). pp. 551-566.
2. Women are also important and effective actors of change in both adaptation to and mitigation of climate change. They often possess strong knowledge and expertise that can be used for climate change mitigation, disaster reduction and adaptation strategies. Women’s responsibilities in households give them a strategic position to develop sustainable habits among their families and communities. Key areas identified by the UN for climate change mitigation in which women should be regarded as agents of change include financing mechanisms and technology development (including energy efficiency).
3. The role of women in energy is often underestimated, as it is associated with electricity and fuels, which are mostly considered ‘men’s work’. As a result, energy policies and regulations are often ‘gender-blind’, missing the opportunity to associate women with roles in policy-making, adaptation and mitigation. This bias also fails to take into account the central role that women play in shaping energy consumption habits. The UN recommends to ‘actively engage women in national energy decision making’ and to give them ‘greater involvement so that energy supplies can be managed more effectively and productively in the face of climate change[59]’.
  [59] UN Women Watch, Women, Gender Equality and Climate Change, Fact Sheet 2009
4. Because women are both more vulnerable to climate change and more likely to play a prominent role in adopting adaptation and mitigation strategies, they are a key target population within this proposed programme. The identified primary benefits are expected to positively impact women’s welfare, notably through generating inclusive growth, creating job opportunities and favouring conditions for climate change mitigation. In developing our programme, we have carefully considered how the different elements of the programme can improve the lives of women and girls. We have conducted a careful review of the evidence available on gender impacts of clean, reliable, affordable energy access to better understand how our programme can contribute to improved gender equality.
5. Women and men play different gender-defined roles in energy production, distribution and utilisation in households, communities and the market[60] and in general women can benefit disproportionately from programmes that make energy more affordable, reliable and clean. However, these potential benefits are not automatic and poor programme design can mean failure to fully realize these benefits.
  [60] UNDP, 2013
6. To ensure women reap the benefits of improved energy access and reduced barriers to business, we will:
- Incorporate women’s voices throughout the design, delivery and evaluation phases of the programme.
- Ensure female participation in consultations and other engagement activities, including individual participation and through community groups and women’s business associations.
- Require collection and analysis of gender disaggregated data (including quantitative data) where possible in project monitoring, reporting, evaluation and learning (MREL).
- Include women in training programmes, e.g. on operation & maintenance of energy infrastructure; micro-enterprise support; regulatory workshops, etc.
- Consider the likelihood of delivering positive impacts for women as one of the criteria when selecting specific interventions during the scoping phase.
- Consider the impact on gender norms at household, community or wider societal levels that could result from improved energy access and business opportunities. We will carefully assess the potential for any unintended negative consequences (e.g. changes in status, power and influence between girls/women and boys/men, which could lead to domestic violence; increased drudgery for women as longer working hours are enabled by electrification, etc.)
### Approach to integrating gender and equality into the programme
Under the HMG partnerships model, we will work with lead suppliers to ensure that activities supported by the programme are gender and equality sensitive. This means that programme design will take into account the different ways activities may impact men and women and disadvantaged groups more broadly. The development of gender and inclusion strategies will be a key selection criterion for suppliers. Table 2 sets out indicative activities to support the mainstreaming of gender and inclusivity into the programme.
Table 2: Possible measures to strengthen the gender and inclusivity contribution of the ASEAN Low Carbon Prosperity Fund Programme
Measure	Description
Gender analysis and impact assessment	Assessing potential interventions from a gender/inclusion perspective before finalising individual pillar plans.
Capacity building and gender mainstreaming skills	Ensuring that suppliers have appropriate gender/inclusion skills-sets and that this capacity can be built and shared with wider partners. That the suppliers have properly budgeted for mainstreaming, with sufficient time allocation and staffing with sufficient level of seniority and experience to influence decision making
Monitor and evaluate against gender impacts	Requiring (where feasible) suppliers to collect sex-disaggregated data; KPIs to monitor and evaluate the differentiated impact on women and men
Gender involvement and consultations	Involve women and other excluded groups in programme design, implementation, monitoring and evaluation with beneficiary feedback and discussions and with partners as activities are undertaken.

1. The programme is intended to improve the lives of women and girls. The use of renewable energy can particularly benefit women and girls in emerging economies. Access to energy services significantly improves women’s lives by freeing up time that was previously taken in gathering fuel and cooking with inefficient stoves, by alleviating health problems caused by burning wood and dung and by increasing access to information services such as television, radio and the Internet[61]. This provides the opportunity for women to assume less traditional roles and generate income, and ultimately leads to higher gender equality[62]. Analysis by the National Bureau of Economic Research has also established a clear relationship between better quality infrastructure (including energy infrastructure) and increased women’s entrepreneurship and economic participation into industry/enterprise. Benefits include safety, time savings and access to public services and markets.[63] Cost savings to government through energy efficiencies can be rerouted to services such as education and health – both with direct correlations to improved gender equality and support to inclusive growth.
  [61] UNDP Policy Brief 4 – Gender and Climate Change, Asia and the Pacific
  [62] Kanagawa, M. and T. Nakata, Analysis of the Energy Access Improvement and Its Socio-Economic Impacts in Rural Areas of Developing Countries (Tohoku University, 2005)
  [63] E. Ghani, W. Kerr and S. O’Connell, Local Industrial Structures and Female Entrepreneurship in India, (National Bureau of Economic Research, 2012)
2. Due regard to the impact of programme funded activity on gender equality will be a requirement of every agreement signed for the delivery of the programme. Each supplier will be required to submit an assessment of the impact of their work on gender equality as part of their annual reports. The programme team will ensure that gender issues and opportunities are addressed in delivery and monitoring to ensure compliance with the Gender Equality Act.

### Energy profile of PF6 countries, including impact on poverty and sustainability
1. The following section provides an overview of each of the 6 countries’ energy profiles, including energy mix, share of renewables, future plans and impact of their energy programmes on development, poverty and gender (such as through energy access or affordability).
2. The Philippines energy demand is growing at about 4.8% per annum. It is heavily dependent on imports and this will rise.  On present plans, the growth of energy supply will be heavily coal based, projected to reach 70% by 2030, which will be the highest in Asia and which will move the country from a relatively low carbon economy to a much higher carbon economy. The share of renewables in the energy mix currently stands at about 30% (40% if fuelwood and charcoal burning is accounted for) - the highest in South East Asia. Under the National Renewable Energy Programme (NREP), the government aims to triple the renewable energy capacity to about 15,000 Megawatts by 2030 but given the current trend towards coal power plants reaching this target is unlikely. 10 million or 1 out of 10 Filipinos still lacks access to basic electricity.[64] According to the World Bank Sustainable Energy For All (SE4ALL) 2014 data, the Philippines has near total urban coverage, but only about 80% of access to electricity in rural areas, particularly in remote islands.[65] Nationwide, household level electrification has reached 88%, approximately 19 million households.[66] 11 of the 20 poorest provinces in the Philippines are in Mindanao and have some of the lowest household electrification rates in the country.[67]
  [64] Energy Secretary Alfonso Cusi, WBF Roundtable Presentation, Makati Shangri La, 27 April 2017
  [65] http://data.worldbank.org/indicator/EG.ELC.ACCS.ZS
  [66] Secretary Arsenio Balisacan, National Economic and Development Authority, EPDP Conference, New World Makati Hotel, 13 January 2016
  [67] Senator Loren Legarda, 4th EU-Philippines Meeting on Energy, 7 October 2016
3. Electricity is not subsidised and consumers pay almost twice the average price of electricity (for residential, commercial and industry) in the ASEAN region.[68] While the Philippines’ power consumption has been increasing, the country’s energy and electricity consumption per capita is still lower than its neighbours like Indonesia, Malaysia, Singapore and Thailand (1983-2013 data).[69] The low per capita consumption of households is highly likely to be affected by the high cost of electricity[70]. Meeting future energy demand is a challenge, where the country’s supply will be short of the 25% reserve requirement beyond 2021, and an additional capacity of 43,765 megawatts is needed by 2040[71].
  [68] Prof. Rowaldo Del Mundo, EPDP Conference 2016, 13 January 2016
  [69] Secretary Arsenio Balisacan, National Economic and Development Authority, EPDP Conference, New World Makati Hotel, 13 January 2016
  [70] Prof. Rowaldo Del Mundo, EPDP Conference 2016, 13 January 2016
  [71] Energy Secretary Alfonso Cusi, WBF Roundtable Presentation, Makati Shangri La, 27 April 2017
4. Malaysia faces a looming energy security challenge with electricity demand forecast to increase by 5.7 percent per annum from 2000 until 2020, which is slightly higher than its GDP growth. Domestic oil production is set to fall against a backdrop of rising domestic demand. Malaysia is now a net oil importer. Current energy plans include the construction of a new coal-fired power station every year for the next five years, replacing domestically produced gas to provide electricity. Malaysia’s current energy mix in electricity generation is: 56% (coal): 37% (gas): 5% (large hydro) and 2% (RE). Coal is expected to peak in 2022 (62%) and is expected to remain the dominant resource in 2030 (by more than 50%). There is a move to increase RE share by 10% by 2030, but challenging barriers remain on making this attractive for investments and uptake. Nuclear has been mentioned as an alternative power generating fuel post-2030.
5. Electrification rate in Malaysia is about 99% with rural electrification of about 98 percent.[72] Most rural electrification is powered by mini/micro hydro, PV-solar or diesel powered generators. However, fossil fuel based generation is expensive in rural areas as the logistics involved to transport fuel into a rural setting are expensive. Ensuring a reliable 24-hour supply of electricity and making it affordable for the approximately 0.2 million in rural communities living off the grid is still a challenge for Malaysia, especially in Sabah and Sarawak. However, investing in a community based or managed RE generating electricity system put in place by government entities/private sector/donor agencies has worked for these rural communities. The challenge is to scale up, diversify RE supplies, provide better interconnectivity (via i.e. establishing mini-grids) and make the RE supply more reliable. Ensuring constant electricity supply will eradicate extreme poverty and hunger; support better school education in these areas; promote gender equality and empower women; reduce child mortality; improve maternal health; combat major tropical diseases; and ensure environmental sustainability (as opposed to extending major grids into rural areas via clearing of vast forested land).
  [72] IEA 2012
6. Energy demand is growing strongly in Thailand with final energy consumption in 2015 increased by four percent compared to the previous year, particularly in the south of the country.[73] This has led the government to focus considerable effort on energy security over the last few years, particularly diversification away from Thailand’s current dependence on gas (with its role in energy supply expected to fall from 64% to 40% by 2036), towards renewables (8% to 30%) and coal (19% to 25%), with several new coal-fired power stations planned. The latter is politically controversial, and will have an impact on Thailand’s ability to reach its emissions targets, but is likely to go ahead. Gas supply will shift to some extent away from domestic sources towards LNG, with BP recently winning the import contract. Thailand has reached 100% access to electricity since 2010,[74] with full coverage in its rural population in 2014.[75] Data from the National Statistic Office during 2000-2014 also shows a reduction of the poverty rate corresponds to improved access to electricity in the rural areas. Generally, electricity in rural areas is transmitted by grid system.[76] Solar PV is also widely used for off-grid areas such as villages in jungle, or islands.[77] Small hydro power plants are installed in many villages. However, firewood and agricultural residues are still the primary energy sources in much of rural Thailand.[78] On average, energy expenditure per household accounts for 8.3% of total income. For the lowest earning group, energy cost is around 9.9% of total income.[79] Because Thailand is heavily dependent on imported energy sources (60% of Thailand’s primary commercial energy; imported oil accounting for 80% of domestic oil consumption), the energy price is therefore vulnerable to externalities.
  [73] http://www.eppo.go.th/index.php/en/energy-information-services/report-2015
  [74] World Economic Forum
  [75] World Bank
  [76] W. Krueasuk et al, Renewable Energy for rural electrification in Thailand: A case study of Solar PV rooftop project (GMSARN, 2015) p.52
  [77] Thailand 2014 (REEEP Policy Database 2014)
  [78] Renewable energy developments and potential in the greater Mekong subregion, (ADB 2015)
  [79] Statistical Data (Thailand National Statistical Office, 2017)
7. Since 2016, Thailand has made significant progress in removing the government's fossil fuel subsidies for 91 gasoline and diesel which is part of a populist policy. Low-income consumers do not really benefit from the subsidies that became a burden for the government.  Starting from May 2017, the electricity price increased by 3.5%.[80] This translates to 13.4% of total income for the lowest earning group. The government plan is to reduce this dependency by increasing renewable energy to 25% of total energy consumption by 2021.[81] Therefore, renewable energy will become increasingly important for Thailand’s energy security as well as livelihoods in rural communities.
  [80] Thailand Nation TV
  [81] ADB
8. The power demand in Vietnam continues to grow rapidly, reflecting the country’s economic development. Between 2000 and 2015, electricity peak demand grew from 4.9 GW to 25.8 GW or by an average of 12% annually. Latest projections are for continuing near-double digit increases with peak demand reaching 42 GW by 2020, 63.5 GW by 2025 and over 90 GW by 2030. Though the current plans represent an important step forward in renewable energy development (i.e. 3.7% in 2015 to 6.5% by 2020 and 10.7 percent by 2030), expansion of coal-fired generation continues. 55 GW of power is scheduled to be fuelled by coal by the year 2030- up from 14 GW today, making Vietnam the eighth-largest user of coal for electricity generation in the world, with levels similar to those of Russia and Indonesia.
9. Vietnam has made remarkable progress in expanding access to electricity, with the percentage of households without electricity decreasing from 50% in 1995 to 2% in 2014.[82] The communities that are not yet connected to the grid are mainly in the less developed and sparsely populated mountainous areas of the northwest and isolated islands. Providing universal access to electricity is a top priority of the government’s power subsector development agenda. However, most of the remaining areas without electricity are far from existing networks and further expansions are not feasible unless existing rural networks are augmented. The estimated investment required for increasing access to electricity during 2014–2020 is around $1.5 billion.[83] In the past few years, energy demand has been growing by 15% per year.[84] To meet such an increasing demand, Vietnam still prioritizes low cost power such as coal fired power plants and hydropower. Electricity demand growth has exceeded income growth; the result has been a rapid rise in electricity intensity. In 2014 it was estimated to take almost 1.5 kWh of electricity for one dollar of GDP (at constant prices). Vietnam is becoming a net energy importer with an estimated 31% of its energy resources imported as of 2020 as a result of increased demand, especially for electricity.[85] Vietnam has substantial potential for renewable energy, especially solar photovoltaic, wind, biomass, and small hydropower. However, current renewable energy generation, apart from small hydropower generation, is negligible. Major FDI projects are waiting to be implemented all over the Southeast Asian region but despite its huge potential, most renewable energy resources are largely untapped in Vietnam. A transition to a low carbon economy would also benefit the country through job creation and infrastructure development.
  [82] Viet nam Energy Sector Assessment, Strategy and Road Map (ADB, December 2015)
  [83] Ibid
  [84] 2016 and 2017 Whitebook of EuroCham on trade and investment issues and recommendations
  [85] Ibid
10. Burma is rich in renewables and has high reliance on biomass and hydro, but old power systems and droughts cause power shortages and some areas lack access. Coal usage is on the increase to meet energy demand, growing an average of 21% per annum from 2000-2012.[86] Less than 1/3 of the population has access to electricity, and the electricity grid has insufficient capacity to power reliably those it does reach (still rolling power cuts across Yangon in the hot season). The grid itself has huge capacity issues and has been poorly maintained. Electricity, especially in rural areas, is often supplied by diesel power generation which produces energy at 3 to 10 times the cost of other larger-scale solutions. Burma lacks power infrastructure, government capacity and technical expertise to drive forward the policies, regulations and standards required. Areas such as energy efficiency (Minimum Energy Performance standards etc.) and energy labelling are at an early stage but offer potential for huge savings. The poorest people in Burma pay the highest price for electricity; but the country more broadly is highly dependent on basic sources for cooking and lighting – traditional charcoal, animal dung, other biomass and candles. Ironically, it is thought that Burma could power itself using alternative energy alone, thanks to its significant domestic resources in hydro, wind and solar. Burma also has huge potential in oil and gas. The pricing of electricity is hugely problematic and heavily subsidised. The government loses money on each unit of electricity sold, with estimates annually of a $300 million shortfall. Consumers in Burma are paying about half that of their counterparts in Thailand, and Burmese rates are less than a third of those in ASEAN overall. Efforts to increase consumer rates are unpopular, are met with resistance and will impact the poorest the most.
  [86] OECD
11. Indonesia is Southeast Asia’s largest energy producer and consumer. It is the world’s 5th largest emitter of greenhouse gases. Energy demand is growing annually by around seven percent. Most of this demand is met by fossil fuels, driving rapidly rising emissions. Indonesia has huge renewable energy potential; including the world’s greatest geothermal energy resource, but only 11% of primary energy comes from renewables. Indonesia plans to increase this to 23% by 2025. On current trends energy has the potential to overtake forestry and land-use as the leading source of GHG emissions by 2030. The relationship between energy and poverty in Indonesia is a close one[87] as 8.8% of total household spending is on energy. Utilising the multi-dimensional poverty approach, while health is still the major contributor to poverty (12%), lack of access to cooking fuel stands as the second biggest contributor (9.5%). Moreover, although access to electricity is relatively small in relation to other dimensions (1.8%), it is important given that it is a critical input into the production processes of most sectors and compounds deprivation in other poverty dimensions.
  [87] World Bank, 2015
12. Our analysis, including consideration of impact on development, poverty and gender shows common themes of:
  1. Increasing energy demand;
  2. Need for improved and more interconnected energy infrastructure;
  3. Recognition by governments that development of renewable energy is critical for future energy development;
  4. A lack of capacity and finance to roll out renewables at a fast-enough rate to cover this demand;
  5. Increased use of coal making it more difficult to meet emissions targets;
  6. Environmental risks associated with current energy usage, including vulnerability to climate change and health ;
  7. Gaps in or lack of implementation of energy polices to expedite low carbon transition (including policies and regulations around energy efficiency);
  8. BAU energy picture representing potential negative impacts on poverty reduction and gender equality.
Energy access was identified as a key barrier to growth in South East Asia. In the main middle-income countries of South East Asia under this proposed programme,[88] there is 100% or near full coverage in Thailand, Malaysia, Indonesia and Vietnam. The Philippines has near total urban coverage, but only about 80% access to electricity in rural areas, particularly on remoter islands. Burma is the exception, with only about 58% of the urban population having access to electricity and 49% of rural population. However, good energy coverage does not take into account affordability and security of supply. In some rural parts of PF6 countries, biomass is still the main energy fuel for households. Conventional energy prices - such as electricity and coal – remain high. Poor grid infrastructure can make energy delivery unreliable in remote areas, with regular blackouts. Further development of efficient, clean and decentralised energy sources is therefore critical to achieve full and quality energy coverage.
[88] World Bank Databank 2015
### UK energy expertise
1. The UK’s deep experience, institutional and commercial expertise means it is well-placed to support South East Asia’s energy and low carbon economy ambitions. Existing BEIS and FCO low carbon projects provide a base from which to develop a larger programme of engagement. Through the CCE network (with dedicated climate and energy attachés in Thailand, the Philippines, Malaysia, Vietnam and Indonesia), and relationships forged through ICF initiatives and the NAMA Faculty, our Posts have an established network of contacts in the relevant energy, environmental, planning and financial ministries – and other energy-related stakeholders – with which to discuss and develop the proposed programme.
2. According to ICF Consulting,[89] the UK’s key low carbon and energy capabilities are:
  [89] Analysis based on ICF, 2017 study: Low-carbon energy scoping study, commissioned by the UK Government Foreign Commonwealth Office.
Table 3: UK’s key low carbon and energy capabilities
World leading:	Strong:
Green finance	Professional and technical services
Offshore wind	Smart energy
	Gas (as a transition fuel)

### What energy focus in SE Asia would best meet PF objectives?
1. The Carbon Trust was commissioned to make a quantitative and qualitative analysis and prioritisation of low carbon programme areas which would most effectively deliver primary and secondary benefits: increasing economic growth and reducing poverty, and provide opportunities for international, including UK companies. The analysis took into account the energy barriers to growth identified above, and the common themes of the 6 countries included in the programme. It included 60 in-country interviews and 10 UK interviews with Ministries, development partners, private sector, NGOs.
2. The categories proposed by interviewees in-country and in the UK were:
- Energy efficiency;
- Green Finance;
- Electricity networks including storage;
- Utility scale renewable energy (i.e. not private solar or mini grids));
- LNG;
- Waste-to-energy;
- Low carbon cities including island pilots;
- Cross-cutting renewable energy (rural electrification);
- Non-power renewable energy use in rural areas;
- Geothermal;
- Bioenergy; and
- Wind and Solar energy.
These were each assessed as low/medium/high (turned into a numerical ranking) against the following criteria:
  - Host government priority;
  - Donor support gap;
  - Emissions reduction; and
  - Opportunities for international, including UK companies
Table 4: Assessment results of Carbon Trust survey based on criteria, converted to numerical weighting
Intervention	Indonesia	Malaysia	Burma	Philippines	Thailand	Vietnam	Ranking
Energy efficiency	2.5	2.5	2.5	2	3	2.5	15
Green Finance	3	2.5	2.5	1	2.5	2.5	14
Electricity networks including storage	1	2	2.5	2.5	1	2.5	11.5
Cross-cutting renewable energy: utility scale	2	2	2.5	2.5	1	1	11
LNG	1	2.5	2	2	2.5	1	11
Waste-to-energy	2.5	2	1	1	1	2	9.5
Low carbon cities including island pilots	1	2	1	1	2.5	1	8.5
Cross-cutting renewable energy: rural electrification	2	1	2	1	1	1	8
Non-Power Renewable Energy Use in Rural Areas	1	1	2	1	2	1	8
Geothermal	2	1	1	2	1	1	8
Bioenergy	1	1	1	2.5	1	1	7.5
Wind Energy	1	1	1	1	1.5	2	7.5
Transport	1	1	1	1	1	2	7

1. From this analysis, we narrowed the field to the 4 top options: Energy efficiency, Green Finance, Electricity networks including storage; Cross-cutting renewable energy.[90] The 4 highest scoring categories, leaving out LNG, were outlined in the concept note submitted to and agreed by Ministers. However, further work to cost these 4 strands concluded that resources would be spread too thinly, risking fragmentation of the programme and reducing the ambition more to one or two interventions in the region rather than the more ambitious programme of activity that the PF Years 2-5 envisages.
  [90] LNG, which scored joint 4th on the above matrix was discounted as interventions would not be applicable in all the priority countries.
2. PF6 posts were therefore asked to limit their preferences, checking again with host governments their priorities. The top two chosen options, by a clear margin, were: Energy Efficiency and Green Finance.
3. The interventions within the 2 components were again selected on the basis of detailed discussions with host governments and stakeholders during the scoping phase. Common threads throughout the target countries were: a) requests for technical and policy support on accessing increased investment in low carbon energy projects and (b) improving and embedding the policy, regulatory and technical support to improve energy efficiency. Delivery of these ambitions also benefits regional energy security and inequalities, through developing greater diversity of energy supply, reduced demand for fossil fuels, and more distributed availability. Both components of the programme are inherently politically and economically attractive (despite some vested interests in some countries) and likely to gain “buy-in”: increased energy efficiency and greater private sector investment are “no cost” policy objectives that increase economic activity and boost competitiveness.
4. The table below summaries the PF6 countries’ energy efficiency and renewable energy ambitions, and the investment calculated to provide these.
Table 5: Summary of countries' EE and renewable energy ambitions and implied investment need to 2030
Country	National energy efficiency and conservation target	Implied cumulative energy savings by 2030 (TWh)	Renewable energy target	Investment need, undiscounted, cumulative to 2030 (£ billion)
Burma	Achieve energy savings equivalent to 15% of annual final demand relative to BAU across all sectors by 2020	309	15% - 20% RE share in installed capacity by 2030	36
Indonesia	Not applicable for this programme	1045	23% RE share in the final energy mix by 2025	411
Malaysia	11th National Energy Plan: reduce energy consumption at 8% in 3 sectors by 2025 (residential, commercial and industry)	140	2 GW RE installed capacity by 2030	10
Philippines	Achieve energy savings equivalent to 15% of annual final demand relative to BAU across all sectors by 2020	542	26 GW RE installed capacity by 2030	124
Thailand	Energy Efficiency Plan 2015: reduce energy intensity by 30% by 2036	4,083	30% new RE share in total energy consumption by 2030	119
Vietnam	EE central part of INDC	930	32% new RE share in electricity production by 2030	97

##### Why green finance?
1. Green finance has been identified by the UN as essential to low carbon development. Financial resources[91] will be needed to implement energy transformations, especially to deliver ambitious global climate plans and Nationally Determined Contributions (NDCs). Countries or aid agencies alone cannot service this financial requirement. Increasing access to finance, and policy and regulatory reform can achieve a step-change in the way energy systems are structured and regulated. It will underpin a shift from an energy system based upon an unsustainable, outdated, centralised, fossil fuel dominated structure, to more sustainable, more balanced, decentralised, and inclusive energy system and pattern of growth. UNEP recently affirmed that, “Financial sustainable development is an urgent, universal imperative. Private capital will be a major contributor in financing the achievement of the Sustainable Development Goals by 2030 and climate commitments following from the successful agreement in Paris.”[92]
  [91] In the New Policies Scenario, $2.9 trillion of investment in energy for South East Asia is needed in the period to 2040.
  [92] Green Finance For Developing Countries, UNEP (2016)
2. Green finance’s role in enabling low-carbon exports fits with the intermediate outcome of innovation and knowledge transfer of low-carbon technologies and the outcome of promoting a sustainable growth path. The green finance programme will directly address climate change, which if left unaddressed, will act as a risk multiplier and drag on global growth.
#### SE Asia green finance needs
1. There is huge untapped potential in renewable resources needing funding beyond each country’s budget or aid coffers. South East Asia’s energy savings targets are ambitious and will require £207 billion in investment to build the necessary enabling environment to attract flows of private capital for clean energy projects and other environmental initiatives.[93] Green finance is an opportunity for PF6 countries, for relevant ministries, local and regional banks and project developers to tap into - but stakeholders need support to understand, evaluate and access the opportunities it presents. At the other end of the pipeline, green finance investors see increased risks when clear standards, regulatory frameworks and technical capacity are lacking. This contributes to an estimation of heighted risk for green finance provision in the area, which disincentivises activity to develop an effective pipeline of sustainable projects.
  [93] IEA
2. The key constraints a green finance component of the programme can address are:
- Policy/implementation gaps – by developing standards and strengthening operational systems required to turn policy into action;
- Capacity gaps – by strengthening skills, developing guidelines, understanding process;
- Finance gaps – by providing support on how to access resources and innovative financing mechanisms, thus generating a more effective pipeline of credible projects
Key interventions would include a roadmap to understand and address the barriers to accessing green finance across the region; training to project developers, governments and financial institutions; provision of policy support to improve and harmonise standards and incorporate them into countries’ policy and regulatory frameworks; work to broker specific projects with suitable finance.
##### Impact of the green finance component
The extensive needs of PF6 countries coupled with excellent expertise could bring significant impact. This would include:
- Increased flows of green finance to recipient countries;
- Improved private sector capability in recipient countries’ financial institutions (FIs) and project developers;
- Developed policy and regulatory frameworks to create an enabling environment that incentivises investment in green infrastructure and encourages international trade;
- Increased investment in low carbon infrastructure;
- Greater economic growth – an average of 0.25% increased GDP growth over the period to 2030 in recipient countries;[94]
  [94] See Economic Appraisal Case
Facilitating greater green investment will have a positive impact on poverty and gender equality in the following ways:
- Reduced carbon emissions will help mitigate the effects of climate change. Evidence shows that the poor and women stand to be the most affected by climate change.
- Increased energy supply, will improve energy access with concomitant benefits of improved health and education.
- Cost saving to governments, business and households, as renewable investments become cheaper than fossil fuels. Money saved can be channelled to other areas such as health, education.
- A diverse and decentralised range of low carbon energy projects and industries, providing local employment, including for women.
- Speeding the decline of coal, other fossil fuels and biomass, bringing significant health benefits.
### UK green finance expertise
1. The UK’s expertise on green finance, through the City of London, is unrivalled, and recognised globally. The UK is the number one provider of financial services. London ranks as the world’s top financial centre by GFCI 20 rating.[95] Globally, the UK is the largest net exporter of financial services – it accounts for 21% of financial exports.[96] One third of global clean energy projects from 2007 to 2012 had legal and financial advice from the UK.[97] The London Stock Exchange (LSE) leads the way in innovative green financial instruments and products. The Green Finance Initiative (GFI),[98] coordinated by the City of London, brings together international expertise to provide leadership on green finance and advocate for specific regulatory and policy proposals to enhance the sector worldwide.
  [95] Global Financial Centres Index
  [96] 2015 data from Trademap.org
  [97] The size and performance of the UK low carbon economy (BIS, 2015)
  [98] Green Finance Initiative 2017
2. A UNEP study recognises the City of London’s role to develop “sustainable finance initiatives that are setting the agenda both domestically and internationally.”[99] Considerable investment in low carbon energy technologies in the UK means that the UK investors are familiar with green investment. The UK offers a broad range of investors with different risk appetites – and accordingly, a diverse offering of capital types. Associated with this commercial acumen, the UK has deep insight into the policy and regulatory frameworks that can drive GF. This experience and expertise lies both within government and the private sector. The UK experience with finance policies that incentivise green investment – from the then Green Investment Bank to the Climate Change Levy and the EU Emissions Trading Scheme and various credit, fiscal and financing policies for the green private, banking and finance sectors – positions the UK as a credible expert in the area of policy and regulatory support. Under the GF component, experts, contracted under a fair and competitive tender process will provide policy and advisory support to local governments and capacity building to local companies.
  [99] The United Kingdom: Global hub, local dynamics (UNEP, 2016)
3. The programme will create opportunities for international, including UK businesses through:
- Accelerating the growth of ‘frontier’ markets, through creating a stronger enabling environment for green projects
- Transaction fees for the increased number of green finance deals
- Increasing market access. As markets develop they tend to become more open to global markets
- Creating opportunities that international and UK companies can bid for
##### Why energy efficiency?
The IEA considers that “Harnessing the potential of energy efficiency is key to transitioning to a sustainable and secure energy system that generates prosperity for our world.”[100] Efficiency is central to making progress on decarbonisation and energy security, while also fostering economic and social development.[101] There is strong evidence that improving energy efficiency has a direct impact on job creation, both in the short and longer term. While supporting the construction and technology industries in short run, it also reduces unnecessary energy spending, which allows redirecting such investment to other industries. The American Council for an Energy Efficient Economy (ACEEE) estimates that, for each million (US$) spent in energy efficiency, about 30 jobs are supported as result of both short term and long-term effects (average for 1 million spent (US$) is 17 job supported)[102]. In addition, greater energy efficiency increases prosperity, reduces poverty (more affordable bills) and reduces reliance on fossil fuels, with their impact on climate change and health.
[100] IEA Energy Efficiency Market Report 2016
[101] Market-based Instruments for Energy efficiency, OECD/OEA 2017
[102] Fact sheet: How does Energy Efficiency create jobs?, ACEEE, (2011)

1. Energy efficiency remains a key pillar of the UN Sustainable Energy for All initiative – aiming since its inception to double the rate of improvement of energy efficiency worldwide. According to the 2016 International Energy Efficiency Scorecard, developing countries have greater potential to build energy efficiency into their continued economic growth.
  Figure 2 - Benefits of Energy Efficiency Improvement

2. The IEA highlights[103] the central role of policy in driving energy efficiency, with the biggest global gains in energy efficiency linked to mandatory policy instruments such as Minimum Energy Performance Standards – MEPS [104]– a core element of our proposed programme. The figure above shows the multiple benefits of energy efficiency, including the benefits to economic development.
  [103] IEA Energy Efficiency Market report 2016
  [104] A MEPS is a specification, containing a number of performance requirements for an energy-using device, that effectively limits the maximum amount of energy that may be consumed by a product in performing a specified task.
#### SE Asia Energy Efficiency needs
1. UNESCAP considers energy efficiency in Asia as the logical first step in the energy transition. Energy efficiency measures in the region could save 35% of energy consumption over the business-as-usual case by 2035.[105] Asia and the Pacific remained the most energy-intensive region in 2014.[106] Improving energy efficiency requires countries to overcome market barriers that prevent consumers and companies from purchasing the most efficient equipment and appliances. These barriers include market failures and imperfections; consumer attention to first costs rather than life-cycle costs; attitudes, behaviours and misinformation; and fiscal policies that discourage gains in energy productivity or reward inefficient energy consumption. These barriers often require government interventions to make labelling mandatory, set national and sector-wide energy efficiency targets and establish the legal frameworks necessary to implement and enforce mandates.
  [105] Asia Pacific: Response to Climate Change, (UNESCAP, December 2015)
  [106] International Renewable Energy Agency, Renewable Power Generation Costs in 2014 (Bonn, 2015)
2. The IEA[107] reports that in the buildings sector, mandatory minimum energy performance standards (MEPS) for appliances, including equipment and lighting, have proven to be one of the most cost-effective energy efficiency measures in many parts of the world, but only half of the countries in Southeast Asia have introduced MEPS. It advocates development of roadmaps setting increasingly stringent standards over time. The IEA advocates that harmonisation of standards across the region would provide equipment and appliance manufacturers with larger market opportunities and reduce the cost of meeting standards, while also lowering consumer costs.
  [107] Southeast Asia Energy Outlook 2015 (IEA 2015)
3. The components of the programme work well also alongside ASEAN’s objectives on energy efficiency. ASEAN’s AEC Blueprint 2025 intends to “Reduce energy intensity in ASEAN by 20% as a medium-term target in 2020 and 30% as a long-term target in 2025 based on 2005 levels”, with the following specific actions outlines for 2016-2020 (good synergies with our programme):
- Develop regional policy and roadmap for MEPS implementation;
- Develop national policy and roadmap for MEPS implementation, including Mutual Recognition Arrangement on testing methods of energy efficiency (EE) standards for air conditioning;
- Develop draft guidelines on ASEAN green building code and promotional scheme;
- Draft guidelines to finance energy efficiency projects;
- Create a pilot project to finance energy efficiency.
1. Efforts to harmonise energy standards have been initiated by the ASEAN Centre for Energy (ACE), but there remains huge potential for further progress to be made. The IEA recommends closer collaboration among member countries through sharing experiences in administration, testing and monitoring activities.
2. ESCAP Asia and Pacific Energy Forum’s 2014-2018 plan of action[108] which includes ideas for:
  [108] Report of the Asian and Pacific Energy Forum, (UN ECSC, July 2013), E/ESCAP/APEF/3
- Strengthening energy efficiency targets and action plans;
- Increasing energy efficiency in mechanical systems, appliances and lighting;
- Promoting harmonized energy efficiency and conservation policies and regulations, codes and standards.
The key constraints an energy efficiency component of the programme would address are:
- Policy/implementation gaps – by developing standards and frameworks to improve energy efficiency plans and strengthening operational systems required to turn policy into action;
- Capacity gaps – by strengthening skills, developing guidelines, understanding process;
- Finance gaps – by providing support on how to access resources for energy efficient projects
#### Impact of the energy efficiency component
The identified needs of the target countries coupled with expertise provided through the programme, could bring significant impact, especially over the medium to longer term. This would include:
- A regulatory framework which incentivises EE and supports action;
- Emissions reductions from EE;
- Greater regional investment in higher performance goods; and
- Increased market for goods and services.
Facilitating greater energy efficiency will have a positive impact on poverty and gender equality in the following ways:
- Reduced carbon emissions will help mitigate the effects of climate change. Evidence shows that the poor and women stand to be the most affected by climate change.
- Efficient energy use will reduce need for coal, and its health impacts.
- Cost saving to governments, business and households. Money saved can be channelled to other areas such as health, education.
#### UK energy efficiency expertise
Recent Prosperity Fund support has helped many countries in SE Asia develop their emissions reductions pledges (INDCs) for the Paris COP, creating strong government and private sector relationships that can be built upon to deliver a new programme. The UK is seen as a world leader due to its own policy and regulatory framework and can be referred to as a useful case study. Equally, the UK is home to many world-leading companies that offer relevant products and services in energy efficiency, green architecture and energy efficiency engineering and consultancy services. As SE Asia’s economies develop on a lower carbon trajectory, with significant urban development in particular, there will be a growing market for high standard energy efficient products and services. The increased emphasis in the UK on energy efficiency, both in the Clean Growth Strategy and Industrial Strategy should provide a useful platform of policy engagement on which we can build.
### Synergies within the programme
1. Green finance and energy efficiency work well in synergy: the green finance component can include financing to support energy efficiency projects. These projects will often be in the industrial sector – an area where there is particular potential for secondary benefit - given that large EE projects are often most suitable for green finance as the size of capital has to be large to attract the investment. Large-scale energy efficiency projects often need PPP funding creating a market for advising on and implementing finance mechanisms for infrastructure projects.
  Figure 3: Green Finance and Energy Efficiency Synergy
2. Furthermore, the utility scale renewable energy option, included in the concept note, can be considered addressed through the green finance interventions to improve the environment for renewable energy projects, and to help bring them to market. Error! Reference source not found.Error! Reference source not found.3 illustrates this:
### How a programme on green finance and energy efficiency adds value to the work of others and existing HMG activity
1. There are many donor initiatives focusing on Low Carbon Energy in SE Asia. Some, such as the UN and World Bank initiatives are more regional; others are more country-based but could be scaled up or replicated elsewhere. On-going coordination will be critical to ensure that the proposed programme maximises complementarities and potential synergies with the work of others.
2. Examples of other donor/NGO initiatives which may have potential for collaboration include the following:
Green Finance
- ICF proposed Sustainable Infrastructure Programme
- SEA Energy Transformation Programme (SEAETP) initiative
- UNDP “seed funds” project helping finance for renewable energy projects;
- Work by the International Capital Markets Association (ICMA) to establish an ASEAN standard for green bonds;
- NDC Financing workshops;
- Work by the Sustainable Insurance Forum, and its Principles for Sustainable Insurance;
- ICF technical assistance to support Climate Investment Programmes;
- IFC capacity building for green finance stakeholders;
- Green Investment Group proposed fund in Philippines, Malaysia and Indonesia.
Energy efficiency
- ASEAN SHINE –work on MEPS for air conditioning and lighting.
- EU SWITCH programme on increasing the deployment of high efficiency motors.
- UNIDO work on industrial and SME energy efficiency in the region
- Green Investment Facility, credit line for EE.
- IFC scheme in Vietnam to pre-approve energy efficient equipment.
1. An extensive consultation process was undertaken to inform this programme and gain buy-in with key actors in Malaysia, Thailand, the Philippines, Vietnam and Burma. In the recipient countries, we engaged with a total of 92 organisations or governmental departments, conducting interviews to understand the recipient country’s needs and to identify appropriate programmes that have buy-in. Of these 92, 37 were key government departments, such as the department for energy; 39 were international donors, such as the World Bank; and the remaining 16 were with key NGOs and private sector actors operating in the region. There was good engagement with governments and other potential stakeholders during the Carbon Trust’s scoping study discussions and with our Posts subsequently.
2. In the UK, we contacted 26 trade associations to assess the UK’s capability across low carbon technologies. We contacted over ten individuals in organisations to assess the UK’s expertise in GF and potential activities in this area.
3. Working at a national level in the key PF6 countries would support ASEAN’s work for the whole region. Our work would help bring every country up to the AEC standards. Different countries have different needs but working with the countries identified could work with earlier movers to set and embed standards, and work with those needing more support would help lift them to the required level, working eventually to harmonise policies and practices around a common approach or standard. Although the initial focus of the programme would be on the Malaysia, Thailand, the Philippines, Vietnam and Burma[109] we would go with the grain if there was scope to push out initiatives under an ASEAN umbrella, most likely as different interventions gain traction over the course of the four-year programme.
  [109] See Country Rationale Section
## Impact description – the headline results the programme will target
## Theory of change
The programme will use the UK’s knowledge, international network, convening power, brokering ability, relationships and technical assistance blended with inputs from partners including contracted implementers, governments in the region and HMG departments to deliver transformational change in the two components identified in the strategic case. The central aim of the ASEAN Low Carbon Energy programme is sustainable growth through increased Energy Efficiency & adoption of Low Carbon Energy, including through the use of Green Finance. The programme will also contribute towards greater investment and trade flows between ASEAN and the rest of the world; and all five intermediate outcomes of the PF’s Theory of Change below:
- Increased investment in low carbon infrastructure and associated low carbon capital
- Improved innovation and knowledge transfer of low carbon technologies
- Trade, financial and economic reform
- Improved policy and regulatory capacity
- Ease of doing business improved
The proposed programme provides policy support, capacity building and technical assistance to:
- Support the selected countries in greening their financial systems
- Build the necessary enabling environment to attract flows of private capital for clean energy projects and other environmental initiatives;
- Strengthen regional energy security by ensuring a more diverse energy supply, reducing energy demand and the cost to business/consumers;
- Reduce adverse health, economic and environmental impacts;
- Act as a catalyst to better regulatory energy efficiency practices such as MEPS;
- Help industry to identify and change areas of energy inefficiencies, seeking to encourage and harmonise best practice across the region;
- Enable countries to take significant strides towards the achievement of their Sustainable Development Goals as well as Nationally Determined Contributions (NDCs) under the Paris Agreement and drive considerable carbon savings;
- Contribute to a cumulative carbon saving of 13.9MtCO2e across the region over the appraisal period, which has a present value £456m.[110]
  [110] This is the present value of the primary benefits, see economic appraisal.
1. The Programme will take care to comply with the International Development Gender Equality Act 2014. In considering the interventions and establishing the KPIs with the lead implementer we will assess the impacts (benefits and losses) of interventions on women and men and the relationship between them. The SRO will only approve initiatives where they are confident that they will not cause harm or worsen discrimination. We have identified opportunities to engage and harness the potential of women to deliver the programme and this will be an important requirement in the procurement process and throughout the life of the programme.
2. Poverty and inequality will be reduced through:
- Indirect income increases (through job creation, increasing productivity, rising wages)
- Price reductions (through greater competitiveness, efficiencies, improved market access)
- Improved access to basic services (more reliable and sustainable energy)
- Improved air quality environment
- Higher quality products and services

## Low Carbon Energy Programme Theory of Change

Table 6: Programme Key Assumptions
OUTCOME ASSUMPTIONS	JUSTIFICATION
Government initiatives / commitment continues	The programme is focussing in areas where there is clear development need and consensus for continued government action.
Capacity and skills are used and retained after the programme ends	Stakeholders will be treated as clients, ensuring they play an active role in programme design. Flexible approach in order to tailor the necessary implementation support, which must be client led.
Private sector responds to the opportunity	Continuous business engagement and past programme performance provide evidence of private sector appetite in the focus sectors, as well as evidence of what barriers the programme must address in order to improve this and translate it into commercial benefits.(non-ODA activity)
Scale up beyond specific project benefits	Effective demonstrator projects in high demand sectors should result in both validated learning and a reduction in perceived risk.
Buy in from central and state government	The programme is focussing in areas where government initiatives are active and demand for assistance is high
Buy in from HMG partners continues	HMG partners have been engaged, are enthused and have participated in previous relevant work in these areas.
Access to the right officials, regulators, businesses	Posts across SE Asia have good relationships with a wide range of key stakeholders, built up over many years, and especially in PF Year 1. There is no reason to believe this should change. South East Asia is a priority for the UK government and high level UK ministerial engagement will continue to facilitate access for UK officials.
Suitable private sectors partners can be found	The market is well developed and the potential commercial spin offs from the work should make it an attractive proposition for suppliers.
Reducing gender inequality	The Programme benefits are expected to positively impact women by creating conditions for inclusive economic growth and job creation likely to attract women.

1. Working with suppliers, the programme will be informed by gender and inequality assessments, ensuring that opportunities are taken to shape activities to further inclusivity aims. See Management case for more detail.
2. Furthermore, tackling the challenges outlined will make an important contribution to South East Asia’s efforts to meet the UN Sustainable Development Goals, particularly SDG 7 (Energy) and SDG 13 (Climate Action).
3. The programme will deliver secondary benefits internationally and to the UK in the form of increased trade flows in Green Finance, Energy Efficiency and Low Carbon technology with SE Asia; and increased influence with host governments.
# Appraisal Case
## Summary
The Appraisal Case builds on the strategic case presented above by:
- Assessing the main options for delivering effective interventions; and
- Outlining the available evidence of expected impact of the programme.
1. The strategic case set out the case for the countries in the programme and the barriers this programme will seek to address. The appraisal case will undertake the following:
  1. Assessing programme options - Make a qualitative assessment to identify the programme option that will best deliver the identified objectives the programme seeks to address.
  2. Quantifying a base-case - Make a quantitative assessment as a base-case of the benefits and costs of the proposed programme based on the identified programme option. This will include sensitivity analysis of the core assumptions.
  3. Shortlisting key delivery options - Based on a qualitative assessment, analyse a range of delivery options from utilising solely commercial or multilateral organisations as delivery partners, or whether to expand the delivery of the programme to a mixed model that also includes multilateral organisations and government-to-government work.
  4. Identifying the final proposed option - Assess how the base-case will be influenced by the delivery mechanism chosen and the associated level of risk and ability for HMG to control outputs. This assessment will also consider how well the delivery model can tackle national barriers and regional barriers.
## Assessing Programme Options
#### Overview
Our consultations identified that overall for the selected countries in South East Asia, the strands of Green Finance and Energy Efficiency were the priority interventions to achieve regional sustainable and inclusive economic growth plus secondary benefits. These two components will help drive the deployment of low carbon energy technologies in the region through addressing the following barriers:
Table 7: Barriers targeted by the Programme
Component	Barriers targeted by the programme
Green Finance	Lack of capacity in financial institutions and low risk appetite and understanding of green finance instruments e.g. green bonds and financing for EE / Lack of project developer experience in accessing commercial finance / Lack of standardised definitions of green projects / Limited pipeline of bankable projects
Energy Efficiency	Lack of regulatory certainty lack of measurement, reporting and verification systems, and unified product standards / Lack of a regional approach to energy performance standards / Unfamiliarity with the technical requirements or benefits of EE in less developed markets / Lack of trust in products suppliers and service providers, immature supply chains and markets

The appraisal case assesses 3 programme design options to meet the needs identified. It calculates the potential costs and the potential primary and secondary benefits that could be achieved. It also appraises a number of mechanisms available to deliver effectively and efficiently the interventions proposed.
## Programme design appraisal
Option 1: Do nothing
A base case which assumes business as usual in the target countries. Individual countries and ASEAN as a whole would make some progress in line with their national energy efficiency and conservation targets and their targets for renewable energy, including through accessing some of the required external financing to support their low carbon transition. Under this option the pace of poverty reduction, sustainable economic development, and progress towards low carbon goals would differ from the other options set out below. The growth of the economy and specific energy targets would be in line with IMF forecasts and national plans. From a UK perspective, we would expect export and investment UK market share around green finance and energy efficient goods and services to remain stable.
Option 2 (recommended option)
A package of interventions across the target countries focussing on green finance and energy efficiency, as identified as the key areas for intervention in the Carbon Trust scoping study, and confirmed by governments in the region. The interventions recommended reflect in particular those raised most clearly by host governments in the course of discussions during the scoping. The initial market assessment work would produce a matrix which recognised which interventions would create most impact in each country, and ensure that each country had a relatively equitable basket of interventions overall. These interventions - to be tested and refined during the inception phase of the programme to ensure up to the minute relevance and impact - would be likely to include (though not necessarily be limited to) some or all of the following:
Green Finance
- A market assessment of each country’s needs of green finance, knowledge and capacity level; mapping where needs match with other PF6 countries in the region to synergise the programme (and/or where working alongside ASEAN might be more beneficial); where we can best intervene independently and where we can work with other donors or initiatives to add value;
- Capacity building across the region.  A limited number of local initiatives to provide training in green finance. All key stakeholders highlighted that there is a critical need for additional training in this space. This programme will build upon on-going activities – using the “market assessment” as a baseline – to add value;
- An assessment of the barriers to a smoother pipeline of green finance between PF6 countries and financiers, and a road map to address these;
- Policy work and advice in SE Asia to support a more enabling environment for green finance: for example, guidelines/advice to improve cooperation between finance and environmental ministries on green finance policies;
- Work to look at how to rationalise green “standards” in region, whether through new initiatives or working with the grain on nascent domestic or regional standards (such as ASEAN green bond standard championed by ICMA). This programme will try to ensure that recipient countries’ standards are harmonised – crucial to avoid the risk that countries choose divergent, incomparable definitions;
- Specific work to develop and strengthen countries’ Climate Investment Plans to facilitate financial planning towards achievement of Paris commitments;
- Specific work to identify and “match” particular projects in each country with the most appropriate green financier;
- Identification of particular strands of green finance work to pilot in a country and then roll out (for example, green insurance perhaps in the Philippines; capital market green finance in Malaysia; green FinTech products (perhaps in Thailand);
- Awareness raising in UK of green finance needs of PF6 countries, together with work to identify and mitigate risk (or perception of risk) and other barriers;
- Awareness raising in SE Asia of the green finance offers available, and how to access them. This could be through initiated events such as a Wilton Park conference, or through support for engagement in regional events such as Asia Clean Energy Forum in Philippines.
Energy efficiency
- A market assessment of each country’s energy efficiency profiles, requirements, level of policy development and enforcement, knowledge and capacity level; where their needs map with other PF6 countries to find intervention synergies (and/or where working alongside ASEAN might be more beneficial); where we can best intervene independently and where we can work with other donors or initiatives to add value.
- Policy and regulatory support to government, agencies and other bodies. Including development of MEPS and HEPS, building off existing work to develop standards in some countries (e.g. Thailand’s Energy Efficiency Plan)
- Support on other regulatory measures (e.g. labelling, packaging), with a view to identifying and harmonising standards that work across ASEAN
- Establish framework for management and development of an Energy Technology List if an individual country or ASEAN wished to adopt one) to list best-in-class companies and suppliers of EE technology to reduce barriers to uptake of more energy efficient equipment and technologies, improve compliance and build consumer confidence.
- A deeper dive on the energy efficiency of one or two industries to assess ways to reduce energy through implementation of standards (such as the NAMA work on air conditioners). We would look in particular at sectors where the UK has particular manufacturing expertise, e.g. EE lighting or double-glazing; or industries identified in the India PF energy efficiency programme scoping which might be equally applicable to SE Asia.
- Capacity building across the region, working with regulators, governments, industry, ESCOs.  This programme will build upon on-going activities – using the “market assessment” as a baseline – to add value, and include setting up an expert working group across the target countries.
- Specific work with SE Asian cities targeted under the “Future Cities” Prosperity Fund programme to build in cutting edge energy efficiency policies in urban planning and flood resistance measures.
- Support to “match” green finance needs for large energy efficiency projects in the selected countries (thus tying in with the green finance interventions of the programme).
- On-going government-to-government dialogue to drive up energy efficiency standards and global harmonisation (through attaché network at Post, relevant visitors, capitalising on visits to the UK).
- Communications and outreach strategy.
Option 3 (not recommended)
Option 3 would largely contain the same proposed basket of interventions as Option 2, focussing on capacity building and technical assistance on green finance and energy efficiency in the target countries, and including support to “match” green finance with projects. However, there would not be a deep dive on energy efficiency in particular industries, or pilot projects on particular strands of green finance. Resources saved from these interventions would instead fund significantly amplified work on the interventions on an Energy Technology List and a Green Finance Standard:
i. ETL As the EE centrepiece, Option 3 would seek to implement a bespoke ETL across the countries in scope (Malaysia, Thailand, Vietnam, Philippines and Burma) that lists international (and domestic) products that meet HEPS. This would be carried out in parallel with targeted country-level dissemination, awareness raising (including among EE manufacturers) and policy support interventions to ensure that the ETL and standards are used to drive interventions in EE, and that policies are put in place to further incentivise EE in conjunction with the ETL. This would be a much more significant intervention than the ETL intervention under Option 2, which would be purely to help an individual country to set up its own list if required, most likely towards the end of the programme after other interventions had been established. This larger-scale ETL intervention would cost about £1.8m to design and implement.
ii. A Green Standard. As the GF centrepiece, Option 3 would seek not to rationalise and advance existing moves towards establishing Green Standards in the region (as in Option 2), but instead work to design and implement a new Green Standard for projects requiring green finance, harmonised across the PF6 countries.
The ideas for a regional ETL and Green Standard were presented in the initial scoping study, though buy-in from host governments was more equivocal than for those in Option 2.
Further research also raised the following concerns:
ETL
  - Whether an ETL would actually gain traction and buy-in as a product serving part but not all of the region (might work in individual countries or across ASEAN, but the scope of the PF programme sitting between regional and national causes a challenge)
  - Mixed evidence from the UK of the tangible benefits of an ETL, particularly without specific measures to incentivise EE in conjunction with the ETL (and gaining agreement of the 5 target countries to offer standardised incentives for inclusion on the list would be unlikely)
  - Risks around legacy of a regional ETL at the end of the PF programme: who would be prepared to update and police it?
Green Finance
  - Whether a Green Standard, initiated by HMG, would actually gain traction and buy-in as a product serving the PF6 but not the entire region or globally.
- In particular, whether such a standard would conflict with other initiatives to harmonise standards around green projects, either globally or regionally – for example, ASEAN committed in March 2017 to sign up to the green bond standard championed by ICMA, and the Chinese are working on a Belt and Road green standards initiative).
- Risks around legacy of a regional Green Standard at the end of the PF programme.
## Likelihood of reform in the baseline or with HMG activity
We assess the change that the programme will achieve as compared against a “no intervention” counterfactual, by examining the current business environment and the likelihood that improvements would happen regardless in the absence of HMG support:
Table 8: Likelihood of reform or opportunity in the baseline or with HMG activity
Criteria	Baseline scenario: No Programme	With HMG Activity: Option 2 (Recommended)	With HMG Activity: Option 3
Political will / appetite for change – the extent to which governments want the changes proposed and buy into the interventions	Medium-High	High	Medium-High
	Governments in all countries vocalised the need for support in EE and GF, relating this to economic development (SDGs) and progress towards Paris Agreement goals. There is also ASEAN support.	As for the baseline scenario, but appetite likely to be strengthened by UK focus and attention. Although governments are at somewhat different stages on EE, all saw scope for regulatory and industry improvement and capacity building/TA. All welcomed better GF understanding and matchmaking	As option 2 where interventions are the same. But less appetite (or understanding) for an HMG-led regional ETL or PF6 green standard, and concerns on sustainability of this option at end of programme.
Space for change – the extent to which changes recommended are possible given the social/economic and regulatory conditions of the country concerned	Medium-High	High	Medium-High
	Countries have broad agreement that EE and private investment are to be encouraged for the benefit of economic development (SDGs) and progress on climate change. While some state-owned enterprises have vested interests (e.g. Vietnam/EVN), these against the political/economic mood: reforms are underway to remove these interests (e.g. market liberalisation)	As for the baseline option. However, the programme, by working across countries and with other donors/stakeholders may be able to create a better space for change across the region.	As for Option 2 for shared interventions. However, work ongoing in region and globally might squeeze opportunity to establish a specific PF6 green standard.
Capacity for change – the extent to which the governments /stakeholders who would need to help implement or embed recommended change have the expertise or knowledge to do so.	Low	High	Medium-High
	Governments often lack the human capacity to design and implement effective, evidence-based policy and regulatory reforms alone. Support is required to enable Governments to act on their ambitions, and to coordinate with other countries. Governments face fiscal barriers to enabling programmes and policies (e.g. Feed-in tariffs)	HMG has the resources and influence to bring about initial change. The suggested interventions will build capacity in country and across the region and are specifically geared to be self-sustaining at the end of the programme.	As Option 2 on shared interventions. However, the regional ETL list and specific PF6 green standard would stretch host government capacity, particularly in the long term, and may be too ambitious even initially to gain traction
Stage in policy-making cycle	Low-Medium	Medium-High	Medium
	Governments have a clear rationale for action in the areas of GF and EE, including poverty reduction. EE policies are underway to some extent, less so on GF. Generally governments have challenges in proceeding beyond the policy design stage as they lack capacity and expertise in these areas, particularly when trying to implement a more regional approach. Support is required to overcome this barrier, and to try to bring all countries to a similar level.	Governments have a clear rationale for action in the areas of GF and EE, including poverty reduction. Using HMG’s expertise e.g. on MEPs, green finance, would provide the support to help host governments proceed beyond the policy design stage, and harmonise across the PF6. Those PF6 countries more advanced in the policy cycle – e.g. Thailand on EE, can also be used as case studies/educators to build capacity across the region.	As for Option 2 for shared interventions. Ideas for a regional ETL or a PF6 green standard are not currently in the policy pipeline in any of the PF6 countries. There is therefore a risk that for these interventions progress is less likely.
Overall likelihood for change	Low-medium	High	Medium
	Though there are variations between countries, a generally low-medium capacity for change and an early stage in the policy-making cycle mean that policy change is likely to be slow and patchy in the absence of additional support.	Governments are supportive of the proposed interventions and, with UK support and expertise, there is strong likelihood that reform will proceed, in individual countries and in raising standards to a more common level across the target countries.	As for Option 2 on shared interventions. But there remains more risk around the interventions for a regional ETL and green standard, which have less buy in and may have difficulty being sustained beyond the programme.

#### Options analysis
Option 1
As the above table shows, the Do Nothing option has only low-medium likelihood for significant policy change. Relative to options 2 and 3, this would significantly reduce our ability to deliver both primary and secondary benefits, and allow the conditions for additional indirect benefits. Doing nothing would put us at a relative disadvantage to those countries that are providing significant support to the PF6 countries’ low carbon transition and the improved relationships this affords, and would hinder progress – and our ability to support progress – on their climate commitments. It is less likely that the region would utilise UK models or ideas to solve major energy challenges, or that international and UK businesses would link into or benefit from these reforms. The only advantages of this option would be that it poses none of the potential financial, delivery, or reputational risks associated with delivering a Prosperity Fund programme, and no administrative cost.
We therefore do not recommend the ‘Do nothing’ Option 1.
Comparison between Options 2 and 3
In essence, the decision between Option 2 and 3 is whether to include as a centrepiece of the interventions 2 directive and ambitious PF6-wide frameworks (an ETL and a Green Standard) but with a higher chance of failure, or to work more to address obvious needs identified by countries and other donors, and use adaptive programming to improve and harmonise standards in energy efficiency and green finance with stronger likelihood of success.
The risks to Option 2 compared with Option 3 are that the interventions are somewhat less of a clear package than a specifically created regional “standard” or “list” which would be a tangible means to badge the UK and the PF contribution. We would thus need to work harder to explain and promote the work we do. However, if, as we assess, the Option 3 “standard” and “list” interventions carry an unacceptable risk of failure, we would not want to tarnish HMG’s reputation by interventions that were more newsworthy yet failed to work.
Recommendation
We conclude that significant change will be slow and fragmented in the absence of intervention on green finance and energy efficiency (Option 1). We conclude that change is likely with implementation of targeted interventions on green finance and energy efficiency (Options 2 and 3) but that Option 2 gives more certainty of policy change, with Option 3’s directive interventions of an ETL and green standard constituting a greater risk to change overall. We therefore recommend Option 2’s range of interventions to deliver lasting change from the PF SE Asia Low Carbon programme. Option 2’s range of interventions to facilitate green investment and greater energy efficiencies in the target countries will have a direct impact on poverty reduction and gender equality, for reasons set out in the Strategic case.
## The proposed programme methodology
The interventions are not set in stone but will have flexibility to respond to the initial market assessment recommendations and subsequent policy developments. Depending on the initial assessment, the interventions will have varying tiers:
- PF6 wide (for GF), or across the 5 target countries (for EE as Indonesia is not included in these interventions – see Strategic case) where the level of engagement and capacity suits a common approach. At times this is likely to include working alongside ASEAN to feed into its whole region objectives. This regional approach provides good economies of scale and avoids fragmentation.
- In clutches of countries – for example working first on developing policy practices with more advanced countries (such as Thailand, Malaysia) before rolling out across the full PF6; or working first in less developed countries – e.g. Burma – to bring them up to a more common standard. This approach allows some policy support to be fast-tracked or more targeted to specific countries and avoids an unsatisfactory blanket approach whereby the intervention either has to operate at the lowest common denominator or does not match the capacity level of all the participants, thus wasting resources.
- A sliding scale approach – interventions with a series of entry points depending on country capacity/expertise. Thus all move towards the same objective but can start at different points/proceed at different rates which provides a good combination of efficient tailoring yet common purpose
- Pilot approach – identifying one country with a particular appetite or knowledge of a green finance or energy efficiency aspect which could form the basis of a pilot project for subsequent wider roll out. This could be particularly useful for the longer-term sustainability of the programme, such as where some countries lack the capacity to adopt the intervention within the PF programme window, but could develop policies as a result of the pilot in slower time.
1. Government to government contacts will be important, using the SE Asia Climate and Energy Network, other FCO and DIT colleagues, and ad hoc HMG visits – increasing programme buy-in and therefore impact, maximising leverage of government resources and expertise and increasing the uptake of policy and regulatory recommendations. There will also need to be ambitious engagement with key energy and finance organisations such as the City of London (and Green Finance Initiative), London Stock Exchange, banking and insurance regulators, the Sustainable Insurance Forum, Climate Bonds Initiative, G20 Working Group on green finance funding, ASEAN Centre for Clean Energy, and city-level authorities in PF6 countries in SE Asia (particularly those working on Future Cities development).
2. Finally, working alongside the existing donor community will be essential, and this will be fully encapsulated in the Statement of Requirements for the lead implementer.
3. It would be optimal for the programme to operate in the PF6 countries in terms of primary and secondary benefit (see strategic case). However, there would be scope to scale up the programme by up to 50% to engage more broadly with all 10 ASEAN countries, including by:
- Amplifying existing interventions (e.g. more capacity building workshops etc; target more industries re EE; matchmake more projects to finance)
- Add new interventions regarding Green Finance and Energy Efficiency (several others identified in Carbon Trust scoping; there may be ideas from EE section of India and Mexico PF programmes we could replicate)
- Include interventions also on energy systems/smart grids and renewable energy as per initial concept note
- Team up with other donor initiatives more intensively to scale up their activities in related areas
- Increased focus on work with ASEAN
- Increase geographical reach (include Indonesia on energy efficiency; include Laos and Cambodia in some intervention

## Economic Appraisal
1. The economic appraisal quantifies the likely benefits and costs of the proposed programme compared to the “do nothing” counterfactual. This quantification is a base-case. The final benefit and cost levels are likely to be influenced by the delivery mechanism chosen and the associated control and risk level, as outlined in the next section.
2. Quantified costs and benefits
The costs of the proposed programme are as set out in the financial case. The following benefits have been quantified under both the counterfactual and intervention scenarios:
Table 9: Quantified Primary and Secondary Benefits
	Quantified Primary Benefit	Quantified Secondary Benefit
Energy Efficiency Intervention	Return on investing in climate change mitigation	Increased UK energy efficiency exports to the region. Due to the nature of the proposed intervention outward investment opportunities have not been included in the secondary benefits for EE
Green Finance Intervention	Return on investing in climate change mitigation	Increased UK green exports to the region / UK return on increased outward green investment opportunities.

1. For both the energy efficiency and green finance interventions, the primary benefit is the return on investing in climate change mitigation. The Carbon Trust estimated the potential investment that could be leveraged with greater uptake of renewable energy and energy efficiency measures. In summary, their approach was to take the capacity growth needed to meet RE and EE targets for each country (MW or MWh, assessed for the primary benefits), and multiplied this by the cost of technology (£/MWh).
2. Investment will be leveraged directly via the development of a pipeline of bankable energy efficiency and green finance programmes. Energy efficiency investment will also be encouraged through embedding energy efficiency incentives in the regulatory framework, and capacity building activities with industry. Similarly green finance investment will be encouraged by increasing the capacity of commercial banks, the regulatory and policy framework, and developing Climate Investment Plans.
3. In order to quantify the primary and secondary benefits, first the overall market failure was estimated – in this case the investment and emissions savings needed to meet individual country national targets. We then considered the extent to which the proposed interventions will correct this market failure, attempting to use conservative assumptions to assess the additionality of the interventions guided by the available evidence. The scale of the overall market failure is such that even though we assume that these interventions have very low levels of additionality, the primary and secondary benefits are substantial.
4. It is acknowledged that there is a large amount of uncertainty involved in this exercise due to multiple factors at work, and the top down approach taken, so caution is advised when interpreting these results. However, based on detailed modelling and estimation we can estimate possible benefits from the programme, of the magnitude shown in the summary tables below:

Summary Tables
Table 10: Main Primary Benefits: Central Scenario
(£m)	Primary NPV / (Benefit to Cost Ratio)	Secondary NPV / (Benefit to Cost Ratio)
Energy Efficiency Intervention	61 / (10.5)	21 / (4.2)
Green Finance Intervention	181 / (24)	55 / (8.3)
TOTAL	241 / (18.2)	76 / (6.4)

*Figures may not add up to total due to rounding
Scenario Modelling
Sensitivity analysis has been conducted by varying key input assumptions, in this case the size of the market failure, and the additionality of the intervention.
Table 11: Sensitivity Analysis
(£m)	Low Sensitivity NPV	Central NPV	High Sensitivity NPV
Primary Benefits	180	241	314
Secondary Benefits	58	76	104

Risk has also been incorporated into the estimates to get the higher and lower NPV estimates below:
Table 12: Risk adjusted sensitivity analysis
(£m)	Risk-adjusted Primary NPV	Risk-adjusted Secondary NPV
High Risk	145	35
Central	181	57
Low Risk	217	94

Summary of complementary primary benefits and unquantified primary and secondary benefits
The following section sets out an additional, complementary methodology to estimate primary benefits through reduced or avoided GHGs, although we have not included these figures in our headline expected returns for the programme. This calculation shows significant carbon savings providing an additional, complementary primary benefit, particularly against the Energy Efficiency component of the programme - £279m NPV. We have assumed that these interventions have very low levels of additionality (increasing the likelihood of renewable energy and energy efficiency targets being met by just 0.5%), but nevertheless, given the size of the overall market failure, these complementary primary benefits are substantial.
Table 13: Additional Complementary Primary benefits: Central estimate
(£m)	Primary NPV
Energy Efficiency Intervention	279
Green Finance Intervention	163
TOTAL	442

In addition to the monetised benefits, are a number of benefits that have not been quantified to due to data limitations. These are summarised in the table below:
Table 14: Unquantified Primary and Secondary Benefits
	Un-quantified Primary Benefit	Un-quantified Secondary Benefit
Energy Efficiency Intervention	Cost savings to consumers due to lower energy bills / Cost savings to host governments due to avoided investment in power supplies. / Avoided reliance on imported energy / Improved air quality and health / Jobs created (for women and men) as a result of increased investment in energy efficiency / Increased level of institutional knowledge of energy efficiency issues	Greenhouse Gas (GHG) Emissions reduced or avoided (tCO2e) (emissions savings are a global public good) / Improved relationship with PF6/ASEAN countries
Green Finance Intervention	Improved environmental sustainability in sectors other than renewable energy or energy efficiency. e.g. projects to support cleaner oceans or protection of species/forestry / Avoided reliance on imported energy / Improved air quality and health / Jobs created (for women and men) as a result of increased investment in green energy. / Increased level of institutional knowledge of green finance issues	Greenhouse Gas (GHG) Emissions reduced or avoided (tCO2e) (emissions savings are a global public good) / Improved relationship with PF6/ASEAN countries

These unquantified primary and secondary benefits are expected to positively impact women’s conditions, as they tend to be more affected by poverty, lack of economic empowerment, air pollution and climate change (see Strategic case). Reducing costs of access to energy, improving environmental sustainability and creating conditions for green and inclusive growth contribute directly to improving women’s welfare.
## Analysis of delivery options
1. This part of the appraisal process considers the delivery options most effective, efficient and value for money for the programme. The final benefit and cost levels are likely to be influenced by the delivery mechanism chosen and the associated control and risk level. As such this options appraisal assesses 4 plausible options below based on a set of additional criteria, and an assessment of whether the option is likely to lead to benefits above/below/in line with the base case.
2. Our criteria are:
- Capability and capacity – Ensuring access to supplier(s) with the correct mix of expertise, contacts and networks to meet requirements. FCO having the right contract management plans, skills, resources and management information to manage contracts when they are let
- Commercial focus – Ensuring the programme includes focus on how best to access secondary benefits, including for the UK
- Value for Money – Delivering the required quality services at the best value.
- Adaptability - Retaining the ability to be flexible, move quickly to grasp opportunities and respond to emerging priorities/learning
- Control over risk and delivery – retaining level of control by Embassy/HMG over the delivery and direction of the programme
- Minimising risk of fragmentation in the programme – ensuring the programme and its interventions have application and impact across the target countries and accelerate transformational change en bloc rather than in a piecemeal, country-by-country approach
Option 1: In house delivery
This option would involve delivery of the full range of green finance and energy efficiency interventions in house.
Option 2: Delivery by multilateral partner
FCO could channel funds into other energy sector multilateral programmes. The multilateral agencies, including the World Bank, Asian Development Bank and UNDP have significant expertise and experience in energy sector programming, and are active and respected in the region. Many have existing programmes covering energy efficiency and/or green finance and have good connections to the relevant stakeholders we seek to engage. This delivery option also considers NGOs.
Option 3: Outsourced delivery split by component
This option would require award of two tenders, with one implementer to lead the green finance component, the other the energy efficiency one. This option has some merits.
Option 4: Outsourced delivery with a lead implementer either delivering the full programme or heading a consortium
This option would entail one lead implementer - likely to be a large consultancy firm with significant energy expertise - responsible for delivery of the full programme. The lead implementer could bring together a consortium of sub contractors to ensure suitable expertise across both components of the programme. This option scores most favourably against the criteria, as shown in the analysis below. We do not recommend in house delivery or delivery led by a multilateral organisation.
Table 15: Comparison of Options
Criteria in bold given double weighting: Low = 1, Medium = 2, High = 3
Option	Capability/ capacity / (primary criterion)	Commercial focus (primary criterion)	VFM	Adaptability	Control over risk/ delivery	Minimise fragmentation	Overall
1: Full in house delivery	Low -2 / Substantial staff uplift required, difficult to source staff with technical and delivery skills in both components	High -6 / Internal staff would be highly focussed on secondary benefits and have easy access to DIT	1 / see separate table below	1 / Difficult to relocate or downsize/ scale up internal staff resources quickly	2 / Mixed. Good control over risk as a short oversight chain. But control over delivery might be hampered by lack of adaptability	1 / Unless core team taking overarching approach, fragmentation risk as country leads may be parochial, not see bigger picture	13 / Lowest
2: Multilateral organisation*	Medium - 4 / Significant expertise. But perhaps less capability to retain bespoke focus just on our selected clutch of countries	Low -2 / Less interest in secondary benefit or commercial outputs	2 / see separate table below	2 / Reach across region means able to adapt reasonably but less easy to scale up/down if work enmeshed with other projects	2 / Would need to cede some control, though delivery would be reasonably assured given reputation and expertise	2 / Less of control of programme might also hinder efforts to avoid fragmentation	14
3: Outsourced delivery, separate strands*	Medium - 4 / Organisations with specialist knowledge more likely to bid. But less cross-cutting capability	High -6 / Likely to have good commercial focus	2 / see separate table below	2 / Reasonably adaptable – built into contracts. But less ability to flex between programme components	2 / Separate implementer for each strand would spread risk. But managing 2 might make delivery management more challenging	2 / Lead implementer for each strand would likely have expertise and resource to flex throughout region. But less coherence over entire programme	18
4: Outsourced delivery, consortium bid*	Medium - 4 / Lead implementer likely to be large consultancy with significant energy capability/capacity, though may have to bring in more specialists to supplement more general expertise	High -6 / Likely to have good commercial focus	3 / see separate table below	3 / Reasonably adaptable – built into contracts. Consortium approach improves ability to flex between programme components	3 / Managing 1 lead implementer may make it easier to assess risk and assure delivery	3 / Having 1 lead implementer would allow shifts between components if one risked becoming fragmented and another gained more regional traction	22 / highest

* There would be some degree of in-house work, alongside and complementary to the outsourced delivery, given the importance of government-to-government relationships
NB The first two criteria - capability & capacity, and commercial focus - are weighted doubly on the scoring matrix, as these criteria are most closely related to primary and secondary benefit and thus considered most important.
	Economy / (minimising the cost of resources used whilst having regard for quality)	Efficiency / (the relationship between outputs and the resources used to produce them)	Effectiveness / (the extent to which objectives are achieved and the relationship between actual and intended impacts of a service)	Overall VFM
Option 1	1	1	2	4 (lowest)
Option 2	2	2	2	6
Option 3	2	2	2	6
Option 4	2	3	3	8 (highest)
Explanation	Option 1 scores the lowest on economy. It would require a substantial HMG staffing uplift across the 6 countries and a central hub (likely to be Singapore). Although in-house staffing costs may be cheaper than external providers, limited flexibility means that staff may have to be recruited on a full time basis in each location. Staff would require technical skills in both components of the programme and specialised delivery expertise, including language skills, which would introduce considerable cost to HMG. / An external delivery mechanism (Option 2, 3 or 4) would score more highly on economy, as external providers would already have the expertise which doesn’t exist within Whitehall or at Posts so there would not be recruitment costs. An external provider would be able to bring staff in and out across the region depending on need and not necessarily full time in each location. From our market engagement we believe that there would be sufficient bidding interest in either option, therefore mitigating the consideration that there might be limited bidders providing less incentive for a competitively priced bid. Option 4 may be more appealing to large energy consultants, thus a more competitive, lower cost process than the two smaller contracts in option 3	In option 1 the substantial staffing requirement, including technical skills and specialised delivery expertise, makes in house delivery within the programme timeline unfeasible. Therefore this is the least efficient option. / Option 2 would be more efficient than option 1, as a multilateral delivery partner would already have the necessary skills. However multilateral projects take time to get off the ground, so option 2 would be less efficient than options 3 or 4. In comparing option 3 vs option 4, we consider that option 4 would be most efficient with potential for economies of scale and synergies across both components of the programme, and a lower administrative burden on HMG staff in the management of 1 rather than 2 contracts.	We consider that all delivery models should be effective in achieving the objectives of the programme. However, given the assessment of the other criteria above (adaptability; capability and capacity; control over risk and delivery; and minimising fragmentation) option 4 is assed to be the most likely to be effective due to the fact that it is the most adaptable with the least risk of fragmentation. / This means that the risk-adjusted NPV for option 4 would be more likely to fall within the higher end of the range presented above

Table 16: Value for Money Assessment
### Programme beneficiaries
1. The main beneficiaries of both programme components are the populations of the recipient countries in ASEAN that will benefit from their countries having energy sectors that are cleaner, more efficiency, more competitive and more sustainable. This will lead to increased likelihood of inclusive green growth, energy access and poverty reduction across the region.
2. Government departments, particularly Ministries of Energy and Ministries of Finance, would receive direct policy support and advice and help with the implementation of their NDCs, and also with attracting international climate finance.
Finally, local financial institutions and industry would be the direct recipients of capacity building and training, and be able to benefit from an improved enabling environment for clean energy projects, opening up new investment opportunities,
1. The GF component does not create fixed costs for which additional funding sources will be required. The component builds self-sustaining capability in the private and public sectors: the skills and knowledge that key stakeholders gain will be retained and ripple more broadly across the sector. Depending upon the capability levels of key stakeholders, it is possible that continued support for pipeline development is necessary on programme end. Should this be the case, funding will be sought from international donors.
2. Environmental
Both components under the programme support greater environmental sustainability. The EE component supports reduced resource use; the GF component supports a shift away from environmentally unsustainable energy technologies to more sustainable energy technologies.
1. The programme will increase the supply of clean, efficient and low carbon energy to recipient countries. Improved access to clean energy is socially desirable. We do not anticipate the programme to create a socially unsustainable situation. Policy and regulatory support will highlight the importance of building inclusive growth and social sustainability into the planning and development process. This will help ensure that the transformation to low carbon energy and increased energy efficiency encouraged by the Programme will benefit all sectors of society in the target countries.
2. The components of green finance and energy efficiency, as set out in the strategic case, have direct correlations to improved gender equality and inclusive growth. Green finance interventions can deliver improved access to energy, and better energy infrastructure, while improved energy efficiency can save resources in households, businesses and government, some of which may be rerouted to improved education, health or other investment.

### Summary Value for Money Statement
The economic appraisal shows a high return for the programme both on a primary and secondary benefits basis. This conclusion is based on conservative assumptions and evidence of the impacts of other similar programmes. VFM in delivery will be ensured through competitive procurement of implementing partners and working closely with other agencies to mobilise resources and jointly deliver greater impact. As a result the ASEAN Low Carbon Energy Prosperity Fund Programme represents a good use of UK taxpayers’ money to enable the region’s continued inclusive growth and poverty reduction and to enable international and UK companies to benefit from the resulting commercial opportunities.
# Commercial Case
The Commercial case will set out the procurement strategy and delivery mechanism by which the programme’s objectives will be achieved. It follows on from decisions taken in the Appraisal case about the best approach to doing that. It will set out the procurement pathway, a value for money assessment, the process for securing and managing delivery partners, and risk management. It will also set out the process to ensure delivery partners comply with the requirements of the IDA, including gender, and how the interventions will promote greater equality.
### Programme delivery
1. This programme will involve outsourced provision of advisory, delivery and management services to provide policy support, capacity building and technical assistance to facilitate green finance flows and improve the regulatory, policy and practical conditions for energy efficiency measures in the target countries.
2. This contract was procured via call-off from Lot B3 of the Cross-Whitehall Prosperity Fund Agreement. Lot B3 consists of 37 suppliers that have been selected based on evaluation of technical and commercial offerings and all framework suppliers were invited to tender for this contract.

1. An initial call-off was issued through the Prosperity Fund Framework on 24 June 2018. 8 bids were received, and a process of clarification, technical evaluation and moderation followed. This process was abandoned on 1 October 2018 before a preferred supplier could be identified. This was due to some tenders submitting day rates which were considered to be excessively high for an Official Development Assistance (ODA) funded contract and therefore unlikely to represent Value for Money.
2. A subsequent call-off was issued through the Framework on 26 October 2018. This included a cap on average day rates for the programme. A total of 8 bidders submitted bids. We ran an evaluation process to assess and make a decision on the bids received. The panel included the Head of Climate and Energy Network (South East Asia), Head of Prosperity Programmes (South East Asia), Regional Programme Manager and a FCO Commercial representative. The evaluation was informed by input from policy leads and programme managers in the region, as well as energy sector leads from FCO and BEIS. The procurement process identified the consortium led by EY (comprising of EY, Carbon Trust & IMC Worldwide) as the supplier offering the ‘Most Economically Advantageous Tender’.
3. The Framework Agreement sets out key contractual terms, to which the suppliers will be required to adhere. The ASEAN Low Carbon Energy Programme Steering Board, in partnership with the ASEAN Low Carbon Energy Working Group (see roles, responsibilities and governance in Management case) will oversee the direction of programme, timely and effective aggregation of results and financial information, and ensure read-across between programme activities, countries and HMG activity.
### Market engagement
1. There were 3 engagement events held in London to validate the overarching design of the Prosperity Fund commercial strategy and of the Framework including the lotting structure. Over 300 suppliers expressed an interest in supplying services with over 200 bids received across the Lots, indicating capability and market interest globally in delivering PF programmes. For the specific ASEAN Low Carbon Energy Programme, the Singapore-based programme team and SE Asia Climate and Energy network engaged with both local and international potential suppliers during and since the Carbon Trust scoping study in autumn 2016 to socialise the existence of the programme and its broad themes. Many potential suppliers were already known to the team through significant earlier Prosperity Fund work in the region. Climate attaches in country fed in names of potential local suppliers, and desk-based research in Singapore provided details of key potential regional or international suppliers.
2. The Framework Agreement is populated by large global providers as well as smaller more specialised suppliers. The market engagement demonstrated that many of the larger suppliers operate in South East Asia and are used to working with smaller providers to deliver requirements.
3. A supplier call relating to this Programme was conducted in November 2017 to socialise design and allow potential suppliers to ask clarifying questions. This also helped construct SoRs which pre-empted certain questions. Several dozen potential suppliers participated. Minutes were available online for further reference and for those unable to make the call. To ensure that the field of potential bidders for tendered contracts was as wide as possible a further supplier engagement event was held in March 2018. The Supplier Day was held at the British High Commission and became the avenue to launch and test the SoRs, including checking whether the inception phase is an appropriate length. It was also used to gather further feedback on supplier appetite to deliver the programme.
4. As a result of supplier feedback, the inception phase for the programme was extended from 4 to 6 months.
### Ensuring Value for Money, including due diligence
#### Value for Money
1. The Programme Team at the Singapore British High Commission will apply best practice programme management principles and the National Audit Office criteria for VFM throughout the planning and implementation processes.
2. The programme has not been prescriptive in how requirements are to be delivered but is clear on the requirements and measures of success.
3. This procurement was one of the first to be called down from the new Prosperity Framework. Lessons learnt will feed into future call-offs.
VFM measures
#### Table 17: VFM Measures
Area	Measure	Detail	Demonstrated if
Economy	Programme and operational costs	Competitive tender ensuring MEAT and robust contractual terms and KPIs. Programme implementation costs: procurement, contracting, programme management, staff costs, implementation, following up on monitoring and evaluation results, etc.	Contractual terms complied with and KPIs met or exceeded. Operational costs remain as forecasted and any increases are properly justified and approved
Efficiency	Disbursement Ratio	Disbursement of funds divided by total undisbursed funds by the beginning of the fiscal year	99% - 101% compliance / ratio
	Implementation progress	Implementation progress measured outputs and outcomes in terms of high value direct procurement	Over 80 percent compliance measured / against initial agreements
Effectiveness	Log framework	All programmes have been designed following the PF Theory of Change, specifically applied for the S E Asia Low Carbon Energy programme. The logic framework will be used to measure progress against relevant indicators. When needed programmes will be re tuned to adjust them to the conditions of the environment	Measured against baselines, milestones and indicators.
Equity	Social and equality performance standards	Implementation of social and environmental sustainability performance standards, monitored throughout implementation process	Compliance measured / against agreed standards

Due Diligence
1. Under the Framework Award process, initial due diligence of potential suppliers has been completed. The call off process provided for a call for further competition in a single stage evaluation process. Bidders needed to provide significant detail on their sub-contractor and Consortium members within their bid as relevant and to provide assurance that they are fit in terms of financial standing and ethical and legal requirements to provide and deliver services to HMG .
2. Contract proposals have been evaluated against a set of criteria (found in Framework Schedule 6: Call off Procedure, Appendix 1) developed to ensure that the successful supplier has evidenced capability and capacity to deliver, a clear understanding of the local and regional dimensions of the Programme and deep insight of how the objectives and outcomes of the programme can be delivered.
### Securing implementers
#### Timeline
The table below sets out the indicative timetable for securing approval to spend and securing delivery partners.
#### Table 18: Indicative Procurement Timetable
Date	Procurement and Approval process	Lead
12 Dec 18	Full Business Case approval by IIOC	APD/PFDU
Dec 18	Approval by Minister and Cabinet Office. 10 day stand still period starts	PFDU/CPG
Jan 19	Contract award	CPG/SE Asia
Jan – Jun 19	Inception phase	SE Asia/ Implementers
Jul 19 – Mar 22	Implementation Phase	SE Asia/ Implementers

##### Creating the Statement of Requirements
1. The scope of activity to be undertaken was defined in a detailed Statement of Requirements, and work plans. The SoRs were written to ensure delivery of the programme outputs as described in this business case and allow for effective supplier management. We specified our required outcomes and impacts and any minimum outputs and required suppliers to set out how they will deliver these. The documents allowed scope for the implementers to use their expertise to input their own innovative ideas as to how best to deliver the required outputs and outcomes.. The SoRs includes an explicit section on Gender Act Compliance requirements.
2. The SoRs, set out the requirements for 2 phases of the programme:
#### Phase 1 – a 6 month inception period: This will scope out, prepare the ground for and delineate the final package of activities and deliverables. This will include refining existing intervention suggestions as well as offering innovative, practicable and timely ideas for interventions based on an up-to-date assessment of the region’s green finance and energy efficiency needs and UK expertise. The inception phase will require advisory services to the FCO in order to finalise the Programme’s design and activities and outputs. Key outputs will include:
- A market assessment of green finance in the PF6 target countries, including work relating to green standards in the region
- A market assessment of energy efficiency standards in the target countries
- A clear report on current donor activity on Green Finance and EE in the target countries with a detailed plan of where we can work in complement to these activities
- Identification of an industry or industries best suited to support of PF consultancy work to i) advise on EE measures and ii) which would yield potential secondary benefits, including for UK business
- An Inception Report, informed by the assessments above, detailing a clear programme of specific activities, in specific countries, and with specific timescales and budgets based on the indicative Logical Framework activities, outputs, outcomes in order to deliver the required impact of the programme.
Phase 2 - the Implementation phase of the programme: This will implement the inception plan mutually agreed at the end of Phase 1 to deliver the programme objectives. The operational phase will require delivery services whereby the lead delivery partner will deliver the interventions to the host countries. Activities will enable the key objectives of the programme: policy support, capacity building and technical assistance to facilitate green finance flows and improve the regulatory, policy and practical conditions for energy efficiency measures.
1. Both phases will require management services in that the lead delivery partner will manage activities – and any additional suppliers or subcontractors that may be required for the successful delivery of the Programme – on behalf of the FCO.
2. The SoRs specified KPIs to measure programme success across the programme. Key outcomes include:
#### GF1: Strengthened policy and regulatory frameworks that incentivise investment in green projects, including through greater alignment of GF standards
#### GF2: Greater interest and action on GF from government, project developers, international and domestic financial institutions in target countries, including through greater awareness and reduced risk perceptions
#### GF3: Improved green finance flows that leverage UK strengths on GF
#### GF4: Governments in target countries enabled to realise the opportunities and set out the pathway to access GF, including via Climate Investment Plans
#### GF5: Increased pipeline of bankable green projects
#### EE1: Strengthened policy and regulatory frameworks, including greater harmonization of standards (MEPs and HEPs), drawing upon UK experience
#### EE2: Improved business environment for products with higher energy efficiency, and EE products and services
#### EE3: More efficient use of energy in targeted industry sector in the region
#### EE4: Pipeline of bankable EE projects developed
##### EY’s key responsibilities
EY will take responsibility for ensuring the aims and objectives of the programme are achieved as set out in the detailed SoRs. EY will manage the delivery of activities, identification and disbursement of funds to any subcontractors (following verified invoices to the FCO), and ensure compliance with FCO’s and the JFU’s financial and management requirements, including MREL requirements. Key responsibilities include:
- Implementing the detailed, costed Work Plan, defined during the Inception Phase, in such a manner as to ensure public funds are spent efficiently, effectively and honestly in order to implement programme activities that deliver core outputs, realise desired outcomes and achieve the anticipated impact.
- Monitoring and reporting on the programme component’s performance against a milestone-based implementation schedule agreed with the FCO, and aligned with the detailed, costed Work Plan, defined during the Inception Phase ;
- Continuously demonstrating how the programme identifies and mainstreams diversity, equality and inclusion throughout design and delivery, including but not limited to actively promoting greater gender equality.
- Ensuring lessons learnt from programme implementation are captured and disseminated externally (to relevant partners in the public and private sector) to ensure the sustainability of outcomes, and internally (to the FCO and other relevant departments) to ensure continual revision and improvement of programme delivery.
##### Pricing Mechanisms
1. The approach to the commercial model will be output based milestone payments and fixed price elements where the detailed requirements provide for a level of risk sharing and incentivisation for suppliers.
2. The initial inception phase was set as a fixed price contract with a detailed set of requirements and quality measures provided within the ITT, ensuring VFM for HMG and incentivising the supplier to deliver to time and quality.
3. Payment for the implementation phase will be based on work plans agreed annually. Pricing will be based on day rates submitted as part of the tender and will be subject to a cap on the total contract.
4. Payments will be in line with HMG standards and via electronic invoice procedures.
### Managing Implementers during delivery
#### Contract forms and duration
1. The Foreign and Commonwealth Office will be the Contracting Authority. Contracts will be awarded on the basis of the Framework Agreement Terms and Conditions of Contract
2. The contract is expected to start from January 2019 and planned to end by 31 March 2022. There may be a possibility of extension. EY’s proposed approach to managing possible extensions was evaluated as part of the procurement process and found satisfactory. All requests for extensions will be managed with reference to SRO’s Delegated authority within Active Portfolio Management and the Prosperity Fund tolerance guide.
#### Contract Management
1. Contract management will refer to guidance from PFDU and JFU and will provide the basis for robust and clear contract management activities, principles and review points. The Regional Programme Manager in Singapore will be the contract manager for the programme, working closely with Programme Managers, Head, Prosperity Fund Programmes and Head, CCE Network.
2. Posts Programme Managers will be responsible for:
  1. Rigorous day to day operational management including on-going due diligence, ensuring management information is received;
  2. Relationship management including working with stakeholders to support the supplier’s progress;
Monitoring progress against Key Performance Indicators and Payment by Results mechanisms such as milestone payments, and reporting on these (see below for further information on Key Performance Indicators and Payment Mechanisms);
  1. Technical quality assurance for quality delivery
  2. Managing contract variations;
  3. Maintaining contract documentation;
  4. Risk and benefit management;
  5. Contract reviews including cost review;
  6. Financial oversight;
  7. Escalation, issue resolution and conflict management;
  8. Mobilisation and exit management as outlined in Schedule 9: Exit Management of the Framework Agreement Schedule 9 – Attachment 2(Template Call of Terms). This details the obligations of the supplier during the call off period and throughout provision of services, and obligations to assist on re-tendering of services. This Schedule also details that the exit plan must be delivered within 3 months of the Call of Commencement Date and what must be included as a minimum.
  9. Ensuring GEA compliance and technical QA for gender, poverty and inclusion.
Programme Managers will be supported by expertise in the following as and when required (full details outlined below in the Management Case):
  1. Intervention performance assurance
  2. Financial Management: their role will include monitoring supplier costs, modelling the impact of proposed significant variations, contributing to contract reviews and assessing financial reports
  3. Legal Assurance: their role will include drafting of variations and legal interpretation
  4. Commercial management and assurance e.g. VfM on contract variations
#### On-going Design Work
While the pipeline of priority interventions will be set out at the implementation stage, this may need to be updated during the lifetime of the programme in line with changing external and internal demands. The delivery partners may also recommend changes as a result of experience on particular projects. Such changes will be in accordance with the Contract Variation Process and SRO’s Delegated Authority within Active Portfolio Management. EY will be asked to submit fixed fees based on tendered daily rates and expenses for approval to FCO were there to be the need for a redesign exercise during the Programme or for delivery of new interventions.
#### Performance and reporting: Payment and Key Performance Indicators
1. Detailed reporting and monitoring requirements will be agreed between EY, the Programme team and MREL contractors; in compliance with GEA guidelines. Regular supplier meetings to discuss monthly KPIs, VFM being achieved and performance will take place throughout the contract duration, and particularly at key stages of implementation, in consultation with programme team. Outputs from these discussions will also be issued to inform the Annual Review Reports. The programme manager will submit quarterly operational reports on the performance of the programme.
2. Prior to the start of the Implementation Phase, KPIs and a payment by results will be agreed. Payment will be made in arrears on the submission of invoices, once the programme team have verified that the milestones have been met.
3. EY will be required to engage constructively with related Prosperity Fund bids. This will include Indonesia’s Renewable Energy programme, the Global Future Cities programme; and the contractors appointed to deliver the Cross Whitehall Prosperity Fund MREL contract to ensure data flows and evaluations are captured effectively.
### Management of Key Procurement and Commercial Risks
The table below provides an overview of the key commercial risks and mitigating actions that will apply to all of the contracts. The Risk Register in the Management Case also includes wider commercial risks and a summary of how these will be mitigated.
#### Table 19: Management of Key Procurement and Commercial Risks

Key Risk	Description	Mitigation
No supplier on Framework suitable to / cover Programme / requirements	Framework Agreement fails to provide sufficient expertise required for the SE Asia Low Carbon Energy programme. Lack of local footprint inhibits the achievement of / programme impacts	SE Asia posts provided input to Framework Agreement TORs and commented on list of suppliers. Suppliers within the FCO Framework Agreement will build as necessary, consortia or supply chains with organisations that have the local expertise and footprint to deliver the programme.
Single / Provider	Difficulty of ensuring value for money when one provider is responsible for designing and delivering high / profile services	Competitive tendering / Include indicative design and delivery requirements and test bidders’ capabilities/prices to deliver these during the procurement / Clear costing profiles which set acceptable cost tolerances for interventions / Open and transparent pricing arrangements established at tender stage (maximising use of output based pricing where possible) / Non-exclusive contract allowing for benchmarking / Robust contract management / FCO Monitoring, Reporting, Evaluation and Learning providers provide challenge / Strong and engaged Strategic Board provides intellectual support and challenges and directs provider activities, particularly the choice of priority countries and interventions / Allow the supplier to amend their supply chain as necessary / Supply chain controls in contract if supply chain performance is not adequate / Range of VFM controls in the contract (see Pricing Mechanism)
Framework Agreement timeframe	Framework Agreement timeframe delays implementation of the programme	Programme team to ensure as much preparatory work for the programme is carried out to ensure swift activation of programme is possible once tender is completed.
No bidders	Market engagement and content of ITT documentations fail to attract commercial bid.	The Central Procurement team will lead the tendering process and have identified good potential bidders on the Lot. Early market engagement has demonstrated that there is sufficient capacity and expertise within the local market to implement a programme of this scope. Market engagement e.g. phone ins and launch will help socialise bid and encourage interest.
Supplier / Organisational / Failure	Supplier bankruptcy, or loss of significant partner organisation or other event leading to failure to deliver contract (e.g. fraud)	Pre-contract and on-going due diligence checks / Milestone payments and payment in arrears limiting liability / Non-exclusive contract to allow spend through other suppliers to augment the supplier’s capacity and skills / Contractual rights e.g. step-in rights, partial or full termination
Design Failure	Supplier design insufficiently scrutinised to ensure interventions deliver the required impact	Include sector specialists on the evaluation panel and on the Strategic Board to ensure that the quality and effectiveness of design proposals are scrutinised and challenged / Robust evaluation of inception report to ensure design of interventions meets objectives / FCO MREL and GEA providers support the process / Ensure deliverables are transferable to any new provider (including through use of an Intellectual Property Rights clause) / FCO sets strong and clear objectives / Supplier to identify key milestones and FCO will measure against these
Delivery stage failure	Supplier fails to deliver interventions as agreed	Payment by Results (PBR) mechanism linked to Key Performance Indicators. Clear KPIs and performance standards. Targets and any sums to be put at risk by the supplier will be agreed on a case by case basis taking account of local factors. / Dedicated, experienced contract managers / FCO’s Monitoring, Review, Evaluation and Learning supplier oversees performance
Contract is / insufficiently flexible	Contract is insufficiently flexible to allow quick and / VFM response to changing requirements as a result of, for example: / Political changes in UK or relevant South East Asia countries / Scope and priority changes / Funding Level Changes / Legislative Changes	FCO will define their requirements as accurately as possible and only change these in exceptional circumstances. / Evaluation of the supplier’s proposals for scaling up and down with associated changes in costs / Non-exclusive contract to allow spend through other suppliers to augment the supplier’s capacity and skills / Early termination clause in the contract / Detailed breakdown of the supplier’s set-up costs to limit liability in the event of early termination / Supplier required to include termination clauses in contracts with partners/sub-contractors or other delivery bodies

### Terms and Conditions
The Framework Terms and Conditions reflect the Government Model Contract Terms for Services and have been developed to reflect the specifics of the Prosperity Fund, ODA and IDA requirements. Key terms include:
1. Data Protections
2. Intellectual Property Rights
3. Transparency
4. Tax Compliance, Termination rights
5. Environment, Health and safety, Equality and Diversity and Anti-Terrorism clauses
Call-off terms provide for a roll down to a more detailed level to be adapted in line with the requirements and the environment in which the services will be delivered.
Additional clauses in Service Levels and Credits, Performance Management, Business Continuity and Exit arrangements are included as relevant to the requirement.
# Financial Case
The financial case will set out the programme budget, financial management and the potential to scale the programme.
## Programme Budget
### What sources of funding will the programme use?
The programme is seeking £15m Prosperity Fund ODA funding over four years for this programme. This includes all implementing activities, staffing and administrative costs.
### What will these funds be spent on and what are the key cost drivers?
1. The main cost across the programme is advisory services to deliver the policy support, technical assistance and capacity building activities. We expect to manage these costs in 3 ways: Selection of lead implementer will include assessment of VFM including costs of programme delivery; implementing partners will run competitive tenders to ensure VFM, benchmarking costings and reducing costs where possible; contracts will be based on milestone payments contingent on delivery of outputs. Fee levels will be managed through the procurement process. FCO staff costs to manage the programme make up 5.1% of the programme which we consider reasonable to ensure effective management of contracts and delivery of programme benefits across the countries in the region, and makes use of local staff to reduce costs. This level of staff is recommended, given the need to have programme managers in each of the target countries (0.5FTE in each) given language requirements and the need for government stakeholder management. These include staff costs for a proportionate amount of the PF6 Programme Office, expected travel costs associated with management of the programme, and communications activities.
2. Of the expected total budget of £15m:
  1. £0.8m will cover essential staffing for programme management.
  2. £12.80m will be for supplier fees and expenses (including tax) to deliver the programme.
  3. The remaining £1.4m will be used flexibly to amplify or scale up programme interventions on Green Finance and Energy Efficiency, in areas where there is potential for impact.
3. First year expenditure is low, given the PF assurance process and procurement timeline.
4. The estimate does not include any assumptions about salary increases or cost rises during the programme. Staffing costs are based on the latest available Full Economic Cost Model.
Table 20: Indicative programme costs
Activity	2017/18 / (‘000)	2018/19 / (‘000)	2019/20 / (‘000)	2020/21 / (‘000)	2021/22 / (‘000)	Total (‘000)	Total share
FCO programme management staff	46	191	191	191	191	764	5.1%
Wilton Park conference	-	35	-	-	-	35	0.23%
Commercial contract	-	-	12,765			12,765	85.10%
Flexible programming	-	-	1,436			1,436	9.5%
Total	46	250	Est. 4,901	Est. 4,901	Est. 4,901	15,000	100.00%

Table 21: Estimated staffing costs
Title	Grade and number	Cost per annum breakdown	Cost per annum
Regional Programme Manager	0.50 C4L	103,678 x 0.5	51,839
Programme Managers in Malaysia, Vietnam, Burma, Thailand, Philippines	0.50 C4L x 5	(57,462 + 55,398 + 44,064 +54,439 + 36,306) x 0.5	123,834
Programme Manager in Indonesia	0.25 C4L	60,962 x 0.25	15,240
Annual Cost to LCE Programme (4 year cost)			190,914 / (763,656)
Head of Prosperity Programmes	0.25 D6UK	212,897 x 0.25	53,224
Prosperity Fund Portfolio Officer	0.25 B3L	89,886 x 0.25	22,472
Proportionate cost of PF6 Programme office (4 years)			75,696 / (302,784)
Total per annum (4 years)			266,610 / (1,066,440)

### How will it be funded: capital/programme/admin?
Funding will be ‘programme’ spending (RDEL). An allocation of £15m has been made by the Prosperity Fund, subject to approval of this business case. All funds are ODA eligible and there are no contingent liabilities associated with this funding.
### Profile of expected costs
1. The programme team will provide a total budget of £15m to March 2022. The allocation of the budget between activities and the profile will be confirmed during the inception phase once the detailed discussions with the supplier(s) on costing the interventions are completed, but it is expected that the budget will be split approximately in half between the Green Finance and Energy Efficiency components.
2. The total cost of this programme is fixed. The allocation of funds between different components and scope of individual activities to maximise impact through adapting to learning and any changing circumstances will be reviewed through the Programme Working Group and Steering Board, as guided by the Prosperity Fund tolerance guide
### How will you work to ensure accurate forecasting?
Forecasting will be undertaken by the FCO, using FCO systems, based on the payment schedule agreed with the implementing partners. For all activities, accurate forecasting will be managed by ensuring payments follow an agreed schedule defined by clear and time-bounded deliverables and costs. Forecasts will be reviewed monthly. Payments schedules will be reviewed bi-annually are monitored monthly and can be adjusted if necessary.
### Disbursement of programme funds
1. As agreed with the Prosperity Fund Management Office, funds will be allocated by SRO letter on a per annum basis. Of this, £764,000 will be for programme management staff posts, travel and subsistence; 5% of the total programme cost. See the Commercial Case for how the disbursement of funds will take place and mechanisms for ensuring financial accountability and risk management.
2. There will be no ongoing liabilities to the Prosperity Fund beyond the lifetime of the Programme.
### How will expenditure be monitored, reported and accounted for?
Robust due diligence processes will be put in place before any expenditure takes place, as detailed in the Commercial case. Financial reporting will be carried out monthly. In accordance with the contractual provisions, funds to the contractors will be posted to receipt on a monthly basis on receipt of a valid invoice supported by a breakdown of activity that has been delivered. In accordance with the Procurement Framework’s standard contractual provisions, each invoice will be supported by a breakdown of the costs being claimed against each budget line in the contract. The Head of Prosperity Programmes (SE Asia) will be responsible for ensuring due diligence in the disbursement of funds, and for taking any action deemed necessary. Where appropriate, full details of forecasted future spend by financial year against the annual work plan will be included in an annual report to HMG leads. The implementing partners(s) will submit annual audited accounts for each of the financial years covered by the project.
## Financial and Fraud risk assessment
1. The main financial risk is that programmes take time to reach implementation and that procurement delays and delivery delays result in drawdown being postponed. We have sought to mitigate this risk by being realistic on year 1 spend, building in sufficient time to complete the procurement processes. We will further manage the risk by effective contracting and working closely with implementers to spot and address any external delivery roadblocks.
2. Any programme of this size and geographical reach needs to consider the potential fiduciary and fraud risk in the operating environment. For this programme these risks will be mitigated in the following ways:
1. Funds will be disbursed through the lead implementer/implementers, following the procedures described above to verify payments before funds are disbursed.
2. A thorough due diligence will be carried out on all recipients of funding throughout the delivery chain, before any payments are made.
3. It is not expected that funds will be transferred through partner government systems or directly to small community based organisations which are likely to present a higher fiduciary risk.
We also consider currency risk, with the potential for volatility surrounding Brexit negotiations and beyond. We will mitigate this by agreeing that implementers bear currency risk, but ultimately this may result in lower levels of service and consequent effect on outputs and impacts.
## The potential for scaling up or down
The economic case provides further details on the potential to scale up the programme. Our initial assessment is that this programme could be scaled-up by up to 50% in its existing components before it would have a significant impact on staffing levels. Further analysis would be needed to judge the impact on staffing of adding new components. To scale down, the number of interventions, or the number of countries in which they are to be rolled out could be reduced.
# Management Case
The management case will cover the governance arrangements, the HMG resources needed to manage the programme, MREL, the major risks, programme adaptation and flexibility and the communication plan.
## Governance
#### Fund Level Governance Structure
1. The Governance structure puts in place the appropriate oversight and support to ensure the programme delivers the results outlined in the Appraisal Case and agreed by the Portfolio Board (PB). The budget for the Low Carbon Programme will be held by the FCO. The FCO (via either the Permanent Under-Secretary or the Director General Economic and Consular) has delegated responsibility for the allocated funds to BHC Singapore, both in terms of management of public money and ensuring compliance with the International Development Act.
2. The senior responsible officer (SRO) at Post with operational responsibility for the ASEAN Low Carbon Energy Programme is the British High Commissioner in Singapore, as regional lead for the Prosperity Fund. The Head of the Climate Change and Energy Network (D6, Singapore) will ensure policy coherence and have day-to-day oversight of the programme. Head Climate Change and Energy Network will be assisted by a 0.5 C4 (L) (Singapore) to help with the initial procurement and set-up phase of the programme and ongoing co-ordination across the region. The Head of Prosperity Programmes (D6, Singapore), leading the Programme Office, will ensure the programme’s adherence to the programme management processes and will manage finance.
#### SRO role
The SRO will have overall responsibility for ensuring the delivery of the programme activity and spend, as well as coherence with x-HMG priorities. The SRO’s delegated authority will be set out in the SRO letter and he or she will carry out the SRO’s responsibilities in line with this delegated authority. An assessment of the incumbent will be carried out and, if necessary, training provided to ensure the SRO is able to carry out his or her responsibilities effectively. This will be repeated if a new High Commissioner is appointed and becomes SRO for the programme.
#### Steering Board
1. A Steering Board has been formed during implementation and has met twice. It will continue to meet every 3 months during the lifetime of the programme to review progress, help shape strategic priorities and support delivery. The Board is chaired by the SRO and will be made up of senior representatives from FCO, DIT, JFU, PFDU, BEIS and PF6 Heads of Mission. Relevant academics and members of the business community will be consulted on an ad hoc basis and their views fed into the Steering Board as needed. Membership will be reviewed annually and adjusted if required to ensure relevant stakeholders are represented. The secretariat function is being carried out by the PF6 Programme Office in Singapore. Minutes of the Board meeting will be made available to PFMO and PFDU to allow them to monitor the programme, alongside formal MREL documentation.
2. The Board will provide overall policy direction for the programme, oversee the activities of the Working Group, sign off financial forecasts and allocations and approve annual progress reviews before submission through departmental processes or to the Prosperity Fund Management Office (PFMO). The Steering Board will have responsibility for liaison with the PFMO and other high level and international stakeholders, and for ensuring wider dissemination of the programme’s learning. The SRO will be responsible for escalating issues to the PFMO and Portfolio Board, taking advice from the Working Group, the Prosperity Fund PF6 team and the Head of Climate Change and Energy. The Steering Committee will be responsible for prioritising future activity, based on the performance of the components against the results framework.
#### Working Group
A Working Group will also be formed during implementation and meets every month during the lifetime of the programme to discuss progress, co-ordinate work between delivery partners and provide day-to-day oversight. It is chaired by the Head of Climate and Energy Network. Membership include programme leads from each post, lead contractors (plus sub-contractors depending on the agenda) the Head of Prosperity Programmes (SE Asia) and relevant policy leads (e.g. CCE attachés). The Regional Programme Manager in Singapore carries out the secretariat function.
Lead Implementer
Chair: SRO
Secretariat: PF6 Programme Office
Chair: Head Climate Change and Energy
Secretariat: Regional Programme Manager
Steering Board
JFU
Working Group
JFU MREL
PFDU
Implementer
Implementer
In-country programme officers
Figure 4 - Governance Structure
The Working Group reviews narrative reports from the Lead Implementer and ensures:
- Programme delivery is on track
- Programme finances are properly managed
- Effective co-ordination between pillars
- Timely problem solving and management of risks
- Lesson learning between countries
- The Strategic Communication Plan is up-to-date and planned activity is taking place
- Monitoring and evaluation and programme learning is taking place, aligned with PF MREL function
- Gender action plan is being implemented by the Lead implementer, including consultation with FCO’s Social Development Advisors and MREL consultants’ Gender leads.
The Working Group manages the project’s finances by:
- Receiving finance reports from the Lead Implementer and clearing payment
- Recommending adjustments to forecasts and allocations between components and countries
- Ensuring appropriate action in the case of any reports of fraud or other misuse of funds.
#### HMG resources needed to manage the programme
### Proposed structure
1. The programme requires on-the-ground resources in each post it operates in. Experience has shown that one officer covering multiple posts without further local support is ineffective[111], primarily because of language barriers and the cultural requirement to be present and build relationships to drive action and facilitate change.
  [111] A PF project in 2013-14 established an LE officer in Bangkok to cover Thailand, Burma and Vietnam. Language difficulties, significant travel commitments and the natural bias towards focussing on Thai-related work made the job specification untenable in practice.
2. The programme is be led on the policy side by the D6 Head of Climate Change and Energy Network (non-PF funded) with 0.5C4(L) Programme Managers in each Post except Indonesia (having only 0.25C4 (L), for just the GF component). A Low Carbon Energy Regional Programme Manager 0.5C4 (L) would be based in Singapore to support roll-out and provide ongoing operational support). Policy input in each Post would be available from the CCE attaché network, economic officers and DIT teams (all non-PF). Leading on the engagement with the delivery partners, finance, governance and liaison with London would be the Delivery Manager - the D6 Head of Prosperity Programmes, a shared PF resource funded 25% by this programme and a B3(L) Prosperity Fund Portfolio Officer (also a shared resource, 25% funded). Together these posts form the PF6 Programme Office which is fully PF funded. The proportion of the PF6 Programme Office charged to this programme will depend on how many programmes are eventually approved for the region. We currently expect the PF ASEAN Economic Reform Programme, the Future Cities programme and the Health programme to share the costs as well.
Figure 5: Staffing structure

Key features:
- A central oversight and co-ordinating function will support and guide programme managers at post.
- The responsibility of assessing the programme’s continued suitability to meet the programme aims will fall to the policy lead.
- The responsibility for programme management – e.g. assessing the programme against delivery milestones will be held by the delivery lead and team.
- Programme Managers at post will monitor and assist implementers in-country and liaise with DIT on secondary benefits.
- The programme will draw on existing (non PF) Communications, Economic, Commercial and CCE policy support from SE Asia FCO and DIT colleagues working regionally and on a country by country basis.

Role	Description	Grade, No & location
Head of Climate Change and Energy Network	Providing overarching policy input and context to Programme Officers. Head of Prosperity Programmes and CCE attaches to ensure joined-up programming that meets HMG and PF goals / Ensuring expertise from within the network (CCE policy, Comms, Commercial, Economic) and that of implementers and other external stakeholders is effectively harnessed to achieve best outcomes and impact / Ensuring programme outputs are converted into tangible outcomes by leveraging activity with stakeholders such as the host government and civil society organisations. / Assessing programme delivery to determine how and whether the programme is achieving impact.	1 D6UK - Singapore / (non-PF funded)
Programme Managers	Building and maintaining relationship with host govt to drive through lasting change on the back of programme activity / Overseeing in-country delivery of the programme’s components by delivery partners and verify monitoring and evaluation by delivery partners, focusing on programme outputs and outcomes / Liaising with DIT colleagues to secure secondary benefits / Liaising with CCE attaché and comms colleagues to secure strong communications activities / Reporting back to Head CCEN and Head of Prosperity programmes to ensure programme meets PF and HMG objectives.	0.5 C4L each PF6 post / (exc. Indonesia: 0.25) / Total 2.75
Low Carbon Energy Regional Programme Manager	Logistical work on procurement and initial roll-out / Operational support to Head of CCEN in assessing delivery and achieving impact / Ensuring coordinated approach across programme managers, including regional comms, sharing best practice and consultation with Head of Prosperity Programmes on L and D / Producing contract management documentation (e.g. records of decisions, variance), monitor implementer compliance (e.g. SLAs) / Working Group Secretariat	0.5C4L Singapore
Head of Prosperity Programmes	Ensuring financial accounting, risk management, contract management and MREL are carried out on time and to a high quality to allow accurate forecasting and assessment of the programme / Contract managing delivery partners, including regularly engaging delivery partners, assessing effectiveness of sub-contracting and partnering arrangements and verifying outputs through Programme Officers at post / Developing and implementing procedures for contract management / Ensuring governance requirements are carried out and add value to the programme / Representing the region to stakeholders in London, including JFU, APD, DIT / Liaising with posts and providing regular updates on PF activity and decisions / Overseeing the PF staff network, identifying learning needs, co-ordinating activity	1 D6UK / Singapore / (shared resource, 0.25FTE for LCE programme)
Prosperity Fund Portfolio Officer	Managing finance system and ensuring accurate forecasting and verification are carried out / Steering board secretariat / Preparing financial returns for London / Briefing and comms	1B3L / Singapore / (shared resource, 0.25FTE for LCE programme)

### Roles and responsibilities
1. The table above sets out the resources needed to manage the programme effectively. It includes staff who are not PF funded and those shared across other programmes. For them, the role description only includes responsibilities relevant to the PF programmes.
2. There are a number of HMG non-PF funded roles which will support aspects of the Programme during its set-up and delivery, as part of their overall remit. These include:
- Asia Pacific Procurement Hub, Manila– provision of area expertise and regional oversight on commercial process, market rates, procurement model and requirements, and contract management;
- FCO Legal Directorate – guidance on legal risks, contracts, legal documentation and contract management;
- Post Economic Adviser - provides sector expertise and in-country monitoring on local economic situation, shares connection and links to relevant stakeholders to help steer activities to targeted areas and generate greater impact, supports MREL activities;
- Department of International Trade– area expertise on the trade and investment, inputs on measures of secondary benefits and successes;
- Post Climate Change and Energy Attachés - provide sector expertise and in-country monitoring on local climate change and energy initiatives, share connections and links to relevant stakeholders to help steer activities to targeted areas and generate greater impact, support MREL activities.
- FCO Social Development Advisor – expertise and advice on gender and inclusion; including on logframe indicators, equality impact assessments and gender action plans.
## Monitoring, evaluating, reporting and learning (MREL)
Departmental leads and the JFU are also be involved in the monitoring and evaluation process to ensure compliance with the aims and objectives of the programme as set out in this business case.
### Results framework
The monitoring, reporting, evaluation and learning (MREL) for this programme will be consistent with the Fund approach to MREL. A draft framework has been created and we will work with the Fund contractors to refine it, develop critical indicators (including gender disaggregated indicators) for Fund and programme level reporting, identifying indicators that can be aggregated for regular reporting and management indicators to allow programme managers to assess progress and impacts. The programme MREL will be consistent with, and regularly test, the programme theory of change and the log frame analysis that flows from it. We will report expenditure monthly and impacts (results) quarterly in line with Fund reporting rhythms.
#### Reporting frequency and costs
Consistent with our Fund requirements we will instruct the implementer for the programme to develop a quarterly results reporting system and will work with the Fund Monitoring and Reporting contractor to ensure consistency with Fund processes and systems – particularly around data quality and consistency. Programme data capture and baselining will be the responsibility of the programme and its implementers but, as instructed, we will charge the costs of this to the central MREL budget. This element of the programme is capped at 1% of programme allocation.
#### Monitoring and Reporting
Responsibility for data capture, baselining and reporting sits with the programme officers and the implementers. Indicators will need to be agreed with the fund level monitoring and reporting contractor, the evaluators and the programme implementers. The monitoring and reporting contractor will identify the data requirement in terms of format and quality. We will work with our stakeholders to ensure that reporting is done in a timely and useful manner.
#### Evaluation and Learning
1. If this programme is selected as one of the sample for fund level evaluation, we will work with the Fund Evaluation and Learning contractor to develop the strategic questions that will be required for both the fund evaluation and to provide feedback to programme managers on routes to impact. The overarching evaluation methodology will be decided by the fund level evaluators and we will work to deliver the required coordination between the various contractors at programme level.
2. If the programme is not selected for Fund level evaluation we will work with the programme level evaluation and learning contractor to develop a set of strategic questions that we will want to answer through the process. These questions may include fund level questions if appropriate.
3. We further note that it may not be possible to evaluate all programmes and as part of the coordination with the evaluation contractors we will assess this and decide on a way forward with the JFU.
### Roles and Responsibilities
The table below sets out where responsibilities lie for each MREL requirement
Table 22: MREL Roles and Responsibilities
MREL Contractors	Programme Managers	Implementers
Advise on the suitability and quality of draft programme Key Performance Indicators (KPIs) / Advise programme managers on MR requirements when they develop ‘terms of reference’ (i.e. going to market) / Construct an IT system to record and analyse KPIs / Produce Fund-level reports and infographics / Provide constructive critique of programmes’ ‘Theories of Change’ / Develop ‘strategic evaluation questions’ with the programme managers / Work with programme managers and implementers to undertake in-depth evaluations / Work with Fund governance (e.g. Portfolio Board) to evaluate Fund performance as a whole / Develop a learning strategy so that emerging lessons from different programmes can be shared across the Fund	Create a programme Log-frame with draft KPIs / Work with EL contractors to establish ‘strategic evaluation questions’ / Monitor their KPIs to make strategic programme decisions / Constructively engage with contractors during evaluation periods, and use findings to make strategic programme decisions	Baseline and collect programme KPIs / Work with EL contractors during evaluation periods

## Risk Management
The risk register will be regularly reviewed and updated as part of ongoing scanning for emerging risks and a proactive approach towards risk mitigation. The table below summarises the risks in each category. Our assessment of the overall risk of the programme across the themes listed below is Moderate.

Table 23: Risk Management
Description	L	I	RAYG	Mitigation	L	I	RAYG
Context – risks include political developments, the economic situation, social unrest and conflict, and other environmental factors.	P	MD		Programming will focus on laying the foundations for long term economic growth, reducing the impact of short term economic changes. / Continued FCO Post engagement with relevant officials and ministers. / Monitoring government announcements to look for early signs of policy change most especially in countries like Burma and the Philippines where the political context is complex and can change rapidly / Focusing on interventions that are not contentious. / Flexible and adaptive programming to accommodate changing host or UK priorities.	U	MN
Delivery – risks include those associated with the partner and its supply chain, to beneficiaries as well as the performance of the programme.	U	MJ		Effective and open communication between delivery partners and FCO programme managers. / Agreement on robust environmental and social protection policies with delivery partners and monitoring of compliance. / Continuous engagement and flexible design to enable programme adaption. / Ensure delivery partner is bought into aims of programme, as well as the activity to be undertaken.	U	MD
Safeguarding – an important aspect of delivery risk is to “avoid doing harm”. Risks include those potentially impacting on social exclusion eg poor gender and inclusivity practice, child protection, slave labour (e.g. for large infrastructure development and construction) and trafficking.	U	MN		Ensure programmes focus on inclusive economic growth and monitor programme’s impact. / Careful financial control with delivery partners and their subcontractors. / Strong liaison with political officers at post. / Retention of flexibility to respond to any new information on the drivers of inequality in SE Asia.	R	I
Operational – these relate to the capacity and capability of the government departments involved in delivery to manage the programme.	P	MJ		Effective and open communication between delivery partners and FCO programme managers. / Strengthen existing experienced team; / Structuring of programme in few, large components; Building buy-in from senior staff. / Establishing robust change management processes.	U	MN
Fiduciary – these relate to the funds not being used for the intended purposes and / or not being properly accounted for.	P	S		Rigorous financial control, ensuring all subcontractors are aware of their obligations and prohibitions. / Finances managed according to the processes set out by PFMO and staff trained for fraud awareness. / Blocks on dispersal if concerns are raised	U	MD
Strategic – any risk that negatively affects the alignment between the Fund programme plus risks that affect international architecture, negotiations and finance and high level visits.	U	MD		Ensuring adequate guidance and training is in place to support the design and delivery of programmes with clear primary purpose. / Testing ODA/IDA compliance as an explicit part of the annual review process, alongside ongoing challenge from the Board.	R	I

## Programme Adaptation and Flexibility
1. It is recognised that programme implementation cannot be standardised across all PF6 countries given their different political, economic and social contexts and needs. Whilst the key components and interventions will be implemented in each of the countries (excepting Indonesia for energy efficiency), the specific content and balance between the components will be designed in consultation with stakeholders to respond as much as possible to country needs as identified during the diagnostic stage. An operational learning approach will be adopted to enable the programme to adjust to lessons from implementation, both within country and across the programme as a whole.
2. The programme design provides a range of options to scale up or down, depending on available budget and timeframe. For example funding could be increased or decreased for individual components or the number of countries could be adjusted. Terms of Reference for the Lead implementer will reflect the importance of an adaptive approach to programming and the potential for adjustment to the scale of time or budget (see Commercial case).
## Communications and stakeholder management
1. This Prosperity Fund Programme is a tool for delivering HMG objectives in South East Asia, in conjunction with other tools and resources at the network’s disposal. External communications will be a significant part of ensuring the programme is successful. In order to maximise awareness and understanding of the programme, and to help ensure that beneficiaries and partners understand that this is a British government initiative, we will be guided by principles of strong HMG visibility and ownership even though some delivery may be outsourced. We will incorporate the JFU Communications Guidance (when issued) as appropriate. We will use the OASIS[112] tool to ensure our communications are effective, efficient and evaluated – an early strategy is set out below.
  [112] A Guide to Campaign Planning https://gcs.civilservice.gov.uk/wp-content/uploads/2015/09/OASIS-Campaigns-Guide-.pdf
2. Objectives
To demonstrate that ODA spend in the PF6 countries in South East Asia can deliver economic development and poverty reduction in the region and opportunities for international and UK business;
- To ensure international and UK companies are aware and able to take advantage of opportunities and access resulting from programme activities;
- To influence national decision-makers to ensure that the programme is implemented and delivered effectively and efficiently;
- To raise the profile and reputation of the UK in the region, using the Programme to build a stronger and wider network with stakeholders in government, NGOs and business communities;
- To seek to ensure awareness and support for this Prosperity Fund programme among UK public, press and Parliament;
- To raise the Programme’s profile through reporting of success/impact;
- To ensure that Post teams and Cross Whitehall partners are well-informed about the Programme’s objectives and processes and are actively engaged and aligned as appropriate.
Audience Insight:
Our audience will be:
- PF6 national governments, in particular decision makers in business environment and finance and business services;
- PF6 businesses, project developers and investors involved in the provision of finance and business services, likely to engage in public procurement and those who rely on IP (e.g. conducting RD&D);
- PF6 public, NGOs, local and regional press;
- Business and investors (including trade organisations such as the CBI, City of London and other sector-specific bodies);
- UK press, public and Parliament;
- Embassy/High Commission teams and Cross Whitehall departments.
1. Strategy/Idea A key focus of the programme is policy reform and capacity building at an official and business level: this will need strong buy in from governments across the region and good linkages to the relevant business sectors. A close association between the programme and HMG will therefore be vital, and careful, consistent external communications with government and business stakeholders will be required. Communications will also need to be managed to ensure a regional approach where appropriate, as well as content tailored to individual countries.
2. We also need to ensure that the potential positive spillover commercial impacts and reputational benefits for the UK are realised. External communications will be needed to ensure that the private sector/business community can inform the focus of programming, is aware of the programme and well positioned to take advantage of commercial opportunities that the programme helps bring to market.
3. Implementation: Strategic communications activities will include:
- Highlighting ongoing programme activities and their longer-term economic value ; ensure we are aware of developing opportunities (e.g. major contracts, policy reforms etc.) and corresponding risks;
- Timely media moments (blogs, tweets, editorials across the PF6 region and/or in specific countries to highlight programme activities and successes to a wide audience capitalising on reputational benefits for the UK; and
- Activities such as meetings, presentations, public lectures, strategic dialogues with host governments, roundtable discussions, forums and trade missions (non-ODA activity) that could benefit from the opening up of opportunities through the programme. This will link to work undertaken by DIT to directly facilitate business wins.
In terms of responsibilities, communications activities will be co-led by the Programme Officers and implementing partners. Programme Officers will work closely with their Communications teams at Post to use their expertise and network and link in the Economics attaches to ensure key messages bolster policy objectives. The Head of the Climate Change and Energy network and the Programme Coordinator will retain oversight and help coordinate regional communications, again working closely with the regional communications hub. The division of key responsibilities is likely to be as follows:
Head, CCE and Regional Programme Manager (with input from Comms, policy and programme leads at Posts):
- Develop and continually update strategic communications plan;
- Identify and undertake media publicity for fund activities;
- Identify and communicate with UK and PF6 companies;
- Ensure programme is promoted through wider Post activity and engagement with stakeholders; and
- Coordinate communications activities with implementing partners.
Implementing Partners:
- Engage with PF6 government to ensure activities are aligned with, and embedded in, their wider implementation plans on green finance and energy efficiency;
- Support outreach to potential beneficiaries; and
- Provide information to Posts to support wider media activity, including timely updates on particularly impactful activities or commercial wins achieved and early warning of any potential negative coverage.
1. Once the market assessment has given a clear trajectory of travel, we will also aim to showcase and market the programme at a suitable regional energy event. Depending on timelines this could be the Asia Clean Energy Forum (ACEF), the Green Growth Business Forum (if held) in Singapore, or the Singapore International Energy Week. We would discuss with the lead implementer which event would provide the best platform to promote the news to key stakeholders and generate interest and buy-in for implementing a successful programme.
2. The ASEAN organisation should be engaged in highlighting the cross-regional aspects of the Programme and encouraging its relevant members to work with the Programme especially where this fits with ASEAN’s regional aspirations. Another channel could be procuring delivery partners with both a local and UK presence, and include in the contracting requirements a degree of dissemination activities through their British branches. This is usually something that independent organisations are usually more than willing to do on their own, as it furthers their brand as well as promoting the programme, so it should come at no extra cost to the FCO.
3. Scoring/evaluation. We will monitor outputs and outcomes throughout the campaign and evaluate during the programme (using timely feedback to improve implementation) and when complete. We will work closely with the implementers of the programme to ensure communication strategies are understood and optimised. The Communications Plan will use the full suite of tools available as appropriate to help measure the effectiveness of the campaign, such as surveys, reviews of media coverage, customer feedback (governments, partner organisations, businesses in region and in UK) and online analytics.

# Resources
ADB. (2015). Renewable energy developments and potential in the greater mekong subregion. Retrieved from Asian Development Bank: https://www.adb.org/sites/default/files/publication/161898/renewable-energy-developments-gms.pdf
ADB. (2015, December). Viet nam energy sector assessment, strategy and road map. Retrieved from https://www.adb.org/sites/default/files/institutional-document/178616/vie-energy-road-map.pdf
ADB. (2016). Asian development outlook 2016: Asia's potential growth. Retrieved from Asian Development Bank: https://www.adb.org/sites/default/files/publication/182221/ado2016.pdf
ADB. (2017). Asian development outlook 2017: Transcending the middle-income challenge. Retrieved from Asian Development Bank: https://www.adb.org/sites/default/files/publication/237761/ado-2017.pdf
ADB and Routledge. (2014). Inequality in Asia and the Pacific: Trends, drivers and policy implications. (R. Kanbur, C. Rhee, & J. Zhuang, Eds.) Retrieved from https://www.adb.org/sites/default/files/publication/41630/inequality-asia-and-pacific.pdf
ADB, Economic Research and Regional Cooperation Department, Development Economics and Indicators Division. (2017, April). Basic 2017 Statistics. Retrieved from Asian Development Bank: https://www.adb.org/sites/default/files/publication/298061/basic-statistics-2017.pdf
Andrews, J., Aroonkit, P., Guevara, M., Jantimapornkli, P., Kimmel, R., Leetranont, K., & Rodrigues, M. (2012, March 2). Improving Energy Supply & Demand in Rural Thai Villages. Retrieved from https://web.wpi.edu/Pubs/E-project/Available/E-project-030212-020648/unrestricted/IQPSSP3_Final_IQP.pdf
ASEAN Secretariat. (2015, November). ASEAN Economic Community Blueprint 2025. Retrieved from http://www.asean.org/wp-content/uploads/images/2015/November/aec-page/AEC-Blueprint-2025-FINAL.pdf
Bank of England. (2015). The role of financial markets: UK as a financial centre. Retrieved from Open Forum 2015: http://www.bankofengland.co.uk/Documents/openforum/pdfs/Infographic.pdf
BBC. (2018 йил 8-MArch). Climate change 'impacts women more than men'. From http://www.bbc.co.uk/news/science-environment-43294221
BEIS. (2015, February 11). 2015 UK Greenhouse Gas Emissions. Retrieved from Final UK greenhouse gas emissions national statistics: https://www.climatebonds.net/files/files/CBI%20State%20of%20the%20Market%202016%20A4.pdf
BertelsmannStiftung. (2016). 2016 SDG Index & Dashboards Report. Retrieved from SDG Index & Dashboards: http://www.sdgindex.org/reports/
BIS. (2009, October). Research to improve the assessment of additionality. Retrieved from BIS Economics Papers: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/191512/Research_to_improve_the_assessment_of_additionality.pdf
BPS. (2017, July). Poverty and Inequality. Retrieved from Statistics Indonesia: https://www.bps.go.id/linkTabelStatis/view/id/1494
CARI. (2015). Thailand Economy Profile. Retrieved from CIMB ASEAN Research Institute: http://www.cariasean.org/asean-2/economy-profiles/thailand-economy-profile/
Carvalho, M., & Fankhauser, S. (2017, April). UK export opportunities in the low-carbon economy. Retrieved from The Centre for Climate Change Economics and Policy (CCCEP): http://www.lse.ac.uk/GranthamInstitute/wp-content/uploads/2017/04/Carvalho-and-Fankhauser-2017.pdf
Climate Bonds Initiative. (2016, July). Bonds and climate change: The state of the market in 2016. Retrieved from Climate Bonds: https://www.climatebonds.net/files/files/CBI%20State%20of%20the%20Market%202016%20A4.pdf
EEVS. (2016). Energy Efficiency Trends volume 17. Retrieved from http://www.eevs.co.uk/latestreport.html
European Chamber of Commerce in Vietnam. (2016 and 2017). EuroCham Whitebook 2017. Retrieved from https://www.eurochamvn.org/Whitebook
Francis, A., Harper, A., & Poggi, C. (2016, June). Will the UK economy succeed in a low carbon world? Retrieved from Green Alliance: http://www.green-alliance.org.uk/resources/UKeconomy_lowcarbonworld
General Statistics Office of Vietnam. (2017). International Statistics. Retrieved from Statistical Data: http://www.gso.gov.vn/Default_en.aspx?tabid=491
GFI. (2016, November). Globalising Green Finance: The UK as an international hub. Retrieved from Green Finance Initiative: http://www.londonstockexchange.com/companies-and-advisors/main-market/documents/cost-of-capital-aninternational-comparison.pdf
GFI. (2017). Retrieved from Green Finance Initiative: http://greenfinanceinitiative.org/
Ghani, E., Kerr, W. R., & O'Connell, S. D. (2012, December). Local industrial structures and female entrepreneurship in India. Journal of Economic Geography, 929-964.
Graves, A., Houghton, M., Edward, M., & Rowell, A. (2015, March). The size and performance of UK Low Carbon Economy: Report for 2010 to 2013. Retrieved from Department for Business Innovation and Skills: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/416240/bis-15-206-size-and-performance-of-uk-low-carbon-economy.pdf
HV, V., Thompson, F., & Tonby, O. (2014, May). Understanding ASEAN: Seven things you need to know. Retrieved from McKinsey&Company Public Sector: http://www.mckinsey.com/industries/public-sector/our-insights/understanding-asean-seven-things-you-need-to-know
IEA. (2015). Southeast Asia Energy Outlook 2015. Retrieved from International Energy Agency: www.irena.org/DocumentDownloads/Publications/IRENA_RE_Power_Costs_2014_report.pdf
IEA. (2016). Energy Efficiency market report 2016. Retrieved from International Energy Agency: https://www.iea.org/eemr16/files/medium-term-energy-efficiency-2016_WEB.PDF
IHS Markit. (2017). Global Trade Atlas: Global Import/Export commodity trade data. Retrieved from IHS Markit: https://www.ihs.com/products/maritime-global-trade-atlas.html
IMF. (2017, May). Asia and the Pacific, May 2017: Preparing for Choppy Seas. Retrieved from Regional economic outlook:: https://www.imf.org/en/Publications/REO/APAC/Issues/2017/04/28/areo0517
International Monetary Fund. (2016, July 19). World economic outlook database. Retrieved from World economic and financial surveys: https://www.imf.org/external/pubs/ft/weo/2016/01/weodata/index.aspx
IRENA. (2015, January). Renewable power generation costs in 2014. Retrieved from Internationla Renewable Energy Agency: http://www.irena.org/DocumentDownloads/Publications/IRENA_RE_Power_Costs_2014_report.pdf
ISO. (2015). Climate change - Mitigation and adaptation. Retrieved from ISO 14080 Briefing Note: https://www.iso.org/files/live/sites/isoorg/files/archive/pdf/en/iso_14080_briefing_note.pdf
Kanagawa, M., & Nakata, T. (2005, September). Analysis of the energy access improvement in developing countries through rural electrification. (T. University, Editor) Retrieved from http://www.iaee.org/documents/denver/kanagawa.pdf
Krueasuk, W., Bhasaputra, P., Pattaraprakorn, W., & Nirukkanaporn, S. (2015). Renewable energy for rural electrification in Thailand: A case study of solar PV rooftop project. GMSARN International Journal 9 .
Malaysian Economic Planning Unit. (2016). Economic Planning Unit Prime Minister's Department. Retrieved from http://www.epu.gov.my/en
Market Analysis and Research, International Trade Centre. (2015). ITC - Trade Map. Retrieved from http://trademap.org/Index.aspx
National Statistical Office. (2017). Statistical Data. Retrieved from Thailand Ministry of Information and Communication Technology: http://web.nso.go.th/en/survey/data_survey/570116_energy_Tables.pdf
NESDB Macroeconomic Strategy and Planning Office. (2017, February 20). Thai Economic Performance in Q4 and 2016 and Outlook for 2017. Retrieved from NESDB Economic Report: http://www.nesdb.go.th/nesdb_en/ewt_dl_link.php?nid=4341&filename=Macroeconomic_Planning
Nicolai, S., Bhatkal, T., Hoy, C., & Aedy, T. (2016, May). Projecting progress: the SDGs in Asia-Pacific. Retrieved from ODI Shaping policy for development: https://www.odi.org/publications/10421-projecting-progress-sdgs-asia-pacific
OEC. (2015). Malaysia Visualisations. Retrieved from The Observatory of Economic Complexity: http://atlas.media.mit.edu/en/
OECD. (2017). Economic outlook for South East Asia, China and India 2017: Addressing energy challenges. Retrieved from OECD Better Policies for Better Lives: http://www.oecd.org/dev/economic-outlook-for-southeast-asia-china-and-india-23101113.htm
Office for National Statistics. (2016, July 29). United Kingdom Balance of Payments - The Pink Book time series dataset. Retrieved from Office for National Statistics - Dataset: https://www.ons.gov.uk/economy/nationalaccounts/balanceofpayments/datasets/pinkbook
Oxera Consulting Ltd. (2006, June). The cost of capital: An international comparison. Retrieved from London Stocke Exchange: http://www.londonstockexchange.com/companies-and-advisors/main-market/documents/cost-of-capital-aninternational-comparison.pdf
Oxford Business Group. (2017). The Report: Myanmar 2017. Retrieved from Oxford Business Group: http://www.oxfordbusinessgroup.com/myanmar-2017
REEEP Policy Database. (2014). Thailand 2014. Retrieved from http://www.reegle.info/policy-and-regulatory-overviews/TH
Tanjangco, B. (2017, April 10). ASEAN Integration: A work in progress. Retrieved from Brink Asia: http://www.brinknews.com/asia/asean-integration-a-work-in-progress/
The ASEAN Secretariat. (2012, November). 2011 ASEAN statistical report on the Millenium Development Goals. Retrieved from ASEANstats: http://www.aseanstats.org/wp-content/uploads/2017/03/ASEAN-Statistical-Report-in-MDG-2012.pdf
The ASEAN Secretariat. (2016, November). External Trade Statistics. Retrieved from Association of South East Asian Nations: http://asean.org/?static_post=external-trade-statistics-3
The World Bank. (2017). Poverty and Equity Database. Retrieved from The World Bank Databank: http://data.worldbank.org/topic/poverty
UN Comtrade data. (2016). International Trade in Goods based on UN Comtrade data. Retrieved from UN Comtrade data: https://comtrade.un.org/labs/BIS-trade-in-goods/?reporter=826&partner=764&year=2016&flow=2
UN Economic and Social Commission for Asia and the Pacific. (2013, July 11). Report of the Asian and Pacific Energy Forum. Retrieved from UN Economic and Social Council: http://undocs.org/en/E/ESCAP/APEF/3
UNDP. (2013, December 10). Gender and climate change - Asia and the Pacific. Retrieved from United Nations Development Programme: http://www.undp.org/content/undp/en/home/librarypage/womens-empowerment/gender_and_environmentenergy/gender-and-climate-change-asia-pacific.html
UNEP. (2016). The United Kingdom: Global hub, local dynamics. Retrieved from Inquiry: Design of a sustainable financial system: http://unepinquiry.org/wp-content/uploads/2015/10/UK_Global_Hub_Local_Dynamics.pdf
Vietnam Customs. (2017). Customs Trade Statistics. Retrieved from https://www.customs.gov.vn/Lists/EnglishStatistics/Default.aspx
Warr, P. (2014, December). The Drivers of Poverty Reduction. In I. Coxhead (Ed.), Routledge Handbook of Southeast Asian Economics (p. 23). Canberra, Australia. Retrieved from http://www.aae.wisc.edu/hoseae/chapters/14-Warr.pdf
WB. (2016, February 23). Vietnam 2035: Toward Prosperity, Creativity, Equity, and Democracy. Retrieved from The World Bank: http://www.worldbank.org/en/news/infographic/2016/02/23/vietnam-2035-toward-prosperity-creativity-equity-and-democracy
WEF. (2016, May 30). Economic Growth and Scoial Inclusion. Retrieved from World Economic Forum: http://widgets.weforum.org/cards/#!economic-growth-and-social-inclusion-in-asean
World Bank Group. (2014, November). Myanmar: Ending poverty and boosting shared prosperity in a time of transition. Retrieved from http://documents.worldbank.org/curated/en/871761468109465157/pdf/930500CSD0P150070Box385388B00OUO090.pdf
World Bank Group. (2017, June). Global economic prospects: A fragile recovery. Retrieved from https://openknowledge.worldbank.org/bitstream/handle/10986/26800/9781464810244.pdf
WTO. (2015). Thailand. Retrieved from World Trade Organisation: http://stat.wto.org/CountryProfile/WSDBCountryPFView.aspx?Language=E&Country=TH