Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, review recommendations and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Prosperity Fund: Global Business Environment Programme
Programme Value: £30m		Review Date: Dec 2018
Programme Code:	Start Date: / Signing of Administrative Arrangement– Nov 2017 / First payment – Dec 2017	End Date: Mar 2021

Summary of Programme Performance
Year	2017/18	2018/19	2019/20	2020/21	2021
Programme Score		B
Risk Rating		Moderate

The scoring of this annual review is a reflection that few outputs can be expected at this early stage. Rating B: outputs moderately did not meet expectation. There is scope to improve the structure, governance and management of the programme, to increase confidence in its success. This is as would be expected as this first review has taken place at an early stage of delivery. Programme-level milestones are still under development and due to be set by April 2019, while country-level milestones were scoped and finalised at inception. It will be vital that a further clear assessment of performance is made at the one-year point (i.e. April 2019). All parties should be clear that milestones will be expected to be on track, to ensure the overall success of this high level and potentially high impact programme, focussed on economic reform and opening up business opportunities in middle emerging economies.

Summary of progress and lessons learnt since last review
N/A
The Global Business Environment Programme (GBEP) aims to improve the business environment, in an initial six developing, middle income economies, and to develop analytical tools and products which focus on evidence-based policy approaches, at a cost of £30m over 4 years. The World Bank Group (WBG) is currently the single delivery partner. The GBEP got off to a later than expected start due to delays in UK decision making. This is therefore a first review, taking account of only around 6 months of evidence of full implementation, following the initial inception phase, on signing the Administration Arrangement in November 2017. As such, it is too early to expect major progress or see significant impacts or secondary benefits. Realisation of secondary benefits arising from the GBEP is a task for HM Government. The review is an opportunity to assess: progress against objectives; value for money; treatment of gender and inclusion issues as an overarching priority topic; overall management of risk and deliverables expected by the next review.
Recommendation: In recognition of the delays resulting from political change in partner countries, the programme should continue to mitigate risk from political change. Delivering the planned geographic diversification will be central to this approach, alongside implementation of the other recommendations in this report. Implementation should continue to be monitored closely and further changes considered as necessary.

The working relations between the FCO (Foreign and Commonwealth Office) and the WBG appear to be strong, professional and objective. The GBEP has been given a good initial steer by the joint Partnership Council. There is scope to improve future reporting, milestones and the results framework.. The initial reporting draws on the priorities in the Business Case.. At this stage it is too early to see wider benefits to international and UK economic interests.
Recommendation: The risk that delivery could diverge from the original business case objectives should be mitigated by the programme team and the WBG further strengthening in-country working, to ensure the successful delivery of primary benefits to partner countries and secondary benefits to international and UK interests.

The GBEP is intended to provide technical assistance to national and sub-national governments to support their reform efforts by improving capacity in the following areas:
- Policies and Regulations - Business regulation and practice
- Value Chains - Developing linkages with local and global value chains
- Transparency - Greater market competition and transparency
- Standards - Quality standards in markets and trade
- Data - Data gathering and sharing on the quality of the business environment.

The review addresses assessment and makes recommendations both for the top level Global Influence Initiative; and for progressing the programme in each of the six pilot countries – Brazil, Indonesia, Nigeria, Pakistan, South Africa and Turkey.
 The programme’s Theory of Change was developed during the business case phase and has been guiding the development of the results framework, as specified in the Administration Agreement (the governing document for the GBEP Trust Fund). Detailed country-level results frameworks were developed in the first six months of the programme and presented to the review team. As the next step, it was confirmed at the Nov 2018 Partnership Council meeting that a Theory of Change for the Global Influence Initiative and a programme-level logframe, would be developed by Apr 2019. (The Theory of Change is a standard economic tool and cascades from the analogous top level model in place for the overall Prosperity Fund). These aspects are key to the rigour of the future monitoring and evaluation of the GBEP.
Recommendation: Continue the good progress on further updating the Theory of Change and capturing programme-level results to provide greater understanding of programme performance.

The results framework is also important in showing how financial support is being used against the different packages of activity. A more accessible process is needed for FCO to assess, record, and mitigate risk through use of a risk register.
Recommendation: Focus on linking finance more closely to activities to and milestones to gain a greater understanding and control of budget performance. The risk register should be developed and maintained, and used actively by FCO as part of overall programme management.

Further recommendations for the next year on Governance and Risk, Financial Management, Monitoring and Results, and Gender and Inclusion, are shown in Section B, Performance and Conclusions.
SRO Commentary:
The main recommendations of this review, for the period to 31 December 2018, provide a useful basis for future Global Business Environment Programme (GBEP) work. I have asked the programme management team to act on them.
 The GBEP is a pioneering partnership between the Foreign & Commonwealth Office (FCO) and the World Bank Group (WBG), as part of the United Kingdom’s cross-Government Prosperity Fund. It has started well. Some challenges, outside the programme management team’s control, particularly political developments in two priority countries - Turkey and Pakistan - somewhat slowed aspects of planned, early progress. Mitigation measures, foreseen in the programme design to meet such eventualities, were activated and are being implemented. Other elements of the programme have achieved more than foreseen in initial plans, for example in respect of: assistance to update Nigeria’s investment climate laws; support to deliver South Africa’s US$100 billion investment objective; and delivery of over one hundred analytical outputs to benefit more than fifty reforming countries.
The lack of a Prosperity Fund-level monitoring and evaluation system (which is under development) has hampered both the programme management team, and the team which carried out this review.
I judge that the standard of work of the FCO and WBG programme management team is high, and fully meets expectations. The programme management team projects full spend and full delivery over the GBEP’s lifetime. I judge that assessment, and the associated moderate level of risk, to be accurate.
A. Introduction and Context (1 page)

Link to Business Case:	https://www.gov.uk/government/publications/global-business-environment-programme
DevTracker Link to Log frame:

The Global Business Environment Programme is a partnership between the Prosperity Fund, delivered by the Foreign & Commonwealth Office (FCO) and the World Bank Group (WBG), delivered by the International Finance Corporation (IFC) through their Improving Business Environment Programme window (IBEP). Total funding allocated is £30million over a 4-year period, of which £28.5m is managed by the WBG via a single donor trust fund.
The programme aims to support the business environment through two main channels- a global programme of activities – the Global Influence Initiative (GII) and through six country programmes. There is scope within the business case to expand the list of countries, but the current list where the programme is active is; Brazil, Indonesia, Nigeria. Pakistan, South Africa, and Turkey. The programme has plans to expand to include Philippines, Malaysia and Vietnam, in line with the business case, and as proposed for consideration by the Portfolio Board and the Joint Council. The proposed geographic diversification is in line with the business case and within the SRO’s delegated limits for change control; this has been agreed with the Joint Funds Unit. The budget envelope and the period for implementation (i.e. up to March 2021) will remain as agreed by the Portfolio Board.
The primary impact envisaged is to support c. 20-25 major economic reforms, resulting in savings to business and additional investment across the countries concerned. Conservative estimates are that c. 9 reforms amount to £1.7bn to aggregate GDP over 10 years. Secondary benefits including opening up markets and promoting investor confidence, which will ultimately lead to greater export and investment returns to international and UK business. Conservative estimates suggest that benefits to the UK alone could range from £50 to £170m over 10 years. Actions to realise secondary benefits are for HM Government (not the World Bank Group).

Recommendation: Future review reports should assess how interventions through the GBEP lead to the primary and secondary impacts envisaged in the Business Case

The core objectives of the global engagement work through the GII (30% of the budget) are to use the World Bank’s global reach and analytical work to support the design and implementation of reforms in the focal countries:
1. Fill existing gaps in business environment data and research.
2. Advance thought leadership by shaping frontier business environment topics
3. Reinforce the analytical foundation of various business environment reform areas.
4. Strengthen the design and implementation of business environment reforms in MICs.
5. Foster peer to-peer learning across a wide cross-section of reforming countries.

At the country level, (70% of the budget) the objectives are to:
1. Strengthen business regulations and practices.
2. Enhance business competitiveness
3. Catalyse shared prosperity through support to subnational efforts and equity.
The major components include analytics and diagnostics, reform toolkits, adaptive evidence-based policy design. It covers both cross-sectoral and sector dimensions with main components around FDI linkages, quality infrastructure and standards, good regulatory practice, markets and competition.
This was summarised in the original Business Case [1] as follows:
[1] https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/706880/Business-Case-Global-Business-Environment-Programme.odt
Figure 2: Programme overview

WINDOWS/ THEMATIC PILLARS	OBJECTIVES/SOLUTION AREAS	BUDGET (£30m)	IMPACTS	RISKS
Global Influence Initiative	Analytics and diagnostics / Reform toolkits / Adaptive policy design / Biennial Business Competitive Report and Forum	30%	Advancing thought leadership and reinforced design and implementation of business environment reforms in MICs. / UK leadership and global knowledge exchange on business environment topics.	Low / Anticipated high-level Government and business community support / Deliverables under purview of WBG
Country Engagements: / I. Strengthening business regulations and practices	Simplifying and strengthening business regulations / Promoting good regulatory practices / Opening markets and competition for investment	70%	More open and predictable markets and improved business regulations in MICs facilitating firm savings, growth, investment, exports, productivity and jobs.	Low / Anticipated high-level Government support / Technical assistance delivery is a core competency of WBG global and country teams / Proven concepts and track records
II. Enhancing business competitiveness	Increasing local value addition and job creation / Supporting firms to meet standards to access investment and exports		Improved competitiveness of locally-operating firms creating jobs, upgrading products and expanding internationally. / Increased linkages with MICs for international and UK firms.	Medium / Cutting edge topics requiring dependence on Government capacity / Sophistication and absorption capacity of private sector unknown
III. Subnational support and equity	Improving subnational business regulations / Improving subnational firm incentives frameworks		More equitable and inclusive growth by engaging at subnational level. / Increased business confidence and opportunities for international and UK firms in MICs.	Low-Medium / Anticipated high-level Government support with known capacity limitations at subnational level / Technical assistance delivery is a core competency of T&C global and country teams

Programme activities are intended to contribute to overall impacts envisaged in the original business case, as follows:
- Creation and growth of firms
- More and better jobs (including for women and youth)
- Greater aggregate productivity
- Higher investment and trade flows
- Increased international and UK exports and market access
- Increased international and UK investments

The GBEP aims to demonstrate added value through alignment with the overall Prosperity Fund Theory of Change, as set out in the Business Case. The GBEP aims to contribute to 3 of the 5 intermediate outcomes identified for the Prosperity Fund – i.e. Trade, Financial and Economic Reform, and Ease of Doing Business. The headline delivery items from the Programme are the flagship Investment Competitive Reports, biennial forums, and technical support to investment entry, promotion and competition reforms as well as improvements in the Ease of Doing Business rankings
Delays in UK decision making and World Bank restructuring, which could not have been foreseen, meant that the 4-year programme could not start as originally envisaged in summer and subsequently autumn 2017[2]. The Administration Arrangement between the FCO and the World Bank was signed November 2017 this report reviews activity from that date until Dec 2018.
[2] Specified on p.45 of Business case
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

The basic premise of the programme and the choice of partner are sound. The World Bank Group’s reach, established reputation and professional networks gives significant scope to expand delivery and optimise leverage in developing a partnership approach. The programme does not aim to open up new frontiers of economic reform. Rather it builds on established WBG products and methodologies to accelerate and deepen the level of interventions to support global ease of doing business. This means that the programme should be able to create significant early returns as well as offering considerable leverage and value for money.
The programme team has now set up a good governance structure, developed an ambitious set of objectives and has also brought together good quality teams. The relationship between FCO programme management and WBG management is excellent, being open, candid and mutually supportive. Good evidence of this was seen by the review team - e.g. recommendations were actively discussed and acted upon even before the formal report has been issued. This will stand the programme in good stead as it moves through the delivery phases. As this programme is still very early in its delivery it is difficult to assess outcomes with any degree of useful accuracy Instead the review team has focussed more of the structure of the programme, attempting to assess the readiness and ability of the programme to succeed in future years. In that regard we do not see any areas that raise major concerns, but we do offer advice and recommendations that we believe would help to ensure delivery and value for money in future years, particularly through tightening up programme governance. The team commends the FCO programme team in setting an excellent example in relationship with the WBG, whilst also recommending that they also learn from other donors, who have been able to get the best out of the WBG in different areas of work.
Annual Outcome Assessment (Primary Benefits– inclusive growth, gender equality, women’s economic empowerment and poverty reduction)
We would expect to see robust results materialising in years 3 and 4 of the programme. Implementation progress is on track program-level indicators are being summarized from country-level results frameworks.. This is in part due to the programme waiting for Fund-level KPIs to be produced that are intended to underpin and guide the programme-level indicators; it is important that Fund-level monitoring and evaluation activities are able to keep pace with programme delivery.
Recommendation: The Results Framework should be finalized by April 2019, including presentation of an overarching summary log frame, and put into active use for monitoring and evaluation.
The WBG have used the funding to set up the ‘Improving the Business Environment for Prosperity (IBEP) Programme as a thematic window to deliver the GBEP. The stated objectives for the IBEP are in line with the objectives, leading to the expected future primary outcomes, as set out in the GBEP Business Case, at both global and country level.
Annual Outcome Assessment (Secondary Benefits)- responsible by the HMG/FCO
The estimated secondary benefits to international and UK business, as set out in the business case, include potentially £540million in additional UK export value over 10years. The programme’s secondary benefits plan sets out the following (non-ODA funded) measures to maximise additional impact:

- Continuous engagement with UK business bodies and representatives during implementation will provide a practical assessment of UK companies’ readiness to compete for secondary benefits in the form of market access, investment and exports;
- Scope to map resulting opportunities to existing pipelines will be explored with DIT, including monitoring DIT pipeline data and overall trade and investment data
- Perception of UK companies along with FDI data will be monitored in surveys and products under the cross-cutting component of the programme.

However, the review team did not see any practical evidence or examples of these activities when conducting interviews. Indeed, in most cases the involvement of the main stakeholder – DIT - was low to non-existent. This is due to the stage of the programme, and the need to engage end-recipients of potential benefits at the appropriate time (if benefits are not likely to start to be realised for several years, there is little point expending HMG resource on them in the early stages of the programme).

Recommendation: FCO/HMG should develop an engagement plan to ensure that DIT are involved and support the realisation of secondary benefits.

Overall Output Score and Description

B- Outputs moderately did not meet expectation

The scoring of this annual review is a reflection that few outputs can be expected at this early stage and there is scope to improve the structure, governance and management of the programme, to increase confidence in its success. As set out above, the programme is at an early stage of delivery.

Outputs largely appear to be on track, however there have been delays both at the global level (due to WBG restructuring), and in several of the country projects, due to changes in government following elections).

The review team feel that the programme is falling slightly short of meeting expectations at this stage for the following reasons:
  - The programme is underspending against initial forecast
  - Governance, including Country Sounding Boards, is still bedding in at country level so is not yet generating sufficient influence and direction over the programme activities
  - The programme implementation plans could have a stronger focus on gender issues, a priority overarching topic set out in the business case.

Key lessons
Set-up and Financial Management:
As specified in the Business Case, this programme necessarily had to be financed through a trust fund administered by the WBG. The Administration Arrangement states that £6.5m would be paid immediately on countersignature, which was expected in Spring 2017, with a further £5.5m on or after April 2018 and each year thereafter. In fact, the first instalment of £6.5m was only paid in December 2017 following the signing of the arrangement in late November 2017. A further £2.7m was paid in August 2018 to cover activities to the end of Year 1, in March 2019. Delays to the originally envisaged start in Summer 2017 led to an underspend in Year 0. As WBG financial years run from July to June, staging of payments in accordance with need for disbursement by the World Bank, has been put in place to ensure optimum use of funds. Going forward it will be important to clarify the implications of the agreed milestone-linked payments on underspend risk, including in relation to the financial years of both the FCO and the World Bank Group
Recommendation: Monitoring expenditure against milestones across financial years (including differing financial years for the World Bank and HMG) will require close scrutiny in future to support programme-level financial management.

1. Recommendation: A biannual financial forecast should be developed for each component, together with profiled spend across the year. This forecast will also need to account for the different financial years and associated reporting requirements and should help build understanding of delivery risk, slippage and acceleration, as well as help identify potential under or overspends in country.
2. Recommendation: Key milestones and activities should be made more easily trackable in the results framework and these should be used to support budget allocation decisions.

Governance:
The programme is unusual in that it aims to create added value by developing a true partnership between the FCO and the WBG rather that the more normal donor implementer relationship. In many ways this is breaking new ground in the FCO’s relationship with the Bank. The governance arrangements aim to strengthen this aim through the biannual Partnership Council meetings. The review team were present at a preparation meeting for the upcoming partnership meeting and can attest to the fact that there is a good, mutually respectful and open relationship between the two HQ based teams. This sets a great foundation from which to manage the programme going forward. This is to the credit of both sides who have worked hard to build mutual understanding of needs and requirements as well as a pragmatic approach to developing achievable objectives, but this could develop further.
The relationship between the FCO programme team in London and WBG Washington is excellent and an example of best practice. There are legacy relationship expectations from WBG country teams, not accustomed to partnership arrangements, to recognise the relationship now goes further than that explaining work completed, but includes discussing and agreeing future plans. It is important to further build the co-operation at country level and to develop the mechanism of the Country Sounding Boards. Also to exchange best practice across countries in the programme. At present, there is a mismatch in personnel on the ground with long-term WBG professionals with significant expertise and track records in place; and FCO personnel still in process of appointment. This also places an undue burden on the team in London. Developing a shared approach and working culture in country is important, particularly with regard to data transparency and accountability, and forward planning in relation to the programme delivery and the original business case
Specific delivery plans need to be developed for each component, as part of the development of the results framework. There have been no major changes to the overall programme plan beyond managing slippage. However due to political change in a number of countries there is a risk that slippage becomes chronic. The team has explored options to expand the geographic scope of the programme to include Philippines, Malaysia and Vietnam to ensure maximum benefits from the programme are realised. A cross-Whitehall Advisory Council was set up in November 2018, which will help facilitate exchange of learning and best practice. Cross-Whitehall engagement will help to realise any additional benefits to international and UK interests from the programme.
Recommendation: There should be a continued drive for the various country programmes to exchange best practice.

1. Recommendation: The FCO admin staffing structure and objectives should be reviewed to improve productivity and oversight, in line with the programme objectives, especially if there is further geographic expansion. This should include deploying FCO employed staff on programme rather than admin to bridge the gap between WBG and mission staff.
2. Recommendation: FCO-held country-level risk registers should follow a more standardised approach and should clearly feed into the programme level register.
3. Recommendation: FCO quarterly reports should be produced at a country level in order to support the programme level reports. This should be done alongside WBG reporting and should represent the views of FCO country project/mission staff.

Risk Management:
With each focal country facing elections in 2018/19, the risk of political uncertainty and its potential impact remains high. The programme would benefit from additional measures to assess and ameliorate the impact of key risks, for example, by maintaining individual country risk registers at each post. This would enable a clearer cascade of risk matrices from the programme to the country level (within the FCO reporting system). It is worth noting that the World Bank system does have formal risk cascade from the country level on to the programme level. Individual country risk registers, which are being adopted, will support a more robust local and wider response to unexpected change.
Recommendation: FCO to review its programme risk assessment methodology.

Monitoring and Reporting:
The WBG is a trusted partner with a long track record of success and the GBEP programme is predominantly building on previous successful work. The WBG therefore already had a Theory of Change (standard economic tool for change programmes) and results framework set up for this work which has provided a significant level of comfort that the programme is and will deliver as expected. However, these Theory of Change and results frameworks do not match exactly those being developed by the Prosperity Fund. Work is underway to develop a methodology to understand and transition between the two approaches – this is being led by the Prosperity Fund MREL contracts and is outside the direct control of the programme team.
1. Recommendation: An aggregate log frame, reflecting all the country programmes and GBEP overall Theory of Change, should be finalised as soon as possible. Progress against this framework should be set out in bi-annual WBG reports to make it easier to monitor progress.
2. Recommendation: All reporting should clarify the relationships between the different reporting year end dates for FCO and WBG
3. Recommendation: (For cross-government Prosperity Fund management): Fund-wide value for money indicators under development should be finalised as soon as possible and monitored (note this is a Prosperity Fund-wide issue and is outside the direct control of the programme team.

1. Recommendation: Appropriate indicators should be developed for the global component.
2. Recommendation: An update of the contribution of other donor activity linked to this programme should be completed to ensure that leverage is properly captured in the Value for Money calculation.

Gender and Inclusion
There are concerns that despite Gender being raised as an area of concern by the joint April GBE Council and recommendations made for action, it remains an important yet relatively weak theme not yet fully reflected in program plans and that the same recommendations are being reiterated (i.e. gender components; develop gender indicators, regular progress reporting; and peer learning). It was confirmed at the Partnership Council meeting in November 2018 that Gender and Inclusion remains an important overarching theme, which is not yet fully reflected in the Programme activities.
The WBG Progress reports do not demonstrate satisfactory progress to ensure consistent and effective delivery of the programme’s proposed approach to gender and inclusion. It should be noted that the business case is compliant with the Gender Equality Act and gender disaggregated indicators for all components are being developed. Progress at a country level on gender and inclusion has been mixed, with only two out of six country programmes demonstrating targeted interventions, in line with recognised international good practice on gender dimensions of the business environment. Promising work is planned in Brazil (strengthening data on women’s entrepreneurship) and Pakistan (reform of business regulations/institutions impacting young and women-owned firms; sector scan to consider the potential of the assessed sectors for women employment; public private dialogue on the role of investment and investment policy in promoting women’s empowerment).
Focused attention, improved capability and institutional incentives are needed in order to ensure systematic, programme-wide delivery of Business Case expectations and alignment with both the Prosperity Fund’s Gender and Inclusion (G&I) Policy and the WBG Gender Strategy for Gender Equality, Poverty Reduction and Inclusive Growth (2016-2023). The WBG’s Gender Strategy raises ambition on gender equality and moves beyond mainstreaming to identifying outcomes and measuring results – requiring country-driven approaches, better diagnostics, and use of evidence of what works.
Recommendation: Prioritise improving progress and performance on gender and inclusion issues across the programme in order to meet and deliver expectations specified in the UK Gender Equality Act compliance statement in the business case. The WBG should report on progress on gender and inclusion in its regular six monthly reports.

Recommendation: The GBEP should, to the extent that this can be effective in the context of the delivery of the programme, develop global/country level Gender and Inclusion Assessments/Diagnostics, Gender and Inclusion Action Plans (with details of specific interventions for each of the components), Gender-sensitive outcomes/outputs/indicators and targets (in line with the WBG Trade and Competitiveness Gender Results Framework), build in institutional incentives, and strengthen systems and processes. Programme plans should identify country programme’s level of ambition (as per the Gender and Inclusion Programme Framework levels) - whether Minimum compliance, Empowerment or Transformative approach.

Summary of changes to the logframe since the last annual review
A Log Frame (standard economic tool for reporting on programme implementation) was developed by the WBG, building on previous work they have done in this area. An overall programme logframe linking the WBG log frame and that of the Prosperity Fund was still being finalised at the time of writing the annual review, due to the Prosperity Fund-wide approach to monitoring and evaluation still being under design.

## C: DETAILED OUTPUT SCORING
*Note: All Outputs, Milestones and Indicators are examples intended to provide a snapshot and do not cover the full range of programme activity. Further detail of milestones and indicators can be found in the country level results frameworks. As this review is taking place at the mid-point of Year 1 and because milestones are for the end of Year 1 and indicators in the logframe are still being developed, the review has not scored or weighted the outputs. A narrative assessment of progress is provided.
Output Title	Roadmaps and recommended action plans developed for government to reduce regulatory barriers and improve competition
Output number		1	Output Score	N/A
Risk:		Moderate	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of new laws/regulations/amendments/codes/government policies drafted, or contributed to the drafting / Number of procedures/firm-level policies/practices/standards recommended for improvement or elimination	Incentives analysis report issued (Turkey)	On track to be achieved at the end of Year 1
	Recommendations on linkages policy (Turkey)
	Doing business action plans issued (South Africa)
	Diagnostic report on legal and institutional framework for dispute resolution (South Africa)	This milestone is not reported against in the recent mid-year report
	Recommendations on improving the environmental licensing system (Brazil)	On track to be achieved at the end of Year 1
	Suggested amendments to competition legislation (1999) and related regulations (Indonesia)

Key Points
Examples of outputs for the first 6 months include:
- In Turkey, the World Bank has focused their work on the data and methodological approach for the incentives analysis. Data gaps have been identified that require data to be transfer onto a new system to move forwards with this. The team also analysed the impact of SME and R&D incentives programmes, which found that the Scientific and Technological Research Council of Turkey is more effective in increasing total factor productivity and the Small and Medium Enterprises Development and Promotion Administration has a greater impact on employment. These analyses can be used as a model for the design or regulation of grant programmes going forwards.
- Also in Turkey, the team prepared a diagnostic/project proposal on FDI linkages with the aim of aligning counterparts and stakeholders around implementation activities. They also worked on a data-driven approach to assess the gap between supply and demand in selected manufacturing sectors.
- In South Africa, 3 technical working groups under InvestSA have been established to drive the reform agenda of multiple Doing Business indicators in preparation of the DB19 report cycle. Updates and memos have been shared with InvestSA and the President’s office, but action plans have not yet been developed (planned for the second half of Year 1).
- In Indonesia, the team drafted 3 policy notes on specific aspects of the competition law and held a workshop with relevant agencies. The results of this analysis aims to inform the upcoming revision of the negative investments list.
- In Brazil, the team drafted a technical report on the environmental licensing process and supervision in Ceara and implemented several transparency measures.
- Progress in Pakistan was hampered by the elections over the summer, however, broad progress was made on strengthening investment attraction and promotion as a whole. This included beginning the process of preparing an investment strategy for the new government.

There are several activities planned in the second half of the programme year, including a mapping of tax and grant-based firm incentives and support schemes that encourage upgrading, foreign investment, R&D and internationalisation (Turkey) and further dissemination of the competition law policy notes in Indonesia, which will include training for officials on competition policy (drawing on experience in other successful countries).

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
As with the other outputs, indicators and milestones should be clearly mapped out and regularly reported against by the World Bank.

## C: DETAILED OUTPUT SCORING
Output Title	Recommend developments for improved data management process and standard data quality across government
Output number		2	Output Score	N/A
Risk:		Moderate	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of institutions supported for implementation of investor relationship management system	Recommendations on process and tracking mechanism for investor grievances (Brazil)	On track to be achieved at the end of Year 1.
	Design and implementation of an investor relationship management system (Pakistan)
	Tools developed at global level (Global)

Key Points
As this review is taking place at the mid-point of Year 1 and because milestones are for the end of Year 1 and indicators in the logframe are still being developed, the review of this output will be light-touch.
In Brazil, the team have implemented a systematic investors reform mechanism (SIRM) for Sao Paulo that will help government respond to feedback from investors on issues they are experiencing. As preparatory work for implementing this, an investor survey is being implemented to identify the type of investor grievances and the possible investment at risk due to government actions. The feasibility of scaling this work up to federal level will be explored during the second year of the programme.
At the global level, highlights include the piloting of a survey tool to assess sources of regulatory unpredictability and its impact on business decisions. In the second half of the year, the World Bank intends to update its methodology for calculating the investment generated from reforms, which is a welcome step forward and will help to generate the evidence on what works and doesn’t work.
Summary of responses to issues raised in previous annual reviews (where relevant) - N/A
Recommendations As with the other outputs, indicators and milestones should be clearly mapped out and regularly reported against by the World Bank. Brazil has plans to support improved capacity for data management across company registries and availability of data on women entrepreneurship, which should be specified in output-level indicators and learning shared with other country programmes
## C: DETAILED OUTPUT SCORING

Output Title	Specific regulatory reforms in priority sectors (including gender)
Output number		3	Output Score	N/A
Risk:		Minor	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of procedures/firm-level policies/practices/standards recommended for improvement or elimination / Number of recommended laws/regulations/amendments/codes enacted or government policies adopted / Number of reports (assessments, surveys, manuals, Phase I/strategic option reports) completed / Number of women participants in workshops, training events, seminars, conferences, etc.	Assessment of business registration data and recommendations for a gender-disaggregated database (Brazil)	On track to be achieved by the end of Year 1, however, not all gender milestones have been formalised.
	Recommendations to simplify port governance procedures (Indonesia)

Key Points
As this review is taking place at the mid-point of Year 1 and because milestones are for the end of Year 1 and indicators in the logframe are still being developed, the review of this output will be light-touch.
The World Bank has obtained and analysed business registration data from 8 states, presented the benefits of having a standardised national database at a national conference and made progress in discussions with the National Department of Business Registration and Integration to collaborate in creating the conditions for greater consistency in business registration data and increase the capacity for data analytics.
In Indonesia, efforts from the World Bank triggered a study for benchmarking port tariff setting in Indonesia, in comparison to other countries, and to provide options for reforms. This work is due to commence in the second half of the year. Going forwards, the project will support the launch of the ship waste management notification and the drafting of a compulsory notification system in parallel. These aim to attract private investment in the sub-sector.
There is a need to continue to give attention to the gender aspects of the programme. There is some evidence of gender elements being included in some country programmes, but more ambition and momentum is required in others.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
As with the other outputs, indicators and milestones should be clearly mapped out and regularly reported against by the World Bank.

## C: DETAILED OUTPUT SCORING

Output Title	Develop policy/institute F/W and investment strategies
Output number		4	Output Score	N/A
Risk:		Minor	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Institutional/strategic changes recommended / Number of entities receiving advisory services / Number of new laws/regulations/amendments/codes/government policies drafted, or contributed to the drafting / Number of documented interests by investors/private partnerships	Report on investment policy assessment and reform roadmap issued (South Africa)	On track to be achieved by the end of Year 1
	Recommendations on amendments to investment law (Nigeria)
	Recommendations to consolidate and modernise investment law (Pakistan)

Key Points
As this review is taking place at the mid-point of Year 1 and because milestones are for the end of Year 1 and indicators in the logframe are still being developed, the review of this output will be light-touch.
Good progress has been made under the investment policy and promotion component of the South Africa programme. A desk-based analysis of trends, opportunities, and barriers to FDI were completed and an FDI strategy development process was launched. One of the highlights of the programme in South Africa, was the ability of the programme to second two expert advisers directly into the office of the President and its support to InvestSA in the run up to the investment summit earlier this year.
In Nigeria, the team completed an assessment of the investment law and found areas that could be improved. In the second half of the year, they will commence institutional reform support to the Nigerian Investment Promotion Commission to take these forwards, as well as looking at the structure and set up of the NIPC.
Progress in Pakistan has been slower than expected due to the elections over the summer; however, activities still moved forwards. This include beginning the process of preparing an investment strategy for the new government, an article-by-article analysis of the investment legal framework and a sector scanning exercise is underway.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
As with the other outputs, indicators and milestones should be clearly mapped out and regularly reported against by the World Bank. At present, there is no gender related indicators, which is a concern.
As there is no evidence of specific gender-focused reforms taking place in Pakistan, despite this being an objective of the country programme, the World Bank should dedicate more attention to ensuring work is aimed at improving women’s economic opportunities.
On Business Regulation Reform, there are plans to support the Government of Brazil in evidence-based policy formulation and implementation; both with focus on regulations and institutions impacting young and women-owned firms. Similar approaches should be explored for replication in other programme countries.

## C: DETAILED OUTPUT SCORING

Output Title	Develop tools and techniques to improve existing systems and processes (global component)
Output number		5	Output Score	N/A
Risk:		Minor	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Indicators still being developed	Launch and update toolkits on investment promotion and entry.	Appears on track to be achieved by the end of Year 1
	Quality infrastructure toolkit peer-reviewed and published.	Achieved
	Develop additional online material and disseminate the Markets and Competition Policy Assessment Tool.	Appears on track to be achieved by the end of Year 1
	Finalise product market regulation for developing economies (developed with OECD).	Not reported in mid-year progress report

Key Points
As this review is taking place at the mid-point of Year 1 and because milestones are for the end of Year 1 and indicators in the logframe are still being developed, the review of this output will be light-touch. The World Bank is not currently reporting against these milestones so it is difficult to fully assess if they are on track for completion.
Significant activity has taken place under this component:
- Under investment promotion, the team have developed a product brochure and case studies highlighting a number of countries. This brochure covers the institutional framework for investment promotion, corporate planning and sector prioritisation and investor services. They are also developing a series of tools for analysing a country’s investment promotion opportunities and challenges (with supplementary tool for measuring investor satisfaction).
- The work on Quality Infrastructure has been one of the highlights of the entire global component. The diagnostic and reform toolkit has been published and was highly commended by World Bank management. The team have also hosted related workshops and events and published a webpage on the topic.
- Other activities have included the early stages of development of a manual for government counterparts to implement a system of risk based regulation; a draft study identifying the key trends in inspections reforms; and continued development of a framework to support outward FDI through a ten-step process.

The global component has an ambitious set of activities planned for the second half of the year, including enhancements to the Markets and Competition Policy Assessment Tool.
During the first year the WBG has produced three guidance notes on Gender and investment climate on:
(1) A “How To” note on strengthening gender-related data collection and analysis in investment climate diagnostics;
(2) A “How To” note on assessing gender-specific implementation gaps in IC reforms; and
(3) a note on best practices for behavioural incentives to promote gender equality.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
As with the other outputs, indicators and milestones should be clearly mapped out and regularly reported against by the World Bank.
Tools developed under the global component should, as much as possible, be utilised in the country programmes.

## C: DETAILED OUTPUT SCORING

Output Title	National and sub-national coordination and collaboration to align with good practice
Output number		6	Output Score	N/A
Risk:		Minor	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of new laws/regulations/amendments/codes/government policies drafted, or contributed to the drafting / Number of procedures/firm-level policies/practices/standards recommended for improvement or elimination / Number of reports (assessments, surveys, manuals, Phase I/strategic option reports) completed / Number of investment leads generated	Legal and institutional recommendations on set up of Ogun State Investment Promotion Agency (Nigeria)	Achieved

Key Points
As this review is taking place at the mid-point of Year 1 and because milestones are for the end of Year 1 and indicators in the logframe are still being developed, the review of this output will be light-touch.
The key milestone for this output was achieved in July 2018. The Ogun State Investment Promotion and Facilitation Agency (OgunInvest) launched on 5th July, which the World Bank supported with technical advice on the strategic development plan. The team also completed a sector scan in September 2018 which identifies the sectors the states should focus its promotional and policy advocacy efforts on.
This year, the team completed the sub-national Doing Business report in Nigeria, which covered all 36 states and assesses 4 indicators. However, there is no evidence in World Bank reporting of collaboration between the national and sub-national levels.
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
As with the other outputs, indicators and milestones should be clearly mapped out and regularly reported against by the World Bank.
The programme should seek opportunities to fill evidence and capacity gaps on gender and wider inclusion dimensions of the investment climate and share learning. In Pakistan, the Supporting Investment in priority sectors will include a gender dimension aimed at understanding the impact on equality that FDI can have in different sectors and maximizing the benefits that FDI can have for women. A sector scan will consider the potential of assessed investment sectors for women’s employment and other dimensions of women’s economic empowerment. It will also assess whether Pakistan’s performance of different dimensions of gender equality has any implications for its attractiveness to investment in these sectors

## C: DETAILED OUTPUT SCORING

Output Title	Improve capability and evidence for more effective business support policies and reforms
Output number		7	Output Score	N/A
Risk:		Minor/Moderate/Major/Severe	Impact weighting (%):	N/A
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Indicators still being developed	Capacity building milestones are reflected in the country projects.	See output 5

Key Points
Key points for this component are captured under output 5 (Develop tools and techniques to improve existing systems and processes) for the purpose of this review.
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
As with the other outputs, indicators and milestones should be clearly defined and regularly reported against by the World Bank.
In delivering this work, the programme should seek opportunities to fill evidence and capacity gaps on gender and wider inclusion dimensions of the investment climate. The programme should share this learning.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key cost drivers and performance
The main cost driver in the delivery of this programme is staffing costs at the World Bank, as is usual for a programme of this type. Additionally, the World Bank takes a 5% fee for administration of the trust fund. The review team understand from the programme team that this was negotiated down from 17.5%. This represents a significant cost savings on the original position. 5% of the total budget is also allocated for FCO admin to cover staff salaries, travel and training over the lifetime of the programme.
Spending has been lower than anticipated. There is no evidence to suggest that this is as a result of efficiency savings or increased value for money, but rather due to disruptions in activities getting up and running as a result of elections in several countries and internal restructuring in the World Bank preventing 2 out of 5 pillars entering into implementation. Despite this lower than anticipated spending, performance appears to be largely on track, although the review team note that the lack of a clear programme-level monitoring framework makes this judgement more subjective than definitive.
It was clear from talking to the WBG that there needs to be more clarity on cost drivers and rate of spend. However, we are confident that the WBG are actively looking into this concern and will actively manage this in the future. Once this exercise is complete, we would recommend that key milestones and activities are more clearly articulated and trackable in the results framework to ensure that the budget is utilised in the most effective manner.
Key equity drivers and performance
The WBG has a gender results framework that should be being implemented in this programme, but to date does not appear to be being utilised. Only 2 out of the 6 country programmes have a specific focus on gender. One of these is Pakistan, but as yet there is no evidence that this is being explicitly considered, which is a concern. There is positive evidence of a gender policy note being developed at the global level.
The World Bank have committed to doing more to integrate gender and inclusion issues into the programme going forwards and are considering having gender as a focus of a peer to peer learning event. The FCO programme team should do more to drive performance from the World Bank in this area, identify a Gender Champion for the team and continue to ensure that the WBG Prosperity Fund’s Gender and Inclusion policy is applied.

Changes in FCO Staffing
The business case indicated staffing levels of 1x D6 Programme Lead + 1x C4 programme manager with 30% of a C4L in each of the countries to provide additional administrative oversight. There have been difficulties in recruiting and retaining staff across the network, but whilst this might cause localised problems, these issues are not unique or detrimental to this programme.
Due to these pressures, there have been a number of changes, including the downgrading of a couple of positions to B3L and the addition of 20% of a C5L in South Africa. The partnership arrangement with the World Bank places additional pressure on in-country teams to provide adequate administrative support as well as strategic oversight and influencing. The original intention of 30% C4 level support in country should be seen as a minimum requirement for providing the increased oversight that is needed and currently the programme is under-resourced in country to ensure effectiveness. Going below this level invites significant delivery risk which could impact value for money.
Even with this minimum staffing level, it will not provide headroom for country project staff to work on wider opportunities (including secondary benefits) to leverage value to HMG. The team should proactively draw on 10% advisory support from the new FCO Social Development Adviser in the Global Programmes Support Team.
VfM performance compared to the original VfM proposition in the business case
It is difficult to fully assess value for money against the business case at this stage of programme delivery, given the challenge of baselining expected benefits for policy reforms over a one year timeframe and the evidence of this available to the review team. The business case states that KPIs will be developed, as specified in the Administrative Agreement; however, these do not appear to have yet been developed. A Fund-level VfM scorecard was intended to support this assessment, but has not been produced in time to support implementation of this programme. This review therefore assesses overall value for money generically. It is a recommendation of this review that VfM indicators are developed and performance against these regularly assessed (see below).
At different stages of the programme cycle, the prominence of the 4 Es (Economy, Efficiency, Effectiveness, Equity) vary. Hence the focus of this review is on economy and efficiency. It is too early in the programme to assess effectiveness, but broadly the 7 outputs look to be on track. Analysis of economy is broadly covered by the above section on key cost drivers, and it is notable that the programme has lower overheads than other similar HMG programmes. At the efficiency level, the greatest VfM has been driven by how rapidly the World Bank was able to move to implementation in comparison to other suppliers (particularly private sector) and to already have established relationships in country. The programme has an ambitious set of activities planned for the second half of the year. Posts appear broadly happy with performance so far and believe these are on track to be achieved despite there being some political delays due to elections in some countries. At time of review the budget for the year is 30% spent (40% of the way through June 30, 2019).
Tangible outputs have been delivered in the first year that will lead to impact in the future, particularly as there is evidence that the WBG is adapting its approach to respond to changing contexts and feedback from stakeholders. It is essential that they continue to adapt their approach and review activities in the second half of the year in order to ensure they are achievable.
The Business Case postulates that the choice of the WBG as the delivery partner helps to drive greater value for money due to the leverage FCO money can get from IFC investments and the wide-reaching relationships with partner governments. The outputs that the World Bank produce are long-established products, which would be cumbersome and inefficient for other delivery partners to replicate. It would therefore be difficult for other delivery partners to achieve greater value for money.
Assessment of whether the programme continues to represent value for money
As there has been no significant shift in the costs from the Business Case, the programme still continues to represent value for money at this stage; however, it will require rigorous monitoring in the future to ensure this is maintained. In some countries, work has been duplicated due to elections and changes in Government. This was unavoidable in these instances, but work plans should be monitored to reduce this risk in future. As discussed in the financial management section, the programme is currently underspending – if this continues to be realised then there is potential that the programme achieves greater value for money that originally envisioned and financial profiling might need to be adjusted
To help the programme team fully measure future value for money in the programme, it is recommended that they set indicators. These are particularly relevant at the efficiency, equity and effectiveness levels, although cost drivers at the economy level should also be monitored. Some suggested indicators are listed in the table below.
Efficiency	Effectiveness
Cost per report or toolkit produced	Cost per dollar investment generated
Cost per intervention	Cost per dollar compliance cost saving generated for firms
Cost per successful policy reform	World Bank lending unlocked by programme

It would also be helpful to establish a benchmark for each of these indicators. A similar programme with the World Bank ran by DFID estimates that it costs £300,000 for each reform successfully implemented and every £1 spent helps to raise £5.88, which demonstrate strong value for money.
Whilst the programme has the potential to demonstrate good value for money, this could be further increased by implementing planned efforts to maximise global coherence and cross-cutting learning in delivery, including through exchange of best practice between the various country programmes (including from other UK Aid-funded work e.g. for the Bangladesh Investment Climate Fund and wider Business Environment Reform Facility) and outputs from the global components being utilised in country.
The impact this programme is aiming to have on poverty reduction is set out in the Business Case. As it is too early in the programme to assess whether results are being achieved, it is assumed that if the activities continue as planned then the assumptions made in the Theory of Change still stand.
Quality of financial management

As this is a programme in partnership with the WBG there is a general assumption that the day to day finances of the WBG element of programme are managed to WBG standards and subject to internal VfM check and balances, and they adopt rigorous auditing procedures. All of which have been vetted and approved by this and previous programmes. The FCO team have access to high-level data regarding spend but cannot investigate individual spend items. It is therefore assumed that the WBG HQ team will implement their own audit and financial management procedures. The review team saw no reason to believe that this is not the case. The WBG have developed a comparative advantage for delivering work in this area; continued monitoring will be required to ensure delivery achieves value for money.

As set out in the financial management section above, the programme is financed through a single donor trust fund arrangement. The rigour and detail of financial forecasting, accountability and monitoring of rate of spend needs to be improved. The programme aims to apply adaptive design and flexibility principles to delivery. As part of this, expansion to delivery in countries beyond the original 6 has been agreed.

Date(s) of last narrative financial report(s)	11/2018
Date(s) of last audited annual statement(s)

E: RISK (1 page)

Overall risk rating: Moderate
Overview of programme risk
The overall risk rating of the programme is Moderate. As previously set out, it is still early in the implementation of the Programme and risks are being identified and mitigated. More systematic risk assessment and plans for mitigation would reduce the overall risk to the programme.
The programme risk register forms part of a wider FCO-led Prosperity Fund programme risk register. This identifies 15 programme level risks. There are no country level risk registers. Analysis of the programme risk register reveals that a number of risks duplicate information and do not seem to have been updated recently.

An example where more systematic use of a risk register would help is the risk that “WBG MREL standards do not meet HMGs requirements, hampering our ability to ensure the programme is properly progressing and succeeding.” This risk is deemed to be unlikely in the register but in reality a related risk has come to pass, with significant difficulties encountered trying to reconcile World Bank MREL methodology with the Prosperity Fund MREL that is still being developed. Placing greater emphasis on the risk to the programme from inefficient/incomplete Fund-level responsibilities needs to be reflected in the risk register.

A significant programme risk is associated with the impacts of political change within the priority countries. This has already happened in a number of the countries and is a key future risk for others. It is important that future political changes and trends are discussed at the Country Boards, and mitigation measures put in place, as appropriate.

In line with the Business Case expectations, Risk management processes should monitor Gender Equality Act compliance and identify, monitor and mitigate potential risks and unintended consequences of programme interventions, including Safeguarding risk mitigation.
	Programme Summary
		Overall Delivery Confidence	Finance	Staff	Commercial	Time
Reporting Quarter Status		GG	YY	YY	GG	YY
Previous Quarter Status		GG	YY	GG	A	YY

Above is the programme teams’ confidence rating for delivery taken from the Q2 2018 quarterly report.

Part 3: Top 5 Programme Risks
Risk Description	Severity at last review	Mitigation Actions to reduce risk to target level; target date; and progress.	Post mitigation RAYG Rating	Requires escalation to JFU?
Emerging political uncertainty and risk in each country.	AA	Increase scope and flexibility to include other countries with different risk profiles.	YY	Yes
Time - World Bank does not meet Key Milestones.	Y	Explore options for accelerated delivery; / Consider extending the delivery period by two additional quarters	G	No
Staffing – Programmes not adequately staffed/resourced	Y	Enable recruitment at risk while clarifying complementary funding commitments from other global programmes.	G	No

Above is the programme teams’ Top 5 risks rating chart taken from the Q1 2018 quarterly report. (Q2 version not available at time of writing)
Outstanding actions and recommendations from risk assessment for FCO
Risk assessment methodology should be replicated at project/country level.
Actively manage rather than track political risk.
The current governance structure allows for the formation of a x-Whitehall advisory group. If used this would present a good opportunity to seek alternative views on the severity of and melioration options for many of the risks.
F: COMMERCIAL CONSIDERATIONS (1 page)
As discussed above, and in line with the Business Case, the programme has been set up as a trust fund arrangement with the WBG. Hence, there are no immediate direct commercial considerations. The programme is targeted at improving the Global Business Environment. As the programme matures and starts to deliver on primary and secondary benefits, involvement of business will be key.
N/A
G: Business Environment (½ page)

How has the business community and business environment responded to the programme?
It is too early within the programme to say definitively, but early indications are that the business community is engaged; in particular, with the flagship Global Investment Competitiveness report is well received.
(Where relevant) What role has non-ODA spending played in promoting programme objectives?
N/A
H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
An approach paper for GBEP Evaluation and Learning in Year 1 is due for completion in December. This evaluation approach is managed at Fund-level and is critical to enabling key programme management functions.
The Year 1 evaluation will explore a total of 12 evaluation and contextual baseline questions, some related to the programme’s theory of change, others to the programme’s performance and the Fund thematic objectives (gender and inclusion, value for money, secondary benefits). Year 1 will generate new evidence through sampling, stakeholders interviews and documentation review. This evidence will in turn be used to validate or challenge the programme design and rationale.
It has been agreed in principle that the Evaluation and Learning cycle will align to, and in so doing inform, the next Annual Review.
The programme has benefited from well-established World Bank M&E practices: all country programmes are now endowed with results frameworks that articulate the country programme’s activities, outputs, outcomes, and indicative targets and timeline. These results frameworks were developed during Year 0 (design) but continued to evolve with the country programmes in Year 1.[3] Overall, the country programmes appear to be in broad alignment with the programme’s Theory of Change, but a slight modification to the programme design may be required, as their respective contribution to the three GBEP country programme objectives, is made more explicit.
[3] World Bank’s M&E practices allow each country team to revise their results framework and indicative targets and timeline throughout the first year. The framework can no longer be changed from year 2.
The lack of an overarching programme results framework mid-way through the first year of implementation leaves an important gap in monitoring and evaluation. This was an output due to be delivered in collaboration with the Fund-level MREL contracts; the programme team has been waiting for these contracts to catch up with programme progress for several months. It is therefore important that the programme team is given greater ability to direct Fund-level contracts to support its needs. The programme team initially assumed that six country result frameworks would be sufficient to monitor the programme as a whole. This approach to monitoring has proved both unsatisfactory and impractical, however, for the following reasons:
- GBEP is more than a collection of stand-alone projects / country programmes. While most indicators in this field will remain country-focused, GBEP needs to demonstrate results as a global programme.
- An outstanding issue concerns the lack of appropriate result-oriented indicators for the Global Component. While a delivery matrix is being used to plan events and products, there has been no attempt yet to identify indicators that could measure the Global Component’s contribution to strengthening and sharing evidence for policymaking, including through peer-to-peer learning.
- Because the country programmes have been developed independently of each other, their result frameworks do not strictly match GBEP country programme objectives. This means that additional mapping (with support from PA consulting) is required before the right indicators can be identified for the programme as a whole.

Evidence products from the Business Environment Reform Facility (BERF) highlights a) Best practice on Gender and Business Environment Reform[4] and b) Gender and Business Environment/Investment Climate Reform in Bangladesh[5] (which informed the programme gender mainstreaming strategy). BERF has a strong emphasis on strengthening the Business Environment for women and girls, as well as for young adults more generally and evidence papers should be drawn upon by this programme to maximise cross-learning and efficiency.
[4] Business Environment Reform Facility, Gender and Business Environment Reform: What is “Best Practice”?, Dan Hetherington, July 2016
[5] Gender and Business Environment/Investment Climate Reform in Bangladesh, Ruta Aidis, March 2017

Monitoring progress throughout the review period
The programme team has produced quarterly reports, while the World Bank Group in Vienna / Washington has met its reporting requirements, by producing two bi-annual progress reports in April 2019 and November 2019. These two reports were subject to in-depth discussion between the WB team and FCO programme team, and the quality of the WB progress report has evidently improved, although more is still needed to improve risk monitoring and result measurement (incl. through the use of sex-disaggregated indicators) and reporting on progress on gender and inclusion.
Looking forward, monitoring the programme – and having an adequate oversight of the programme performance is likely to face some continuous challenges. The programme’s institutional set-up is currently at odds with the World Bank’s usual ways of working, which the use of multi-donor trust funds and the delegation of authority to the country teams largely characterise. As a result, the World Bank’s country teams have not been forthcoming with information and the FCO country staff have found it difficult to get a regular update of the programme’s performance, an acknowledgement of the UK ‘s contribution, and some visibility on finance and future activities. This situation was common to all target countries.
The WBG is applying its Trade and Competitiveness (T&C) M&E Framework for Gender and ensure co-ordination with the Prosperity Fund MREL Framework and programme delivery approach, in line with both the WBG’s Gender Strategy and the Prosperity Fund G&I Policy and programme guidance. The programme’s M&E intends to align to the centrally run Prosperity Fund MREL contracts, however these are yet to engage in sufficient detail in the programme. Outcome and Output-level indicators should be disaggregated by gender, age and income quintile, wherever possible, and disability where data is available. The T&C Results Framework includes clear gender-sensitive indicators that should be consistently translated through to country plans, design and implementation of activities to achieve measurable improvement in G&I at impact and outcome levels (e.g. on Number of new direct jobs created for Women, Number of predominantly women-owned firms that benefit from reformed registration requirements, Number of women-owned firms/entrepreneurs receiving investments).