Annual Review - Summary Sheet
PROGRAMME TITLE: PAKISTAN RULE OF LAW PROGRAMME
Country/Region:	Pakistan
HMG Partners / (LEAD in bold)	Department for International Development (DFID); Foreign and Commonwealth Office (FCO); Ministry of Defence (MoD); Home Office (HO); National Crime Agency (NCA); Crown Prosecution Service (CPS)
Total Spend:	ODA £5.95m	Non-ODA £.049m
Start Date: 01/04/2016 (some components were already in place prior to this)		End Date: 31/3/2020
Outputs				Score
DFID-led projects complete inception stage and move to full implementation				B
Government and Judicial Leadership and delivery of legal, regulatory and institutional reforms				A+
Increased accountability and oversight of law enforcement and justice institutions (more legitimate institutions)				B
Improved criminal justice coordination, planning and operations				A
Enhanced institutional performance				A
Overall output score				A
Outcome: Increased public confidence and trust in the rule of law / Outcome Assessment: The outcome is ambitious. The programme scores a B against the outcome this year because focussed work to influence citizens’ perception and experience of the justice system has been delayed. We are pleased to note however that since December 2017, rapid progress to address this gap has been made. Work includes the design of new citizen focussed initiatives, including on strategic communications and addressing sexual violence – a high profile issue in Pakistan at present. At the same time, we note the considerable achievements of one project in particular during the year in beginning to influence behavioural change across the justice system, which other programme components can complement and benefit from, a key principle in the programme design. / The work on supporting Pakistan’s forensic science capability is equally of merit. We also note the programme’s considerable achievement in supporting the development of government and judiciary led Rule of Law Roadmaps in Punjab, Balochistan and Khyber Pakhtunkhwa (KP), and one forthcoming in Sindh also with UK support. These are the first of their kind in Pakistan, setting out the challenges across the judicial system – police, forensics, prosecution, judiciary, prisons, probation and parole - and the priorities for reform. They have informed the 2018/19 budget process and are beginning to inform where international donor support should be focussed to best effect. We expect these to be key pillars for delivering the programme outcome going forward. / Smaller programme components include the design of new work on Serious and Organised Crime (SOC) and the consolidation of other Home Office led initiatives. These have been slightly delayed but are now making progress.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*
Programme Score	A+	A	A	B
Risk Rating	High	High	High

*output/outcome scores

What support is the UK providing?
The programme was initiated following the attack on the Army Public School in Peshawar in 2014 and the consequent decision by the Government of Pakistan to introduce military courts to try civilian terrorism cases until the civilian system was considered fit to provide a credible alternative. The programme is delivered by six UK departments – DFID, FCO, MOD, Home Office, NCA, CPS – and combines some existing projects pre-dating this work (for example an FCO led counter-terrorism project) with new initiatives to help tackle some of the systemic challenges in the system. These included DFID led projects to enhance institutional performance and improve citizen engagement (and thus underpin more narrowly focussed projects led by other government departments), and new work on SOC. Work on citizen engagement is currently being redesigned. The geographical focus of the work is in the provinces of Punjab and Khyber Pakhtunkhwa (KP), with smaller interventions in Balochistan, Sindh and the Federally Administered Tribal Areas (FATA). The project components include:
- Justice System Support Programme (JSSP) in Punjab and KP, DFID led, which is helping Pakistani institutions improve their performance, deliver priority legal, regulatory and institutional reforms and strengthen the ability of the justice sector to coordinate and plan.
- Justice programme in Sindh, DFID led, to support the development of a Rule of Law Roadmap and provide support to quality assurance in the Sindh Forensic Science Agency, thus extending the UK’s engagement in forensics from Punjab and KP.
- UNDP managed justice project, DFID led, to develop a Roadmap in Balochistan and undertake studies in FATA designed to inform thinking on FATA reform.
- Counter-Terrorism project in Punjab, led by the FCO, aims to increase Pakistan’s civilian capacity to investigate, detain, prosecute and try terrorists in line with international standards and human rights norms.
- Counter-Improvised Explosive Device (C-IED) project, led by MoD, supports Pakistani military and civilian institutions to counter the threat of IEDs.
- Serious and Organised Crime (SOC), led by the Home Office and NCA. During 2017/18, some support was given to the National Accountability Bureau (NAB) while a new umbrella project is being designed to address illicit financial flows and organised immigration crime.

Summary of progress and lessons learnt/actions taken since last review
A number of the recommendations in the 2016-17 Annual Review are still relevant, in part because they are likely to run through the lifetime of the programme, and in part because of the challenges of combining a wide range of activities by six departments under one programme. The review team were pleased however that they are all being tackled. Specifically:
1. Delivering results – where progress has been slow often due to circumstances beyond the control of the team, work needs to gather momentum – the evidence this year is that this is now demonstrated by the cross component contributions to many of the outputs;
2. The importance of policy engagement – something which we observed was very well done this year
3. Continued close management of human rights risks – a concern which we continue to stress in this report;
4. Continued effort to encourage other donors to invest in implementing roadmaps, especially in provinces where HMG is unlikely to have a long term engagement;
5. Paying attention to Value for Money (VFM) in the actions of suppliers, which we directly observed in relation to the management of JSSP, but VFM more widely across the programme now requires a deep analysis;
6. Improving financial performance – we report this year that financial management has been good and difficult financial decisions made;

This Annual Review visited projects being implemented in two provinces (Punjab and KP) and also assessed the work completed in Balochistan and beginning in Sindh. We had meetings with senior members of the bureaucracy, police and legal hierarchy. This year has demonstrated good progress particularly around strengthening the justice chain and forensic science, coupled with the roll out of Pakistan’s first ever rule of law roadmaps to 4 provinces.
Key issues:
- This is a demanding set of individual projects led by 6 different UK government departments. Different timelines between component projects and the difficulties of forging separate projects – some of which were already in implementation – into one CSSF programme, remain a challenge.
- This year there is greater evidence of CSSF developing working relationships across UK government departments in pursuit of a one-HMG approach to delivery. Coupled with significant strategic re-thinking to ensure a common shared understanding and a newly drafted Results Framework to reflect this, next year should ensure greater programme synergies between the components.
- Exemplary political, executive and judicial engagement with the provinces gives confidence that provincial buy-in to the reforms by the different institutions is in place.
- Good progress has been made on some of the components – particularly in respect of provincial roadmaps in three provinces (with the fourth currently underway).
- Variable progress on two components as inception phases took longer than expected. Lessons have been learned. We feel confident that with the work currently underway, the lagging components are now in a better place which will ensure good progress over the next 12 months.