## Monthly Report
Templatesco Ltd
Monthly report (commercialisation)
2018-12-01
Completed by:
Signature:
Approved by:
Signature:
Issue date:
HNIP Application Reference Number:
PROJECT DASHBOARD
[5 empty] | Email | Phone
Project name
Project type
Location
Shareholders / sponsor
Debt providers
Principal contractor
Technical advisor
Legal advisor
O&M provider
ESCO directors
Main project contact name
[Other category 1]
[Other category 2]
[Other category 3]
Please include contract details for "Shareholders/sponsor" through to "ESCO directors"
EXECUTIVE SUMMARY
For a project at the commercialisation stage, to include a summary of progress since the last report, detailing (c. 1 page): • Identification of key risks and proposed mitigations • Technical design • Procurement progress • Planning / other permitting • Contract / legal update • Offtaker / commercial • Overall project commercials, returns and funding requirement
KPIs (EXAMPLE - CAN BE TAILORED AS RELEVANT
As at 31 December 2018 |  | Current estimate |  | Original estimate
Target planning permission (date)
Technical feasibility completion (date)
Target commercialisation date (approval of full business case) (date)
Target construction start date (date)
Total project capex forecast (£'000)
Costs incurred to date (£'000)
% of heat load secured (%)
Forecast project IRR (%)
Project gearing (Debt / EV) (%)
Next HNIP drawdown date (date)
Funding source 1 - total (£'000)
Funding source 1 - drawn (£'000)
Funding source 2 - total (£'000)
Funding source 2 - drawn (£'000)
• All changes in KPIs from the previous reporting must be explained as part of the reporting text
• If possible, add in some sort of graphical representation illustrating project progress to
date / planned progress to achieve commercialisation and the start of construction
• Please note that all dates in the above table must be in the format dd/mm/yyy
TECHNICAL UPDATE
Expand on the executive summary giving a c.1-2 page + update of the technical feasibility of the scheme, including any information around planning/permitting. Also includes a summary of key risks and opportunities around project delivery. Full detail of risks to be included in the appended Risk Matrix, with only the highest risk items brought through to this narrative summary.
FINANCIAL UPDATE
Detailed commentary of expected financial performance of the scheme (c.1-2 pages), including forecast returns (IRR), funding requirements focusing on any changes from the previous report and identifying any financial risks together with proposed mitigation and the impact on the scheme overall. To include a “sources and uses” for funding as per commercial modelling which has been carried out.
COMMERCIAL UPDATE
D&B procurement complete
O&M procurement complete
% Forecast heat load virtually certain
% Forecast heat load subject to negotation
% Forecast heat load - discussions yet to commence
To discuss any commercial / customer / contractual points e.g. procurement of D&B / O&M contracts, status of commercial negotiation with key heat load, % of forecast heat load which is virtually certain, % which is subject to negotiation, % for which discussions have not commenced etc. (c.1 page).
GOVERNANCE
Summary of any relevant corporate or governance matters which stakeholders which investors / financing providers should be aware of. This section should also include a matrix of commercial relationships for the scheme (c. 0.5 pages)
OTHER
Any other material items not covered elsewhere in the report (c. 0.5 pages)
APPENDICES (to include risk matrix and CP matrix as per attached templates, as well as any additional relevant detail, e.g. copies of relevant correspondence, reports from subcontractors, copies of internal approvals for the scheme etc.)

## App 1- Risk Matrix
Templatesco Ltd
Risk matrix
2018-12-01
[7 empty] | PRE-MITIGATION |  |  |  | POST-MITIGATION
Number | Risk name | Risk type | Details* | Date identified | Update from previous report (if relevant) | Date updated | Risk Probability (1-5) | Risk Impact (1-5) | Risk Score (PxI) | Actions to mitigate | Risk Probability (1-5) | Risk Impact (1-5) | Risk Score (PxI) | Open/Closed
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
[9 empty] | 0 |  |  |  | 0
*Fixed once the risk has initially been identified and described - updates to be provided in column F as part of subsequent reports to allow for tracking of risks by the monitoring and reporting team

## App 2 - CP Matrix
Templatesco Ltd
Matrix of Conditions Precedent to Funding Drawdown
2018-12-01
Number | CP name | CP details | Completed (Y/N) | Evidence submitted (Y/N) | Current status (if still open) | Estimated completion date

## App 3 - BEIS data sheet
Templatesco Ltd |  | Document guidance for projects:
Raw Data Reporting |  | Please ensure that this data sheet is completed and updated with every report which is submitted.
Commercialisation |  | Depending on the status of the project (whether it is in pre-commercialisation, construction or operations - and this can be updated by changing the field in cell A3 from the drop-down list), the
2018-12-01 |  | below table will display the required fields together with information as to whether the required data is planned/estimated or actual data which should be available to projects. Should any clarification
be required on how to complete this table, or any of the specific data which is required, please contact your Triple Point Heat Networks Asset Manager
Monitoring Data Overall |  | Note that the provision of this data with each report submitted is mandatory.
| Data Requirement | Data required at this stage? | Planned or Actual Data? | Confirm Data Type (if required) | Data Point (Complete this Field) | Units | Completion guidance (as applicable) |  |  |  |  | ORDER | COMMENTS | Commercialisation | End of Commercialisation | Construction | End of Construction | Operational
| Confirm that the project has not deviated and is not expected to deviate >10% from application on key criteria | Yes | Actual Data |  |  | List | Yes/No |  |  |  |  | 1 |  | Y | Y | Y | Y | Y
| Date of completion of distribution network(s) [date for each network] | Yes | Planned/Estimated Data | Actual Data |  | Date | [5 empty] | 2 |  | P | P | P/Y | Y | N
| Date of completion of energy centre | Yes | Planned/Estimated Data | Actual Data |  | Date | [5 empty] | 3 |  | P | P | P/Y | Y | N
| Date of start of construction contract | Yes | Please Confirm |  |  | Date | [5 empty] | 5 |  | P/Y | Y | Y | Y | N
| Date of end of construction contract | Yes | Please Confirm |  |  | Date | [5 empty] | 6 |  | P/Y | P/Y | P/Y | Y | N
| All environmental permits attained? | Yes | Actual Data |  |  | - | Have all environmental permits been awarded? Yes/No |  |  |  |  | 9 |  | Y | Y | Y | Y | N
| Date of network handover to operator | Yes | Planned/Estimated Data |  |  | Date | [5 empty] | 10 |  | P | P | P | P/Y | P/Y
| Details of planned distribution network replacement/upgrades | Yes | Planned/Estimated Data |  |  | - | Please provide a narrative response |  |  |  |  | 12 |  | P | P | P | P/Y | P/Y
| Date of intended energy centre replacement/upgrade/decarbonisation | Yes | Planned/Estimated Data |  |  | Date | Please provide a target date for scheduled energy centre decarbonisation, or otherwise enter "n/a" |  |  |  |  | 13 |  | P | P | P | P/Y | P/Y
| Planning application approved? | Yes | Please Confirm |  |  | List | Yes/No |  |  |  |  | 14 |  | P/Y | P/Y | P/Y | Y | Y
| Commericialisation stage - start date | Yes | Actual Data |  |  | Date | [5 empty] | 14.1 |  | Y | Y | Y | Y | Y
| Commericialisation stage - end date | Yes | Please Confirm |  |  | Date | [5 empty] | 14.2 |  | P/Y | P/Y | Y | Y | Y
| Construction stage - start date | Yes | Planned/Estimated Data |  |  | Date | [5 empty] | 14.5 |  | P | P/Y | Y | Y | Y
| Construction stage - end date | Yes | Planned/Estimated Data |  |  | Date | [5 empty] | 14.6 |  | P | P | P/Y | P/Y | Y
| Operational stage - start date | Yes | Planned/Estimated Data |  |  | Date | [5 empty] | 14.7 |  | P | P | P | P/Y | Y
| Operational stage - end date | Yes | Planned/Estimated Data |  |  | Date | [5 empty] | 16 |  | P | P | P | P | P/Y
| Overall Project RAG rating | Yes | Actual Data |  |  | List | Please provide your own internal assessment of the project's risk rating |  |  |  |  | 17 |  | Y | Y | Y | Y | N
| Total project CAPEX costs | Yes | Actual Data |  |  | £ | Project total capex cost |  |  |  |  | 18 |  | Y | Y | Y | Y | N
| Total project OPEX costs (per year) | Yes | Actual Data |  |  | £ | Total average annual opex for the scheme (2019 prices) |  |  |  |  | 19 |  | Y | Y | Y | Y | Y
| Total project revenues (per year) | Yes | Actual Data |  |  | £ | Please provide average annual project revenues (2019 prices) |  |  |  |  | 19.5 |  | Y | Y | Y | Y | Y
| Heat Trust registration status | Yes | Actual Data |  |  | List | [5 empty] | 24 |  | Y | Y | Y | Y | Y
| Number of buildings on the network | Yes | Please Confirm |  |  | - | [5 empty] | 25 |  | P/Y | P/Y | P/Y | Y | Y
| CIBSE Code of Practice compliant based on stage 1 checklist | Yes | Actual Data |  |  | List | Is the project CIBSE compliant? Yes/No - pre-commercialisation |  |  |  |  | 27 |  | Y | N | N | N | N
| CIBSE Code of Practice compliant based on stage 2 checklist | No | No |  |  | List | Is the project CIBSE compliant? Yes/No - end of commercialisation |  |  |  |  | 28 |  | N | Y | N | N | N
| Average price of heat interface units | No | No |  |  | £ | Please provide the average [mean] price for the project |  |  |  |  | 29 |  | N | Y | N | Y | N
| Average price of pipe/metre | No | No |  |  | £ | Please provide the average [mean] price for the project |  |  |  |  | 30 |  | N | Y | N | Y | N
| Average price of trench/metre | No | No |  |  | £ | Please provide the average [mean] price for the project |  |  |  |  | 31 |  | N | Y | N | Y | N
| CIBSE Code of Practice compliant based on stage 3 checklist | No | No |  |  | List | Is the project CIBSE compliant? Yes/No - construction period |  |  |  |  | 32 |  | N | N | Y | Y | N
| Proportion of construction complete | No | No |  |  | - | Percentage progress |  |  |  |  | 33 |  | N | N | Y | Y | N
| Date of first loan repayment | Yes | Planned/Estimated Data |  |  | Date | [5 empty] | 34 |  | P | P/Y | P/Y | P/Y | Y
| Capability to contribute to grid - 7x criteria | No | No |  |  | List | [5 empty] | 37 |  | N | P/Y | P/Y | Y | Y
| Heat capacity of the network | No | No |  |  | Kw | [5 empty] | 38 |  | N | P/Y | N | Y | Y
| Heat generation on the network | No | No |  |  | Kwh | Please provide the actual generation for the total project to date |  |  |  |  | 39 |  | N | P/Y | N | Y | Y
| Heat supply via the network | No | No |  |  | Kwh | Please provide the actual supply for the total project to date |  |  |  |  | 40 |  | N | N | N | Y | Y
| Peak heat/power demand of the network | No | No |  |  | Kw | [5 empty] | 40.05 |  | N | N | N | Y | Y
| Number of building level meters installed | No | No |  |  | - | [5 empty] | 40.1 |  | N | N | P | Y | Y
| Number of customer level meters installed | No | No |  |  | - | [5 empty] | 40.2 |  | N | N | P | Y | Y
| Increase/expansion of network capacity after initial operational launch | No | No |  |  | Kw | Please provide the total expansion of capacity since the start of initial operations, if any |  |  |  |  | 42 |  | N | N | N | Y | Y
| Future network expansion plans | No | No |  |  | - | Please briefly detail the future expansion plans for the heat network |  |  |  |  | 43 |  | N | P | N | P | Y
| Total number of complaints received | No | No |  |  | - | Cumulative to date |  |  |  |  | 45 |  | N | N | N | N | Y
| Number of complaints by type - Price | No | No |  |  | - | Please provide the number of complaints cumulatively to date |  |  |  |  | 45.1 |  | N | N | N | N | Y
| Number of complaints by type - Billing | No | No |  |  |  | Please provide the number of complaints cumulatively to date |  |  |  |  | 45.2 |  | N | N | N | N | Y
| Number of complaints by type - Delivery of Heat/Technical | No | No |  |  |  | Please provide the number of complaints cumulatively to date |  |  |  |  | 45.3 |  | N | N | N | N | Y
| Number of complaints by type - Customer service | No | No |  |  |  | Please provide the number of complaints cumulatively to date |  |  |  |  | 45.4 |  | N | N | N | N | Y
| Number of complaints by type - Complaints handling | No | No |  |  |  | Please provide the number of complaints cumulatively to date |  |  |  |  | 45.5 |  | N | N | N | N | Y
| Number of complaints resolved | No | No |  |  | - | Cumulative to date |  |  |  |  | 47 |  | N | N | N | N | Y
| Average length of time required to address each complaint | No | No |  |  | Days | Mean, in days, over all time |  |  |  |  | 48 |  | N | N | N | N | Y
| Backlog (number) of complaints not addressed at end of reporting period | No | No |  |  | - | [5 empty] | 49 |  | N | N | N | N | Y
| Number of outages <24hrs long | No | No |  |  | - | Cumulative to date |  |  |  |  | 50 |  | N | N | N | N | Y
| Number of outages >=24hrs long | No | No |  |  | - | Cumulative to date |  |  |  |  | 50 |  | N | N | N | N | Y
| Total duration of all outages | No | No |  |  | Days | Cumulative to date |  |  |  |  | 51 |  | N | N | N | N | Y
| Dates on which outages occurred | No | No |  |  | - | Please comment on the dates of any outages since the last report, in free text |  |  |  |  | 52 |  | N | N | N | N | Y
| Number of service interruptions | No | No |  |  | - | Cumulative to date |  |  |  |  | 53 |  | N | N | N | N | Y
| CIBSE Code of Practice compliant based on stage 4 checklist | No | No |  |  | List | Is the project CIBSE compliant? Yes/No - operations period |  |  |  |  | 54 |  | N | N | N | N | Y
Monitoring Data Split by Customer
| ORDER | 11 | 11.5 | 11.75 | 40.5 |  | 40.3 | 11.8 | 11.8
COMMENTS
| Commercialisation | P | P | P | P/Y |  | N | P | P
| End of Commercialisation | P | P | P | P/Y |  | N | P/Y | P/Y
| Construction | P | P | P | P/Y |  | N | Y | Y
| End of Construction | P/Y | P/Y | P/Y | P/Y |  | N | Y | Y
| Operational | P/Y | P/Y | P/Y | Y |  | Y | Y | Y
| Data Requirement | Date (for each customer) of heat supply switch on | Date (for each customer) of cooling supply switch on | Date (for each customer) of power supply switch on | Number of end customers supplied by/represented within this customer |  | Volume of heat consumed | Average heat price charged - unit price (per kWh) | Average heat price charged - standing charge (daily)
| Units | Date | Date | Date | - |  | Kwh | £ | £
| Data required at this stage? | Yes | Yes | Yes | Yes |  | No | Yes | Yes
| Planned or Actual Data? | Planned/Estimated Data | Planned/Estimated Data | Planned/Estimated Data | Please Confirm |  | No | Planned/Estimated Data | Planned/Estimated Data
| Completion guidance (as applicable) | [5 empty] | Where there are a number of different consumer types, please provide the volume of heat by each consumer type | Average [mean] domestic heat price | Average [mean] domestic heat price
1 | Customer Name (this should be the contracting party to the heat network, not an individual end consumer)
Confirm Data Type (if required)
Data Point (Complete this Field)
2 | Customer Name (this should be the contracting party to the heat network, not an individual end consumer)
Confirm Data Type (if required)
Data Point (Complete this Field)
3 | Customer Name (this should be the contracting party to the heat network, not an individual end consumer)
Confirm Data Type (if required)
Data Point (Complete this Field)
4 | Customer Name (this should be the contracting party to the heat network, not an individual end consumer)
Confirm Data Type (if required)
Data Point (Complete this Field)
Add more as applicable / if necessary
Monitoring Data Split by Supplier
| ORDER | 55 | 56 | 57 | 60 | 60 | 59 | Suggest removing "no UK company" - a foreign company would still fit into that sizing? | 62 | 63 | 64 | [7 empty] | 65 | 66 | 67
COMMENTS
| Commercialisation | N | N | N | N | N | N | N | N | N | N | [7 empty] | N | N | N
| End of Commercialisation | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | [7 empty] | Y | Y | Y
| Construction | N | N | N | N | N | N | N | N | N | N | [7 empty] | N | N | N
| End of Construction | Y | Y | P | Y | Y | Y | Y | Y | Y | Y | [7 empty] | Y | Y | Y
| Operational | N | N | N | N | N | N | N | N | N | N | [7 empty] | N | N | N
| Data Requirement | Supplier company name | Supplier market offering | Supplier market segment | Supplier UK address | Post Code | Supplier ownership type | Supplier size | Supplier contact name | Supplier contact email | Supplier contact phone | [7 empty] | Supplier Global HQ address | Supplier contract description | Supplier contract price*
| Units | - | List | List | - | - | List | List | - | - | - | [7 empty] | - | - | -
| Data required at this stage? | No | No | No | No | No | No | No | No | No | No | [7 empty] | No | No | No
| Planned or Actual Data? | No | No | No | No | No | No | No | No | No | No | [7 empty] | No | No | No
| Completion guidance (as applicable) | Please provide this information of each key supplier to the project - only if it has changed from application
1 | Supplier Name
| Confirm Data Type (if required) | Actual Data | Actual Data | Actual Data | Actual Data | Actual Data
Data Point (Complete this Field)
2 | Supplier Name
| Confirm Data Type (if required) |  |  |  | Actual Data |  |  | Actual Data | Actual Data | Actual Data
Data Point (Complete this Field)
3 | Supplier Name
| Confirm Data Type (if required) |  |  |  | Actual Data
Data Point (Complete this Field)
4 | Supplier Name
| Confirm Data Type (if required) |  |  |  | Actual Data
Data Point (Complete this Field)
Add more as applicable / if necessary
Free text box (if required)
*Please present this information in as granular format as possible. If you have access to supplier pricing for individual works packages carried out by subcontractors to your main contractor, it is important that this information is provided.

## Lookup (hidden)
Market offering | Market segment | Company size | Ownership type | Risk type | Project type | Risk P/I | Y/N | Risk ratings | Type of customer | Grid criteria | Heat trust status | Risk O/C | Report Type | Data Type
Design, Build, Operate | Combined Package | Micro (<10 staff, <£2m turnover) | Limited Liability Partnership (LLP) | Design | Local Authority - owned | 1 - Lowest | Yes | Red | Residential | Ancillary Services | Registered | Open | Commercialisation | Actual Data
Design | Professional Services | Small (<50 staff, <£10m turnover) | Private Ltd. company | Legal | Local Authority - ESCO | 2 | No | Red/amber | Commercial | Capacity Market | Not registered | Closed | End of Commercialisation | Planned/Estimated Data
Build | Construction | Medium (<250 staff, <£50m turnover) | UK-headquartered multinational company | Commercial | Corporate - owned | 3 |  | Amber | Industrial | Balancing Mechanism | Committed to register |  | Construction
Operate | Hardware | Large (>250 staff, >£50m turnover) | UK-owned business (With operations only in UK) | Planning & consents | Corporate - ESCO | 4 |  | Amber/green | Local Authority | Demand Side Response |  |  | End of Construction
Legal | Services |  | UK-subsidiary of multinational organisation | Finance | Other | 5 - Highest |  | Green |  | Smart City |  |  | Operational
Project |  |  | Other (please give details below) | Construction
Technical |  |  |  | O&M
Financial |  |  |  | Other
Civils
Installation
Buildings
CHP
Boilers
Pumps
HIUs
Steel pipes
Plastic pipes
Detection systems
Heat exchangers
Meters
Control systems
Valves
Chemical Water treatment
Data systems
Tools
Lubrication oil
Testing and Technical review
Detection services
Data processing
Control systems
Technical Audits