## Parts 1 and 2
| DfT letter ref | Critical path to Aug '19 | Comment | HS1 response | HS1 document ref
Part 1: Recommendations for HS1 to action | 1 | Y | HS1 to clearly specify how asset condition has been used to inform the need for asset renewal and therefore the LTC. | Stations Strategic Asset Management Statement (SSAMP) updated. | Sections 2.4.1, 2.9, SSAMP
| 2 | Y | In line with the HS1 stated purposes of the SASs, it is recommended that the current approaches to be taken for renewal of asset classes are made clear in the SASs. | Strategic Asset Strategies (SASs) updated. | Section 1.1, SASs
| 3 | Y | HS1 to explain how the source for criticality stated in the SASs has been applied. | SASs updated. | Sections 3 and 9.2, SASs
| 4 | Y | HS1 to explain in the SAS the exclusion of the ‘Passenger Comfort’ business attribute and the movement of its weighting to ‘Cost’, and the nature of the agreement achieved with stakeholders. | SASs updated. | Section 1.3, SASs
| 5 | Y | HS1 to explain in the SAS the rationale behind the sub-division of the ‘Safety’ and ‘Cost’ business attributes used for determining asset criticality together with the weighting assignments, and the nature of the agreement achieved with stakeholders. | SASs updated. | Section 1.3, SASs
| 6 | Y | HS1 to explain in the SASs how the age of the assets is connected into the strategy and renewal decision making. | SASs updated. | Section 2.3, SASs
| 7 | Y | HS1 to use consistent terminology throughout its suite of SAS documents and rectify inconsistencies between the documentation defining their asset management intentions. | SASs updated. | Section 1.3, SASs
| 8 | Y | HS1 to validate and verify the content of Appendix 9.5 Asset Inventory and Age in all SAS documents and the inventory and age in the LCC models and update accordingly | SASs updated. | Section 9.4, SASs
| 9 | Y | HS1 to consider streamlining SAS documentation to avoid duplication of content | Agree - HS1 will look to streamline the SAS documents in future iterations. | N/A
| 10 | Y | HS1 to complete Sections 7.2 EAM Initiatives, 7.3 Implementation Plan and 9.2 Related Standards, Legislation and Regulations or make it explicit that nothing applies in these sections. Where completion is required, a note should be added within the document to highlight the status of completion and indicate an expected completion date. | SASs updated. | (Former) Sections 7.2, 7.3 and 9.2
| 11 | Y | HS1 to clearly describe the intent of the asset management capability maturity roadmap (Appendix E), and identify the progress to-date. | SSAMP updated. | Section 4 and (former) Annex E, SSAMP
| 12 | Y | HS1 to prepare a Cost Efficiency Plan and submit it for review by the Reviewer, such that recommendations may be made to the DfT before publication of the Final Consultation document at the end of May 2019. | See HS1 letter to DfT, 26 June 2019. | N/A
| 13 | Y | DfT to require HS1 to provide a copy of the Oxera Enhancements Framework to the Reviewer such that a review can be undertaken and any findings advised to DfT before publication of the Final Consultation document at the end of May 2019. | See HS1 letter to DfT, 26 June 2019 and Annex C to that letter. | N/A
| 14 | Y | HS1 to review the structure of the Asset Management System and provide a definitive guide demonstrating the interaction of documents and how they combine to meet the requirements of the Lease and HS1’s aspiration to achieve ‘world leading asset management’ | See drafting changes to SSAMP and SASs, described here, HS1 letter to DfT and Annex B to that letter. | N/A
| 15 | Y | HS1 to update the LCC and LTC models to correct current shortcomings/known actions and submit models for an additional review by the Reviewer such that any findings can be advised to DfT before publication of the Final Consultation document at the end of May 2019. | LCCs have been updated with correct price basis and revised references in the 'notes tab'. The Stations LTC review submission sets out our approach to contingency, which is also reflected in the LTC model. | N/A
| 16 | N | HS1 and DfT to clearly define the asset health hand back provisions, and the DfT to actively manage the review of asset health during regular quarterly renewal decisions. | See HS1 letter to DfT, 26 June 2019. | N/A
| 17 | Y | HS1 to modify the LCC models to encapsulate all assets over a rolling 40-year period to provide foresight of renewal costs of assets beyond the existing Lease period. | The models will be updated using the LTC agreed by DfT as the baseline. | N/A
| 18 | N | HS1 to clarify how longer life assets are considered in the uncertainty study report. | See HS1 letter to DfT, 26 June 2019. | N/A
| 19 | Y | HS1 and DfT to agree a Change Management Process or provide documented evidence of a change Management Process to the Reviewer if one exists such that a review can be undertaken and any findings be advised to the DfT before publication of the Final Consultation document at the end of May 2019. | This is captured through the normal renewals governance process, overseen by DfT. We note that GHD were not provided key documentation, including the Annual Stations Portfolio Funding Paper and meeting minutes. In view of this, should the DfT wish to progress a change management process, HS1 is open to discussing this. | N/A
| 20 | Y | HS1 to produce a change management process document for how elements that effect the LTC are managed. | See above. | N/A
| 21i | N | What funding mechanisms should be employed for the funding of long-term assets? E.g. St Pancras station roof. | See HS1 letter to DfT, 26 June 2019. | N/A
| 21ii | N | What forward funding period should be considered for asset renewal to capture long life assets where renewals is expected beyond 2060? | See HS1 letter to DfT, 26 June 2019. | N/A
| 22 | Y | HS1 to provide documented evidence of their approach to project delivery to the Reviewer such that a review can be undertaken and any findings be advised to the DfT before publication of the Final Consultation document at the end of May 2019. | The ARUP report sets out our intended future state. The current state is overseen by the DfT/HS1 renewals governance process, as described above. Our practice is then to procure renewals activities according to the procurement frameworks of HS1, NR(HS) or other suppliers. We will look to improve documentation of this process in future. | N/A
| 23 | Y | HS1 to provide a summary of the scope and timing of the renewals planned for CP3 to the Reviewer so that a review can be undertaken and any findings advised to the DfT before publication of the Final Consultation document at the end of May 2019. | The CP3 Delivery Plan will be developed in light of the DfT's funding approval in PR19. The LCC models contain high-level information and costs for the planned interventions, which are further explained in the Stations LTC review submission. | N/A
| 24 | Y | HS1 and DfT to consider through the CP3 process the appropriate terms of reporting and establish the requirement. | HS1 reports significant detail to the DfT in the Annual Stations Portfolio Funding Paper, the Asset Management Annual Statement, and quarterly regulatory reporting. We would welcome specific views from DfT on what it considers it requires further information on. | N/A
| 25 | Y | HS1 should document how adjustments and transfers to Qx and LTC will be managed and recorded. | Changes are approved by DfT as part of renewals governance, with supporting commentary provided in Annual Stations Portfolio Funding Paper and associated workbooks. | N/A
| 26 | Y | HS1 to log historical and future changes during CP3. | As above. | N/A
| 27 | N | HS1 to document lessons learned such that what worked well, what was improved and what still needs attention from experience through CP2 is considered in an appropriate manner to provide an enduring and usable source of learning. | HS1 considers there will be significant value in a lessons learned exercise for PR19, and will work with DfT to agree an approach and timing of the process. | N/A
| 28 | Y | HS1 to consider actions that can be implemented immediately for CP3 to improve the overall submission process (e.g. optionality). | As above. | N/A
Part 2: Further recommendations | N/A | Y | Retail contribution to LTC Would HS1 consider implementing retail contributions into the LTC as a more equitable arrangement for funding to the LTC? | See HS1 letter to DfT, 26 June 2019. | N/A
| N/A | Y | TOC/Thameslink contribution to LTC Have HS1 considered alternatives for splitting costs between operators? And what assessment has been made on potential alternative options? | See HS1 letter to DfT, 26 June 2019. | N/A

## Part 3 - LCR compliance
Clause | Obligation | What it falls under | Section within document as indicated by HS1 | Likelihood of compliance (RAG) | Comments | HS1 Response | HS1 document ref | HS1 assessment of compliance (RAG)
5 | Life Cycle Report | Title
5.1 | The Tenant shall submit a Life Cycle Report to the Government's Representative for each Station no later than nine (9) months prior to the end of each Review Period. | LCR |  | G | Review periods end on 31 March. Review Periods are 5 years in length. Review Period 1 ended on 31 March 2015. Therefore CP2 ends 31 March 2020. Life Cycle reports are therefore are to be submitted by end of 1 July 2019. | LCR's have been updated based on comments from DfT and GHD. Submitted 26 June. | LCRs | G
5.2 | Each Life Cycle Report shall, in respect of each Station, include: | LCR
| Works undertaken and costs incurred | Title
5.2.1 | a summary of the following in respect of the current Review Period | LCR
5.2.1 (A) | the Life Cycle Works carried out by the Tenant (or that it is anticipated will have been carried out by the end of the current Review Period); | LCR | 4.1.2 | R | Requires further information. It is not clear if the list of works includes works carried out from the start of CP2 up to this time. For example, Table 5 in Section 4.1.2 for Stratford contains 9 items. 3 items are stated to be likely deferred to CP3. 3 items are stated to be completed by June 30, 2018. 1 item is stated to be underway. It is therefore assumed that 2 items were completed prior to the development of the LCR. Additionally, Table 5 in Section 4.1.2 for Stratford only contains non-standard LTC Asset System Category for "5- Services" is included; it is unknown whether other asset system categories (refer Appendix B, table in B1) are absent because no work was done or is planned or because they have been inadvertently omitted. Additionally, there is no breakdown by year. | Section 6.1.2 in the LCRs has been updated to reflect the '2019/20 Annual Stations Portfolio Funding Paper.' The items previously stated as 'likely to be deferred to CP3' have been removed, as this table is only reflecting works likely to be completed in CP2. Those CP3 deferrals have not reached Gate 4 in the renewals governance cycle, therefore their current status is uncertain hence removal from this report. Table 5 is in section 6.1.2. The asset category column in Table 5 has been removed as it does not materially add to the document. For more detailed programme detail and period breakdowns regarding projected and actual expenditure reporting, see the annual and quarterly programme reports as submitted to DfT. | Section 6.1.2, LCRs | G
5.2.1 (B) | the Available Life Cycle Funds at the end of each Financial Year (or the anticipated Available Life Cycle Funds by the end of the last Financial Year in the current Review Period); | LCR | 4.2.1.5 | R | Requires further information. The graph in 4.2.1.5 "shows the change in the Escrow balance". "Escrow" is defined but not in the context of 5.2.1 (b); the figure in Section 1.1 appears to relate 'Escrow' to 'Annuity'. The line on the graph for "Total Escrow Cash" is not defined; it is assumed this is the forecast situation for CP2, presumably the forecast made prior to CP2 commencing. The "Actual", however, seems to be a flat line of always being £5,000k. It is, therefore, unclear what the interpretation of this graph should be. Notwithstanding, it does not appear to provide the "Available Life Cycle Funds at the end of each Financial Year". | This information is provided in the LCC and LTC models, the Stations LTC review submission, and the Annual Stations Portfolio Funding Paper. A new table has been added to section 7 of the LCR documents, which copies the information shown in the Stations LTC review submission. | Section 7, LCRs | G
5.2.1 (C) | the Life Cycle Works Cost (or anticipated Life Cycle Works Cost by the end of the current Review Period); | LCR | 4.1.2 | R | Requires further information. Comments as for 5.2.1 (a) are applicable to 5.2.1 (c). | This information is provided in the LCC and LTC models, the Stations LTC review submission, and the Annual Stations Portfolio Funding Paper. A new table has been added to section 7 of the LCR documents, which copies the information shown in the Stations LTC review submission. | Section 7, LCRs | G
5.2.1 (D) | the Deferred Life Cycle Works Savings (if any) approved in previous Life Cycle Reports; | LCR | 4.2.1.3 | G | Compliant. It is stated that "No Life Cycle Works savings are identified" | N/A | N/A | G
5.2.1 (E) | the Life Cycle Works Savings (if any) brought forward from previous Review Periods; | LCR | 4.2.1.3 | G | Compliant. It is stated that "No Life Cycle Works savings are identified” | N/A | N/A | G
5.2.1 (F) | the effect of any Relevant Changes of Law that have occurred during the Review Period; | LCR | 4.2.2 | G | Compliant. It is stated that there "…have been no changes in law during CP2 that have changed our approach to the management of the asset." | N/A | N/A | G
5.2.1 (G) | an analysis of breakdown frequencies and the performance of the Elements of the Station which were identified in the Asset Management Strategy as being monitored by the Tenant; | LCR | 4.3.1 |  | Requires further information for Stratford, Ebbsfleet and St. Pancras. The key word in the clause is "analysis". We observe, for example, for Stratford that Table 8 in Section 4.3.1 states that all asset groups (Stratford) achieved 100.00% availability for P6; whereas, Table 10 in Section 4.3.1 states that there were 702 reactive faults in P6, and states that there were 84 overdue faults in P6. The report for Stratford does not comment on how 100.00% availability is achieved when there are 702 reactive faults and 84 overdue faults. The report for Stratford does not comment on the recent significant increase (P5 and P6) in overdue faults. Further information is not required for Ashford other than improving Table 8 in Section 4.3.1 to differentiate between "Reactive Works" and "Not Completed". | The 100% figures refer to availability under the terms of HS1's operating contracts. These contracts allow assets to be unavailable during specified periods (e.g. during less busy periods of the day) without affecting the overall availability score. In these circumstances, it is possible to have a fault and show 100% availability. Further, Network Rail (High Speed) can identify long-term reactive works as a requirement, which are then not counted in the availability statistics. To provide oversight and assurance, HS1 monitors availability 'as seen' by passengers vs the contractual benchmarks and challenges its contractors on performance. | N/A | G
5.2.1 (H) | the renewals and replacements (if any) undertaken by the Station Operator in order that it discharged its Safety Obligations in respect of the Station but which were not identified in the current Life Cycle Report ("Station Safety Works"); | LCR | 4.1.3 | R | Requires further information for Stratford and Ebbsfleet. While it is stated for Stratford and Ebbsfleet that no Safety Obligation renewals or replacements were undertaken by the SFO, it does not state if HS1 Limited undertook Safety Obligation renewals or replacement, and it does not state that no Safety Obligation renewals or replacements were required. Further information is not required for Ashford and St. Pancras. | Section 6.1.3 (not section 4.1.3) Stratford and Ebbsfleet altered to read as follows: 'There were no renewals and replacements required to be undertaken by the SFO in order that it discharged its Safety Obligation in respect of the Station.' | Section 6.1.3, LCRs | G
5.2.2. | in respect of the current Review Period a progress report, comparison and reconciliation by reference to the Life Cycle Report approved for the current Review Period of | LCR
5.2.2 (A) | the Life Cycle Works actually completed to date against those anticipated giving the reasons for any differences | LCR | 4.1.2 | R | Requires further information. The Life Cycle Works listed in Table 5 of Section 4.1.2 are only those stated "…to be completed in the remainder of CP2." It is not known if there were other Life Cycle Works that have already been completed. | This information is provided in the LCC models, the Stations LTC review submission, and the Annual Stations Portfolio Funding Paper. Updates have been made to Section 6 of the LCRs. | Section 6, LCRs | G
5.2.2 (B) | the Life Cycle Works Cost incurred to date against those anticipated giving the reasons for any differences; | LCR | 4.1.2 | R | Requires further information. For those items listed in Table 5 of Section 4.1.2 the budgets and costs are provided. However, there is no information in Section 4.1.2 on the reason for the differences between budgets and costs. | As above. Reasons for variance is discussed in the Annual Stations Portfolio Funding Paper. | Section 6, LCRs | G
5.2.2 (C) | the Life Cycle Works Savings achieved to date against those anticipated; | LCR | 4.2.1.3 | A | Conditional compliance. It is stated in Section 4.2.1.3 that no savings were identified. However, it is not clear if this means none were anticipated, or that no savings have been identified where they were previously anticipated. | No savings are anticipated for the portfolio overall, however variance per project is shown in the Annual Stations Portfolio Funding Paper and Stations LTC review submission. | N/A | G
5.2.3 |  | LCR
a summary of the following up to the end of the previous Review Period for each Element of the Station of:
5.2.3 (A) | the aggregate amount of the Life Cycle Works Cost; | LCR | 4.2.3 | R | Requires further information. Stated that aggregate Life Cycle Works data is not yet available for CP2. | We have clarified that 'The anticipated LC works costs against budget for CP2 are shown in section 7'. | Section 7, LCRs. | G
5.2.3 (B) | the aggregate amount of the Deferred Life Cycle Works Savings (if any); and | LCR | 4.2.3 | R | Requires further information. Stated that aggregate Life Cycle Works data is not yet available for CP2. | As above. | Section 7, LCRs. | G
5.2.3 (C) | the aggregate amount of the Life Cycle Works Savings (if any); | LCR | 4.2.3 | R | Requires further information. Stated that aggregate Life Cycle Works data is not yet available for CP2. | As above. | Section 7, LCRs. | G
| Forecast Life cycle works | Title
5.2.4 | in respect of the next Review Period: | LCR
5.2.4 (A) | the Tenant's detailed proposals for the carrying out of the Forecast Life Cycle Works including any notices consents and approvals required in order to carry out and complete them; | LCR | 5.2.4 | R | Requires further information. Requires access to other documentation. Reference is made to an "Asset Change Control process", with general text provided for discrete project stages. Stated that "specific detail" will be in the "CP3 Delivery Plan". | The CP3 Delivery Plan, and the supporting commentary on notices, consents and approvals, will be developed in light of the DfT's funding approval in PR19. In general, we expect a combination of Station Change approval and potentially town planning may be necessary increasingly over CP3 and beyond, given heightened renewals activity. | N/A | A
5.2.4 (B) | the Forecast Life Cycle Works Cost; | LCR | 5.2.2.1 | G | Compliant. CP3 CAPEX estimates for renewals is provided. | N/A | N/A | G
5.2.4 (C) | the effect of any Relevant Changes of Law that will occur during the Review Period; | LCR | 5.2.3.2 | R | Requires further information. Appendix A in all four LCRs states that "Clause 5.2.4c" is addressed in "Section 5.2.3.2". It is noted that only St. Pancras LCR contains a Section 5.2.3.2. The other three LCRs do not contain a Section 5.2.3.2. It is noted that Section 5.2.3.1 in the other three LCRs is entitled "Future Changes in the Law" and appears to contain a response to Clause 5.2.4(c). The basis for assessing compliance with Clause 5.2.4(c) is based upon the text contained in Section 5.2.3.2 in St. Pancras LCR and Section 5.2.3.1 in the Stratford, Ashford and Ebbsfleet LCRs. The response includes reference to a review by the SFO that "could cause additional funds to be spend in the remainder of CP2" as a result of the Grenfell fire. The "effect" is not stated. | Incorrect document reference. See Section 6.2.2. | Section 6.2.2 | G
5.2.4 (D) | the forecast amount of Available Life Cycle Funds at the end of each Financial Year; | LCR | 5.2.2.2 | R | Requires further information. It is stated in the Stratford, Ebbsfleet and St. Pancras LCRs that the forecast amount of Available Life Cycle Funds will be provided in a later version of the LCR. It is noted that Table 12 in Section 5.2.2.2 of the Ashford LCR contains information that appears to meet the requirements of Clause 5.2.4(d); however, the data in the table appears to be for St. Pancras, not Ashford. | Section 7.2.2.2 (not 5.2.2.2) updated with CP3 Forecast of Available Funds. | Section 7.2.2.2, LCRs | G
5.25 | in respect of the remainder of the Life Cycle Period a summary of any changes to | LCR
5.2.5 (A) | the Forecast Life Cycle Works to be undertaken in each subsequent Review Period and Overhang Period in respect of each Element of the Station; | LCR | 5.3 | R | Requires further information. Requires access to other documentation. Reference is made to "Lifecycle Cost models", with a 45 year profile provided in response to Clause 5.2.5(a). References to station elements is included in the 45 year profile. Note that the Stratford LCR, the Ashford LCR and the Ebbsfleet LCR all incorrectly include the St. Pancras 45 year profile, not the 45 year profile for the station that is the subject of the LCR. | This detail is provided in the LCC and LTC models, which have been provided to DfT and GHD. Section 7.3 (not 5.3) - 40 year profiles added from LTC spreadsheet showing 'Available LC Funds' versus 'LC Works Costs.' | Section 7.3, LCRs | G
5.2.5 (B) | the Forecast Life Cycle Works Cost in each subsequent Review Period and Overhang Period in respect of each Element of the Station; and | LCR | 5.3 | R | Requires further information. Requires access to other documentation. Reference is made to "Lifecycle Cost models", with a 45 year profile provided in response to Clause 5.2.5(a). References to station elements is included in the 45 year profile. Note that the Stratford LCR, the Ashford LCR and the Ebbsfleet LCR all incorrectly include the St. Pancras 45 year profile, not the 45 year profile for the station that is the Subject of the LCR. | As above. | As above. | G
5.2.5 (C) | a forecast of the amount of Available Life Cycle Funds for each subsequent Review Period and Overhang Period; | LCR | 6.2.3 | R | Non-compliant. It is determined that the information in Section 6.2.3 does not address Clause 5.2.5(c). Further, the information in Section 6.2.3 appears to be from a LCR for the end of CP1/start of CP2. | As above. | As above. | G
| Deferrals | Title
5.2.6 | the Tenant's proposals (if any) for: | LCR
5.2.6 (A) | the deferral to any later Review Period or Overhang Period or the permanent omission of any Life Cycle. Works that are identified in the Asset Management Strategy as being required in the Review Periods and/or Overhang Periods following the Review Period in which the Life Cycle Report is produced: and/or | LCR | 6.1 | R | Non-compliant. Section 6.1 does not appear to have been updated for the CP3 submission. Section 6.1 makes reference to "F&G models" and "F&G plans". "F&G" is not defined in the LCR Glossary. | Section 6 (now Section 8) pertains to the LTC and is addressed in both the Stations LTC review submission and Annual Stations Portfolio Funding Paper. Clarifying text has been added to this effect. | Section 8.2.2, LCRs | G
5.2.6 (B) | the distribution of any Deferred Life Cycle Works Saving pursuant to paragraph 7.1; | LCR | 6.1 | R | Non-compliant. Section 6.1 does not appear to have been updated for the CP3 submission. Section 6.1 makes reference to "F&G models" and "F&G plans". "F&G" is not defined in the LCR Glossary. | As above. | As above. | G
| which shall include: | LCR
5.2.6 (C) | in respect of a proposal in relation to a proposed deferral or permanent omission | LCR
5.2.6 (C) i | confirmation by the Tenant that the proposed deferral or permanent omission will not result in the Tenant being unable to comply with its obligation under Clause 4.3.1 and 4.14 or the Life Cycle Purpose to be achieved; and | LCR | 6.1 | R | Non-compliant. Section 6.1 does not appear to have been updated for the CP3 submission. Section 6.1 makes reference to "F&G models" and "F&G plans". "F&G" is not defined in the LCR Glossary. | As above. | As above. | G
5.2.6 (C) ii | a report setting out the likely effect on performance arising out of or in connection with the proposed deferral or permanent omission; | LCR | N/A | G | Compliant. HS1 Limited states that this clause is not applicable ("n/a"). It is inferred that there are no proposed deferrals or permanent omissions, and therefore no report on the likely effect on performance. | N/A | N/A | G
5.2.6 (D) | the forecast Deferred Life Cycle Works Saving arising from paragraph 5.2.6(a); and/or | LCR | 6.1 | R | Non-compliant. Section 6.1 does not appear to have been updated for the CP3 submission. Section 6.1 makes reference to "F&G models" and "F&G plans". "F&G" is not defined in the LCR Glossary. | As above. | As above. | G
5.2.6 (E) | the forecast reduction in the Long Term Charge, the LTC and the Tenant's Share arising from paragraph 5.2.6(b); | LCR | 6.1 | R | Non-compliant. Section 6.1 does not appear to have been updated for the CP3 submission. Section 6.1 makes reference to "F&G models" and "F&G plans". "F&G" is not defined in the LCR Glossary. | As above. | As above. | G
| Distribution of Life Cycle Works Savings | Title
5.2.7 | the Tenant's proposals for any distribution of any Life Cycle Works Saving pursuant to paragraph 7.2, identifying the amount of the Life Cycle Works Saving, the reduction in the Long Term Charge, the LTC and the Tenant's Share, setting out the reasons why the Tenant considers such distribution should be made and providing all relevant supporting information; | LCR | 6.1 | R | Non-compliant. Section 6.1 does not appear to have been updated for the CP3 submission. Section 6.1 makes reference to "F&G models" and "F&G plans". "F&G" is not defined in the LCR Glossary. | Any deferrals are reflected in our CP3 LTC proposals, provided in the Stations LTC Review submission. This then informs the starting escrow balance for CP2. | As above. | G
| Adjustments to Available Life Cycle Funds | Title
5.2.8 | details of any Adjustment to the Available Life Cycle Funds made pursuant to paragraph 6.4.4 in the current Review Period (or anticipated to be made prior to the end of the current Review Period) and the arrangements (if any) which the Tenant has implemented and/or proposes to implement in order to mitigate the likelihood that any of the circumstances described in paragraph 5.4.7(a) to (c) will occur ("Adjustment Arrangements"): | LCR | 6.1 | R | Non-compliant. Section 6.1 does not appear to have been updated for the CP3 submission. Section 6.1 makes reference to "F&G models" and "F&G plans". "F&G" is not defined in the LCR Glossary. | As above. | As above. | G
| Long Term Charge | Title
5.2.9 | a description of any arrangements the Tenant has reached with Users pursuant to the terms of the Station Access Agreement to modify the LTC; | LCR | 6.2 | R | Non-compliant. No information is provided on any arrangements HS1 Limited has reached with the Train Operating Companies to modify the LTC. Further, the information in Section 6.2.3 appears to be from a LCR for the end of CP1/start of CP2. | Pursuant to Clause 5.2.9 of the HS1 Lease, the arrangements HS1 has in place to modify the LTC in the Station Access Agreements with operators forms part of the DfT's regulatory process in PR19; the revised agreements will be provided and explained to operators in the implementation phase following the DfT's decision in August 2019. Out of date financial information has been updated in Sections 7 and 8. | Sections 7 and 8, LCRs. | G
5.2.10 | any proposals by the Tenant for a modification to the LTC to recover | LCR
5.2.10 (A) | any Increased Life Cycle Costs which it has funded in accordance with paragraph 6.4; and/or | LCR | 6.2 | R | Non-compliant. No information is provided on proposals by HS1 Limited to recover Increased Life Cycle Costs from the Train Operating Companies. Further, the information in Section 6.2.3 appears to be from a LCR for the end of CP1/start of CP2. | See Stations LTC review submission. Out of date financial information has been updated in Sections 7 and 8. | Sections 7 and 8, LCRs. | G
5.2.10 (B) | any costs which it has suffered or incurred in connection with the Station Operator carrying out Station Safety Works in the current Review Period; | LCR | 6.2 | R | Non-compliant. No information is provided on proposals by HS1 Limited to recover any costs resulting from the Train Operating Companies carrying out Station Safety Works. Further, the information in Section 6.2.3 appears to be from a LCR for the end of CP1/start of CP2. | See Stations LTC review submission. Out of date financial information has been updated in Sections 7 and 8. | Sections 7 and 8, LCRs. | G
5.2.11 |  | LCR
any proposal by the Tenant for a modification to the LTC (other than pursuant to a proposal in paragraphs 5.2.6(b). 5.2.7. 5.2.9 or 5.2.10) to take effect from the beginning of the next Review Period
5.2.11 (A) | setting out the reasons why the Tenant considers that such modifications should be made and providing all relevant supporting information; and | LCR | 6.2 | R | Non-compliant. No information is provided on any proposal by HS1 Limited to modify the LTC, and no information on the reasons for those modifications Further, the information in Section 6.2.3 appears to be from a LCR for the end of CP1/start of CP2.. | See Stations LTC review submission. Out of date financial information has been updated in Sections 7 and 8. | Sections 7 and 8, LCRs. | G
5.2.11 (B) | In the case of a modification resulting from a Relevant Change of Law, confirming that the Tenant has notified each User of the Relevant Change of Law and of its assessment of the amount of the modification, and provided Users with such information as they shall reasonably require, in a form and amount of detail which is sufficient to enable Users to make a proper assessment of the effect of the Relevant Change of Law and of the Tenant's assessment; and | LCR | 6.2 | R | Non-compliant. No information is provided on any proposal by HS1 Limited to modify the LTC due to a Relevant Change of Law. Further, the information in Section 6.2.3 appears to be from a LCR for the end of CP1/start of CP2. | See Stations LTC review submission. Out of date financial information has been updated in Sections 7 and 8. | Sections 7 and 8, LCRs. | G
| Modifications to the Asset Management Strategy and the Life Cycle Budget | Title
5.2.12 | the Tenant's proposals for any modifications to the Asset Management Strategy (including the Life Cycle Budget) that are required to reflect its proposals in respect of the matters set out in paragraphs 5.2.1 to 5.2.11 above and/or to ensure that the Asset Management Strategy continues to satisfy the requirements set out in Annex 1 to this schedule; and | LCR | 3.1 | G | Compliant. It is noted that HS1 Limited is stated to be developing a Strategic Asset Management Plan and a "…series of Specific Asset Strategies…". It is not reported that there are any modifications to the Asset Management Strategy. | N/A | N/A | G
| General | Title
5.2.13 | such further details in respect of the matters described in paragraphs 5.2.1 to 5.2.11 as may be reasonably required by the Government's Representative. | LCR | N/A | A | Presumably, after the Government's Representative has reviewed the GHD report there will be an opportunity to formally respond to HS1 Limited to request further details as per the comments contained above. | Covered in this responses, and any further DfT-HS1 correspondence. | N/A | A