## Sheet1
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	20	21	22	£	£
Division name / DGC Category	Reference Number	Spend category	Spend Sub category	Short Description	Procurement Project/ Contract Title	Commercial Strategy	Existing Contract / s end date/s	Is there an extension option (Y/N + number of years)	Existing Supplier	Next Business Case Stage*	Planned date for next business case stage	Procurement start date	Required Contract Commencement Date (from the business/expiry)	New Contract end date (excluding options)	Value of new contract (excluding options)	Procurement Sourcing Route	Level of Competition	Contract Tiering	Business Area	Business SRO	Potential Sourcing / Commercial Lead	Current Contract Value / Estimated Contract Value	Estimated £ Savings Target	DGC Linked project no
Buildings	Unknown	Unknown	Unknown	SCAH Masterplan (Weybridge) - various contracts (design, consultancy, construction, demolition, renovation etc.)	SCAH Masterplan (Weybridge) - various contracts (design, consultancy, construction, demolition, renovation etc.)	New	Not Applicable	Not Applicable	Not Applicable	OBC	To be Confirmed	31/12/2019	31/12/2020	Unknown	£1,200,000,000	Unknown	Unknown	Gold	APHA	To be Confirmed	Heather Pearce	£1,200,000,000	Unknown	Unknown
Technology	Unknown	Unknown	Unknown	Application Development and Management Services	Application Development and Management Services	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	31/03/2020	31/03/2021	Unknown	£80,000,000	Unknown	Unknown	Gold	Defra	To be Confirmed	Paul Wanless	£80,000,000	Unknown	Unknown
EG&S	Unknown	Unknown	Unknown	Carbon Credits Project (cross category procurements, Incl DDTS)	Carbon Credits Project (cross category procurements, Incl DDTS)	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	01/12/2019	01/12/2020	Unknown	£50,000,000	Unknown	Unknown	Gold	NE	To be Confirmed	Nick Jones	£50,000,000	Unknown	Unknown
Corporate Services	Unknown	Unknown	Unknown	Public Sector Resourcing	Public Sector Resourcing	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	20/07/2023	16/01/2024	Unknown	£50,000,000	Unknown	Unknown	Gold	Defra	To be Confirmed	Steph Galliford	£50,000,000	Unknown	Unknown
Corporate Services	ecm_48381	U99.34.12.12	Travel Management - Unclassified	Crown Travel and Venue Services	Crown Travel and Venue Services	Re-procurement	03/01/2020	None	Redfern Travel Ltd	Renew	05/10/2019	07/07/2019	03/01/2020	03/01/2024	£48,000,000	Unknown	Unknown	Gold	Defra group	To be Confirmed	Steph Galliford	£48,000,000	Unknown	ecm_48381
Corporate Services	project_25044	Unknown	Unknown	National Temporary Staff Framework (Contingent Labour One) (Non IT)	National Temporary Staff Framework (Contingent Labour One) (Non IT)	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	01/04/2019	04/10/2019	01/04/2020	Unknown	£24,000,000	Open OJEU	Open OJEU	Silver	EA	To be Confirmed	Steph Galliford	£24,000,000	Unknown	Unknown
Technology	ecm_42947	U99.23.12.12	IT Managed / Outsourced Services - Unclassified	Application Maintenance and Support with Systems and Service Integration for the Genesis IT Application	Application Maintenance and Support with Systems and Service Integration for the Genesis IT Application	Re-procurement	31/01/2021	Accounted For	Atos	Renew	02/11/2020	02/12/2020	01/02/2021	04/05/2026	£17,737,488	Open OJEU	Open OJEU	Gold	Defra group	Andrew Evitt	Paul Wanless	£17,737,488	Unknown	Unknown
Technology	ecm_48126	U81.11.15.00	Software or hardware engineering	Policy Engine	Policy Engine	Re-procurement	30/09/2020	N/A	Abaco SpA	Renew	02/07/2020	01/08/2020	01/10/2020	01/10/2024	£15,613,668	Unknown	Unknown	Gold	Defra group	To be Confirmed	Andy Lockwood	£15,613,668	Unknown	Unknown
Technology	ecm_51870	U80.18.00.00	Business Process Outsourcing Services	Digitising & Remote Sensing	Provision of Digitising & Remote Sensing services for Rural Payments Agency	Re-procurement	31/05/2020	2+1+1+1	Cyient Europe Limited	Renew	02/03/2020	01/04/2020	01/06/2020	02/06/2025	£15,000,000	Unknown	Unknown	Gold	Defra group	To be Confirmed	Nicholas Wright	£15,000,000	Unknown	project_23203
Technology	ecm_50009	U81.11.22.00	Software maintenance and support	Microsoft Enterprise agreement	Microsoft Enterprise agreement	Re-procurement	30/06/2020	N/A	Comparex UK Ltd	Renew	01/04/2020	01/05/2020	01/07/2020	02/07/2023	£14,629,748	Unknown	Unknown	Gold	Defra group	To be Confirmed	James Green	£14,629,748	Unknown	project_21634
Technology	ecm_40567	U77.10.15.05	Environmental (Land Use & Biodoversity) monitoring	ISSC2 - Independent Shared Service Centre 2	The provision of shared services for Natural England from 1 Nov 2013.	Re-procurement	31/10/2020	1 X 3 Years	Shared Services Connected Ltd	Renew	02/08/2020	01/09/2020	01/11/2020	01/11/2027	£12,326,815	Direct Award Under Framework	Direct Award Under Framework	Gold	Corporate Services	To be Confirmed	Pam Vines	£12,326,815	Unknown	project_7689
EG&S	Unknown	Unknown	Unknown	Quality Assurance & Quality Control services for the Automatic Urban & Rural Air Quality Monitoring Network (AURN) & Diffusion Tube Network + Central Management and Control Unit for AURN	Quality Assurance & Quality Control services for the Automatic Urban & Rural Air Quality Monitoring Network (AURN) & Diffusion Tube Network + Central Management and Control Unit for AURN	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	13/05/2019	16/12/2019	Unknown	£12,000,000	Unknown	Unknown	Silver	EA	To be Confirmed	Nick Jones	£12,000,000	Unknown	Unknown
Corporate Services	Unknown	Unknown	Unknown	Estates Professional Project Support and Land Agency Services	Estates Professional Project Support and Land Agency Services	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	02/10/2022	31/03/2023	Unknown	£10,000,000	Unknown	Unknown	Silver	EA	To be Confirmed	Steph Galliford	£10,000,000	Unknown	Unknown
Technology	ecm_53736	U43.23.15.00	Business function specific software	Micorsoft EU Exit	Defra Digital Transformation Partner	Re-procurement	30/09/2019	1+1 + 1	Microsoft	Renew	02/07/2019	01/08/2019	01/10/2019	21/07/2020	£9,000,000	Unknown	Unknown	Gold	Defra group	To be Confirmed	Andy Lockwood	£9,000,000	Unknown	project_25298
EG&S	Unknown	Unknown	Unknown	National Groundwater Monitoring Framework	National Groundwater Monitoring Framework	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	01/07/2019	01/04/2020	Unknown	£8,500,000	Unknown	Unknown	Silver	EA	To be Confirmed	Nick Jones	£8,500,000	Unknown	Unknown
Technology	Unknown	Unknown	Unknown	VARIOUS	VARIOUS	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	01/12/2019	01/12/2020	Unknown	£8,400,000	Unknown	Unknown	Silver	Defra group	To be Confirmed	Karen O'Brien	£8,400,000	Unknown	Unknown
Corporate Services	ecm_49402	U12.18.15.04	Petrolatums	20479 - Fuel Cards	Fuel Cards	Re-procurement	31/03/2020	2 + 1 + 1	Allstar Business Solutions Ltd	Renew	01/01/2020	31/01/2020	01/04/2020	09/04/2024	£8,000,000	Unknown	Unknown	Silver	Defra group	To be Confirmed	Steph Galliford	£8,000,000	Unknown	project_20479
Corporate Services	Unknown	Unknown	Unknown	National Office Waste Collection	National Office Waste Collection	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	03/10/2019	31/03/2020	Unknown	£8,000,000	Unknown	Unknown	Silver	All	To be Confirmed	Steph Galliford	£8,000,000	Unknown	Unknown
Buildings	Unknown	Unknown	Unknown	National Contract for the Provision of Furniture	National Contract for the Provision of Furniture	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	01/09/2019	28/02/2020	Unknown	£7,500,000	Unknown	Unknown	Silver	Defra	To be Confirmed	Heather Pearce	£7,500,000	Unknown	Unknown
Corporate Services	Unknown	Unknown	Unknown	Media Buying Framework RM6003 Call-Off	Media Buying Framework RM6003 Call-Off	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	30/08/2019	01/11/2021	Unknown	£7,500,000	Unknown	Unknown	Silver	All	To be Confirmed	Steph Galliford	£7,500,000	Unknown	Unknown
Corporate Services	Unknown	Unknown	Unknown	Vehicle Hire	Vehicle Hire	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	01/01/2021	30/06/2021	Unknown	£7,000,000	Unknown	Unknown	Silver	Defra & EA	To be Confirmed	Steph Galliford	£7,000,000	Unknown	Unknown
Technology	Unknown	Unknown	Unknown	Defra CAP Platforms Support	Defra CAP Platforms Support	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	03/03/2020	31/07/2020	Unknown	£6,388,897	Unknown	Unknown	Silver	RPA	To be Confirmed	Karen O'Brien	£6,388,897	Unknown	Unknown
Buildings	Unknown	Unknown	Unknown	Regional Laboratory Starcross – Renovation, Rearrangement & Upgrade	Regional Laboratory Starcross – Renovation, Rearrangement & Upgrade	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	01/12/2020	01/12/2022	Unknown	£6,000,000	Unknown	Unknown	Silver	Defra & APHA	To be Confirmed	Heather Pearce	£6,000,000	Unknown	Unknown
Buildings	Unknown	Unknown	Unknown	Regional Laboratory Carmarthen – Renovation, Rearrangement & Upgrade	Regional Laboratory Carmarthen – Renovation, Rearrangement & Upgrade	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	01/12/2020	01/12/2022	Unknown	£6,000,000	Unknown	Unknown	Silver	Defra & APHA	To be Confirmed	Heather Pearce	£6,000,000	Unknown	Unknown
Technology	ecm_42945	U99.23.12.12	IT Managed / Outsourced Services - Unclassified	Hosting for the Genesis IT Application Contract	Hosting	Re-procurement	31/01/2021	Accounted For	Rackspace Ltd	Renew	02/11/2020	02/12/2020	01/02/2021	04/12/2025	£5,896,244	Open OJEU	Open OJEU	Silver	Defra group	Andrew Evitt	Paul Wanless	£5,896,244	Unknown	project_4193
Buildings	Unknown	Unknown	Unknown	Weybridge Incinerator Building Extension	Weybridge Incinerator Building Extension	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	01/09/2019	28/02/2020	Unknown	£5,700,000	Unknown	Unknown	Silver	Defra & APHA	To be Confirmed	Heather Pearce	£5,700,000	Unknown	Unknown
Technology	ecm_42946	U99.23.12.12	IT Managed / Outsourced Services - Unclassified	Application Development for the Genesis IT Application Contract	Application Development	Re-procurement	31/01/2021	Accounted For	Atos	Renew	02/11/2020	02/12/2020	01/02/2021	04/05/2026	£5,096,646	Open OJEU	Open OJEU	Gold	Defra group	Andrew Evitt	Paul Wanless	£5,096,646	Unknown	project_4194
Technology	Unknown	Unknown	Unknown	Defra Future Contact Centre	Defra Future Contact Centre	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	02/05/2019	01/07/2020	Unknown	£5,000,000	Unknown	Unknown	Silver	Defra	To be Confirmed	Karen O'Brien	£5,000,000	Unknown	Unknown
Buildings	Unknown	Unknown	Unknown	Weybridge Building Renovation & Upgrade – Building B150	Weybridge Building Renovation & Upgrade – Building B150	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	01/12/2020	01/12/2022	Unknown	£5,000,000	Unknown	Unknown	Silver	Defra & APHA	To be Confirmed	Heather Pearce	£5,000,000	Unknown	Unknown
Buildings	Unknown	Unknown	Unknown	Regional Laboratory Penrith – Renovation, Rearrangement & Upgrade	Regional Laboratory Penrith – Renovation, Rearrangement & Upgrade	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	01/12/2020	01/12/2022	Unknown	£5,000,000	Unknown	Unknown	Silver	Defra & APHA	To be Confirmed	Heather Pearce	£5,000,000	Unknown	Unknown
Buildings	Unknown	Unknown	Unknown	National Framework for the provision of Professional Services	National Framework for the provision of Professional Services	New	Not Applicable	Not Applicable	Not Applicable	Unknown	To be Confirmed	01/12/2019	29/05/2020	Unknown	£5,000,000	Unknown	Unknown	Silver	Defra	To be Confirmed	Heather Pearce	£5,000,000	Unknown	Unknown
Corporate Services	Unknown	Unknown	Unknown	Print Services Call Off for the RPA	Print Services Call Off for the RPA	Re-procurement	To Be Confirmed	To Be Confirmed	To Be Confirmed	Renew	To be Confirmed	17/12/2020	15/06/2021	Unknown	£5,000,000	Unknown	Unknown	Silver	RPA	To be Confirmed	Steph Galliford	£5,000,000	Unknown	Unknown