Prosperity Fund Business Case

Global Future Cities Programme

“To work with a select number of cities in middle income countries over a three year period to improve the way their cities are planned and managed, resulting in increased local prosperity and quality of life, including a reduction in levels of poverty and gender inequality, together with creating mutually beneficial two-way trade opportunities.”

Approved

Introduction

The Global Future Cities Prosperity Fund Programme is a three year £80.0 million (£74.6 million discounted to 2018) ODA programme. The programme will support inclusive and sustainable urban economic growth and increase global prosperity through targeted interventions on transportation, urban planning and urban resilience in ten countries worldwide (Brazil, Indonesia, Malaysia, Myanmar, Nigeria, Philippines, South Africa, Thailand, Turkey and Vietnam). The programme is FCO led but supported by DFID and DIT. The UK is acknowledged as a global leader in the industries involved in future cities and is well-positioned as the partner of choice for future cities development.

What is the development need?

Rapid urbanisation is an unstoppable global trend: the world’s urban population is expected to surpass nine billion by 2045, and today, about 80% of the world’s GDP is generated by cities. However, unless cities are well planned and managed, urbanisation exacerbates poverty, inequality, exclusion (e.g. 30% of urban residents in Asia live in slums), overcrowding, congestion, pollution, crime, and inadequate and inaccessible basic public services and infrastructure.

There are a number of increasingly urgent urban challenges which act as barriers to achieving greater prosperity, poverty reduction, inclusive economic growth and gender equality. Progress in these areas is essential to enable access to increased economic opportunities, increased productivity, a healthier environment, improved health outcomes and a better quality of life for men and women across the lifecycle. The three key areas that have been identified are:
- Transportation: The ability to travel quickly, cost effectively, safely and in a way that emits the least possible amount of pollutants is crucial for any inclusive, productive and healthy city.
- Urban planning: Urban planning which promotes transit-oriented development, affordable housing, disaster resilience, access to community facilities and shared and safe public space for all, all via improved spatial planning. Better planning aims to help address many of the inequality, exclusion and poverty-related problems associated with chaotic and unplanned urbanisation[1].
  [1] See for example: http://www.jchs.harvard.edu/research/publications/advancing-inclusive-and-sustainable-urban-development-correcting-planning
- Resilience: Improving resilience in city environments will have significant benefits for large numbers of low-income inhabitants. This includes avoiding settlements in areas prone to flooding or landslides and future-proofing existing and new developments against storm-related flooding, earthquakes and future rises in sea levels.

How can the UK help?

Forecasts indicate that the global future cities market will be worth £328 billion pa by 2020. There is a clear opportunity now to work with selected partner country governments to positively influence the shape of their city plans and investments to drive inclusive and sustainable local growth and open up opportunities for international business, including the UK.

The UK follows a multi-sectoral, holistic approach to urban development, taking into account social, environmental, economic and political factors. The UK’s business and public sectors (including across infrastructure services, consultancies, construction, technology, and standards) together with academic institutions, civil society and government-funded programmes (e.g. ICED), all have extensive expertise in delivering sustainable urban solutions that can be built upon to help meet our partner country development needs.

What will the programme deliver?

1. The overall impacts of the programme are defined as:
  1. Primary: The development of urban environments that enhance inclusive economic growth, reduced poverty and gender inequality, have cleaner air and safe environments, and are resilient to disasters.
  2. Secondary: Opportunities and sustainable economic relationships are developed with cities in sectors where the UK has a comparative advantage, leading to a mutually beneficial two-way increase in future cities trade.

The programme will realise the above impacts through implementing proven, short-term, interconnected, enabling interventions (e.g. capacity building, strategy, governance, frameworks, plans, feasibility, regulatory change, citizen engagement). The interventions all fit within three integrated pillars, that respond to the identified barriers to prosperity, trade and poverty reduction in selected cities:
- Transportation – technical assistance to support cities to develop integrated multi-modal public transport systems
- Urban planning – technical assistance for spatial restructuring (city strategies, urban renewal, regeneration, master planning and planning frameworks)
- Resilience – technical assistance to develop strategies to address the impact of climate change (e.g. flooding) and ensure development is sustainable

The programme will work jointly with partner governments to implement the above pillars, supported by two cross-cutting themes: smart technology/data and project financing, and act as a catalyst for further investment within the selected cities and beyond. All the city-specific interventions have been designed and assessed to ensure they address a clear city prosperity need, have a high degree of additionality, and are feasible.

This programme will also help deliver the UK’s commitment to support implementation of the UN’s Sustainable Development Goals (SDG), especially SDG 11 to “make cities and human settlements inclusive, safe, resilient, and sustainable”, but also SGD 1 “No Poverty, SDG 5 “Gender Equality”, and SDG 9 to “Build resilient infrastructure”.

# The Strategic Case
This business case supports inclusive economic growth in middle-income countries through the development of more resilient, inclusive, sustainable, prosperous cities (Future Cities) and investigates opportunities for increasing global prosperity. This Prosperity Fund programme would deploy £80m (£73m discounted) of Official Development Assistance (ODA) to pursue these objectives, creating £107 million of discounted primary benefits and £25 million of discounted secondary benefits.
Introduction
1. The UK Government is aware[2] that the current critical global trends of rapid urbanisation, climate change and resource depletion are all integrated, and recognises the importance of sustainable management of cities. The Ministerial Board, in September 2016, identified ‘smart and future cities’ as a priority sector for the cross-Government Prosperity Fund (PF). The National Security Strategy[3] (NSS) highlights that one of the drivers of instability and exclusion is “rapid and unplanned urbanisation”. Both the NSS and UKAid Strategy (2015), commit that in order to support growth and economic development in developing countries the Government will build on existing work and fund new prosperity work to “unlock private and public investment in energy, infrastructure and urban development.”
  [2] https://publications.parliament.uk/pa/cm201617/cmselect/cmintdev/103/103.pdf, https://www.gov.uk/guidance/national-planning-policy-framework/achieving-sustainable-development,
  [3] https://www.gov.uk/government/publications/the-national-security-strategy-a-strong-britain-in-an-age-of-uncertainty
2. UK government policy and funding towards sustainable urban development therefore fits with both National Security Council (NSC) and UKAid Strategy objectives. It is also aligned with the UK’s commitments to support implementation of the UN’s Sustainable Development Goal (SDG) 11 to “make cities and human settlements inclusive, safe[4], resilient, and sustainable” and SDG 9 to “Build resilient infrastructure”. The programme has defined future cities as:
  [4] http://www.unwomen.org/en/news/in-focus/women-and-the-sdgs/sdg-11-sustainable-cities-communities
“An approach to planning the growth of cities that increases levels of productivity, generates sustainable wealth, helps alleviate poverty, addresses gender inequality, increases quality of life for all societal groups, allows more people to live in an existing urban area, improves resilience, minimises any negative impacts on the environment and proactively involves the city’s citizens and businesses in the process. Future cities are innovative, sustainable and utilise technology in a smart way”.
Context
Definition of future cities and the New Urban Agenda
1. There is no singular acknowledged definition of a ‘future city’, not surprising given the broad nature of the topic and the variety of cities worldwide. Future and smart city ideas and concepts were discussed at the last United Nations (UN) Conference on Housing and Sustainable Urban Development (Habitat III) during October 2016 in Quito [5]. An output of HABITAT III was the “New Urban Agenda”[6]which aims to guide international efforts around urbanisation of a wide range of actors, including nation states, city and regional leaders, international development funders, United Nations programmes and civil society, for the next 20 years. The Agenda sets out the transition ‘roadmap’ and key principles to follow towards more sustainable cities.
  [5] http://habitat3.org/the-new-urban-agenda/
  [6] http://habitat3.org/wp-content/uploads/NUA-English.pdf
2. While the New Urban Agenda provides the framework, principles and desired outcomes for sustainable urban development, the detail of how to achieve this is left to context specific solutions, in which urban development actors must be collaborative and innovative. The New Urban Agenda principles have been endorsed by the full UN Generally Assembly, and whilst clearly there will be different interpretations across member states, there is a definite theme of ensuring that current and future developments adhere as much as possible to these principles.
Global urban trends
1. Cities only occupy 2% of the earth’s land surface, yet they house over half of the human population[7]. Rapid urbanisation appears an unstoppable global trend and the global urban population is set to rise from 55% in 2018 to 68% in 2050[8], increasing the global urban population from 3.9 billion to 6.3 billion. The majority of this growth is forecast to be in Asia and Africa. In 2050, some 3.3 billion people[9] will live in cities and towns across Asia, an increase from 2.1 billion today; this is equivalent to adding an entire new city of 3 million people, approximately the size of Singapore, every month for the next 35 years. In Latin America and the Caribbean, 80% of the population already lives in cities[10]. Although this is the largest proportion in the world, this figure is projected to grow to 86%[11] by 2050, adding pressure to cities with already saturated infrastructure and services. Currently 40% of Africa's 1.1 billion inhabitants currently live in urban areas, and by 2050 that proportion is predicted to rise will have risen to 56%[12]. According to UN Women[13], women and youth continue to make up the majority of people living in poverty in urbanised areas, with limited control over assets.
  [7] http://www.unep.org/ietc/sites/unep.org.ietc/files/Key%20messages%20RE%20Habitat%20III_en.pdf
  [8] UN, DESA, World Urbanization Prospects: The 2018 Revision
  [9] UN, DESA, World Urbanization Prospects: The 2018 Revision
  [10] UN, DESA, World Urbanization Prospects: The 2018 Revision
  [11] UN, DESA, World Urbanization Prospects: The 2018 Revision
  [12] UN, DESA, World Urbanization Prospects: The 2018 Revision
  [13] UN Women, http://asiapacific.unwomen.org/en/focus-areas/women-poverty-economics
2. Some 82%[14] of cities globally, home to 1.9 billion people in 2014, were located in areas that faced high risk of mortality associated with natural disasters. Similarly, 89%[15] of cities, home to 2.1 billion people in 2018, were located in areas that were highly vulnerable to economic losses associated with at least one of six types of natural disaster.
  [14] http://www.un.org/en/development/desa/population/publications/pdf/urbanization/the_worlds_cities_in_2016_data_booklet.pdf
  [15] http://www.un.org/en/development/desa/population/publications/pdf/urbanization/the_worlds_cities_in_2016_data_booklet.pdf
3. Cities are drivers of economic growth[16] – 80%[17] of the world’s gross domestic product (GDP) is generated by cities. Studies[18] have shown that as a general rule, when the population of a city doubles, economic productivity goes up by an average of 130%; and that this effect is largely due to the face-to-face networking opportunities and cross-fertilisation of ideas that the urban workspace enables. Successful cities create economic value which drives prosperity. Using data from 2005 to 2012, the World Bank Report “Competitive Cities for Jobs and Growth”[19] found the following shared characteristics between top performing cities:
  [16] http://www.worldbank.org/content/dam/Worldbank/Publications/Urban%20Development/EAP_Urban_Expansion_full_report_web.pdf
  [17] UN, http://www.worldbank.org/en/topic/urbandevelopment/overview
  [18] Nature magazine, Issue 467, 2010
  [19] http://www.worldbank.org/en/events/2015/12/08/competitive-cities-jobs-growth
- Accelerated economic growth – the top 10% of cities achieved 13.5% annual GDP per capita growth, compared with 4.7% in an average city
- Outstanding job growth – the top 10% of cities achieved 9.2% annual job growth, while the remaining 90% only achieved 1.9%
- Increased incomes and productivity – the top 10% of cities increased the average disposable income of their households by 9.8% annually, while the bottom 10% of cities only achieved 0.1%
- Magnets for foreign direct investment (FDI) – the top 5% of cities obtained as much FDI as the bottom 95% of cities combined
This rate of growth is drawing increasing levels of resources (i.e. labour) from rural economies as people increasingly seek better lives. However the extent to which growing competitive cities are sustainable, resilient and safe, is an important issue. In many cases heightened growth rates also bring increased levels of inequality and poverty – sometimes, extreme poverty[20].
[20] Global Monitoring Report (GMR) 2013, World Bank and International Monetary Fund (IMF).

Prosperity challenges and opportunities
1. There are a number of urban challenges which act as barriers or constraints to poverty reduction, inclusive economic growth and gender equality. During the programme development, detailed independent scoping studies were undertaken in order to identify the constraints to growth. The studies then looked at strategies for overcoming these constraints which would achieve the primary objectives of the programme: the development of urban environments that enhance inclusive economic growth, reduce poverty and gender inequality, have cleaner air and safe environments, and are resilient to disasters.
2. The studies established 14 themes relevant to future cities including Future Smart Cities, Infrastructure and Service Provision, Urban Planning and Resilience. A detailed assessment of these thematic constraints was undertaken to shortlist the countries and cities for the programme to operate in. The assessment undertaken in each short-listed city ensured that the programme design is locally relevant and grounded in reality, focused on addressing the city-specific constraints to prosperity and poverty reduction. The criteria used to assess the constraints were:
- Local development need
- Additionality and feasibility
1. A summary of the assessment findings is set-out below.
2. A cross Government Steering Committee agreed a framework, based on the above assessment, containing a short-list of three thematic constraints, which form the basis for the development of the proposed interventions.
3. The three shortlisted thematic constraints are transport, urban planning and resilience and are briefly summarised here:
Transportation: Poverty and lack of access to urban transport are often strongly correlated as peripheral low-income districts are often lacking in all forms of infrastructure. This is particularly the case in rapidly expanding cities where planning is often non-existent or unenforced. The long travel times needed to reach employment or amenities reduces productivity and quality of life. Traffic congestion is estimated to cost cities huge losses in productivity e.g. Sao Paulo is estimated to lose £9bn pa, 7.5% of its GDP[21], affecting primarily poorer populations, and especially women; congestion on city roads in ASEAN countries costs 2-5% of GDP every year due to lost time and higher transport costs[22]; Bangkok drivers spend 72 minutes in traffic jams and 24 minutes finding a parking spot (equivalent to 24 days per year)[23].
[21] FGV, The Congestion Costs in the City of Sao Paulo, 2014
[22] https://www.adb.org/sectors/transport/key-priorities/urban-transport
[23] https://www.uber.com/en-SG/newsroom/asian-traffic-turns-people-away-car-ownership/
- Urban planning: Urban population growth has been accompanied by an expansion in built-up areas, with physical urban expansion occurring in many cities at a faster rate than population growth. This has negative impacts on access to services, safety, employment and income earning opportunities and affordable housing, also affecting primarily poorer socio-economic groups and more excluded populations, including women (two-thirds of the 1.4 billion living in extreme poverty are women)[24]. Lack of access to basic infrastructure – such as energy, water and sanitation, is inefficient and has a major impact on women and children because of the additional time required for domestic chores and household care.
  [24] UN Women, http://asiapacific.unwomen.org/en/focus-areas/women-poverty-economics
- Resilience: Lack of resilience often affects low-income groups of society as unplanned, poorly constructed peripheral urban developments are typically most impacted by disasters such as flooding, storms and landslides due to inadequate or lack of basic infrastructure. Women below the poverty line are particularly impacted[25], but also because of their burden of managing their domestic unpaid household and care work with employment and income earning.
  [25] UN Women, http://asiapacific.unwomen.org/en/focus-areas/women-poverty-economics
Gender perspective and Gender Equality Act
1. Gender inequality is a crucial aspect to understand in urban contexts. The programme design has taken a meaningful view of how it will contribute to reducing gender inequality, in accordance with the UK’s International Development (Gender Equality) Act. Demographic data[26] shows there is already a higher proportion of women within the urban population, and a concentration of women-headed households in urban centres. Women move to urban areas for a number of different reasons, such as to seek higher income, flee conflict, avoid environmental degradation, or to escape family breakdown, violence and discrimination. While many hope to find better livelihoods in cities, the majority end up in urban slums in which housing and living conditions are especially harsh. Close to one third of the world’s women are homeless or live in inadequate housing[27].
  [26] Gender Equality and the New Urban Agenda, UN Women, 2015
  [27] UN Habitat, http://mirror.unhabitat.org/content.asp?typeid=19&catid=283&cid=1507
2. Urbanisation does not impact women and men equally. Lack of urban transport, reliable power, clean water and sanitation vastly reduces potential educational and income-generating activities as more time is spent on domestic tasks, often female dominated[28]. For example, access to affordable electricity reduces the time spent by women on household tasks by 70%[29]. Improving transport systems is a game-changer and enhances women’s mobility, leading to higher paying jobs for women and new opportunities for business expansion[30]. In some contexts, cities can be made more accessible to women through encouraging less car-reliant urban environments (66% of drivers in Brazil are male[31]) via improved spatial planning and public transport options.
  [28] International Institute for Environment and Development & UNFPA (2012) Urbanization, gender and urban poverty: paid work and unpaid care work in the cities.
  [29] Asian Development Bank (2015) Balancing the Burden? Desk Review of Women’s Time Poverty and Infrastructure in Asia and the Pacific
  [30] UN (2016) Infrastructure: a Game-Changer for Women’s Economic Empowerment
  [31] Sistema MPA http://www.sistemampa.com.br/noticias/mulher-no-volante-perigo-contante-as-estatisticas-mostram-que-nao/
3. Gender-based violence is also prevalent in many cities. Research[32] carried out in 143 countries in 2011 shows men are considerably more likely than women to say they feel safe walking alone at night in their communities. This perception often represents reality, as a high number of women living in cities report having been subjected to street harassment e.g. 86% in Thailand and 89% in Brazil[33]. Domestic violence also fuels female poverty as women often settle in slums and informal housing solutions to escape.
  [32] http://www.refinery29.uk/women-safer-cities
  [33] Action Aid (2016) http://www.actionaid.org.br/news/em-pesquisa-da-actionaid-86-das-brasileiras-ouvidas-dizem-ja-ter-sofrido-assedio-em-espa
4. Gender neutral approaches to urban planning often lead to unequal gender outcomes which systematically disadvantage poor people and women. Research suggests that more gender-sensitive approaches to cities and urban development leads to more efficient and inclusive economic growth. As stated by the UN Secretary General’s High-Level Panel (HLP) on Women’s Economic Empowerment: “Empowering women in the economy and closing gender gaps at work are central to the 2030 Agenda for Sustainable Development”[34].
  [34] Leave No One Behind, A call to action for gender Equality and Women’s Economic Empowerment, Report of the UN Secretary General’s High-Level Panel on Women’s Economic Empowerment, 2016
5. Improved infrastructure service delivery, better urban planning and resilience processes have the potential to create significant benefits for women and girls. For example:
- Improved access to infrastructure and transport services can reduce time poverty for women and girls by reducing the burden associated with their unpaid care and domestic work responsibilities[35].
  [35] Koolwal,G. and Van de Walle, D (2009) Access to Water Women’s Work And Child Outcomes World Bank Policy Research Working Paper No. 5302
- Better urban and spatial planning can reduce the risk of violence against women and girls, for example through providing access to safe transportation and street lighting[36].
  [36] Action Aid (2011) Women and the City: Examining the gender impact of violence and urbanisation
- Where transport is designed with the specific needs of women in mind, it can release mobility constraints (which can prevent women accessing jobs, information, health and education) and drive women’s access to education, employment or business opportunities and therefore increased incomes.
- Reduced vulnerability to climate and other disasters through improved planning and implementation, as women and girls are more likely to die in disasters than men[37].
  [37] Bradshaw, S. & Fordham, M. (2013) Women, Girls and Disasters: A Review for DFID. Available at https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/236656/women-girls-disasters.pdf
1. The programme will take measures to ensure compliance with the UK’s Gender Equality Act (GEA) and give clear regard to reducing gender inequality through the design of the programme and its interventions. It will ensure alignment with the Prosperity Fund’s Gender and Inclusion (G&I) policy, and seek to implement recommendations of the HLP on Women’s Economic Empowerment. The programme will adopt a gender-sensitive approach to urban planning in order to address the systemic constraints that contribute to persistent gaps in women’s economic opportunities and quality of life. Social and gender analysis and expertise will be integrated in the design and implementation of interventions. Full G&I Analysis and Assessments will be developed during the inception phase, prior to implementation, together with G&I Action Plans. This will be based on consultations with key stakeholders, including women, other excluded groups and their representatives (e.g. Civil Society Organisations, Women-led NGOs and enterprises and Disabled People’s Organisations), in order to ensure that their views and concerns are heard and responded to. This will help to identify, mitigate and/or address risks, opportunities and constraints with regard to the impact of the programme on gender equality, women’s economic empowerment and inclusion of other excluded groups, such as people with disabilities. Well planned infrastructure and inclusive urban services are also fundamental to unlocking the potential of people with disabilities[38]. This approach reflects the New Urban Agenda, which calls on city authorities to take into account the needs of women, youth and children, people with disabilities, marginalized groups, older persons, indigenous people, among other groups.
  [38] ICED Briefing: Disability Inclusion through Infrastructure and Cities Investments
2. The programme will ensure that appropriate gender/ social development expertise and technical assistance is provided where necessary to support women’s empowerment and gender mainstreaming. Implementing partners will be required to take gender equality and inclusion into consideration throughout the programme cycle and share learning, applying the Prosperity Fund’s G&I policy, framework and guidance. There will be a requirement on delivery partners to consider and report on progress on gender in programme delivery. Impact of proposed interventions on gender equality and inclusion will be monitored and assessed through the collection, tracking, analysis and measurement of data disaggregated by sex, age and poverty quintile in line with the PF MREL central system, and by disability where possible.
Poverty perspective
Well-planned and managed urbanisation can drive prosperity, but poorly planned urbanisation leads to extreme poverty[39] (e.g. 30%[40] of citizens in Asia and 23%[41] in Latin America and the Caribbean live in slums without access to basic services such as housing, clean water and sanitation), overcrowding, congestion, pollution, and inadequate and inaccessible basic public services. In Brazil, 45 million people live in slums[42]. Even though the percentage of the population living in slums is decreasing as overall prosperity increases, the total number of people living in slums is still rising – see the chart below. Those living in slums are particularly vulnerable, as they usually work in the informal sectors of the economy as a result of poor transport, limiting access to employment opportunities. Those working in the informal sector tend to be the lowest income earners and lack job security and associated benefits, such as health insurance and retirement schemes.
[39] UN, The State and of Asian and Pacific Cities, 2015
[40] UN, Are we building competitive and liveable cities, 2011
[41] UN Economic Commission for Latin America and the Caribbean, 2013
[42] UN Habitat, Slum Almanac, 2015-2016

The projected urban population growth over the next 35 years is expected to exacerbate this problem with a further increase in the number of people living in slums unless there is more concerted ‘intervention’ to support a more sustainable growth profile.
Environmental perspective
In an environmental context, cities are responsible for 80% of global greenhouse gas emissions[43] and half the global urban population is exposed to air pollution levels at least 2.5 times WHO standards[44]. Within Asian cities, around 80% of air pollution is produced by road transport[45]. Due to the nature of their housing, vulnerable populations, including low-income population, women and children, are more exposed to air pollution, extreme weather events, floods and droughts. For example, around 4.3 million people a year (a majority of women and children) die prematurely from illness attributable to the household air pollution caused by the inefficient use of solid fuels for cooking[46].
[43] New Climate Economy, http://2014.newclimateeconomy.report/cities/
[44] UN (2016) Progress towards the sustainable development goals
[45] https://www.adb.org/sectors/transport/key-priorities/urban-transport
[46] http://www.who.int/mediacentre/factsheets/fs292/en/
Health perspective
Air pollution, typically concentrated in urban areas, accounts for seven million premature deaths per year[47], one in eight of total global deaths. Regionally, low and middle-income countries have the largest air pollution-related burden, with South-East Asia alone accounting for 2.3 million deaths, impacting primarily vulnerable populations e.g. low-income populations living close to major transport routes.
[47] http://www.who.int/phe/health_topics/outdoorair/databases/FINAL_HAP_AAP_BoD_24March2014.pdf?ua=1
Human rights perspective
Urbanization can only be a force for positive transformation if it respects and promotes human rights[48]. Human rights challenges in cities range from access to secure housing and basic services, security issues, forced evictions, gender specific concerns, child labour, sexual exploitation, the rights of vulnerable groups like children, older people, LGBT groups or migrants. G&I Analysis and Assessments will also incorporate Human Rights Assessments of the different contexts and interventions.
[48] OHCHR, Human Rights and Urbanization
Security perspective
Although hard to quantify, future cities that focus on inclusively increasing prosperity through adopting participatory planning approaches and wider citizen engagement, are less likely to host the kinds of marginalised communities which may be open to radicalisation and pose a security threat. This is acknowledged in the UK’s National Security Strategy[49] which highlighted that one of the drivers of instability and exclusion is “rapid and unplanned urbanisation”.
[49] https://www.gov.uk/government/publications/the-national-security-strategy-a-strong-britain-in-an-age-of-uncertainty
UK as a development partner
Fit with the HMG policy and the Prosperity Fund
1. The programme objectives align with the UK’s Aid Strategy[50], NSC and NSS/SDSR[51]. The NSC highlighted that one of the drivers of global instability and exclusion is “rapid and unplanned urbanisation”, and that the UK should seek to “unlock private and public sector investment in energy, infrastructure and urban development” overseas. This programme aligns with key government policy and international commitments: Habitat III[52], SDGs 11[53], 9[54] and 5[55], Industrial Strategy Green Paper[56], the UK’s Digital Strategy[57], Industrial Strategy Challenge Fund[58], DFID’s Economic Development Strategy[59], IEUK[60], BEIS’ Local Energy programme, DfT’s Smart Cities Partnership[61],and Innovate UK’s Urban Living Partnership with seven Research Councils.
  [50] HM Treasury and DFID, UK aid: tackling global challenges in the national interest, 2015
  [51] HM Government, National Security Strategy and Strategic Defence and Security Review, 2015
  [52] UN Habitat III, The New Urban Agenda, 2016 https://habitat3.org/the-new-urban-agenda
  [53] https://sustainabledevelopment.un.org/sdg11
  [54] https://sustainabledevelopment.un.org/sdg9
  [55] https://sustainabledevelopment.un.org/sdg5
  [56] https://www.gov.uk/government/news/developing-a-modern-industrial-strategy
  [57] https://www.gov.uk/government/news/uk-digital-strategy-the-next-frontier-in-our-digital-revolution
  [58] https://www.gov.uk/government/news/first-industrial-strategy-challenge-fund-engagement-begins
  [59] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/587374/DFID-Economic-Development-Strategy-2017.pdf
  [60] Infrastructure Exports UK
  [61] http://www.smartcitiespartnership.org.uk/what-scp
2. The programme will deliver the following PF Theory of Change (ToC) intermediate outcomes: investment in infrastructure; human capital, innovation and technology; financial and economic reform, and ease of doing business.
3. This programme has significant levels of synergy with other PF programmes (see table below), amplifying the overall impact of the PF. The programme will actively manage the linkages with other programmes to ensure synergies are realised, avoid overlap or duplication, and ensure programme additionality is maintained. This will be achieved through a combination of the Strategic Programme Board (ensuring strategic linkages are identified and progressed), the Country Steering Committees (ensuring local linkages at Posts are identified and progressed), the Programme Lead liaising with their equivalents in other programmes, and design support provided by the strategy and knowledge partner and via the Prosperity Fund Learning Platform.
Programme	Link
Anti-corruption (Mexico, Colombia, Brazil, Turkey, India, China and Indonesia)	The Anti-Corruption programme will help create the right environment that the proposed future cities interventions will build upon to maximise both primary and secondary impact e.g. addressing city level corruption will facilitate international investment and trade in cities
Global Business Environment (Brazil, Nigeria, South Africa, Turkey and SE Asia)	The Global Business Environment programme will help create the right environment that the proposed future cities interventions will build upon to maximise both primary and secondary impact e.g. opening up markets for investment will help the financing of city infrastructure projects
Global Trade (Brazil, Mexico, Colombia, South Africa, Pakistan, India, Nigeria, SE Asia, Turkey and China)	The Global Trade programme will help create the right environment that the proposed future cities interventions will build upon to maximise both primary and secondary impact e.g. supporting the adoption of international standards will encourage leading practice to be followed in future cities development and facilitate international investment and trade, in newly opened up markets
Global Infrastructure (Mexico, Colombia, South Africa, Brazil and SE Asia)	The Global Infrastructure programme will build a pipeline of potential infrastructure projects and that the infrastructure programme can develop into full business cases, and the UKEF and AIIB can support scaled up finance
Global Better Health (Mexico, Brazil, South Africa, SE Asia)	The Global Better Health programme will improve the health and productivity of city workforces. By reducing congestion and pollution, and increasing access, the future cities programme will help improve health standards[62] and reduce pollution[63]
ASEAN Low Carbon Energy	The SE Asia low carbon energy programme will focus on complementary interventions covering on energy efficiency and green finance at the national level (regulatory framework, setting national standards), which can then be applied at the city level
Digital Access (South Africa, Nigeria, Indonesia, Brazil)	The Digital Access programme will improve internet access, enhancing inclusivity and employment opportunities for marginalised populations within cities
Global Skills (Mexico, Brazil, SE Asia, Nigeria and South Africa[64])	The Global Skills programme will improve professional standards which could include building standards (e.g. building information modelling - BIM[65]) that could then be applied at the city level
Brazil programme	Future cities interventions aligned to the global programme are included within the global future cities programme while Brazil unique elements are included within the Brazil country programme
[62] WHO, Hidden cities – unmasking and overcoming health inequities in urban settings, 2010
[63] Compact of Mayors - https://www.compactofmayors.org/press/co-chairs-michael-r-bloombeg-maros-sefcovic-announce-mayoral-leadership-global-covenant-mayors-climate-energy/
[64] Final countries still to be finalised
[65] http://www.bimtaskgroup.org/

1. UK High Commissions/Embassies/Consulates (Posts) are active in all of the cities this programme plans to work with and have actively driven the design of the programme and associated interventions. HMG Post staff (primarily DFID, DIT and FCO) will be essential to manage local stakeholders, ensuring the programme’s outputs result in the projected primary and secondary outcomes and impacts. There are several UK government initiatives promoting the UK’s future cities expertise, such as DIT trade missions.
2. The programme is additional to and complements DFID’s urban development programmes such as CIG and Infrastructure and Cities for Economic Development (ICED) which typically focus on lower income countries and on poverty alleviation rather than overall prosperity, but have important innovations, tools and lessons e.g. on gender and inclusion. The FCO and DFID teams will liaise closely to ensure any potential synergies are realised e.g. there are significant opportunities to link the Nigeria Infrastructure Advisory Facility (NIAF) programme on energy in Nigeria with this programme.
3. The programme can build on the knowledge and international credibility established by UK policies relating to future cities, including:
- Industrial Strategy Green Paper[66] including battery technology Faraday challenge[67]
  [66] https://www.gov.uk/government/news/developing-a-modern-industrial-strategy
  [67] https://www.gov.uk/government/news/business-secretary-to-establish-uk-as-world-leader-in-battery-technology-as-part-of-modern-industrial-strategy
- UK’s Digital Strategy[68]
  [68] https://www.gov.uk/government/news/uk-digital-strategy-the-next-frontier-in-our-digital-revolution
- Industrial Strategy Challenge Fund[69]
  [69] https://www.gov.uk/government/news/first-industrial-strategy-challenge-fund-engagement-begins
- DFID’s Economic Development Strategy[70]
  [70] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/587374/DFID-Economic-Development-Strategy-2017.pdf
- DIT’s Infrastructure Exports UK forum with the private sector
- DfT’s Smart Cities Partnership[71]
  [71] http://www.smartcitiespartnership.org.uk/what-scp
- Cabinet Office’s Community Resilience Framework[72]
  [72] https://www.gov.uk/government/publications/community-resilience-framework-for-practitioners
- Innovate UK’s Urban Living Partnership with all seven Research Councils
- UK’s Clean Growth Strategy[73]
  [73] https://www.gov.uk/government/publications/clean-growth-strategy
UK strengths
1. The growth of global cities provides significant opportunities for UK organisations; forecasts indicate that the global future cities market will be worth £328b pa by 2020[74]. There is a clear opportunity now to work with selected country national and local governments to positively influence the shape of their city plans and investments to drive inclusive and sustainable local growth and open up opportunities for international business, including the UK. The UK is well-positioned as the partner of choice for future cities development, creating mutually beneficial two-way trade opportunities.
  [74] BIS, The Smart City Market: Opportunities for the UK, 2013
2. UK organisations have a major role to play in helping to lead, plan, design and implement future cities. Core strengths lie in the three proposed themes:
- Transport – integrated transport masterplans, project design, project planning and management, financing (e.g. Public Private Partnership [PPP]), architecture, operations and technology (e.g. Geographic Information System [GIS] and smart mobility)
- Urban planning – master planning, citizen engagement, architecture, public safety, enterprise partnerships, city standards and technology (e.g. city data hubs and GIS)
- Resilience – weather forecasting, flood planning and management, project design, project planning and management, financing, architecture, operations, technology (e.g. city data hubs and GIS) and heritage conservation
1. A report by the Future Cities Catapult[75] identified over 32,000 companies in the UK providing solutions to the smart cities market. With additional UK expertise in architecture (contributing £1.7b a year to the UK economy and growing at 7.6% pa[76]) and urban design already contributing £16bn and 400,000 jobs to the UK economy – the UK has the potential and desire to deliver holistic solutions on a global scale. Research into UK organisations[77] showed that the UK has the required capabilities and appetite to assist in addressing the issues that Cities are facing.
  [75] UKTI and Future Cities Catapult (2014) How can the UK innovate for the World’s Cities?
  [76] Mayor of London’s economics team, 2017
  [77] ICF, ITP, KPMG, Prospectiva, Oliver Wyman and Vivid Economics Future Cities Scoping Reports, 2016 and 2017
2. This programme has been explicitly designed to address the local prosperity (primary benefit) barriers but in doing so will also help address the barriers to exporting and trade (secondary benefit). Indeed, the primary and secondary constraints and therefore associated benefits go hand-in-hand; by successfully addressing the constraints to cities sustainably growing, international business opportunities will naturally be created. The implementation of this enabling programme will result in a pipeline of major implementation projects.
Objective, Impact and Outcome
Based on the above cities context in middle income countries, HMG policy and the strengths of the UK future cities industry; the objective of this programme is as follows:
“To work with a select number of cities in middle income countries over a three year period to improve the way their cities are planned and managed, resulting in increased local prosperity and quality of life, including a reduction in levels of poverty and gender inequality, together with creating mutually beneficial two-way trade opportunities.”
The overall impacts of the programme are defined as:
- PRIMARY: The development of inclusive, safer, resilient and sustainable cities to support economic growth, poverty reduction and gender equality.
- SECONDARY: Opportunities and sustainable economic relationships are developed with cities in sectors where international business, including the UK has a comparative advantage, leading to a mutually beneficial two-way increase in future cities trade and investment.

The Programme outcome is: inclusive urban economic growth and increased prosperity through targeted interventions on transportation, urban planning and urban resilience in ten countries.

The programme will deliver distinct and attributable outputs. However, due to the complex nature of cities and the fact that subsequent implementation projects will often be required, the programme will contribute positively to the outcomes and impacts but there are too many other factors for direct attribution.

The Programme also aims to contribute to the UN Sustainable Development Goals and Targets (SDGs) as set out below:

Future Cities – UN 2030 Agenda for Sustainable Development Goals
SDG Goals	SDG Targets	Programme Contribution
	11.2 By 2030, provide access to safe, affordable, accessible and sustainable transport systems for all, improving road safety, notably by expanding public transport, with special attention to the needs of those in vulnerable situations, women, children, persons with disabilities and older persons. / 11.3 By 2030, enhance inclusive and sustainable urbanization and capacity for participatory, integrated and sustainable human settlement planning and management in all countries / 11.4 Strengthen efforts to protect and safeguard the world’s cultural and natural heritage / 11.5 By 2030, significantly reduce the number of deaths and the number of people affected and substantially decrease the direct economic losses relative to global gross domestic product caused by disasters, including water-related disasters, with a focus on protecting the poor and people in vulnerable situations	The Programme is looking to implement a number of projects that will either: / 1) contribute to the UN’s Goal 11 by providing access to safe, affordable, accessible and sustainable transport systems for all, with special attention to the needs of those in vulnerable situations, including women and children and people with disabilities. / 2) contribute to the UN’s Goal 11 by improving Urban planning and processes to that it leads to sustainable development in a particuipatory way including taking in the views of women and those from vulnerable groups / 3) contribute to the UN’s Goal 11 by improving the way cities plan for climate change building in resilience.
	9.1 Develop quality, reliable, sustainable and resilient infrastructure, including regional and transborder infrastructure, to support economic development and human well-being, with a focus on affordable and equitable access for all	The programme is looking to undertake projects that will result in resilient infrastructure which support economic development and human well-being, with a focus on affordable and equitable access for all.
	1.4. By 2030, ensure that all men and women, in particular the poor and the vulnerable, have equal rights to economic resources, as well as access to basic services, ownership and control over land and other forms of property, inheritance, natural resources, appropriate new technology and financial services, including microfinance.	The Programme will look to contribute to the objective of eradicating extreme poverty by 2030 by increasing productivity, and large-scale investment in city level infrastrucure (including transport services, urban planning) therefore improving quality of life and decreasing the vulnerabilities of excluded populations in urban planning aspects to ensure equal access to basic services.
	5.4 Recognize and value unpaid care and domestic work through the provision of public services, infrastructure and social protection policies and the promotion of shared responsibility within the household and the family as nationally appropriate. 5.8 Enhance the use of enabling technology, in particular information and communications technology, to promote the empowerment of women.	The Programme will look to empower women by providing better and safe transport systems and by developing skills for Industry 4.0, providing access and inclusion to the digital economy, with a particular focus on mobility.
	13.2 Integrate climate change measures into national policies, strategies and planning.	The Programme will also support targets adopted through the New Urban Agenda and COP 21, including tackling health risks related to poor air quality in cities and the impact of climate change on cities by improving resilience.

# The Appraisal Case
Introduction
1. This Appraisal Case has been prepared with reference to HM Treasury’s Green Book (A Guide to Investment Appraisal in the Public Sector) [78] and also presents the value for money appraisal of the programme.
  [78] https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent
2. It provides an overview of the range of delivery options considered for delivering the core programme objective identified in the Strategic Case; and also the options assessment undertaken in order to short list the Countries and Cities the programme would operate in, to overcome the constraints and barriers to poverty reduction and prosperity.
3. The options assessment was overseen by a cross-Government Steering Committee[79], and involved wider consultation across the UK government, extending to DFID and DIT, as well as with the UK private and third “Future Cities Sector”. Outside the UK, the design process involved consultations with multilaterals (including WHO, World Bank, IFC) and local stakeholder governmental and non-governmental organisations. Independent consultants carried out the detailed scoping of opportunities for the options assessment, while market engagement was held to test and refine the Steering Committee’s preferred options for programme structure and delivery.
  [79] See 22

Post the options assessment, UN Habitat were appointed to refine the opportunities identified by the independent consultants. The Global Future Cities Strategic Programme Board who were convened post Strategic Outline Business Case stage oversaw the final review process of the list of options.
Strategic option appraisal
In order to achieve the programme’s objectives, as set out in the strategic case, a number of strategic options were assessed by the Steering Committee. These included the following:
- Run a generic call for bids with either delivery partners or city administrations, based on the programme’s objectives
- Provide grant funding to a multilateral trust fund e.g. via UN Habitat
- Design and implement a specific programme based on applying a standard set of interventions in selected cities
- Design and implement a specific programme based on applying a flexible framework of interventions in selected cities
- Do-nothing
Each option was qualitatively assessed against the following assessment criteria:
- Primary benefits – achievement of primary (local prosperity) outputs, outcomes and impacts
- Secondary benefits – achievement of secondary (trade) outputs, outcomes and impacts
- Gender equality and poverty alleviation – achievement of inclusive growth outputs, outcomes and impacts
- Cost – financial cost to HMG
- Delivery confidence – overall confidence that the outputs, outcomes and impacts will be achieved
A summary of the assessment is set out below. This is followed by a table that outlines the advantages and disadvantages of each option (green indicates a strong assessment and therefore in theory highly appropriate for this programme).

Strategic option	Advantages	Disadvantages
Generic call for bids	Variety of interventions; innovation	Fragmented with low level of thematic or geographic focus; lack of synergies with other PF programmes
Multilateral grant funding	Strong mission-driven focus on primary benefits; inclusive growth	Lack of HMG positioning, branding and control; concern over secondary benefits not being a focus; lack of synergies with other PF programmes
Specific programme based on applying a standard set of interventions in selected cities	Standardised approach potentially minimising management overheads	A ‘one size fits all approach’ may not match local city needs; nor encourage local city ownership
Specific programme based on applying a flexible framework of interventions in selected cities	Interventions explicitly designed to address city-specific prosperity needs	Potentially complex management overhead required
Do-nothing	None	With urban population growth and the number of people living in urban slums both increasing, the do-nothing option worsens poverty

Based upon the above assessment, the Steering Committee concluded that the preferred strategic option was a ‘specific programme based on applying a flexible framework of interventions in selected cities’. The management complexity of this option can be managed through careful design of the delivery model – see the commercial case.
## Programme Design Methodology
Once the strategic approach was agreed, an assessment was undertaken to short list the Countries and Cities that the programme would operate in. This process is summarised in the diagram below.

1. Independent consultants carried out scoping studies in the long list of Countries and Cities in order to help with the short listing process. Once the Steering Committee had agreed the short list of Countries and Cities the scoping studies were used to undertake a matchmaking assessment that identified a list of 42 interventions which would help overcome the barriers to poverty reduction and prosperity and meet the programme’s objectives.
2. The final prioritised cities, as agreed by the Steering Committee, are set out below:
Country	Target Cities
Nigeria	Lagos and Ogun/Abeokuta
South Africa	Cape Town, Durban and Johannesburg
Turkey	Ankara, Bursa and Istanbul
SE Asia	Ho Chi Min City, New Clark City (formerly Clark Green City), Cebu City, Iskandar, Melaka, Bangkok, Yangon, Surabaya and Bandung
Brazil	Belo Horizonte and Recife

UN Habitat were then appointed to carry out further scoping and validation of the 42 interventions identified through the matchmaking assessment from April to October 2018. The process undertaken during Phase 1 Transition Delivery in each City was as follows:
1. Appoint Local City Specialist to work in City for period of 3 months
2. Kick off meeting with UN Habitat, Local City Specialist, UKFCO Post
3. Re-engage City Authorities on intervention and check validity:
  1. If Intervention valid, work to increase detail of scoping
  2. If Intervention no longer valid either i) Stop ii) Change and scope
4. Undertake Planning Charrette on intervention with members of City Authorities, Representatives of Civil Society, Academia, Private Sector
5. Incorporate views to scope of interventions
6. Finalise scope of Intervention and feed into i) City Context Report ii) Terms of Reference
7. Validation workshop of City Context Report and Terms of Reference with City Authorities.

1. During the Transition Delivery Phase the original list of 42 interventions that were tested have now been consolidated to 28 interventions, across the same 19 cities...
2. The City Context Reports that have been prepared set out the current status of the City and the context for why the particular intervention is required, including the barriers and constraints that the intervention is trying to overcome. It also contains a “Technical Viability Assessment” (TVA) across the themes: Capacity, Market Maturity, Financial, Legal, and Spatial. This is a review of the Cities capabilities in each area and has been rated as low, medium and high capability. The TVA is an assessment based on the Transition Delivery Partners experience and provides an indication of areas that will need to be addressed by the City Authorities and our Intervention Delivery Partners in order for the projects proposed to be a success. The TVA has also helped inform our economic analysis (see section D below).
3. The Terms of Reference sets out the detail of the technical intervention scoped by UN Habitat and agreed by the City Authority at the validation workshop. The Terms of Reference form the main technical specification for the project that will be procured for the programme (see Commercial section for our approach to appointing delivery partners for this).
Overview Interventions identified

The table below presents an overview of the interventions that have been consolidated during the Transition Delivery Phase.
Country	City	Project Description
South Africa	Cape Town	Supporting the implementation of the City's Big Data Strategy: provide technical support to the City of Cape Town to give effect to the City of Cape Town's Data Strategy through data use and application case studies related to transport, economic analysis, resilience, and human settlements.
South Africa	Johannesburg	Review the fourth industrial revolution trends and effects on urban mobility in Johannesburg: Provide technical assistance to the City's Transport Department to review the existing Strategic Integrated Transport Plan Framework (SITPF) of the city of Johannesburg.
South Africa	Johannesburg	Strategic Area Framework and Associated Implementation Tools: Provide technical assistance to the Johannesburg Planning Department for the development of a Strategic Area Planning Framework and Implementation Tools for Soweto area.
South Africa	Durban	a) Data integration, collection and analysis for informal settlement planning and management: Provide technical support to Durban's Chief Resilience Office Team to develop an integrated data system for the city. B) Enhance institutional and government coordination for supporting the alignment of stakeholder plans on Transit-Oriented Development: Technical support to the eThekwini Transport Authority in the development of a coordination tool and change management process with the focus on urban regeneration and transport corridor development.
Brazil	Recife	Data Eco-system for Urban Governance in Recife: Provide technical assistance and capacity building to: i) Develop a Municipality Data Governance Framework with the Municipality ICT Company (EMPREL) ii) Set-up an Urban Information Hub with the Strategy and Innovation Recife Agency (ARIES) iii) Prepare a Society Engagement Action Plan with the group of main stakeholders led by Porto Digital
Brazil	Belo Horizonte	Intelligent Mobility in Expresso Amazonas: Provide technical assistance to BH-TRANS (the Public Transport Agency) to develop a strategy and implementation plan for adding smart technology and analytics to the Expresso Amazonas bus corridor.
Philippines	Cebu	City Roadmap for the SDGs' Implementation and Evidence-based Planning in Cebu: Provide technical assistance and capacity building to the Office of the City Administrator of Cebu to develop a city-wide strategy, a data center roadmap, and the identification of catalytic projects for Cebu.
Philippines	New Clark City	Comprehensive Sustainability Plan for New Clark City (CSP-NCC): Provide technical assistance and capacity building to BCDA (Bases Conversion and Development Authority) to develop: i) A participatory design for NCC Central Park ii) A Sustainable Integrated Housing and Livelihood Strategy iii) A strategy for setting up a Sustainability Unit within BCDA
Myanmar	Yangon	Revitalizing Streetscapes – unlocking potential of Yangon’s city assets. Provide technical assistance to Yangon City Development Committee (YCDC) to develop city-wide regulation/policy on improving and managing streetscapes through pilot projects in downtown Yangon to be implemented in participatory and community-based manner
Vietnam	Ho Chi Minh City	Establish a Smart-Ticketing System for the public transport network, and provide technical assistance and capacity building to the Management Centre of Public Transport (MCPT).
Vietnam	Ho Chi Minh City	Developing a Digitalised Inventory of the Drainage System in Ho Chi Minh City: Provide technical assistance and capacity building for the Urban Flood Control Centre to develop a digitalised inventory of the drainage system.
Thailand	Bangkok	Data Hub Roadmap for Integrated Planning: Provide technical assistance to the Bangkok Metropolitan Administration to develop a strategy for a data Hub that enhances integrated solutions for urban development.
Thailand	Bangkok	Transit-Oriented Development (TOD) Plan for the Khlong Bang Luang area: Development of an integrated Site Plan for the Khlong Bang Luang area for the Traffic and Transportation Department, thereby enhancing the socio-economic benefits of the upgrading of transport infrastructure in the area.
Thailand	Bangkok	Decision Support System (DSS) for Flood Management: Technical assistance to the Drainage and Sewerage Department for the set-up of a DSS to improve Bangkok Metropolitan Administration's ability to identify solutions for flood adaptation and mitigation and facilitate evidence-based decision-making.
Turkey	Ankara	Increasing Quality and Accessibility of Streets in Çankaya Neighbourhoods: Provide technical assistance and capacity building to develop urban designs, implementation plans, and replicable methodologies for Çankaya District Municipality.
Turkey	Ankara	Multimodal Transport and Bicycle Strategy for Ankara: Provide technical assistance to Ankara Metropolitan Municipality for the preparation of a city-wide Bicycle Strategy and Master Plan and a pilot implementation in a prioritized neighbourhood.
Turkey	Istanbul	Training and Capacity Development Programme: Implement a capacity development programme for the Istanbul Metropolitan Municipality civil servants, and provide technical assistance to prepare plans and strategies on transport management, urban resilience, and urban transformation.
Turkey	Istanbul	Sustainable Urban Mobility Planning for Istanbul: Provide technical assistance and capacity building for developing a city-wide Sustainable Urban Mobility Plan for the Istanbul Metropolitan Municipality
Turkey	Bursa	Bursa Smart City Strategy: Provide technical assistance and capacity building to the Bursa Metropolitan Municipality to develop a city-wide Strategy for transforming Bursa into a Smart City, and preparing the implementation of a pilot project in transport management.
Turkey	Bursa	Sustainable Urban Transformation Approach for Bursa: Provide technical assistance to the Bursa Metropolitan Municipality to prepare a comprehensive urban renewal plan in a central neighbourhood in Bursa.
Nigeria	Lagos	Urban Renewal Guidelines for Lagos: Technical assistance to the Lagos State Urban and Renewal Authority (LASURA) and the Ministry of Physical Planning and Urban Development (MPPUD) to develop state-wide Urban Renewal Guidelines.
Nigeria	Lagos	Water Transport Feasibility Study: Technical assistance to the Lagos State Waterways Authority (LASWA) in the form of a Water Transport Feasibility Study for Lagos State.
Nigeria	Abeokuta	Transport Policy for the City of Abeokuta: Capacity building and technical assistance to the Ogun State Bureau of Transportation for the development of a Transport Policy for the City of Abeokuta, with potential for expansion to the state-level.
Nigeria	Abeokuta	Urban Masterplan for the City of Abeokuta: Technical assistance to Ogun State Ministry of Urban and Physical Planning (MUPP) for the development of an Urban Masterplan for the City of Abeokuta and the preparation of an urban renewal pilot scheme.
Indonesia	Surabaya	Urban Transformation Plan for Putat Jaya: Provide technical assistance to the Surabaya Planning Department to develop Urban Planning and Design Guidelines for the neighbourhood of Putat Jaya.
Indonesia	Surabaya	Earthquake Preparedness Strategy: Provide technical assistance to Surabaya Planning Department to create an Earthquake Preparedness Strategy including an implementation plan, an awareness campaign, and capacity building of departments and institutions.
Indonesia	Bandung	Development of an Integrated Public Transport system in Bandung: Provide technical assistance and capacity building to Bandung City Transport Agency to develop a city-wide Integrated Transport Plan including planning and design, legal and financial models and an implementation roadmap.
Malaysia	Melaka	Heritage Area Mobility Plan and Green Transport Corridor Feasibility Study: Provide technical assistance to the Malaysia Industry Government Group for High Technology (MIGHT) and the Melaka Green Tech Corporation in the form of the development of a Heritage Area Mobility Plan for the UNESCO heritage area in Melaka and a feasibility study of a green transport corridor connecting the city center to the strategic road network.
Malaysia	Iskandar	Iskandar Malaysia Smart Integrated Mobility Management System (IMSIMMS): Provide technical assistance to the Iskandar Regional Development Authority for the design of the IMSIMMS (management system; operational management centre and pilot project) and capacity building for using data in urban and transport planning.

Costs and benefits
Introduction
In accordance with Joint Funds Unit (JFU) guidance, the detailed assessment of costs and benefits has been undertaken on the proposed programme. The proposed programme interventions have all been designed to explicitly address the local obstacles to prosperity i.e. not all pillars apply to all cities and undertaking additional activity in a city wouldn’t necessarily lead to greater impact. Many of the cities are ‘lead cities’ in their countries, resulting in other cities following them so there isn’t necessarily a rationale for increasing the number of cities in any one country. A modular/thematic approach means that dynamic programming can be employed to scale up or down as appropriate.
Summary of the Primary and Secondary Benefits of the Future Cities Programme
The primary benefits of the programme are those accrued by the Cities and Citizens as a result of interventions to address transport, urban planning and resilience challenges. The secondary benefits are estimated as the increase in UK exports to the programme countries as a result of the interventions. The specific benefits estimated in the analysis for each programme pillar are:
Transport. The programme’s transport interventions include the development of city transport strategies plans, feasibility studies for potential transport infrastructure projects, capacity building for city transport institutions and the use of smart technologies and data to improve transport management. For the analysis, it is assumed that these interventions lead on to subsequent transport infrastructure projects which result in primary and secondary benefits.

The main primary benefit estimated for this pillar is the value of travel time saved by citizens through reduced traffic congestion as a result of improved transport infrastructure. Reduced vehicle operational costs from substituting private transport for public transport have also been estimated, though these contribute a small share of total benefits.

Secondary benefits are estimated as an uplift in UK professional services and transport goods exports to directly support the “follow on” projects. A further increase in exports arises as a result of increased programme city incomes due to reduced travel times i.e. it is assumed that some of the saved time is spent productively.

Urban Planning. The programme’s urban planning interventions focus on the development of urban plans, the formulation of building and development guidelines and the use of data and training to enhance the capabilities of city planning authorities.

The primary benefits of the interventions are assumed to arise as a result of cities’ subsequent expansion following a compact spatial layout rather than following an “urban sprawl” pathway. Two different methods are used to estimate benefits: the first uses a similar methodology to the transport appraisal in order to estimate (only) the time savings from reduced travel distances under a compact city layout. The second method draws upon modelling projecting the effects of six South African cities following a compact versus urban sprawl layout in the future. This second method looks at changes in a broader set of costs than just transport e.g. infrastructure and housing costs.

The direct secondary benefits are estimated as an uplift in UK exports of architectural, engineering and technical services to the programme cities to support a more compact spatial pathway. Indirect benefits are again realised from improved city incomes due to travel time saved.

Resilience. There are four resilience interventions in the programme that focus on capacity building to mitigate the impact of earthquakes (Surabaya), mitigate the impact of flooding (Bangkok, Ho Chi Minh City) and support heritage conservation (Yangon). The primary benefits are estimated respectively as reduced economic loss due to injuries from earthquakes, a reduction in flood damages to urban infrastructure and increased tourist revenues.

Secondary benefits from the resilience interventions arise as a result of improved city incomes through avoided economic damages and increased tourist revenue. There may also be direct export opportunities for UK firms to supply flood early warning system technology and architectural services to support heritage conservation.
1. For each intervention, the primary benefits have been adjusted to account for a likelihood of success and also by an “attribution factor” to estimate the proportion of total benefits attributable to the intervention if, for example, other resource costs not covered by the Prosperity Fund’s funding are required to realise the economic benefits. Secondary benefits have also been adjusted by the respective success factor in each case.
2. The benefits have been estimated over two different appraisal periods: a ten-year period over 2018-2027 in line with other Prosperity Fund economic appraisal work and also a twenty-year appraisal period over 2018-2037. The latter is the principal appraisal period length used for the Value for Money assessment as it is more appropriately aligned with the timeframe over which benefits are likely to be realised for the interventions; the returns to transport and planning projects in particular are unlikely to be realised within a ten year timeframe.
3. The programme’s strategic delivery partner, UN Habitat, have estimated the costs of each of the interventions building upon the evidence developed at the Strategic Outline Business Case stage. In addition, the programme’s management costs have been estimated and apportioned to each intervention in proportion to intervention costs. Benefits and costs are expressed in 2017 prices and have been discounted to financial year 2018/19; primary benefits have been discounted at 10 per cent per annum and secondary benefits and intervention costs discounted at 3.5 per cent per annum. Table 1 summarises the estimated Future Cities programme costs and benefits.
Table 1 – Summary of Future Cities Programme Costs and Benefits. 2017 £m, discounted to 2018/19. Appraisal Period 2018/19 – 2037/38
Pillar	Costs	Primary Benefits	Primary BCR	Secondary Benefits	Secondary BCR
Transport	32	34	1.1 : 1	11	0.40 : 1
Planning	32	47	1.5 : 1	12	0.40 : 1
Resilience	9	26	2.8 : 1	0.3	0.03 : 1
Total	73	107	1.5 : 1	23	0.30 : 1

1. The primary benefits assessments indicate the three intervention pillars offer value for money at the aggregate level with benefit cost-ratios ranging between 1.1 : 1 and 2.8 : 1. Further, the economic appraisal excludes various benefits that have not been monetised in the analysis e.g. the transport interventions will potentially deliver improvements through improved air quality and reduced carbon emissions from lower traffic congestion; the planning interventions could improve access to jobs for low income workers through smarter spatial layout and integration of residential and business districts.
2. The secondary benefits assessment indicates the estimated UK export benefits are around £25m for the programme. The benefits are restricted by the fact that the UK has a low share of goods and services markets in the programme countries (1.0% and 0.5% respectively on average) which limits the uplift in exports from increased city incomes (indirect benefits) and the potential UK share of direct follow on export opportunities e.g. transport projects. A possible upside however, which has not been factored in to the analysis, is that the interventions could increase the UK’s market share/likelihood of winning contracts through building relationships between the UK and programme city supply chain purchasers.
3. There could also be wider secondary impacts, including opportunities for UK investors to invest in the partner countries (e.g. new transport infrastructure projects) and opportunities for the UK to benefit from reverse innovation utilising niche areas of local expertise e.g. potential for new smart city technologies to be ‘road-tested’ in the target cities and the lessons applied in the UK.
4. The results of the cost-benefit analysis vary by pillar, country, city and intervention; not all interventions are break-even on the primary benefit-cost ratio for example.

Wider benefits
1. This section sets out significant wider benefits covering poverty, gender equality, environmental and health. Although classified here as wider benefits, these are the themes that constrain the sustainable growth of cities and have therefore been integral to programme design. During the more detailed design of the programme in phase 1, an implementation framework will be developed to ensure these themes are central to all programme activity. This will include detailed output and outcome measures, delivery partner performance measures and programme management arrangements (e.g. risk monitoring). In addition, this programme will help support the more effective delivery of city services by governments as a result of improved urban planning (citizen engagement, spatial planning, data analytics etc.), e.g. refuse, police, fire, which will facilitate sustainable economic growth.
2. This programme has been designed to address absolute and relative poverty. Urban elites often capture the benefits of urbanisation with the poor continuing to live and work precariously, especially women. The programme will directly alleviate poverty by improving access to: employment opportunities via improved transport links to economic centres and creation of polynucleated cities; basic services (housing, health etc.) via improved spatial planning; and resilience (poor and unplanned peripheral developments are typically most impacted) via improved spatial planning.
3. This programme has also been designed to address gender inequality and increase women’s economic empowerment. The relevant programme activities, outputs and outcomes are set up in the table over the page:

Programme activity	Output	Outcome
Improve transport links and access to basic services [80] (e.g. access to affordable electricity as a result of improved spatial planning reduces the time spent by women on household tasks by 70%[81])	Reduced time spent on domestic tasks (female dominated[82])	Increased educational and income-generating activities
Improve the transport system (including routes, modes, accessibility, affordability and making it safer for women through improved lighting, security, women only carriages and zero alcohol)	Enhanced women’s mobility and drives women’s economic participation[83]	Higher paying jobs for women and new opportunities for female business expansion[84]
Improved spatial planning	Less car-centric urban environments which is typically a male-orientated transport mode (66% of drivers in Brazil are male[85])	Increased access to employment opportunities for women
Inclusive spatial development strategies/urban renewal instruments	Improved basic services that enable the growth of home-based enterprises (female dominated[86])	New opportunities for female business expansion
Improved urban service planning	Encouraging greater participation in future cities service provision such as transportation which is typically male dominated (the female participation in the Indonesian transport sectors is between 5-7%[87])	Increased access to employment opportunities for women
Improved spatial planning focused on increasing safety e.g. street lighting	Reduction in crime and perception of crime, especially by women (86% of women suffered harassment in both Brazilian and Thai cities[88])	Increased access to employment opportunities and quality of life (e.g. good street lighting can have a range of socio-economic benefits: people feel safe to go out at night which helps to boost economic/ social activity after sunset, such as Street markets, especially for women)
[80] Brighton: Institute of Development Studies, Gendered Patterns of Time Use in Tanzania: Public Investment in Infrastructure Can Help, 2008
[81] Asian Development Bank, Balancing the Burden? Desk Review of Women’s Time Poverty and Infrastructure in Asia and the Pacific, 2015
[82] International Institute for Environment and Development, and UNFPA “Urbanization, gender and urban poverty: paid work and unpaid care work in the cities” 2012 http://pubs.iied.org/10614IIED.html
[83] Day, McKenna and Bowlus, The Economic Costs of Violence Against Women: An Evaluation of the Literature, 2005
[84] UN, “Infrastructure: a Game-Changer for Women’s Economic Empowerment”, 2016
[85] Sistema MPA http://www.sistemampa.com.br/noticias/mulher-no-volante-perigo-contante-as-estatisticas-mostram-que-nao/
[86] UN, “Infrastructure: a Game-Changer for Women’s Economic Empowerment”, 2016
[87] Spoken at EU-Indonesia Roundtable: Sustainable Innovative Transport Solution, 29th September 2017

1. The programme also seeks to reduce gender-based violence through improved spatial planning, as research suggests physical design and management of built environment play a significant role in diminishing opportunities for crime and violence [89] (especially lighting, landscape maintenance and physical planning for public activities).
  [89] Enhancing Urban Safety and Security: Crime and Violence, UN Habitat, 2007
2. Gender neutral approaches to urban planning often lead to unequal gender outcomes which systematically disadvantage poor people and therefore, women. Adopting a gender sensitive approach is key to address the systemic constraints that contribute to persistent gaps in women’s economic opportunities. This includes reducing and redistributing unpaid household work and care as well as building assets for women. Research also suggests gender sensitive approach to cities and urban development leads to more efficient and inclusive economic growth, as stated by the UN Secretary General’s High-Level Panel on Women’s Economic Empowerment: “Empowering women in the economy and closing gender gaps at work are central to the 2030 Agenda for Sustainable Development”[90]. The HLP report notes that considering the different user needs of men and women in areas such as transport planning (e.g. routes and schedules), water and sanitation in public places (important for street vendors and other informal employment dominated by women) and housing, can contribute to improved economic and social outcomes for women[91].
  [90] Leave No One Behind, A call to action for gender Equality and Women’s Economic Empowerment, Report of the UN Secretary General’s High-Level Panel on Women’s Economic Empowerment, 2016
  [91] Mohun, R., and Biswas, S. (2016) Infrastructure: A game-changer for women’s economic empowerment. A background paper for the UN Secretary-General’s High-Level Panel on women’s economic empowerment. Available at: http://womenseconomicempowerment.org/reports/
3. The programme will be compliant with the International Development (Gender Equality) Act (2014) as a result of clear regard to reducing gender inequality through the design of the programme and its interventions. Outcome and impact measures will include gender analysis, both qualitative and quantitative. Prior to intervention implementation, a full gender equality impact assessment will take place. In addition, the technical assistance element of the programme will include citizen-centric participatory approaches to planning, ensuring gender perspectives are taken into account in urban design[92] e.g. women entrepreneurs, safer transport etc. Also, there will be a requirement on delivery partners to consider gender in their delivery of the programmes and report on it. MREL will be gender and age disaggregated wherever possible.
  [92] http://www.sddirect.org.uk/media/1332/icedinfrastructurefull-paper-20161130173941.pdf
4. There are also significant environmental benefits. Cities are responsible for 80% of global greenhouse gas (GHG) emissions[93] and half the global urban population is exposed to air pollution levels at least 2.5 times WHO standards[94]. This programme will reduce congestion through improved transportation planning, reduce pollution levels through more efficient transport systems; reduce the risk of urban sprawl (and associated reduction in natural habitat and green space); and help create a circular economy (where waste is minimised and recycled) through improved urban planning. In addition, failure to incorporate low-carbon design and construction into infrastructure planning and delivery risks high-carbon lock-in for decades. The programme will work with the JFU and the MREL contractor to investigate how GHG reductions can be best tracked.
  [93] New Climate Economy, http://2014.newclimateeconomy.report/cities/
  [94] UN (2016) Progress towards the sustainable development goals
5. There are also significant health benefits. Air pollution, typically concentrated in urban areas, accounts for seven million premature deaths per year[95] one in eight of total global deaths. Regionally, low- and middle-income countries have the largest air pollution-related burden, with South-East Asia alone accounting for 2.3 million deaths, impacting primarily vulnerable populations e.g. low-income populations living close to major transport routes. Within Asian cities around 80% of air pollution is produced by road transport[96]. This programme will help address this issue through the interventions in transport and urban planning, reducing the number of vehicles (through improved public transport), their time on the road (through improved road transport planning) and their emissions (increasing average speeds significantly decreases air pollution[97]). In addition, there are wider health benefits, for example, integrated multimodal transport interventions reduce exposure to road safety risks, increase physical activity levels and improve access to health facilities.
  [95] http://www.who.int/phe/health_topics/outdoorair/databases/FINAL_HAP_AAP_BoD_24March2014.pdf?ua=1
  [96] https://www.adb.org/sectors/transport/key-priorities/urban-transport
  [97] https://www.ncbi.nlm.nih.gov/pmc/articles/PMC4243514/
6. Furthermore, establishing stronger bilateral relationships will help create the right environment for positive discussions on future Free Trade Agreements (FTAs) that will benefit both the UK and the partner countries.
7. Through not acting, the negative impact of poorly planned city development on prosperity (including externalities such as increased levels of pollution) will only get worse as city populations continue to increase.
Sustainability
1. The interventions have been selected on the basis of strong alignment with partner country policies and national priorities e.g. stakeholders in Lagos have confirmed their interest in learning from the UK regarding multi-disciplinary spatial expansion policy and strategy. Phase 1 activity will include developing local ‘collations of the willing’ that will build momentum. Combined with the proposed capacity building, this will help to mitigate the risk that plans developed by this programme are not implemented. Once local prosperity barriers have been overcome as a result of the programme, the primary benefits should be sustained without further significant HMG involvement e.g. capacity building will allow city and metropolitan governments to subsequently update their future strategies and plans without further HMG funding. Political economy issues can arise with urban development, involving delicate power relations between local and national government and communities. These will be fully considered during the delivery phase and continually updated during implementation. In addition, by working with national governments, there will be opportunities for the approaches to be rolled-out to other cities.
2. For sustained secondary benefits, DIT centrally has committed to follow up the UK business opportunities created. Discussions are taking place at the PF level to plan appropriately for this. Over 150 UK organisations have been consulted (including professional institutions representing thousands of members e.g. RIBA, RITP and techUK) and expressed their desire to enter these markets or increase their market share.
Preferred programme
The conclusion of the economic appraisal, based on an assessment of efficiency, effectiveness and equity (consistent with the programme’s theory of change and log frame), is a recommended future cities programme which focuses on transformation interventions:
- In 19 targeted cities
- Covering transport, urban planning and resilience themes
1. The total discounted cost of the programme is £73m (excluding contingency but including programme management costs).
2. The total discounted benefits of the programme are £107m in primary benefits and £23m in secondary benefits. This means a primary benefit-cost ratio (discounted benefits divided by discounted costs) of 1.5 : 1 and a secondary benefit cost-ratio of 0.3 : 1 for the overall programme.
# The Commercial Case

This section of the business case considers the commercial case for the programme and how its objectives will be delivered.
Required Services
The approach to delivering the programme was informed by the original cross-Government Steering Committee, by Phase 1 design work and by market testing. Programme design and implementation was split into two phases as follows:
Phase 1 Transition Delivery (12 months): A multilateral/NGO delivery partner is commissioned based on their strength of existing local relationships, expertise and independence, to test the identified interventions and gain buy-in from the recipient city Government for the full Phase 2 delivery of the programme. An MOU was used to agree scope and terms of the project (see section B Phase 1 Transition Delivery below).

Phase 2 Implementation (24-36 months):
1. A multilateral/NGO organisation is commissioned to be the programme’s strategy and knowledge partner based on their high level of expertise and independence using an MOU (see Procurement Route section below for more detail).
2. A private sector organisation is commissioned to be the programme’s programme management partner based on their high level of programme management expertise using the CCS Framework (see Procurement Route section below for more detail).
3. Private sector organisations are commissioned to be the programme’s intervention delivery partners based on their high level of global delivery expertise using the Prosperity Fund Programme Framework Future Cities Lot (see Procurement Route section below for more detail).

Phase 1 Transition Delivery

Phase 1 of the programme commenced in April 2018, with UN Habitat as the transition delivery phase partner. An MOU was agreed with UN Habitat and two partners the International Growth Centre (IGC) and UK Built Environment Advisory Group (UKBEAG). It has involved deploying a sector specialist in each of the 19 Cities in order to:
Review and develop further the provisional set of interventions identified to overcome a barrier in each City under the pillars of Urban Planning, Transportation and Resilience.
- Run stakeholder workshops, including members of civil society, to ensure demand side issues inform and shape proposed interventions
- Confirm strategic fit of interventions in the City and, where partners prioritise other interventions within the pillars of the programme, assessing the impact and feasibility of alternative options
- Ensure the Interventions contribute to poverty reduction and gender equality, and that an inclusive approach is embedded among them that leads to measurable impacts in these areas
- Seek buy-in for and validation of the interventions from the City Authority for the Phase 2 of the programme.
- Work to build a network of Cities for learning, knowledge transfer and dialog that can continue through the Phase 2 of the programme.

The outputs were transferred into Statements of Requirements for the programme, and were used as the basis of procurements for Phase 2.

Phase 2 Implementation
Due to the size and complexity of the programme, the cross-Government Steering Committee originally considered a number of delivery options for the Phase 2 intervention delivery. These were carefully considered in Steering Committee workshops and meetings, informed by extensive market engagement with all sectors (see ‘market engagement’ section below). The assessment criteria used to assess the above options included:
- Gain local buy-in
- Drive integration at the city level
- Enable primary benefits including gender equality and women’s economic empowerment
- Enable secondary benefits
- Deliver innovation and additional benefits
- Deliver sustainable benefits (including climate smart and resilient) over the long-term
- HMG effectively and efficiently manages suppliers
- Affordability / cost
- HMG control over programme direction and risk
- Flexibility to respond to changes in context
- Realise synergies with other PF programmes
The options considered are as follows:
Option	Strengths	Weaknesses	Conclusion
1. HMG contracts with a single intervention delivery partner	Facilitates programme wide learning / Single procurement / One delivery partner to manage / Delivery partner manages integration across pillars / Relatively easy to commercially manage dynamic programming	Delivering in all countries may constrain number of bidders / Financial cost of supplier margin on margin / Potentially limits ability to access niche expertise / Potentially low levels of innovation / Likely to be a complex supply chain	Although provides the easiest supplier interface for HMG, likely to provide poor VfM as constrains bidders and involves margin-on-margin (both the prime contractor and their sub-contractor include profit/margin for delivery)
2 HMG contracts with 3/5 intervention delivery partners each covering a pillar/theme	Facilitates learning across cities addressing similar challenges / Reactive to evolving pillar-based leading practice / Small number of procurements / Access to pillar/theme domain experts	Risk constrains an integrated view of a city / Complex model cutting across countries / HMG will need to manage links across pillars / Potentially hard to commercially manage dynamic programming across pillars	Appealing as matches the architecture of the overall programme. Major concern over integration at the city level
3. HMG contracts with 5 intervention delivery partners covering Country/ Regions (SE Asia, Turkey, Nigeria, South Africa and Brazil)	Natural match to national government and Post remits / Enables synergies across cities within a country / Reactive to the needs and emerging opportunities of individual cities / Access to country domain experts / Encourages replication in follower cities	Risk constrains learning and linkages across countries / Potentially hard to commercially manage dynamic programming across countries / HMG will need to manage links across countries	Although potentially harder for HMG to manage due to the large number of contracts, major advantage in terms of integration at the city level, dynamic programming and potential secondary benefits. The learning across countries risk can be mitigated through the activity of the strategy and learning partner and Posts proactively ensuring learning is shared.
4. HMG contracts with Intervention delivery partner per intervention(multi-country) delivery partners	Enables buy-in at city level, natural unit of analysis / Enables learning and linkages across similar cities / Reactive to the needs and emerging opportunities of individual cities / Access to city domain experts	Large number of procurements and contracts / Complex model cutting across countries / Risk lose country buy-in at national level / Potentially hard to commercially manage dynamic programming across different networks of cities / HMG will need to manage links across networks of cities	Appealing as adopts a city perspective, but prohibitively complex to manage and deliver in practice

1. Based on the above assessment, the Steering Committee recommended that option 3 (country level delivery partners) for the intervention delivery service. Due to the economic synergies and typical delivery partner footprints within SE Asia, it is recommended that a single intervention delivery partner is commissioned for SE Asia. This is based on an overall assessment of VfM, driven by the strong fit with national and city agendas (effectiveness), combined with the maximum degree of competition (efficiency). This was also supported by a number of organisations during market engagement.
2. The model of Country by Country intervention delivery model (with SE Asia delivered as a region) was tested again with the Prosperity Fund Framework: Future Cities Lot during the transition delivery phase. Overall this approach was supported (see Market Engagement Section below).
3. It was also decided that a Strategic and programme management partner would be required to help manage and govern the overall programme. The design therefore makes provision for these with the bulk of the technical work undertaken by the delivery partners but with the Strategic partner supporting the FCO in overseeing the outputs (see paragraph 93 below) and the programme management partner providing operational support.
Market engagement
Extensive market engagement was undertaken in the design phase to assess the capability, capacity and interest of the market to deliver the Programme. This included:
- One-to-one meetings with over 70 potential delivery partners.
- Structured supplier questionnaire issued with 18 returns.
- Major half day soft market testing event with 44 potential delivery partners in attendance.
- Strategy and training phase workshop with 9 multilaterals/IFIs/NGOs in attendance.
- “Request for Information” sent to Prosperity Fund Framework Suppliers to comment on the proposed programme structure with 22 returns.
The outputs from the above market engagement informed the recommended programme design and delivery model. It is clear from the exercise that there is market capability, capacity and interest in delivering the Programme. The key findings are as follows:
- Organisations have extensive and relevant experience of undertaking similar urban work (across all themes) in the chosen middle-income countries, including trade facilitation
- Capability and capacity exists in both the private and multilateral/IFI/NGO markets
- A limited number of companies have a presence in all the target cities and this has informed our bundling of services approach (i.e. by county)
- Concerns raised about some of the countries in relation to corruption and security. However, this was not uniform and organisations stated that they would need to undertake a risk assessment before commencing any work
- Election cycles could impact delivery and this risk would need to be monitored closely
- The majority of global organisations stated that they would plan to use niche and local partners as part of their supply chain
- Local organisations in many cities have expressed an interest in supporting delivery of the programme
In January 2018 the Prosperity Fund Framework was procured. The Future Cities Lot has 22 suppliers who have since been engaged on the programme design. A “Request for Information” was issued in September 2018 on the programme design. In general it was found that:
- More than three quarters of the responses welcomed a country-by-country intervention delivery model approach - given the complexity of each country and the need to engage with Central Governments and stakeholders in each Country as well as local governments.
- 84% of the responses preferred a holistic regional route for the South-East Asia countries; this approach was supported by the reduction of administrative costs, the efficiency in the operational management of the contract, and the boost of economies of scales.
- Most organisations who participated in this survey expressed an interest in the ten countries where the programme is planning interventions, with eight of them having a very strong commercial and operational presence and supply chain in place in each of the countries proposed.
Procurement route and evaluation approach
1. For the Phase 2 Strategy and Knowledge Management Partners we are negotiating a further MOU with UN Habitat. We have decided not to negotiate this role with other NGOs as UN Habitat’s knowledge of the Programme and relationships they have built up with UKFCO Posts and City Authorities would be lost if another took over the Strategic Partner role at this point and would not offer value for money. The MOU will be reviewed by Commercial, Finance and FCO Legal and approved by the Strategic Board before signing.
2. UN Habitat have shown through the Phase 1 strategic development phase that they have the required expertise and independence to carry this role out. As Strategic and Knowledge Management Partner they have designed a Strategic and Knowledge management plan which:
  1. Ensures the interventions that are being delivered at the City level remain aligned with Future City Programme and Prosperity Fund Portfolio Objectives, align to UK aid strategy including poverty and gender equity, and also to local and national strategies for UK and recipient.
  2. Ensures the Programme is an example of best practice including for Gender and Inclusion practices in Urban, transportation and resilience planning and consultation.
  3. Utilises UN Habitat’s reputation as urban planning experts in order to access central Governments, where this is required to ensure successful delivery or implementation of an intervention.
  4. Champions the Global Future Cities Prosperity Fund Programme to outside organisations and ensure synergies with other similar programmes are realized in order to amplify value for money.
  5. Maps the interventions against the UN Sustainable Development Goals so that City Authorities and UK Government can report against progress.
  6. Ensures learning from across the Cities is captured and shared with delivery partners and City Authorities in an appropriate way including bringing them together on a yearly basis to share insights and increase dialog with each other.
  7. Plans and implements a programme of capacity building workshops and events for the City Authorities in order to ensure they have the right skills to implement the interventions and ensure sustainability of the work.
  8. Provides monthly view of Programme to feed into FCO Reporting and Governance of programme, including assessment of risks from intervention delivery partners, advice on change requests received and dynamic programming that may need to be undertaken to either decrease or increase overall size of programme.
3. The Phase 2 Programme Management Partner which falls under the professional services/consultancy category under the Cabinet Office Controls (V.5.0) will be procured from the appropriate CCS Framework (i.e. MCF2), and as set out in the Controls, approval to procure and award such a contract will be sought in accordance with the process. The reason for procuring this requirement under a different route to the Intervention Delivery Partner is due to most suppliers on the PF Framework indicated they would not be interested in bidding for the role as it would mean they could not bid to become the intervention delivery partner. It also opens the opportunity up to organisations who have specific PPM expertise. The contract will be awarded to the organisation offering the ‘Most Economically Advantageous Tender’ which will be identified by assessing the quality of bidders’ proposals and their pricing proposals. This will be procured after the delivery partners, to avoid conflict of interest and may be procured as separate services e.g. PPM set up, portfolio management.
4. The Phase 2 Intervention delivery partners were procured through the PF Framework: Future Cities Lot. The contract was awarded to the organisations offering the ‘Most Economically Advantageous Tender’, which was identified by assessing the quality of bidders’ proposals and their pricing proposals. A range of weighted quality criteria, appropriate to each service element was developed – including gender equality, environmental and inclusion compliance and used to evaluate suppliers’ proposals.
5. The cross Government Strategic Programme Board (including Posts) agreed the final list of criteria and weightings, and evaluated supplier responses. The Strategic Programme Board will also be responsible for ensuring that the terms of reference and other contractual documentation properly reflect HMG’s requirements. All final decisions will be taken by the SRO.

Accessing expertise
This was a complex procurement and the programme team accessed expertise in the following areas:
- Commercial – FCO Commercial Procurement Group (CPG)
- Procurement – FCO Commercial Procurement Group (CPG), with Posts facilitating local supply chains
- Legal – FCO Legal
- Financial – FCO Finance and Joint Funds Unit (JFU)
- Communications – FCO Communications and Joint Funds Unit (JFU)
- Economic – FCO Economics Team
- Primary benefits – UN Habitat, DFID urban team and cross-Government international urban development expert community of practice
- Secondary benefits – DIT infrastructure and technology teams and cross-Government international urban development expert community of practice
- Gender and inclusion – Prosperity Fund and JFU Social Development Advisor and FCO Gender Equality Unit and WoW Helpdesk (Work Opportunities for Women).
- Urbanisation – UN Habitat, DFID, DIT and FCO urban experts and cross-Government international urban development expert community of practice
The procurement exercise ensured that delivery partners have the requisite social development expertise and demonstrated experience in design and delivery of gender and inclusion-sensitive interventions, in order to ensure Gender Equality Act compliance and support women’s economic empowerment and poverty reduction.
Potential for risk transfer
Contracts will follow the general principle of transferring risk to the party best able to manage them. The following table outlines the proposed allocation of risk in a number of key areas. The spread of risk allocation will be similar for all contracts, albeit not all categories will be relevant to all contracts.
Risk Category	Party	Mitigation measure
Design of interventions (risk that interventions are poorly designed and do not enable efficient and targeted delivery of expected impact)	Strategic Partner and Intervention Delivery Partner	Terms of Reference define outcomes/outputs to allow suppliers to indicate how they would most efficiently deliver the impact. Terms of Reference are be non-prescriptive in terms of activities
Gender equality compliance (risk that interventions are not designed to be compliant with the Gender Equality Act)	Strategic Partner and Intervention Delivery Partner	Terms of Reference include GEA components to allow suppliers to indicate how they would most efficiently comply.
Inclusion compliance (risk that interventions are not designed to limit risks of unequal impact	Strategic Partner and Intervention Delivery Partner	Terms of Reference include inclusion requirements to allow suppliers to indicate how they would most efficiently achieve inclusive impact.
Mobilisation	Shared (all)	The FCO is responsible for mobilisation of budgetary resources whilst the supplier will hold the risk in terms of beginning activity as per the timelines indicated in the Terms of Reference and their tenders
Delivery of interventions and outputs	Intervention Delivery Partner	Intervention Delivery Partners will be accountable for delivery of the outputs of the programme, as per contractual arrangements, including gender equality and inclusion
Achievement of impacts	FCO	Due to the complex and long-term nature of the programme’s impacts, often impacted by factors and stakeholders outside the control of suppliers, the FCO is best positioned to own this risk. However, the Terms of Reference for suppliers specify how interventions align with the impacts and the programme’s theory of change
Scoping change	Shared	All parties will work in partnership to ensure the scope of programme activity remains in line with policy priorities of HMG. Dynamic programme will be employed where appropriate. Any scoping change with a commercial implication will require the approval of all parties

Managing performance and value for money
General approach
Managing performance and value for money will be assessed against the following general principles:
- Economy (optimising costs and spending)
- Efficiency (ensuring thorough and efficient delivery of each intervention)
- Effectiveness (maximising impact for each intervention)
- Equity (ensuring equal and inclusive output for each intervention)
Payment approach
1. For the Strategic and Knowledge Management Partner and also the PPM partner, a mix of monthly invoicing and milestone based KPIs will likely be the most appropriate form of payment.
2. For the Intervention Delivery Partner, payments will be based on milestones and KPIs such as deliverables, timeliness etc.
3. Each delivery partner will produce a monthly report setting out progress against plans, KPIs, finances, issues, risks, benefits, communications, scope and lessons. This will include delivery on Gender Equality Act compliance and inclusion components. Monthly performance meetings will take place with each delivery partner where these items will be discussed as required. This will feed into the formal governance arrangements (see management case). This includes the requirement of each delivery partner to produce a formal annual review document.
Type of contract
1. An MOU is being used for the Partnership with UN Habitat as the Phase 2 Strategic and Knowledge Management Partner. As a multilateral they do not enter into commercial contracts with Governments. The MOU includes scope of work, cost, deliverables, and timeline. The MOU was approved by the FCO Legal, Commercial, Portfolio Management Office (PMO) and the SRO.
2. For the PPM partner a commercial contract will be issued as per the Crown Commercial Service (CCS) Framework from which they are selected, with the FCO as the contracting authority. The commercial agreements, will utilise the terms and conditions set-out in the CCS Framework. With supplementary terms and conditions to be included as appropriate and agreed with the FCO commercial team.
For the Intervention Delivery Partners commercial contracts will be issued as per the Prosperity Fund Framework with the FCO being the contracting authority. The commercial agreements, will utilise the terms and conditions set-out in the PF Framework (See section S – Terms and Conditions below). Contract length
1. The MOU with the Strategy and Knowledge Management Partners is expected to start 1st July 2019 and run to 31st March 2021, with the option to extend for one year to 2022.
2. The PPM and Intervention Partner Contracts are expected to start when the in August 2019 and run to 31st March 2021 with the option to extend for one year until 2022.
Personnel implications (including TUPE)
As this is a new requirement, it is anticipated that the TUPE – Transfer of Undertakings (Protection of Employment) Regulations 1981 – will not apply to this programme as outlined above.
FRS5 accountancy treatment
It is not envisaged that there will be any assets underpinning the delivery of services.
Risks
The headlines commercial risks and mitigations are set out below.
Risk	Mitigation
Fraud or misuse of funds by delivery partners	Comprehensive due diligence of delivery partners before appointment. Use of pre-checked suppliers from the PF framework. Annual reviews with all delivery partners including financial auditing by a third party. No advance payments.
Delivery partner organisational failure (e.g. bankruptcy) or personnel failure (e.g. safeguarding)	Comprehensive and enhanced due diligence of delivery partners before appointment, including on safeguarding measures. Milestone payments and payment in arrears limiting liability. A variety of delivery partners reduces the impact of this risk and potentially enables other partners to scale up
Lack of competition results in poor value for money	Utilise the PF framework for the majority of commissioned delivery partners. Also consider using multilaterals or NGOs where the private sector is not deemed to be the most appropriate delivery partner.
PF Framework supplier are at capacity on other Programmes or return low quality proposals	The programme team has actively engaged suppliers and most have Future Cities specific teams who bid for the work. We worked with FCO Commercial to ensure that the Future Cities ITTs were launched as per the pipeline that Framework suppliers were aware of. We ran pre-procurement events and shared outputs from Transition Delivery Phase so that suppliers were aware of project details.

Summary efficiency, effectiveness, economy and equity
In terms of overall efficiency, effectiveness, economy and equity; the proposed ‘mixed economy’ delivery partner model and commissioning approach is assessed as providing overall high value for money, as set out in the table below.
VfM factor	High/Medium/Low assessment	Rationale
Efficiency	High	As a result of specifying specific interventions and predominately running competitions via the PF Framework with strong HMG control
Effectiveness	Medium/High	As a result of appointing independent expert partners with strong knowledge of both primary and secondary benefit agendas, and including annual reviews and dynamic programming
Economy	Medium/High	As a result of predominately running competitions via the PF Framework with maximum day rates and breaking the programme into service and geographic components to encourage maximum competition and not limit the number of potential delivery partners
Equity	High	As a result of specifying specific interventions designed to address high levels of poverty, inequality and exclusion and marginalisation in the target cities and to support an inclusive approach to interventions

The Statement of Requirements
1. The scope of work to be undertaken in each of the 5 programme contracts was defined in a consolidated Statement of Requirements (SORs) supported by Terms of References and a programme level logframe developed during Phase 1 of the programme. These provided a clear breakdown of the required programme outputs, as developed in partnership with in-country stakeholders, and indicative activities. Suppliers were invited to build upon and add value to the indicative activities. Service level KPIs were also set out in this document.
2. The SoRs requested that bidders for the five procurements set out how they would mobilise and allocate resources to deliver the Set Up, Inception, Implementation and Closure phases of the programme. The Inception phase will confirm the package of work that will be delivered during the implementation phase. Key outputs of the inception phase include:
- A detailed, costed annual outputs-based work plan for the first 12 months after the Inception Phase, including an agreed list of early activities/outputs to be delivered, agreed with the FCO to ensure it is realistic and offers good value for money;
- Outline output-based work plans for subsequent years, these will be negotiated annually with the FCO to ensure they are realistic and offer good value for money;
- Revised/validated Logical framework, including baseline data;
- A Monitoring and Evaluation Plan (to demonstrate with quantitative and qualitative evidence progress against delivery of activities and outputs and their contribution to achieving the programme’s outcomes and impact);
- Delivery of a high quality inception report.
Procurement Process
1. Five procurements (for Brazil, Nigeria, South Africa, Turkey and South East Asia (comprising six countries)) were launched in separate ITT documents published on 27 February 2019 using the PF Framework. The PF Framework Agreement - designed specifically for the Prosperity Fund Programme - awarded 22 suppliers the right to bid against these lots. The five Global Future Cities contracts were competed via a call off competition.
2. Use of the Framework Agreement as the key sourcing route offered a number of advantages:
- Due diligence will have been carried out on each supplier centrally and procurement timescales are significantly reduced (by four – eight weeks) as a result.
- There will be improved VFM on rates and costs because the bidders’ maximum rates are likely to be significantly reduced from the day rates submitted when joining the Framework.
- Suppliers have not been required to identify their consortium or sub-contractors to bid for a place on the Framework Agreement. This means that flexibility is retained for the suppliers to identify their supply chains to meet specific local requirements as and when they arise. As part of the bidders’ response they detail the sub-contractors, many of which are in-country SME’s, to support delivery.
- The Framework Agreement set out key contractual terms which the suppliers were required to adhere to when delivering at local level. The Framework Agreement will be managed robustly by FCO’s Central Procurement Group which will provide backup to contract managers locally. Poor performance by suppliers locally may affect their prospects on receiving further work elsewhere thereby incentivising good performance.
There were 15 bids received against the five procurements from 10 suppliers. Most bids received were of a good standard and demonstrated effective understanding of what the programme is looking to deliver and how bidders would be able to deliver it. All framework suppliers formed partnerships involving - varyingly - a mix of UK, local and international expertise. The successful bidders were able to demonstrate ability to access to breadth of expertise and the beneficiaries (including host Governments) targeted by the programme.
Evaluation and Moderation
1. Following the close of the deadline for the ITT returns, the FCO Commercial team – with support from the programme team ran an evaluation process to assess and reach conclusions regarding the 15 bids received. Proposals were evaluated individually and independently over a period of 4-5 weeks by evaluation panels (one per procurement), comprising a minimum of four panellists.
2. Moderation panels were all held in London and brought together a mix of geographic, urban planning, development and programme management expertise. They all were chaired and moderated by a member of the FCO’s Commercial team. The panel reviewed respective views of the members and experts of the panel at length in order to reach a consensus on the score for each section of each bid. FCO Commercial ensured that the moderation was fair and impartial. Changes and convergence in scoring was documented as were reasons for awarding scores and a set of clarification questions to be used in the event of a requirement to interview or to support the downstream contracting process.
3. Panels were held in person and involved between 15 hours and in excess of 60 hours of input by the respective panels, depending on the number of bids and size of moderation panels involved. Ahead of the panels FCO Commercial delivered training to panellists, while cross-cutting advice was provided by a central team comprising GESI, Secondary Benefits and VFM experts.
4. The evaluation was carried out against a set of criteria developed to ensure that the successful supplier evidenced capability and capacity to deliver, a clear understanding of the local and global dimensions of the Programme and deep insight of how the objectives and outcomes of the programme can be delivered. These criteria included: methodology; expertise; capacity; project plan; relevant geographical experience; stakeholder management; contract management approach; and management reporting.
5. As noted above, the scoring for the evaluation was weighted 70% Technical to 30% Commercial, reflective of the Framework evaluation weightings. Accounting for price testing through the Framework competition, this provided for the optimum balance of quality vs price and means of delivering the Most Economically Advantageous Tender (MEAT).

Contract Award
1. The synthesis of technical and commercial scores resulted in clear distance between the first and second place bidders in four of the five procurements. In the fifth one – Brazil – only one bid was received and this was assessed in terms of its suitability for award.
2. The bidder with the highest score for Nigeria was Adam Smith International; the highest score for Turkey was Ove Arup and Partners International Ltd and for South Africa it was Pricewaterhouse Coopers; the highest score for South East Asia was achieved by Mott McDonald. The only bid for Brazil was submitted by Ernst and Young LLP. All winning suppliers (and bidding partners) demonstrated ability to deliver in the following key areas:
- Ability to work collaboratively with governments to ensure delivery of target outcomes
- Track record of working on related projects at scale
- Track record of delivering results and VFM
- The capability needed to deliver results in this programme

The contract award notices for each of the procurements can be found on the Contracts Finder website and via the links below:
- Brazil: https://www.contractsfinder.service.gov.uk/Notice/6ab604d3-b5f2-410f-b065-0660f2e5b527
- S Africa: https://www.contractsfinder.service.gov.uk/Notice/5fe8453b-6b04-49e6-b0d5-22e080ba3572
- Turkey: https://www.contractsfinder.service.gov.uk/Notice/19ae2c85-8026-4b31-a2e4-1eeef0dbe568
- Nigeria: https://www.contractsfinder.service.gov.uk/Notice/36572fd0-c5fa-483b-8473-34b674c33126
- SE Asia: https://www.contractsfinder.service.gov.uk/Notice/2fcc4e6d-1521-4ea6-8c8f-065c621d81d5

Contract Management
1. Key programme governance structures are defined in the Management Case. The Strategic Programme Board and monthly Programme Committees will be the key bodies providing overall strategic oversight and operational decisions. These will be supplemented and supported at the national or regional level by in-country Steering Committees or Delivery Boards and the Strategic Partner.
2. The Contract Manager will be based in London in the central Programme Team, but working closely with the Global Future Cities Programme Managers at the individual Posts and the Strategic Partner to ensure contractual obligations are fulfilled. The Contract Manager’s work will be framed by a contract management plan that will provide the basis for robust and clear contract management activities, principles and review points. Country-based Programme Advisers will be responsible for:
- relationship management including working with stakeholders to support the supplier’s progress;
- monitoring progress against Key Performance Indicators and Payment by Results mechanisms such as milestone payments, and reporting on these (see below for further information on Key Performance Indicators and Payment Mechanisms);
- ensuring GEA compliance and technical QA for gender, poverty and inclusion.
They will be supported by expertise from UN Habitat as the Strategic Partner when required.
Performance and Reporting
1. Detailed reporting and monitoring requirements will be agreed with the central Monitoring, Reporting, Evaluation and Learning (MREL) teams, both in the Joint Funds Unit and Prosperity Fund Department. Monthly financial reports will enable the FCO to make key decisions regarding the direction of the programme. This also ensures efficiency levels are maintained and effective delivery against outputs achieved. Regular supplier meetings to discuss monthly KPIs, VFM being achieved and performance will take place throughout the contract duration, and particularly at key stages of implementation. Outputs from these discussions will also be issued to inform the Annual Review Reports.
2. Prior to contract signature, Key Performance Indicators (KPIs) and a payment by results approach – linked to delivery of outputs - will be agreed. The FCO’s MREL provider and the programme Strategic Partner will play an important support role in the development of indicators against which to set these output-based payments.
Terms and Conditions
The Framework Terms and Conditions reflect the Government Model Contract Terms for Services and have been developed to reflect the specifics of the Prosperity Fund, ODA and IDA requirements. Key terms include:
- Data Protections
- Intellectual Property Rights
- Transparency
- Tax Compliance, Termination rights
- Environment, Health and safety, Equality and Diversity and Anti-Terrorism clauses
1. Call-off terms provided for a roll down to a more detailed level to be adapted in line with the requirements and the environment in which the services will be delivered.
2. Additional clauses in Service Levels and Credits, Performance Management, Business Continuity and Exit arrangements were included and as relevant to the requirement.
Pricing Mechanisms
1. Payment will be milestone and output-based payments in order to ensure quality and value for money (VFM).
2. Payments will be in line with HMG standards and via electronic invoice procedures.
Risks
An assessment of the key commercial risks, and associated mitigations, has been undertaken and kept under review in the programme level Risk Register.

# The Financial Case
Introduction
1. The purpose of this section is to set out the forecast financial implications of the programme (as set out in the economic case section) and the proposed delivery model (as described in the commercial case).
2. The programme is seeking £80.0m of Prosperity Fund ODA funding over four years. This includes all implementing activities, such as administrative costs, with the exception of Portfolio MREL activities that will be covered by the PF MREL ring-fenced budget[98] and central FCO PF PMO costs.
3. At the Strategic Outline Business Case Stage, £4.1m of ODA funding was sought and granted from the £80m total for transition delivery activities.
Financial expenditure and cost drivers
The projected cost profile is set out below.
	2018/2019	2019/2020	2020/2021	2021/2022	Total
£m	4.1	25.0	35.0	15.9	80.0

1. The main cost across the programme are services to deliver the intervention specific technical assistance. The selection of external intervention delivery partners will be via a lot specific competitive tendering exercise within the PF framework. Rates will be subject to the PF maximum allowable rates. Selection of intervention delivery partners will include a VfM assessment including costs of programme delivery. Contracts will be based on milestone payments contingent on delivery of outputs. Annual reviews will include an assessment of financial performance.
2. The key cost driver items for the programme are set out below, together with their projected cost.
Cost item	Cost (£m)
Phase 1 Strategy and Training (transition delivery funding including HMG programme Hub 2018/19)	4.1
Phase 2 strategy and knowledge management	4.0
Phase 2 programme management partner	2.0
Phase 2 intervention delivery	62.9
HMG programme hub over Phase 2 (London and Singapore hubs plus Posts)	5.0
Phase 2 intervention contingency	2.0
TOTAL	80.0

The breakdown of phase 2 intervention delivery by pillar is as follows.
Pillar	Cost (£m)
Transport	27.1
Urban planning	26.3
Resilience	9.5
TOTAL	62.9

The breakdown of phase 2 intervention delivery budget by country is as follows.
Country	Cost (£m)
Nigeria	10.8
Turkey	11.5
South Africa	8.0
Philippines	5.8
Vietnam	5.5
Malaysia	5.8
Indonesia	6.0
Myanmar	2.0
Thailand	4.5
Brazil	3.0
TOTAL	62.9

1. The per country cost projections which make up the table in paragraph 145 above was originally presented in the Strategic Business Case and was built on bottom up estimates of the cost of each specific intervention, which were initially informed by the scoping studies and have since been updated by UN Habitat. These will be updated after the inception phase is complete but represent an upper limit of spend (see assumptions below).
2. All of the programme’s costs relate to delivery with zero administrative costs (central FCO PF Programme Support Team costs are not included). HMG staffing costs represent 5.75%[99] of the programme’s overall cost. HMG staff costs cover the following activities:
  [99] This includes an element of MREL activities
- Business case development and procurement
- Central programme leadership and management
- Regional/Post oversight of delivery partners and government-to-government engagement
1. This level of HMG resource to manage the programme is considered reasonable and required to ensure there is effective overall programme management, management of delivery partners, sharing of knowledge across cities, and coordinated local engagement at the city level to position the realisation of primary and secondary benefits. Without this level of resource there would be a high risk that the programme would not be successful, in particular the risk that city level strategies and plans (key outputs of the programme) are not implemented by city governments, and therefore the local development need is not addressed and associated trade opportunities for the UK not realised.
2. The estimates do not include any assumptions about salary increases or cost rises during the programme i.e. all costs are in today’s money. Staffing costs are based on the latest available Full Economic Cost Model for 2018/19.
Key underlying assumptions
The key financial assumptions which underpin the programme are:
- Phase 2 intervention delivery budgets are based on costs received during procurement. The costs from suppliers have been developed based on the information given in the invitation to tender, which although detailed, will not be confirmed until the inception stage planning is complete. However, the overall contract value is capped.
- There are no contingent liabilities. All HMG programme staff will either be permanent UK based civil servants (who can be subsequently redeployed) or locally engaged staff on fixed term contracts matching their role on the programme
- All contracts with delivery partners will be in pounds sterling but the MOU with UN Habitat is in US Dollars ($). A yearly currency review will take place to assess the impact of currency fluctuations on the delivery of the Strategic and Capacity Building work. Some of the £2m contingency project funding will be allocated to cover the currency fluctuation risk to the programme.
- All costs are in current prices e.g. staff costs use current FECs
- Central FCO PF Programme Support Team costs are not included
Accountability
The funds will sit in the FCO after being cascaded from NSC/HMT. The FCO is the Department responsible for spend compliance. The funds will be approved by NSC/HMT and FCO in accordance with delegated authority transmitted from Cabinet Office/HMT through FCO PUS. The SRO and senior budget holder (SBH) for the programme is the Director of Economic Diplomacy.
Impact on the balance sheet
The proposed expenditure does not cover any assets or equipment and will therefore have no impact on the FCO’s balance sheet.
Overall affordability
1. The proposed cost of the programme is £80.0m over the expected lifespan of the programme. Funding will be ‘programme’ spending (RDEL). An allocation of £80.0m has been made by the Prosperity Fund, subject to approval of this business case. All funds are ODA eligible and there are no contingent liabilities associated with this funding.
2. There will be no ongoing costs to be covered once this programme has finished as there are no plans to establish structures with future HMG resource implications under programme design.
Monitoring, reporting and accounting of expenditure
1. Programme spend and forecasts will be monitored by the Programme team using FCO financial systems. Budgets will be entered onto the FCO's systems using Hyperion, the FCO's online forecasting tool, at the start of each financial year. The central programme team will use the FCO’s financial dashboard, Oracle Business Intelligence Enterprise Edition (OBIEE) and Hyperion systems to monitor and report spend to date and forecasts. The programme team will work closely with delivery partners to ensure accurate forecasting. Accurate forecasting will be managed by ensuring payments follow an agreed schedule defined by clear and time-bounded deliverables and fees. Payment schedules will be monitored monthly, reviewed bi-annually and can be adjusted if necessary.
2. The programme team will formally report spend and forecasts to PFDU and the JFU, in line with their financial requirements. An audit trail will be maintained to show all financial decisions taken.
3. All delivery partners will be obliged to adhere to open book accounting principles and submit an annual report containing audited accounts for each of the financial years covered by the programme.
4. The programme team will produce a programme level annual report, which will be approved by the programme’s SRO and contain a summary of historic financial information and forward forecasts.
5. In accordance with contractual provisions, funds to the delivery partners will be disbursed in arrears on receipt of a valid invoice supported by a breakdown of activity that has been delivered/outputs produced. Each invoice will be supported by a breakdown of the costs being claimed against each budget line in the contract.
6. The Programme Lead will be responsible for ensuring due diligence in the disbursement of funds, and for taking any action deemed necessary. Where appropriate, full details of forecasted future spend by financial year against the annual workplan will be included in the annual report.

Scaling
1. The programme will adopt the principle of adaptive programming to ensure that the programme’s impact and value for money are optimised. The central programme team will recommend any changes to the programme’s portfolio, including scaling up or down, to the Strategic Programme Board and for subsequent approval by the SRO. Any such changes to the portfolio may have financial implications and these will be thoroughly assessed before any decisions are made, with updates to financial forecasts made after any decisions have been taken.
2. The programme is inherently scalable due to the modular nature of interventions across cities under a common framework. To scale down, the number of cities included within the programme or the number of interventions within a specific city could be reduced. To scale up, either additional interventions within the identified cities could be increased or additional cities included within the identified countries. Both these scale up options have already been identified by the scoping work that has been undertaken in the identified countries.
Financial and Fraud risk assessment
1. The main financial risk is that the programme take time to reach implementation and that procurement delays and delivery delays result in drawdown being delayed. The timeline is based on a realistic assessment of the time required to undertake the required procurement activity and intervention implementation based on similar historic projects. Timelines and associated expenditure will be monitored carefully by the core programme team, with corrective action taken as required. This will involve close working with both delivery partners and partner city stakeholders. Adaptive programming will be deployed if appropriate.
2. Several of the countries that this programme will operate in have environments that present a fiduciary and fraud risk. These risks will be mitigated through:
- No funds will be transferred to any partner governments, all payments will be made to appointed delivery partners[100]
  [100] One possible exception may be for travel and subsistence related to partner government officials attending major international programme events
- Funds will be disbursed directly by HMG to a limited number of delivery partners
- The majority of funds will be dispersed to pre-vetted delivery partners on the PF Framework. Due diligence will be carried out on all delivery partners not commissioned via the PF Framework before any payments are made
- Standard FCO procedures will be followed to verify payments before funds are disbursed
- Delivery partners will be obliged to follow similar suitably robust procedures to ensure probity of their supply chain
- All payments will be for services received with appropriate payment by results points. Funds will be disbursed in arrears
- All suppliers will be obliged to follow the Public Contracting Regulations
- Each invoice will be supported by a breakdown of the costs being claimed against each budget line in the contract

1. A zero-tolerance approach to be taken to fraud and corruption. The programme will be may be independently reviewed by the FCO’s Internal Audit Department. Delivery partners may be subject to a formal FCO audit assessment if deemed appropriate.
2. As a result of the above, the financial risk and fraud is assessed as low throughout the programme. The financial and fraud risks will be kept under review by the programme via its governance arrangements.
Financial risks
The key financial risks, together with their associated mitigations are set-out in the table below.
Risk	Mitigation
Expenditure is delayed as a result of delayed procurement or delivery partner implementation	Robust financial reporting, including forecasting and risk analysis, will be adopted. The accuracy of financial forecasts will be monitored by the core programme team and be included within delivery partner KPIs. This approach will ensure the early capture of any potential delays. Corrective action will be taken as required. This will involve close working with both delivery partners and partner city stakeholders. Dynamic programming will be utilised to reallocate expenditure as appropriate. Subject to agreement with the SRO and the JFU, programme expenditure could move into the 2021/22 financial year
Fraud or misuse of funds by delivery partners	Comprehensive due diligence of delivery partners before appointment. Use of pre-checked suppliers from the PF framework. Annual reviews with all delivery partners including financial reporting. No advance payments
The value of sterling changes and impacts costs	All contracts will be in pounds sterling. It is possible that estimated costs could rise if sterling depreciates and therefore local supply costs increase. This risk would lie with lead delivery partners once contracts are agreed. Before contracts are signed this risk would lie with the FCO. The programme team will monitor this risk closely in conjunction with FCO finance and commercial teams, and dynamic programme used as required to scale back the portfolio of interventions

# The Management Case
Introduction
This section of the business case describes how the overall programme will be implemented and governed. All elements will be subject to the governance arrangements outlined within this case.
Programme Principles
The Steering Committee has agreed a set of over-arching programme principles that have been successfully followed during the development of this business case and Phase 1 delivery. These principles are set-out in the diagram below.

Programme Governance
1. The programme will be led by the FCO and the SRO will be the Director of Economic Diplomacy.
2. The SRO is accountable for the development, delivery and closure of the programme. This includes being accountable for the delivery of its objectives and policy intent; for securing and protecting its vision; for ensuring that it is governed responsibly, reported honestly and that risks escalated appropriately; and for influencing constructively the context, culture and operating environment of the programme. The key aspects of the SRO’s role include:
- Approval and governance
- Programme design and delivery
- Contracting and procurement
- Monitoring and evaluation
- Financial management and reporting
- Transparency
- Compliance with the International Development Act and the International Development (Gender Equality) amendment.
1. The SRO will receive a letter from PUS setting out the SRO’s delegated accountability for the programme, the setting of the SRO’s delegated authority and escalation thresholds.
2. The SRO will report via the PFDU and JFU to the Portfolio Board and NSC Sub-Committee in accordance with standard PF reporting arrangements. Reporting to DG (Global Britain), on behalf of the PUS, will take place through the PFDU.
3. The cross –Government Steering Committee which directed the development of the programme have now been invited to continue as members of the Strategic Programme Board.
4. The overall governance structure for the programme is set out in the diagram below.

1. Rapid decision making and issue resolution will be enabled through clear delineation of remits between the Programme Management Committee and Strategic Programme Board, meaning that items do not necessarily need to be tabled at the Programme Management Committee before being tabled at the Strategic Programme Board. In addition, escalation direct to the SRO for immediate decision making can take place at any time as needed.
2. The key roles of the above governance levels are as follows.
Governance level	Roles
NSC Ministerial Sub-Committee	Strategic direction of the PF
Cross Government PF Portfolio Board	Cross Government approval of the programme in terms of strategy and VfM
Permanent Under Secretary (PUS)	Ultimate accountable officer for delivery of programme funds
Joint Funds Unit (JFU)	JFU approval of the programme and change control
Prosperity Fund Delivery Unit (PFDU)	FCO coordination of PF programmes and reporting to PUS
Programme SRO	Accountable for the delivery of the programme. Direct the programme and take key decisions
Strategic Programme Board	Drive the programme forward strategically, support the SRO and ensure alignment with PF and HMG strategy
Programme Management Committee	Responsible for the delivery of the programme and taking operational decisions
Country Steering Committees	Drive the programme forward locally and taking local decisions

1. The Strategic Programme Board members will include the following members:
  1. The SRO (chair)
  2. Senior representatives from Posts (e.g. Head of Prosperity)
  3. Senior representatives from DFID, DIT and FCO
  4. Senior representatives from delivery partners (to be invited as required to report)
  5. The programme lead

1. The Programme Management Committee will include the following members:
  1. The programme lead (chair)
  2. Working level representatives from Posts
  3. Members of the core programme team
  4. Representatives from the programme management partner (advisory role)
  5. Representatives from the delivery partners by invitation (advisory role)

1. The Country Steering Committees will include the following members:
  1. Senior representatives from Posts (e.g. Head of Prosperity) (chair)
  2. Working level representatives from Posts
  3. Representatives from the partner government (advisory role)
  4. Representatives from the delivery partners (advisory role)
  5. Wider stakeholders as appropriate (advisory role)

1. The Strategic Programme Board is planned to meet quarterly, the Programme Management Committee and Country Steering Committees monthly. These frequencies will be reviewed during the lifespan of the programme and adjusted as appropriate. In addition, the chair will be able to call exceptional meetings at any point in time as required.
2. Decision making for all governance fora will be taken by the relevant chair with escalation to the SRO as required.
Programme Staffing
1. Delivery of the programme’s interventions will be undertaken by delivery partners (predominately private sector). HMG’s role in the programme will be predominately focused on:
  1. Government to government engagement;
  2. Supplier management, including holding suppliers to account on ensuring a development and inclusive approach is applied throughout the whole programme, specifically, but not limited to, gender equality and inclusion;
  3. Ensuring programme outputs subsequently lead to the longer-term planned outcomes and impacts, both primary and secondary. Monitoring compliance with the Gender Equality Act.
2. A ‘hub and spoke’ operating model will be utilised to both maximise shared efficiencies and ensure local oversight (see diagram below). There will be a global hub in London, together with a South East Asia hub in Singapore (jointly referred to as the ‘core programme team’), and representation in each city via Posts (representing DFID, DIT and FCO). The programme will also be supported by the FCO Prosperity Fund Programme Support Team on MREL, benefits management, gender and social inclusion. Future cities and urbanisation expertise will be provided by the ‘core programme team’, supported by the strategy and knowledge management partner, together with the local team at Post, supported by delivery partners. Local country and city expertise will be provided by Posts, again supported by delivery partners.

The broad split of roles between the London/Singapore hubs and Posts is set out in the table below.
Function	Role of London/Singapore	Role of Posts
Leadership	Global leadership across the programme	Programme leadership in- country and across cities
Delivery co-ordination and assurance	Global co-ordination, quality assurance, dynamic programming adjustments and knowledge management	Oversight of local delivery partners, quality assurance, accountability and interdependencies
Architecture	Ensure global programme coherence and integrity	Ensure local programme coherence and fit with other local programmes (including PF)
Benefits	Co-ordinate global benefits management, including primary, secondary, gender and poverty	In-country benefits management, including primary, secondary, gender and poverty
Finance	Budgeting, forecasting and payments	Sign-off local delivery partner milestones
Communication	Global programme communications and UK communications	In-country communications and ensuring coherence of HMG branding
Stakeholder management	Management of UK stakeholders (including across Government)	Management of in-country stakeholders and ensuring coherence of diplomatic engagement
Commercial/procurement	All contractual activity and supplier management	Facilitate local supply chains / Highlight any local risks or issues
Reporting	Reporting to the Strategic Board, PFDU, JFU, Portfolio Board and Ministerial Board	Reporting to the core programme team
Issue management	Capture and resolve/escalate global issues	Capture and resolve/escalate local issues
Risk management	Identify and manage global risks	Identify and manage local risks
Governance	Own and manage the global governance framework	Own and manage the local governance framework
Staffing	Appoint and manage core programme team	Appoint and manage local programme team

1. The London hub will have ultimate responsibility for the overall management of the programme. The Singapore hub will work closely with the London hub and support it by providing a pan-SE Asia view and input on the functions outlined above, and liaise directly with the six individual Posts, leaving London to liaise directly with the remaining four Posts.
2. The FCO team structure[101] is set out below (precise Post team structures vary from Post to Post but generally follow the model below). Note that not all roles are full-time.
  [101] These vary from formal staff management reporting lines

Programme Management Methodologies
1. The programme will be managed in accordance with the HMG best practice, following MSP and PRINCE2 principles. Electronic programme management tools (ePMO) tools are currently being investigated to support the efficient management and operation of the programme.
2. The programme team will be supported by technical experts in relevant fields, including on private sector development, social economic and governance issues, social development, inclusive growth, gender equality and benefits management. This is one of the key roles of the strategy and knowledge partner, as well as the FCO Prosperity Fund Programme Support Team.
Implementation Plan
The key milestones for each programme component will be developed with delivery partners as part of the inception phase post procurement. Full Gender and Inclusion (G&I) Analysis and Impact Assessments (incorporating Human Rights Assessment of the different contexts and intervention) will be developed during the inception phase, prior to interventions, together with a G&I Action Plan. These will be based on consultation with key primary stakeholders, including women, other excluded groups and their representatives (e.g. women-led NGOs, women entrepreneurs, Disabled People’s Organisations). Gateway reviews for each project will be undertaken at appropriate key points in the programme to ensure that management arrangements remain robust, the route to benefit delivery is clear and lessons learnt.
Flexible Programming
The programme has been designed to enable dynamic, adaptive programming to take place and will explore options for citizen feedback and engagement mechanisms. The key area where dynamic programming is most appropriate is intervention delivery. Intervention delivery can be scaled up or down in a number of ways e.g. scaling up or down a specific intervention within a city, changing the portfolio of interventions within a city, or changing the city portfolio within a country. The contracts with delivery partners will all include annual reviews with monies being allocated annually, enabling the programme to adapt to changing situations. If for whatever reason a component is underperforming, budget can be fully or partially reallocated to other components where expected impacts will be higher. This process will be managed by the core programme management team as part of their ongoing monitoring role with decisions taken by the Strategic Programme Board/SRO. Decisions would be made as part of the annual review process or out of the review cycle by exception. The deliberately designed component structure of the programme means there are multiple ways to adapt the programme to maximise impact and value for money.
Monitoring, Reporting, Evaluation and Learning
1. The monitoring, reporting, evaluation and learning (MREL) for this programme will be consistent with the PF approach to MREL. The core programme management team and Posts have started working, and will continue to do so, with the PF MREL contractors to define the indicators that will be developed and base lined for the programme to ensure consistency and quality of reporting across the whole PF portfolio.
2. If this programme is selected for the PF Fund level evaluation, the core programme management team, Posts and implementation partners will work closely with the evaluation team to support the process. The core programme management team have also already started to work with the PF-level evaluation and learning contractor to define the strategic questions for evaluation and learning.
3. Learning across the programme, in particular from one city to another, will be key to success and this is a key role of the strategy and learning partner.
Results Framework
The programme management team are working with the PF MR contractors to develop the critical indicators required for programme level reporting, identifying aggregate indicators for regular reporting and management indicators to allow the core programme team and Posts to assess progress and impacts e.g. number of MoUs signed with partner cities. The programme’s indicators will be consistent with the programme’s theory of change and the log frame analysis that flows from this. Outcome and output statements will capture the ambition on gender equality and women’s economic empowerment as appropriate, with G&I key performance indicators (quantitative and qualitative) included in the logframe. The programme’s indicators will include disaggregated results by gender, age and socio-economic group where relevant (and by disability where possible), in compliance with the GEA and aligned to the MREL system.
Reporting Frequency and Costs
Expenditure will be reported monthly and impacts (results) quarterly in line with PF reporting rhythms. Consistent with PF requirements, the core programme team will instruct delivery partners to develop a quarterly results reporting system and will work with the PF monitoring and reporting contractor to ensure consistency with PF processes and systems – particularly around data frequency, quality and consistency. Programme data capture and base lining will be the responsibility of the core programme team, Posts and delivery partners.
Annual Reviews
Annual reviews of the overall programme will take place, fed by sub-reviews of each component. The annual review process will be led by the core programme team and Posts, involving delivery partners and seeking citizen views and feedback as appropriate. Annual reviews will assess the contribution of the programme to gender equality and women’s economic empowerment. They will use an assessment of performance against gender commitments in the Business Case/G&I action plan using the PF G&I scorecard. The results of the annual reviews will be reported to the SRO and the Strategic Programme Board.
Communications
1. Communications will be a vital part of ensuring the programme is a success, in particular ensuring the potential positive spill-over impacts and reputational benefits for the UK are realised e.g. ensuring businesses are aware of the high-level pipeline of investment projects created by the programme.
2. The programme lead will have overall responsibility for setting, maintaining and updating the programme’s communication strategy; working with the JFU, FCO Media Office, the FCO PF PST communications manager, Posts and delivery partners; and ensuring coherence across individual components of the programme. The programme manager will also be responsible for developing, maintaining and updating a communications plan for pan-programme communications.
3. The communication strategy will contain (and build upon) a specific plan for each component, working with Posts (including local media managers), partner governments and delivery partners.
4. The key objectives of the communications strategy will be to:
  1. Ensure all stakeholders are actively involved in the programme
  2. Positively influence partner government future cities policy making
  3. Ensure UK organisations are aware of the future cities opportunities in the target countries resulting from programme activities
  4. Disseminate good news stories to help build programme momentum, public support and further develop bilateral relationships
  5. Influence national, state and city decision-makers to ensure effective implementation and delivery of the programme, including maximising potential spill-overs
  6. Use the programme to raise the profile and reputation of the UK while facilitating access to stakeholders in national, state and city government, and in the private sector

1. Our main audiences are:
  1. UK business and investors
  2. Partner country businesses and investors interested in partnerships with UK companies
  3. Partner country national, state and city government, in particular decision makers targeted by the programme
  4. Partner country media and citizens
  5. HMG departments e.g. DFID and DIT
  6. HMG Posts and the programme team
  7. UK and partner country Civil Society Organisations (CSOs).
2. The programme does not expect to directly target UK audiences beyond potential beneficiaries (i.e. UK companies). However, if there are significant successes resulting from programme activity, the programme will consult with both the appropriate departmental teams (e.g. the FCO Media Office) and the JFU communications team on the potential for informing UK media. The programme will develop defensive press lines and FAQs in readiness for any parliamentary questions or negative UK media interest about the programme.
3. Strategic activities will therefore include:
  1. Communications activities including meetings and presentations with UK companies that could benefit from the opening up of opportunities in the partner cities. This will link to work undertaken by DIT to directly facilitate business wins
  2. Ongoing engagement with relevant national, state and city departments and officials in the partner countries to raise the profile of programme activities; advertise the potential of UK companies; and ensure we are aware of developing opportunities (e.g. major contracts, policy reforms etc.) and any risks
  3. Timely media moments (blogs, tweets, editorials) to highlight programme activities and successes to a wide audience, further enhancing the reputational benefits for the UK
4. Internally, the programme will ensure departmental staff are engaged with the programme and information is available for them to take advantage of in creating further opportunities e.g. regular newsletters.
5. The communications strategy will use the Government Communications Service (GCS) OASIS framework:
  1. Objectives – what the communications is intending to achieve
  2. Audience – who are you targeting and what attitudes or behaviours do you want to influence
  3. Strategy – approach, messages, channels and partners
  4. Implementation – delivery plan
  5. Scoring – monitoring, evaluating and feedback loop
6. All programme outputs will be branded with the UK aid logo and recognise UK Government funding.

Risk Management
1. The core programme management team will develop and own the risk management strategy and ensure it is complied with across the whole programme. The approach to risk management will follow the following steps:
  1. Risk capture – initial capture and identification of a risk
  2. Risk assessment and evaluation – categorisation of risk[102] and assessment of likelihood and impact
    [102] This follows DFID’s best practice risk approach for aid programmes
  3. Risk treatment and response – development of options and preferred mitigation strategies and actions to avoid the risk, minimise its likelihood of occurring or reduce its impact
2. All identified risks will be assessed and if required, allocated an owner to ensure that the risk is continually assessed and mitigation strategies and actions are implemented. This will include consideration and mitigation of specific risks in relation to gender. Political and human rights risks will be monitored and integrated into programme decision making and programme risk matrices.
3. Risk tolerances will be agreed by the Strategic Programme Board and feed into the above assessment of individual risks.
4. Review of risks will take place monthly at Programme Management Committees where they will be assessed for escalation to the Strategic Programme Board. The Strategic Programme Board will review risks quarterly and these will then feed into the Portfolio risk register.
5. The programme as a whole is assessed as being medium/high risk. This is a direct result of the high-return ambitious nature of the programme where we are seeking to achieve impacts where their external factors are not within the direct control of the programme.

References