Guidance for Departments and Review Teams / Project Validation Review (PVR) v3.0
September 2019

[Back of cover – for printed publications, leave this page blank]

Crown copyright 2018
Produced by the Infrastructure and Projects Authority

You may re-use this information (excluding logos) free of charge in any format or medium, under the terms of the Open Government Licence. To view this licence, visit http://www.nationalarchives.gov.uk/doc/open-government-licence/ or email: psi@nationalarchives.gsi.gov.uk

Where we have identified any third party copyright material you will need to obtain permission from the copyright holders concerned.

This information is also available on the IPA website:

https://www.gov.uk/government/organisations/infrastructure-and-projects-authority

Contents

# 1. Executive Summary

Evidence shows that projects to deliver policy-initiated or other business or transformational change have a far greater chance of success if they are established on a sound basis from the outset[1]. The Project Validation Review (PVR) is an independent review to support the initiation of any form of business change project or programme.[2]  It is particularly valuable as policy development begins to turn towards implementation planning.
[1] https://www.nao.org.uk/report/nao-guide-initiating-successful-projects-3/
[2] The IPA provides advice and assurance to such projects and programmes (the IPA Early Development Pool) recognising that it will not always be clear at an early stage whether major project status is appropriate.
This short (1 - 3 days), usually workshop-based, review provides:
- A more robust engagement between Departments and the centre at an earlier stage
- The alignment of objectives (policy and project) with the organisation’s wider change portfolio
- Support and challenge to help understand what is required to ensure a project is set-up effectively for success (i.e. to deliver to time, cost and quality, and that the benefits are understood), before fully developing its strategic options (in the feasibility/discovery stage)
- The sharing of views, opportunities and risks with key stakeholders
- Consideration of early strategic delivery options and standards

The Project Validation Review (PVR) is a mandatory, enhanced validation process for all new major projects and programmes.[3] Following a PVR for a prospective major project, the Infrastructure and Projects Authority (IPA) and HM Treasury (HMT) must be confident that all of the requirements outlined in Annex A have been robustly considered, evidenced and are being progressed.
[3] A major project is defined as any central government funded project or programme that requires HM Treasury approval during its life, as set out in Delegated Authority letters, would entail significant contractual commitments for plans that have still to be set, set an expensive precedent, is novel or contentious, requires primary legislation and and/or is of special interest to the Government.

The PVR replaced the Starting Gate review for all new major projects. Depending on the outcome of this first review, subsequent assurance reviews should be scheduled using an Integrated Assurance and Approvals Plan (IAAP). The next review would normally be in advance of the Strategic Outline Case (SOC) approval point.

# The Project Validation Review

2. Introduction

While the precise timing for each review will be confirmed following discussion with IPA and the department, a PVR should be scheduled early enough to be able to inform the development of the initial (Strategic) business case.[4] If an agile management delivery approach is being considered the PVR should be undertaken prior to commencement of the “Discovery stage”.
[4] https://www.nao.org.uk/wp-content/uploads/2010/06/Assurance_for_high_risk_projects.pdf

The PVR approach is tailored for each project, however it is likely that the review will primarily use facilitated discussions or workshops with key stakeholders, policy and project staff, and if appropriate, it may include a small number of one-to-one interviews with key stakeholders. At such an early stage documentation is likely to be limited but any documentation that explains the scope and objectives will normally be provided to the PVR team. The timing and duration (between 1 and 3 days) of the review will be confirmed following discussions between the department and IPA.

The purpose of a PVR is to establish whether the programme or project is being set up to succeed. A PVR does not assign a formal RAG rating assessment of delivery confidence. However, the PVR will assign a ‘Progress Assessment’ rating to show the readiness to move to the next stage of the project life-cycle. The review also helps inform whether and when the project enters the Government Major Projects Portfolio (GMPP) and IPA oversight or if assurance provision remains with the department.
If a PVR has not taken place before the formal Strategic Outline Business Case (SOBC) HMT approval point, the project will normally be required to schedule an IPA assurance review immediately before proceeding. The joint HM Treasury and Cabinet Office “Major projects assurance and approvals guidance” details HMT approval processes.

# 3. Commissioning

Departments should have visibility of emerging change initiatives through their portfolio management processes. Change initiatives that may be appropriate for a PVR should be identified through the Departmental Portfolio Office (DPO) (or equivalent), policy development teams or by the potential sponsor and/or the Senior Responsible Owner (SRO) designate of the major change projects.

If the HMT, DPO or the department identifies that a new project may be initiated in the future, early engagement with IPA is essential. All new major projects must be added to the IPA’s Early Development Pool (EDP) pipeline via the IPA Strategic Delivery Advisor (SDA) and Departmental Portfolio Office records, even if it is believed that a PVR will not add value in the near term and the timing of a review may be at a later date. Ideally, the project would be added to the IPA pipeline significantly before a detailed Ministerial announcement is made.

A PVR may be commissioned:
- For an entirely new project or programme
- For a new constituent project of an already existing Government Major Projects Portfolio (GMPP) programme
- When a project needs to re-consider new major change requirements or when assessing revised strategic options

The timing of a PVR should normally be before a request for HMT SOBC approval. A PVR may be repeated if considered appropriate by IPA.

The department’s role: The department is required to submit a summary of the proposed change, e.g. a policy statement, business plan extract, or equivalent preparatory work and complete Annex A of the Risk Potential Assessment (RPA) form. Completion of Annex B is optional.
This document should be completed with support from the Departmental Assurance Co-ordinator (DAC) or Portfolio Office within the department and discussed with the relevant IPA SDA before submission.
IPA and HMT’s role: The IPA SDA (and HMT spending team representative and other digital or commercial specialist if appropriate), will hold a short, informal commissioning meeting to discuss the expected review scope and confirm the format of the PVR. IPA will then draft the terms of reference for the PVR.
HMT may indicate what scrutiny following the PVR (either via a Major Projects Review Group (MPRG) panel, a Treasury Approval Point (TAP) Panel or a spending team review) is likely to be required. Where a MPRG panel is required the MPRG secretariat must be informed immediately.
The IPA SDA will work with the department to schedule an assessment meeting with the Sponsor/SRO to set up the review. The commissioning and assessment meeting may be rolled into a single meeting.
The assessment meeting will enable IPA SDA to ascertain the latest progress situation, identify the most appropriate format for the review and agree the timing of the review.
It is recommended the facilitated discussion/workshop should have no more than 10-12 participants at any given time. If numbers exceed this, consideration should be given at the planning meeting to holding more than one workshop. Consideration should also be given to how any 1:1, or smaller facilitated group discussions might be used, as matters emerge from the larger workshop(s).

The Terms of Reference (ToR) are developed by the IPA SDA with input from HM Treasury and other functions at the centre, as appropriate. For each PVR, the ToRs are tailored, but in every instance the review must assess the following, as a minimum:

  - The understanding of the project purpose, policy, objectives and, where applicable, the intent of any prior Ministerial announcement. As part of this, the review should consider:
    - the strategic alignment of the project with the department’s wider portfolio, and if appropriate, the Department’s Capital Infrastructure Plan
    - wider public sector initiatives

  - Affordability and options analysis, which must include:
    - whether the department has considered the full extent of financial, commercial and delivery options available, and their strategic financial implications
    - the use of optimism bias

  - Governance, capability and deliverability, which must include consideration of the:
    - project structure, governance arrangements and stakeholder commitment to the project
    - the delivery approach and standards to be followed
    - risks, controls and performance monitoring requirements
    - plans to mitigate any capacity or capability gaps which may impede delivery
    - whether the Department intends to utilise the IPA’s Project Initiation Route Map (where appropriate)
    - Plans to manage interdependencies with other projects

A list of areas to probe is included in Annex A. This should be considered as a guide for the workshop discussions. It is not exhaustive and should not be used as a checklist that must be covered. The Review Team may identify other areas on which it may seek views that emerge during the workshop(s).

The ToR is drafted following the initial assessment meeting with the project’s SRO and/or Senior Policy Lead. This assessment meeting will also determine the dates for the planning meeting and the review. The planning meeting will normally be within two weeks of the date of the review.

The draft ToR and a planning meeting agenda will be submitted to the project and Review Team by the IPA in advance of the review planning meeting.

# 4. Planning and resourcing

The planning meeting is an essential part of the assurance review process as it may be the first time members of the Review Team will have met each other and worked with the Review Team Leader (RTL). It should take place up to two weeks prior to the review. The IPA SDA does have the discretion to decide not to hold a planning meeting if this is not required.

The planning meeting gives an opportunity for the Review Team and the IPA SDA to discuss how best to work together and establish a Code of Conduct (a statement of professional principles that will be adopted) applicable to the review, the Review Team and the SRO.
Establishing a code of conduct at the outset of any assurance review is essential to ensure that the Review Team and their review participants have a common understanding of how the review will be undertaken. It will clarify and align expectations in advance and will help to prevent any differences from affecting the quality and effectiveness of the review. For a workshop-based review such as this, it is imperative that participants are able to express their views freely, that discussions are not dominated by seniors or strong personalities and ‘group-think’ is avoided. The Review Team must be able to both identify this and manage it accordingly. It is essential that all participants buy-in to the code of conduct.
Some typical items in a Code of Conduct include:
- Open and honest contributions, avoiding “group think”
- Valuing diversity/difference
- Reporting will be objective and non-attributable
- Robust management of time
- Valuing best practice, using lessons learned, as well as identifying areas for improvement
- Independence and objectivity
- Positive team working and respect for others views
- A learning experience that add value
- Confirming that the review is not an audit

The planning meeting will enable the SRO to advise the Review Team of progress to date, challenges, risks and areas of concern. This information will help the Review Team to familiarise themselves with the programme/project and identify the key potential issues for the review. The planning meeting is also used to finalise the logistics for the review (security passes, booking rooms etc.), interview schedules and documentation requirements.
A generic planning meeting agenda is available to enable the RTL and the SRO to arrange the sequence of the meeting. As the RTL is accountable for the review, they are expected to chair the planning meeting. The SDA/Departmental Assurance Coordinator (DAC) will attend to facilitate or assist where necessary, provide the latest view of the project from an IPA/Cabinet Office/HMT perspective and ensure that the correct process for the review is followed.

Details of how a PVR is resourced is set out in Annex B along with format for planning meeting.

# 5. Undertaking a review

The PVR normally uses a facilitated workshop(s), where the Review Team are the facilitators. The optimum size of the workshop should be around 10-12 participants who represent the key stakeholders. If the participant numbers are larger than this then a second workshop should be undertaken. A workshop should normally last about three hours. The numbers of participants would be determined in discussions between the SDA and project team when planning the PVR.

If after the workshop(s) there are issues that the Review Team consider warrant further discussion they have the option of using a small focus group session or 1:1 interviews. This cannot be planned in advance so participants may have to be advised in advance that they may be required to keep some time available at the end of the day or the review for such an eventuality.

It is recommended that for very senior stakeholders (e.g. Ministers, Permanent Secretaries or Director Generals) consideration is given to using one-to-one interviews.
Key PVR principles are:
- There must be commitment from all participants to adhere to the agenda and code of conduct
- There will be an open and frank airing of views, opportunities and risks is encouraged
- The Review Team will challenge assumptions and seek assurance that options assessments have been undertaken in draft plans and strategies. It is recognised that there may not be much written evidence available at this early stage
- Honest, constructive and evidence-based recommendations will be developed
- While the Review Team will be given an opportunity to consider privately the evidence provided, they will provide feedback to the SRO after the workshop(s)
- At the end of the review, the Review Team will produce a draft a report for the SRO

# 6. Reporting and recommendations

The RTL will draw together a draft review report, using a template provided by the IPA, which outlines the review findings, a Progress Assessment (PA), see below, recommendations and any issues raised in discussions during the review.
The Review Team presents the draft report to the SRO on the final day of the review. The SRO is given the opportunity to provide their comments on the review and correct any factual inaccuracies or grammatical errors. However, the Progress Assessment is non-negotiable.
The RTL is then responsible for completing and delivering the final report to the SRO, within 5 working days of the end of the review. The RTL should also submit a copy to the IPA Gateway Helpdesk (gateway.helpdesk@ipa.gov.uk), IPA SDA and to the DPO. A copy will also be submitted by the IPA SDA to the relevant HMT spending team representative immediately.
The SRO is responsible for developing an Action Plan to address the recommendations made and this should be sent to the IPA within 14 days of the report being finalised.
The final report and its Progress Assessment (PA) is owned by the Centre and will inform any HMT early scrutiny of the project. The Sponsor/SRO will be responsible for ensuring any actions are taken to address any recommendations.

In the report, recommendations can be made to help the project achieve its objectives or manage risks more effectively and the descriptors below in bold support that. All Review Team members are expected to help formulate the recommendations. To help prioritise these recommendations, each will be considered in light of its immediacy for action. Each recommendation should use the following descriptors to help the project focus which recommendations to address:
Critical (Do Now) – To increase the likelihood of a successful outcome, it is of the greatest importance that the programme/project should take action immediately.
Essential (Do By) – To increase the likelihood of a successful outcome the programme/project should take action in the near future.
Recommended – The programme/project should benefit from the uptake of this recommendation.

Progress Assessment (PA)

In addition to the Review Team’s recommendations, the Review Team will provide a Progress Assessment (PA) in the report. The PA should be looking to assess the readiness to move into a project delivery mode, it is not a Delivery Confidence Assessment. The narrative to be used for the PA is as follows:

	Criteria Description
1	There are no significant issues to resolve. Progression to next key decision point should be made.
2	A number of issues require consideration and/or resolution, before the next key decision point but these appear resolvable. Progress with an awareness of risk.
3	Significant issues have been identified that require resolution before progression to the next stage or decision point. Escalation may be required to a higher level (relevant to the organisation structure) to resolve issues.

Where the Review Team identifies that there is a significant risk that the project will not deliver its long term objectives, this must be clearly evidenced in the report and highlighted as such in the report’s executive summary. The Review Team should ensure that the IPA and HMT are put on notice that further action needs to be taken to address those risks.

# 7. Post review actions

Following the review, a discussion should take place between the SRO and IPA to agree the level of support and scrutiny required as the project progresses. The PVR may also trigger help on expert resourcing by IPA where there are concerns that resourcing shortfalls may impede successful delivery of the project. Consideration should also be given to when (if appropriate) the project might commence reporting on the GMPP.
As part of the project initiation documentation an Integrated Assurance and Approvals Plan (IAAP) for future assurance and approval points should be developed.
The PVR Action Plan will be used to monitor the project’s progress against individual review recommendations and overall delivery against its critical path. It may also help in IPA’s role of providing support, as well as challenge progress against this plan, intervening where required. By adhering to the action plan, it is expected that the project will evidence the remaining validation requirements, which will be double-checked at approval points.
Where there are serious concerns raised by the PVR report and the Sponsor/SRO fails to take appropriate action, IPA will highlight this to HMT spend team, who may consider escalation to the Major Projects Review Group (MPRG) or impose conditions on spend approvals when it goes to a Treasury Approvals Panel.

# Annex A

As a minimum, the following areas should be assessed in the PVR and addressed in advance of Strategic Outline Business Case being submitted for approval. / These areas must be reviewed during the initial Project Validation Review to assure IPA and HMT of the deliverability of their proposed solution during the validation phase.
Purpose, Policy and Objectives: areas to probe / Is there an agreed understanding of what the desired outcomes are and are they / realistic? / Has the policy, and where applicable the intent and impact of any prior Ministerial announcements, been understood across the policy, delivery and stakeholder communities? / Are the objectives aligned to current organisational objectives? / Does the project align with organisational priorities and with any wider portfolio and national/sector direction? / Has the project scope been defined, documented, and commonly understood by key stakeholders? / Have any policy and delivery assumptions been captured, challenged and agreed with all the key stakeholders? / Can the Department articulate what success would look like and when the project can be considered as closed? / Has the Department assessed its materiality, impact on and relationships with the other projects and activities the Department change and business portfolio? / Has the impact of the project on the Department’s wider change and business portfolio, including in the context of (where appropriate) the Department’s Capital Infrastructure Plan been considered? / Does the business have the capacity and capability to undertake the magnitude of business change envisaged and realise the benefits envisaged? / Are leaders creating an environment for success? / Has alternative options for the commercial model been considered? / Does the commercial model incentivise good practices, innovation? / Has the magnitude of benefits (and dis-benefits) expected been challenged and are they measurable and achievable? / Have the arrangements for managing benefits been assessed and are they realistic?

Affordability and options analysis: areas to probe / Has the Department considered the full extent of policy and delivery options available? Including whether other departments are undertaking or considering similar projects / Have different funding approaches been considered? e.g. grants, philanthropic, private funding / Are scope and schedule variations being assessed and possible impact on the business case considered? / Have different delivery models been considered e.g. agile versus waterfall? (Note the business case so have a minimum of 3 deliverable options should be considered in full) / Has a robust internal feasibility challenge been undertaken? / Is a “discovery” stage envisaged to consider delivery options, and if so it clear what its outcomes are? / Has the associated risks, constraints and impact of the options considered being sufficiently considered? / Is the budget realistic? / Has optimism bias been applied to time, cost or financial estimates, has it been challenged and is it realistic relative to risk? / Has the impact of changing the optimism bias been considered and documented? / Has sufficient analysis been undertaken to support the most likely solution offering the best Value for Money? If not, is there evidence that the likely cost would be justified? / Has the Department considered what form a robust and workable contingency plan would require, should the project be delayed or stopped? / Has this project’s funding priority been agreed in the context of the Department’s Capital Infrastructure Plan and resource spending plans? / Has advice been sought from with Cabinet Office commercial, digital and property related functions (as appropriate) for possible support and guidance? / Has due account in the options been taken of past lessons from similar projects? / If infrastructure is involved has consideration be given to using IPA’s Project Initiation Route Map?
Governance, capability and deliverability: areas to probe / Are fit-for-purpose governance arrangements (including escalation plans) in place? / Are accountabilities and responsibilities understood and defined? / Has a fully resourced project leadership and management framework been developed? / Has the resourcing requirements, capability and capacity, been identified? / Is there a resourcing strategy and plan in place? / Are plans in place to sufficiently mitigate any capacity or capability gaps which may impede delivery? / Is there a commitment from senior stakeholders to provide and empower resources as required? / Has a stakeholder analysis and management strategy been established / Has an adequate communications strategy been established? / Have stakeholders shown that there is the capability, capacity and the will to deliver business change and benefits? / Have critical success factors or a minimal viable product been identified and agreed? / Are the timelines proposed realistic and achievable? / Have the plans been assessed against resource need? / Has a critical path to delivery been sufficiently developed, with key decision points identified? / Have critical success factors been identified? / Are mechanisms in place to manage any change of design/scope? / Have contingency options been considered should delivery be delayed / Is previous departmental delivery performance in planning for business preparation, transition and operational phases being considered and taken into account? / Has the department sufficiently considered its commercial model and contract management framework? / Is the level of risk understood and risk appetite appropriate? / Are plans in place to mitigate any risks, including development of a strategic risk management plan? / Has a funding model and/or expenditure trajectory been mapped out? Is the envisaged spend affordable? / Are the budget and its management arrangements sufficiently robust? / Has the Department (or elsewhere in government) successfully completed projects of similar nature, size and complexity? / Have lessons learned and issues identified during these previous projects informing this project? / Has the need for a delivery partners and possible delivery chain been considered or identified? / Have the legal issues or dependencies (e.g. State Aid approval; procurement timetables) been adequately considered? Are legal advisors engaged? / Have the appropriate regulatory impact assessments been undertaken? e.g. covering equality, sustainability, justice, family / If legislation (primary or secondary) is required are the timelines realistic given other parliamentary business? Has the risk of delay been assessed? / Are there any privacy/IT Security issues? Are security specialist advisors engaged?

Annex B
Resourcing the Review Team

The IPA SDA submits a ‘Resource Request’ to the IPA Resourcing Team and a minimum of a two-person Review Team is selected from the IPA reviewer pool.
Review Team Leader (RTL) is lead facilitator for the review. The RTL is required to ensure that IPA’s agenda and ToR are followed in full. Through challenging discussion, the RTL must ensure that the Review Team has the evidence needed to provide constructive and measurable recommendations where there are concerns or where progress is needed.
The RTL is responsible for the drafting and submission of a review report to IPA and the SRO. The final review report should, ideally, be delivered to the SRO within 5 working days of the review concluding and a copy sent to IPA SDA and Gateway helpdesk. (Gateway.Helpdesk@ipa.gov.uk).
Review Team Member (RTM) works alongside the RTL providing challenging and constructive discussion with the project. The RTM, with input from the IPA SDA, supports the RTL by driving out critical observations and recommendations. Alongside the RTL, the RTM is responsible for co-drafting the report submitted to IPA and the SRO.
An IPA SDA may participate in the review to ensure the team captures the level of detail required to make a valid judgement regarding the project’s deliverability at this stage. The IPA SDA may give direction to the Review Team where they feel the team is heading off-track. It is also useful if a support administrator is available to independently note key issues and support the Review Team with time-keeping and practical support.
Planning Meeting structure
The Planning meeting is managed as a three-part process

Review team only meet: this is an opportunity for the Review Team and the IPA SDA to meet alone to ensure that they fully understand the ToR and review format and confirm any clarification required from the project team at this stage.

Review team and project team join the meeting: this brings together the Review Team, SRO and senior policy or project team members. A presentation should be given by the SRO to cover:
- The project objectives and benefits to be delivered;
- The operating (political, business, financial) environment
- Progress in developing project and key artefacts e.g. initiation documents, delivery models, analysis findings, governance and business case;
- The risk environment
- Current issues and challenges.

The Review Team will have the opportunity to seek clarification and ask questions. The meeting should agree the ToR for the review, those who will be participating and any practical logistics required. At the end of the meeting the Review Team should understand the current position and all the practical issues required to undertake the review.

Review Team only follow-up: The Review Team can share observations and agree review logistical arrangements. The RTL is responsible for liaising with the Department on the detail from this stage.

[inside of the back cover – for printed publications, deliberately left blank]