## Strengthening Defences
APPENDIX 1
Calderdale Flood Action Plan - revisions to 2018 plan
Revisions to action/ organisations/ timeline
Action complete
Action closed
Action moved to another theme
Action is ongoing/business as usual
Action with no current timeline
Strengthening Defences
Action No. 2019 | Action No. 2018 | Action No. 2017 | Original Ref No/Year | Action in 2018 Plan | Revised Action | Agreed Completion Date | Revised Completion Date | Lead Organisation | Revised Lead Orgnisations | Supporting Organisation | Lead Supporting Organisation | Revised Supporting Organisations | Summary of Changes
1 | 1 | 70 | 51/2016 | Introduce the Community Infrastructure Levy in Calderdale, which will allow for potential use on flood risk mitigation schemes. |  | End of 2019 | End of 2020 | Calderdale Metropolitan Borough Council |  |  |  |  | Revised timeline due to adoption of Community Infrastructure Levy.
Appendix 3 and Appendix 2 | 2 and Appendix 2 | 2 | 8/2016 | The Environment Agency will submit a flood management programme on behalf of the Calderdale Flood Partnership for the endorsement of the Regional Flood and Coastal Committee. The programme will be based on evidence of risk and impact and include flood risk reduction schemes and capital maintenance projects. The programme will be refreshed annually. |  | Complete since June 2017, also ongoing |  | Environment Agency |  | Calderdale Metropolitan Borough Council Yorkshire Water |  |  | Action now archived - completed before Sept 2018 - Appendix 3; Action is also ongoing annually- Apendix 2.
2 and Appendix 2 | 3 | 3 | 9/2016 | Compile a detailed register of all flood risk assets, including all potential flood defences, high risk culverts, watercourses, highway drains and other drainage assets, structures and locations. (Links to action 49; 64/2016). |  | Ongoing to end of 2018 | Complete since September 2018, also ongoing | Calderdale Metropolitan Borough Council |  | Yorkshire Water Environment Agency |  |  | Action complete, also ongoing - Appendix 2.
3 | 4 | 4 | 10/2016 | Carry out further investigations into the level of risk of flooding from groundwater, ordinary watercourses and surface water across Calderdale. |  | End of 2021 |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
4 |  |  | 5/2018 | Investigate, develop and deliver flood risk reduction schemes, in addition to those in FRRS 1 and FRRS 2 programmes, identified through a review in 2018 of flood investigations at sites across Calderdale. |  | 2021 onwards |  | Calderdale Metropolitan Bourough Council |  | Environment Agency Yorkshire Water |  |  | No change
5 | 6 | 6 | 19/2016 | Carry out a study to upgrade the existing culvert and reduce the risk of flooding to downstream properties at Stoodley Grange/Lee Bottom Road. |  | 2021 onwards | End of 2020 | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | Revised timeline
6 | 7 | 7 | 20/2016 | Carry out a study of and improvements to the Swineshead Clough reservoir to reduce the risk of flooding from the nearby watercourse. |  | End of 2023 |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
7 | 8 | 8 | 21/2016 | Investigate the condition, location and capacity of the culverted watercourse on the steep hillside at Willowfield Estate to reduce the risk of flooding to nearby houses. |  | 2021 - onwards |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
8 | 9 | 9 | 22/2016 | Update existing surface water management plans using information from studies on the existing drainage system to identify where there is not enough capacity. |  | Ongoing to end of 2019 | Ongoing to end of 2020 | Calderdale Metropolitan Borough Council |  | Yorkshire Water |  |  | Revised timeline
9 | 10 | 10 | 23/2016 | Identify joint schemes to reduce the risk of flooding by better understanding the links between surface water and sewer networks. |  | Ongoing to end of 2019 | Complete since September 2018 | Calderdale Metropolitan Borough Council |  | Environment Agency Yorkshire Water Network Rail |  |  | Action complete
Appendix 3 | 11 | 11 | 25/2016 | Work with partners to investigate the feasibility of measures to reduce sewer flooding in Todmorden. |  | Complete since June 2017 |  | Yorkshire Water |  | Environment Agency Calderdale Metropolitan Borough Council |  |  | Action archived - complete before September 2018 - see Appendix 3.
Appendix 3 | 12 | 12 | 26/2016 | Work with partners to investigate the feasibility of measures to reduce sewer flooding in Brighouse. |  | Complete since June 2017 |  | Yorkshire Water |  | Environment Agency Calderdale Metoprolitan Borough Council |  |  | Action archived - complete before September 2018 - see Appendix 3.
Appendix 3 | 13 | 13 | 29/2016 | Investigate feasibility of measures to solve flooding in properties on Rochdale Road, Walsden. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
10 | 14 | 14 | 30/2016 | Investigate feasibility of measures to solve flooding in properties on Oldham Road, Ripponden. |  | To be confirmed | Complete since September 2018 | Yorkshire Water |  |  |  |  | Action complete
Appendix 3 | 15 | 15 | 32/2016 | Investigate feasibility of measures to solve flooding in properties on Armytage Road, Brighouse. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
Appendix 3 | 16 | 17 | 34/2016 | Investigate feasibility of measures to solve flooding in properties on Prospect Place, Norwood Green, Halifax. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
Appendix 3 | 17 | 18 | 35/2016 | Investigate feasibility of measures to improve free discharge from combined sewer overflow to reduce flooding at Old Bridge Inn, Ripponden. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
11 | 18 | 19 | 70/2016 | Identify and review historical water infrastructure such as old mill ponds, water tanks, dams, land drains, to understand whether they can be reused to reduce flood risk. |  | Ongoing to March 2021 |  | Environment Agency |  | Yorkshire Water Calderdale Metropolitan Borough Council |  |  | No change
Appendix 3 | 19 | 21 | 157/2017 | Complete regional study to understand the impacts of using water supply assets to reduce flooding (flood attenuation). |  | Complete since June 2017 |  | Yorkshire Water |  | Environment Agency |  |  | Action archived - complete before September 2018 - see Appendix 3.
12 | 20 | 22 | 158/2016 | Evaluate the options and costs of works required at the Hebden group of reservoirs in order to utilise them to reduce the risk of flooding. | Evaluate the options, costs and benefits of works required at the Hebden group of reservoirs in order to utilise them to reduce the risk of flooding. | Ongoing to end of 2018 | Ongoing to Spring 2020 | Environment Agency |  | Yorkshire Water |  |  | Timeline revised and action updated.
| 21 | 22 | 158/2016 | Work to agree operational principles for using the Hebden group reservoirs to reduce the risk of flooding whilst also balancing other critical needs including water resources and reservoir safety. |  | Ongoing to end of 2018 |  | Environment Agency / Yorkshire Water |  |  |  |  | Action closed - not reflective of work being delivered.
13 | 22 | 22 | 158/2016 | If cost beneficial and practicable, seek to agree programme for implementation of works required at Hebden group of reservoirs to reduce the risk of flooding. | If cost beneficial and practicable, seek to agree operational principles for using the Hebden group of reservoirs to reduce the risk of flooding. If agreeable secure funding and develop a programme for implementation of works. | Ongoing to end of 2019 | To be confirmed | Yorkshire Water |  | Environment Agency |  |  | Action updated; timeline to be confirmed dependant on progression of action 12.
Appendix 3 | 23 | 23 | 159/2016 | Build a drainage area plan model for Luddenden Foot drainage area zonation. Carry out a full hydraulic and serviceability assessment of foul, combined and surface water network to understand the risk of flooding to the network under a range of conditions. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
Appendix 3 | 24 | 24 | 160/2016 | Build a drainage area plan model for Sowerby Bridge drainage area zonation. Carry out a full hydraulic and serviceability assessment of foul, combined and surface water network to understand the risk of flooding to the network under a range of conditions. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
Appendix 3 | 25 | 25 | 161/2016 | Build a drainage area plan model for Elland drainage area zonation. Carry out a full hydraulic and serviceability assessment of foul, combined and surface water network to understand the risk of flooding to the network under a range of conditions. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
Appendix 3 | 26 | 26 | 162/2016 | Build a drainage area plan model for Hebden Bridge drainage area zonation. Carry out a full hydraulic and serviceability assessment of foul, combined and surface water network to understand the risk of flooding to the network under a range of conditions. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3.
14 | 27 | 28 | 164/2016 | Investigate the lowering of canal pounds, and determine if they could be used to store flood water. |  | Ongoing to end of 2018 | Ongoing to end of 2020 | Canal & River Trust |  |  |  |  | Revised timeline
15 | 28 | 29 | 165/2016 | Study the impact and possibility of using canals to protect against flooding, considering navigational safety (boating customers), water resource losses, damage to canal infrastructure, and the wider network. |  | Ongoing to end of 2018 | Ongoing to end of 2020 | Canal & River Trust |  |  |  |  | Revised timeline
Appendix 2 | 29 | 30 | 167/2016 | Review and map past flood data and information to identify the most significant issues on the canal system, to inform and help prioritise alleviation or mitigation actions on the canal system where cost beneficial. |  | Ongoing to end of 2018 | Ongoing | Canal & River Trust |  |  |  |  | Action in ongoing in response to ongoing flood events - Appendix 2 BAU.
16 | 30 | 5 | 5/2016 | Develop and deliver a flood alleviation scheme for Brighouse |  | Ongoing to end of 2020 | Ongoing to July 2023 | Environment Agency |  | Calderdale Metropolitan Borough Council Yorkshire Water |  |  | Revised timeline
17 | 31 | 31 | 1/2016 | Develop and deliver a flood alleviation scheme for Mytholmroyd. |  | Ongoing to end of 2019 | Ongoing to Summer 2020 | Environment Agency |  | Calderdale Metropolitan Borough Council |  |  | Revised timeline
18 | 32 | 32 | 2/2016 | Develop and deliver a flood alleviation scheme for Hebden Bridge. |  | Ongoing to end of 2020 | Ongoing to March 2023 | Environment Agency |  | Calderdale Metropolitan Borough Council |  |  | Revised timeline
19 | 33 | 33 | 3/2016 | Develop and deliver, where feasible, flood risk management work as part of the first phase of the flood risk reduction schemes at: • Pin Hill Lane, Midgley • Burnt Acres Wood, Callis Bridge • Park Road, Elland • Woodland View, Eastwood • Shop Lock, Todmorden • Nutclough, Hebden Bridge • Bacup Rd, Todmorden |  | Ongoing to 2019/2020 | Complete since September 2018 | Environment Agency |  | Calderdale Metropolitan Borough Council |  |  | Action complete
20 | 34 | 34 | 6/2016 | Carry out improvements to access and telemetry at Hebble Brook screen to prevent blockage of screen and potential flooding. |  | End of 2018 | Complete since September 2018 | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | Action complete
21 | 35 | 35 | 11/2016 | Work with partners to inspect and carry out work to address any structural defects in the Hebble Brook culvert. |  | End of 2021 | Ongoing to March 2022 | Environment Agency |  |  |  |  | Revised timeline
22 | 36 | 36 | 12/2016 | Assess, design and carry out improvements to Cragg Road culvert. |  | 2021 - onwards |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
23 | 37 | 37 | 13/2016 | Repair the Harley Wood bypass channel that is currently in a poor condition. |  | 2022 - onwards |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
24 | 38 | 38 | 15/2016 | Carry out a feasibility study to remove or raise the Kingfisher Chase, Sowerby footbridge that prevents water flowing in times of high floods. |  | 2022 - onwards |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
25 | 39 | 39 | 4/2016 | Develop and deliver (if feasible) flood risk management works at the following locations, as part of the Flood Risk Reduction Schemes Phase 2 (Group A): 1. Shaw Wood Rd., Todmorden 2. Calderside, Hebden Bridge 3. Machpelah screen, Hebden Bridge 4. Copley Village |  | Ongoing to end of 2021 | Ongoing to March 2021 | Environment Agency |  | Calderdale Metropolitan Borough Council Yorkshire Water Network Rail Canal and River Trust |  |  | Revised timeline
26 | 40 | 39 | 4/2016 | Develop and deliver (if feasible) flood risk management works at the following locations, as part of the Flood Risk Reduction Schemes Phase 2 (Group A): 1. Rossendale View / Harvelin Park 2. Railes Close, Midgely 3. Cottonstones |  | Ongoing to April 2020 |  | Calderdale Metropolitan Borough Council |  | Environment Agency Yorkshire Water Canal and River Trust |  |  | No change
27 | 41 | 39 | 4/2016 | Develop and deliver (if feasible) flood risk management works at the following locations, as part of the Flood Risk Reduction Schemes Phase 2 (Group B): 1. Walsden 2. Cross Stone Rd., Todmorden 3. Oak Hill Clough, Todmorden 4. Commercial St., Todmorden 5. Calder-Ryburn, Sowerby Bridge 6. Lower Bank House, Barkisland 7. Dean Clough, Halifax 8. Luddenden Brook |  | Ongoing to March 2024 |  | Environment Agency |  | Calderdale Metropolitan Borough Council Yorkshire Water Network Rail Canal and River Trust
28 | 42 | 40 | 16/2016 | Remove the weir at Lobb Mill to reduce flood levels to reduce the risk of flooding in Todmorden. |  | 2024 - onwards |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
29 | 43 | 41 | 17/2016 | Carry out a study of and improvements to the Shoebroad Clough reservoir to reduce the risk of flooding from the nearby watercourse. |  | 2021 - onwards |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
30 | 44 | 42 | 18/2016 | Improve the culvert to reduce the risk of flooding at Smithy Lane, Colden. |  | 2021 - onwards |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | No change
Appendix 3 | 45 | 43 | 43/2017 | Removal of land drain to solve flooding in properties at West Street, Brighouse. (Follow- on from action 33/2016) |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 3 | 46 | 44 | 37/2016 | Investigate the feasibility of automating the radial gate at Turvin Clough. This would mean the gate could be opened automatically in the event of a flood warning, diverting floodwater away from Turvin Clough, helping to protect properties on Cragg Brook and in Mytholmroyd. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3
31 | 47 | 46 | 44/2016 | Investigate the feasibility of using low risk areas to manage highway flooding from overland flows in a sustainable manner. |  | End of 2018 | End of 2020 | Calderdale Metropolitan Borough Council |  | Environment Agency |  |  | Revised timeline
32 | 48 | 47 | 45/2016 | Develop further planning guidance that encourages sustainable drainage systems in areas with critical drainage problems, and reduces run-off in line with greenfield sites. |  | End of 2018 | Complete since September 2018 | Calderdale Metropolitan Borough Council |  | Yorkshire Water |  |  | Action complete
33 | 49 | 50 | 50/2017 | Create physical demonstration interventions in high profile locations, to showcase and encourage uptake of the principles detailed in the ‘You Can Slow The Flow’ project. Opportunities to be investigated and developed in 2018-19 include: Further promotion using case studies documented through the online resource, including Hebden Bridge Town Hall demonstration; Working with Neighbourhood Development Plans to promote SUDS; Supporting ideas for new urban SUDS sites as they arise and promoting as ‘You Can Slow The Flow’ case studies on completion - expressions of interest include Gibson Mill and Flood Wardens’ stores. | Encourage physical demonstration interventions in high profile locations, to showcase and encourage uptake of the principles detailed in the ‘You Can Slow The Flow’ project. Opportunities to be investigated and developed in 2020-21 include: Further promotion using Opportunity Mapping, documented through the online resource; Further promotion using case studies documented through the online resource, including Hebden Bridge Town Hall and Mytholmroyd Flood Wardens demonstrations; Working with Neighbourhood Development Plans to promote SuDS; Supporting ideas for new urban SUDS sites as they arise and promoting as ‘You Can Slow The Flow’ case studies on completion - expressions of interest include Gibson Mill, further Flood Wardens’ stores, central Mytholmroyd housing redevelopment. | Ongoing to end of 2019 | Ongoing to end of 2021 | Slow The Flow: Calderdale (SOURCE Partnership) |  | SOURCE Partners |  |  | Action and timeline updated
34 | 50 | 51 | 51/2017 | Develop clear online information to enable anyone to identify highway issues (in particular around drainage) which affect flooding. |  | End of 2019 | Ongoing to end of 2020 | Calderdale Metropolitan Borough Council |  |  |  |  | Revised timeline
35 | 51 | 52 | 52/2017 | Change management of drainage gullies to minimise blockage and silting issues; including improved data on condition of drainage gullies to enable smarter, tailored management based on silting levels. |  | Ongoing to end of 2019 | Ongoing to end of 2020 | Calderdale Metropolitan Borough Council |  |  |  |  | Revised timeline
Appendix 3 | 52 | 53 | 53/2017 | Bid for funding to replace existing drainage gulley lids with improved designs. |  | Complete since June 2017 |  | Calderdale Metropolitan Borough Council |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3
36 | 53 | 54 | 54/2017 | Work to enable reporting on online maps regarding location of drainage gulley issues. |  | Ongoing to end of 2019 | Ongoing to end of 2020 | Calderdale Metropolitan Borough Council |  |  |  |  | Revised timeline
Appendix 3 | 54 | 59 | 91/2016 | Carry out structural lining of a sewer in Savile Park Mills and Moorfield Street in Halifax, reducing the risk of flooding in the area. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 2 | 55 | 60 | 60/2017 | Work with stakeholders and communities to create a plan for deploying temporary defences at key locations as part of the CMBC Emergency Procedures Plan | Work with flood groups to support deploying temporary defences at key locations as part of the CMBC Emergency Procedures Plan | Ongoing until end of 2019 |  | Calderdale Metropolitan Borough Council |  | Flood Protection Solutions Hebden Bridge Flood Group |  |  | Action revised and ongoing - Appendix 2
37 | 56 |  | 56/2018 | Following on from investigations to reduce sewer flooding, and depending on PR19 Final Determination, work to secure funding to deliver identified options, in Todmorden, Brighouse and Ripponden |  | Ongoing to March 2025 |  | Yorkshire Water |  | Calderdale Metropolitan Borough Council Environment Agency
Appendix 2 | 57 | 102 | 87/2016 | Deliver a communications and engagement campaign to raise awareness amongst landowners and communities of the roles and responsibilities of managing and maintaining watercourses along with flood risk assets as riparian owners. |  | March 2019 then ongoing | Ongoing | Calderdale Metropolitan Borough Council |  | Landowners Agents Brokers Yorkshire Water National Trust Environment Agency |  |  | Action is ongoing - Appendix 2

## Natural Flood Management
APPENDIX 1
Calderdale Flood Action Plan - revisions to 2018 plan
Revisions to action/ organisations/ timeline
Action complete
Action closed
Action moved to another theme
Action is ongoing/business as usual
Action with no current timeline
Natural Flood Management
Action No. 2019 | Action No. 2018 | Action No. 2017 | Original Ref No/Year | Original Action | Revised Action | Agreed Completion Date | Revised Completion Date | Lead Organisation | Revised Lead Orgnisations | Supporting Organisation | Revised Supporting Organisations | Summary of Changes
38 | 58 | 61 | 61/2017 | Collate and evaluate what is known about the connections between land management and flooding in general, and specifically in relation to the Calder catchment, including a gap analysis to advise further research where appropriate, to help inform strategic priorities for Natural Flood Management and ensure affected communities can better understand that relationship. |  | Ongoing to end of 2019 | Ongoing to October 2020 | Calderdale Metropolitan Borough Council |  | Leeds University - iCASP Environment Agency |  | Revised timeline to reflect revised iCASP catchment modelling project delivery.
39 | 59 | 62 | 63/2016 | Coordinate the production of natural flood management opportunity maps to show places where the risk of flooding could potentially be reduced through NFM techniques, and multiple benefits to people and the environment realised. |  | Ongoing to end of 2019 | Ongoing to October 2020 | Calderdale Metropolitan Borough Council |  | Leeds University - iCASP | Leeds University - ICASP Environment Agency | Revised timeline and update to supporting organisations.
40 | 60 | 64 | 68/2016 | Carry out modelling to identify communities and properties where natural flood management measures could potentially reduce the risk of flooding. |  | Ongoing to end of 2019 | End of 2020 | Environment Agency |  | Calderdale Metropolitan Borough Council Leeds University - iCASP |  | Revised timeline to review outputs of iCASP Calderdale modelling project.
41 | 61 | 65 | 71/2016 | Model the risk of rural highway flooding and resulting impacts. Identify ways of using NFM solutions where practical, for modelled critical flood risk areas (rural highways). |  | Ongoing to end of 2018 | Ongoing to May 2020 | Calderdale Metropolitan Borough Council |  |  |  | Revision to timeline.
42 | 62 | 66 | 72/2016 | Investigate/model the impacts of boundary features to manage water flow pathways and attenuating flows to identify and understand any opportunities to reduce flood risk. Specifically looking at: blocking features in water channels; hedges/walls/gates on the land. |  | Ongoing to end of 2019 | Ongoing to Spring 2020 | Calderdale Metropolitan Borough Council |  | Leeds University - iCASP Environment Agency |  | Revision to timeline.
43 | 63 |  | 63/2018 | Set up an open source to encourage partners to share NFM data and reports |  | March 2019 then ongoing | March 2020 then ongoing | Calderdale Metropolitan Borough Council |  |  |  | Revision to timeline.
44 | 64 |  | 64/2018 | Collate and analyse NFM monitoring data collected through various modelling and partner projects. Identify effective NFM interventions and gaps in data monitoring |  | Ongoing to March 2019 | End of 2020 | Environment Agency |  |  |  | Revised timeline to allow review of iCASP modelling outputs.
45 | 65 |  | 65/2018 | Research the connection between NFM measures delivering overland flow interception on steep slopes and landslides. |  | To be confirmed | Autumn 2020 | Calderdale Metropolitan Borough Council |  | Environment Agency Leeds University |  | Revision to timeline
48 and Appendix 2 | 66 | 69 | 50/2016 | Develop a funding strategy for the Calderdale Natural Flood Management programme, ensuring linkages are made to the Leeds City Region Green Infrastructure Investment Plan and other local, regional and national funding strategies. | Delivery of funding strategy for the Calderdale Natural Flood Management programme, ensuring linkages are made to the Leeds City Region Green Infrastructure Investment Plan and other local, regional and national funding strategies. | Onoing to end of 2018 | Complete since September 2018 and ongoing | Calderdale Metropolitan Borough Council Environment Agency |  | Natural Flood Management Operational Group |  | Action complete and review of progress now ongoing.
49 | 67 | 71 | 64/2016 | List natural flood management structures on an asset register and produce a natural flood management asset map of the catchment. (Links to action 2; 9/2016). |  | Ongoing to March 2019 | Ongoing to February 2020 | Natural Flood Management Operational Group |  | Calderdale Metropolitan Borough Council Environment Agency Slow the Flow |  | Revision to timeline
Appendix 3 | 68 | 72 | 66/2016 | Produce a map of land use to inform potential locations for natural flood management. |  | Complete since June 2017 |  | Environment Agency |  |  |  | Action archived - complete before September 2018 - see Appendix 3
50 | 69 | 73 | 48/2016 | Produce a tree and woodland management strategy for Calderdale which will include strategic actions for the creation and management of woodlands (created by all relevant partners) for natural flood management. |  | Ongoing to Spring 2019 | Complete since September 2018 | Calderdale Metropolitan Borough Council |  | The National Trust Forestry Commission Woodland Trust Treesponsibility Pennine Prospects Yorkshire Water Slow the Flow South Pennine Facilitation Fund White Rose Forest |  | Action complete
51 | 70 | 74 | 74/2016 | Secure GIS data and license to establish existing tree canopy cover in Calderdale as base line to help set targets for tree planting as part of the Leeds City Region wide White Rose Forest Plan. |  | Ongoing to January 2019 | Complete since September 2018 | White Rose Forest Partnership |  |  |  | Action complete
Appendix 3 | 71 | 75 | 65/2016 | Use geographical information systems and partnership analysis of Yorkshire Water owned-land across the region to find the best areas to create woodland and carry out natural flood management. |  | Complete since June 2017 |  | Yorkshire Water |  | White Rose Forest Environment Agency Calderdale Metropolitan Borough Council Woodland Trust Forestry Commission |  | Action archived - complete before September 2018 - see Appendix 3
53 | 72 | 77 | 77/2017 | Complete tree planting at Hardcastle Craggs and plant 50,000 trees in Upper Calder catchment by the end of 2018. | Complete tree planting at Hardcastle Craggs and plant 50,000 trees in Upper Calder catchment by March 2020. | Ongoing to March 2019 | Ongoing to March 2020 | Treesponsibility |  | Woodland Trust White Rose Forest Moors for the Future |  | Revision to timeline
54 | 73 | 78 | 49/2016 | Production of revised Clough Woodland Project Guiding Principles to support the following activities across the South Pennine Moors National Character Area: • Appropriate (careful and considered) design of landscape scale native broadleaved woodland creation schemes, to deliver benefits to reduce downstream flood risk, stabilise eroding soils, improve water quality and enhance biodiversity. • Gaining consent from Natural England under the Habitat Regulations, to ensure woodland creation does not have a detrimental impact on the interest features of designated/protected areas. |  | Ongoing to end of 2018 | Complete since September 2018 | Moors for the Future Partnership |  | Clough Woodland Project Partners Calderdale Metropolitan Borough Council SOURCE Partnership White Rose Forest South Pennines Local Nature Partners |  | Action complete
55 | 74 | 79 | 76/2016 | Work to address soil erosion and landslide stabilisation in Upper Calder Catchment: Treating landslips with fascines; Removing Himalayan balsam; Removing/thinning shallow rooted beech trees to encourage woodland understorey. |  | Ongoing to end of 2020 |  | Treesponsibility (SOURCE Partnership) |  | National Trust Facilitation Fund Sticks and Stones Calder Future Calderdale Metropolitan Borough Council |  | No change
56 | 75 | 81 | 81/2017 | Deliver physical NFM interventions to slow the flow and contribute to reducing downstream flood risk in high priority sub catchments, particularly at Hebden Water, Walsden, Calder from Source, Cragg Vale. Develop demonstration sites at multiple locations including Hardcastle Craggs and Gorpley. |  | Ongoing to end of 2020 |  | Treesponsibility (SOURCE Partnership) |  | Environment Agency Calderdale Metropolitan Borough Council Slow the Flow National Trust EGG Consultants Cragg Vale Business Park |  | No change
57 | 76 | 82 | 78/2016 | Carry out a project to create plate weirs, woody debris and leaky dams on sites within and adjacent to Crimsworth Dean Beck, Hardcastle Craggs and Hebden Water to reduce flood water and flood peak. |  | Ongoing to end of 2021 |  | National Trust |  | Slow the Flow Natural England Environment Agency Calderdale Metropolitan Borough Council Yorkshire Water Various private landowners |  | No change
58 | 77 | 84 | 52/2016 | Investigate how heather cutting, as a preferred management technique, could be introduced into future land management agreements. Produce clear guidance for partners on basis of best practice. |  | Ongoing to June 2020 |  | Natural England |  |  |  | No change
59 | 78 | 86 | 79/2016 | Through the support of MoorLIFE 2020, identify priority blanket bog restoration areas and appropriate techniques within the South Pennine Moors Special Area of Conservation located in the Upper Calder Valley. |  | Ongoing to end of 2020 | Ongoing to February 2022 | Moors For The Future |  | Pennine Prospects Yorkshire Wildlife Trust Natural England Environment Agency Yorkshire Water Moorland Association National Trust |  | Revision to timeline - project funding extended.
60 | 79 | 88 | 83/2016 | Improve Clifton Beck as part of the Clifton Beck Diffuse Pollution Project to also reduce the risk of flooding through: Creating buffer zone strips, planting trees and plants on river banks, restricting livestock access to the beck and removing invasive non-native plants. |  | End of 2021 | Ongoing to January 2022 | Yorkshire Wildlife Trust |  | Environment Agency Calder & Colne Rivers Trust Riverfly Landowners |  | Revision to timeline.
61 | 80 | 89 | 80/2016 | Create wetland habitat and wet woodland, linked to environmental education work at Brearley Fields, Mytholmroyd. |  | 2021 |  | Calderdale Metropolitan Borough Council |  | Canal & River Trust Calder & Colne Rivers Trust Environment Agency Yorkshire Wildlife Trust |  | No change
62 and Appendix 2 | 81 | 90 | 84/2016 | Develop a long-term, evidence based strategy for managing invasive plant species. The strategy will identify the damage caused, ways of managing both invasive species and the soil, and how we will fund and carry out this work. | Delivery of the strategy to reduce INNS in Calderdale. | Ongoing to end of March 2019 | Complete since September 2018, also ongoing | Yorkshire Wildlife Tust and Yorkshire Invasives Species Forum |  | Calderdale Metropolitan Borough Council Environment Agency Riparian owners Calder Future Calder Valley Clean-up Team Treesponsibility River Stewardship Company Yorkshire Water Canal & River Trust |  | Action complete, updated ongoing action - see Appendix 2
64 | 82 | 91 | 85/2016 | Prepare an evidence based channel maintenance programme (to include vegetation, gravel, silt and debris) that has been developed with the community and which allocates activity between the Environment Agency and other (including voluntary sector) providers. |  | Ongoing to January 2019 | Complete since September 2018 | Environment Agency |  | Riparian owners Community organisations Calder Future Calder Valley Clean-up Team Calderdale Metropolitan Borough Council Treesponsibility |  | Action complete
Appendix 3 | 83 | 93 | 89/2016 | Investigate with local groups carrying out river stewardship work where access to river channels needs to be improved to enable community led maintenance. |  | Complete since June 2017 |  | Environment Agency |  | Calderdale Metropolitan Borough Council Canal & River Trust Landowners Calder Future Calder Valley Clean-up team |  | Action archived - complete before September 2018 - see Appendix 3
65 | 84 |  | 84/2018 | Promotion of monitoring protocol for all new projects: ICASP development of monitoring protocol building on existing DEFRA NFM protocol |  | December 2018 then ongoing | Ongoing to March 2020 | Calderdale Metropolitan Borough Council |  | Environment Agency Leeds University - iCASP |  | Revision to timeline.
66 | 85 |  | 85/2018 | Scope a clough woodland project to increase the extent of woodland at Hardcastle Crags to several Yorkshire Water sites in the Calder Valley. To be achieved by working with a range of partner organisations and private landowners. |  | Ongoing to end of 2020 |  | National Trust |  | Woodland Trust, Treesponsibility, Whiterose Forest, Yorkshire Water, South Pennines Facilitation Group, Pennine Prospects |  | No change
67 | 86 | 96 | 54/2016 | The Calderdale Catchment plan will draw from the research projects into the learning identified across the 4 Pioneer projects. These should identify insights in terms of working with natural capital and partnership working, recognising the intrinsic value of the environment across the health and economy agendas and helping to achieve environmental outcomes for local communities through broader collaboration. |  | Ongoing to 2020 |  | Environment Agency |  |  |  | No change
68 and Appendix 2 | 87 | 97 | 57/2016 | Develop a plan to coordinate the engagement of landowners and land managers, (across the Calderdale Flood Partnership), to support landowners and land managers in identifying and implementing a range of natural flood management measures; and publicise the extent of engagement. | Deliver plan to coordinate the engagement of landowners and land managers, (across the Calderdale Flood Partnership), to support landowners and land managers in identifying and implementing a range of natural flood management measures; and publicise the extent of engagement. | Ongoing to March 2019 | Complete since September 2018, also ongoing | Calderdale Metropolitan Borough Council |  | South Pennines Facilitation Fund Moors for the Future Yorkshire Wildlife Trust Treesponsibility Slow the Flow Natural England Pennine Prospects Environment Agency Canal & River Trust |  | Action complete, now business as usual - see Appendix 2.
Appendix 3 | 88 | 98 | 58/2016 | Create natural flood management guidance, specific to Calderdale, for farmers, landowners and other practitioners similar to that being produced in the Dales National Park. |  | Complete since June 2017 |  | Natural Flood Management Operational Group |  | Environment Agency Yorkshire Dales National Park White Rose Forest Aire & Calder Catchment Partnership Natural England Leeds City Region Natural Flood Management Task Group |  | Action archived - complete before September 2018 - see Appendix 3
69 | 89 | 99 | 59/2016 | Through the Countryside Stewardship Scheme and the South Pennine Facilitation Fund, encourage more farmers in specific areas to carry out and maintain natural flood management for the 2018 application year. |  | Ongoing to end of 2018 | Complete since September 2018 | Natural England |  | Yorkshire landowners Environment Agency Calderdale Metropolitan Bourough Council |  | Action complete
70 | 90 | 101 | 62/2016 | Work with landowners/occupiers to progressively review the three existing burning consents and agreements as part of the consideration for the long-term management requirements for the restoration of blanket bog. |  | 2019 onwards |  | Natural England |  | Yorkshire Water Private Landowners |  | No change
Appendix 3 | 91 | 105 | 56/2016 | Undertake habitat regulations assessment of all emerging Local Plan policies and proposals prior to publication of the plan in the autumn of 2017. |  | Complete since June 2017 |  | Calderdale Metropolitan Borough Council |  | Natural England Environment Agency |  | Action archived - complete before September 2018 - see Appendix 3
71 | 92 |  | 92/2018 | Seek funding for and conduct an ecological data review of target NFM catchments with outputs to include ecological maps, the identification of gaps in survey data and recommendations for survey priorities and techniques, to ensure known areas of ecological importance are not compromised by NFM interventions. Seek funding for and implement a prioritised programme of ecological surveys in target NFM catchments to identify any unknown sites of existing ecological importance. | Seek funding for and produce ecological RAG mapping for target NFM catchments to enable the identification of land for which landowners should be approached and ecological assessments undertaken. Seek funding for and implement a prioritised programme of ecological surveys of land prioritised by the ecological RAG mapping. | February 2019 November 2020 | Ongoing to January 2020 Ongoing to October 2020 | Calderdale Metropolitan Borough Council |  |  |  | Update to action and timeline
46 |  |  | New | To assist with providing evidence for NFM interventions, install river level monitoring sensors to enable river flows to be measured at a local scale |  | End of 2020 |  | Slow the Flow |  | Environment Agency |  | Action revised and transferred from community resilience
47 |  |  | New | Share learning from the developing DEFRA England Peat Strategy and current national moorland pilots to improve understanding of baseline function and input to development of a new programme of Pennine moorland restoration post 2020 where relevant to support Calderdale NFM. Investigate opportunities to produce a summary report on current condition of Calderdale moorland. |  | Ongoing to December 2020 |  | Environment Agency |  | Moors for the Future |  | New action
52 |  |  | New | Enhance the resilience of habitats in the catchment against future risks such as climate change and wildfire – considering likelihood and severity of the risks; protecting all associated outcomes, NFM, clean water provision and storage, carbon capture, biodiversity, local economy and community. |  | To be confirmed |  | Moors For The Future |  | Calderdale Metropolitan Borough Council Environment Agency National Trust Yorkshire Water |  | New action in response to moorland fires. Timeline to be confirmed dependant on funding.
63 |  |  | New | Develop new initiatives for sustainable control and management of invasive species (follow- up to action 62, 84/2016) |  | Ongoing to December 2021 |  | Calderdale Metropolitan Borough Council |  | Environment Agency Calder Future Calder Vally Clean-up Team River Stewardship Company Yorkshire Wildlife Trust |  | New action resulting from delivery of action 81/2018

## Resilient Infrastructure
APPENDIX 1
Calderdale Flood Action Plan - revisions to 2018 plan
Revisions to action/ organisations/ timeline
Action complete
Action closed
Action moved to another theme
Action is ongoing/business as usual
Resilient Infrastructure
Action No. 2019 | Action No. 2018 | Action No. 2017 | Original Ref No/Year | Original Action | Revised Action | Agreed Completion Date | Revised Completion Date | Lead Organisation | Revised Lead Orgnisations | Supporting Organisation | Revised Supporting Organisations | Summary of Changes
72 | 93 | 107 | 107/2017 | Recover (remove the equipment) from the following sites Hebble End 2243, HX7 6AT, Mayroyd 641, HX7 6AT, Calder Mill 196, HX7 5NA, Market Street 633, HX7 6AT, Cheetham St 1827, HX7 8EJ to new sites at Bridge Lanes and Hollins Place. |  | End of 2020 | Complete since September 2018 | Northern Power Grid |  |  |  | Action complete.
73 | 94 | 108 | 40/2016 | Relocate current power substations at: Calder House Mill 1225, HX7 5QF; Scout Road 864, HX7 5DU; Der Street Mills 1145, OL14 5QT; Gauxholme 383, OL14 7PD. |  | End of 2018 End of 2017 End of 2022 | End 2020 Scout Road - Complete End 2022, Spring 2020 | Northern Power Grid |  |  |  | Revised timelines for three of the substantions; work at Scout Rd. complete.
74 | 95 | 109 | 41/2016 | Improve resilience of power substations at Walton St 775, HX6 1AN, Lock Hill Mill 577 HX6 2LA. |  | End of 2018 | Complete since September 2018 | Northern Power Grid |  |  |  | Action complete.
75 | 96 | 113 | 104/2016 | Design and delivery of scheme to manage railway-related flood risk (surface water) at three sites east of Luddendenfoot. |  | Ongoing to March 2019 | Deferred to 2021/2022 | Network Rail |  | Environment Agency |  | Revision to timeline.
76 | 97 | 114 | 114/2017 | Develop programme and secure funding to improve the resilience of the main highway routes in Calderdale, in particular the A646 in the Upper Calder Valley. (Links to actions 17 - 18 [1 and 2/2016], 35[52/2017]) and 93[147/2016]) |  | Ongoing to summer 2019 | Ongoing to 2022 | Calderdale Metropolitan Borough Council |  | Environment Agency Department for Transport |  | Revision to timeline.
Appendix 3 | 98 | 115 | 96/2016 | Repair and maintain rights of way to prevent them from flooding and becoming eroded. |  | Complete since June 2017 |  | Calderdale Metropolitan Borough Council |  | Local Access Forum Pennine Prospects Canal & River Trust CROWS |  | Action archived - complete before September 2018 - see Appendix 3
77 | 99 | 118 | 28/2016 | Replace storm pumps and control panel at Elland Lowfield sewage pumping station. |  | Ongoing to end of 2019 | Complete since September 2018 | Yorkshire Water |  |  |  | Action complete.
Appendix 3 | 100 | 120 | 36/2016 | Investigate the feasibility of repairing abutments of reservoir overflow crest bridge at Baitings. |  | Complete since June 2017 |  | Yorkshire Water |  |  |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 3 | 101 | 124 | 166/2016 | Ensure relevant water control assets on the Rochdale Canal have been updated and proportionate maintenance plans are in place. |  | Complete since June 2017 |  | Canal & River Trust |  |  |  | Action archived - complete before September 2018 - see Appendix 3
78 | 102 | 125 | 168/2016 | Review feeder arrangements for the Rochdale Canal, to identify where improvements could be made, taking into account heritage and environmental factors. |  | Ongoing to mid-2018 | Ongoing to mid-2020 | Canal & River Trust |  |  |  | Revision to timeline
79 | 103 | 126 | 126/2017 | As part of the preparation of their first National Flood Risk Management Strategy in 2017, the Canal & River Trust will use experiences and lessons learnt on the Rochdale Canal, from the December 2015 floods, to inform and influence national approaches and policy development in relation to flood risk management. The creation of the Strategy will also present relevant outputs to feed into the Calderdale Flood Action Plan work, particularly actions 14-15, ([164, 165/2016]) and ongoing actions. |  | Ongoing to end of 2018 | Ongoing to late 2020 | Canal & River Trust |  |  |  | Revision to timeline.
80 | 104 | 127 | 127/2017 | Complete outstanding Calderdale highways recovery work, subject to funding, including work or repairs to damaged bridges – collapsed bridges, scour damage, repairs to inverts; landslips, and repairs to a culvert, a wall and drainage. | Complete outstanding Calderdale highways recovery work at Scout Road, Phase 3 Drainage Works. | Ongoing to August 2019 | Ongoing to June 2020 | Calderdale Metropolitan Borough Council |  |  |  | Action and timeline updated to reflect outstanding work.
81 | 105 | 128 | 42/2016 | Find information on landslips that have occurred in the past and investigate the possibility of them happening again. |  | Ongoing to end of 2018 | Ongoing to end of 2020 | Calderdale Metropolitan Borough Council |  |  |  | Revision to timeline.
82 | 106 |  | 106/2018 | Carry out temporary stabilisation on landslips where ongoing risks have been identified and where required develop capital schemes to deliver long term solutions |  | Ongoing to end of 2020 |  | Calderdale Metropolitan Borough Council |  |  |  | No change
Appendix 2 and Appendix 3 | 107 and Appendix 2 | 129 | 95/2016 | Ongoing inspections of critical assets such as silt traps, gullies and screens to inform inspections and maintenance. |  | Complete since June 2017 and ongoing |  | Calderdale Metropolitan Borough Council |  | Public to report blockages |  | Action archived - complete before September 2018 - see Appendix 3, also ongoing action Appendix 2
83 and Appendix 2 | 108 | 130 | 86/2016 | Host an annual maintenance meeting to discuss and review the planned maintenance work of Calderdale Metropolitan Borough Council, Environment Agency and Canal & River Trust. Involve local community representatives to promote a joined up approach and increase community involvement. |  | Spring 2019 | Complete since September 2018 and ongoing | Calderdale Metropolitan Borough Council |  | Local community representative Calder Future Calder Valley Clean-up Team Canal & River Trust |  | Action complete and ongoing.
Appendix 3 | 109 | 131 | 88/2016 | Support communities to share knowledge of how to report maintenance issues and requirements, who to report to and the roles, remits and responsibilities of organisations |  | Complete since June 2017 |  | Calderdale Metropolitan Borough Council |  | Canal & River Trust Environment Agency |  | Action archived - complete before September 2018 - see Appendix 3
84 | 110 |  | 110/2018 | Develop maintenance plans for critical flood resilient infrastructure identified in the Calderdale Metropolitan Borough Council Flood Asset Register. |  | End of April 2020 | Ongoing to October 2020 | Calderdale Metropolitan Borough Council |  | Environment Agency |  | Revision to timeline due to resources.

## Community Resilience
APPENDIX 1
Calderdale Flood Action Plan - revisions to 2018 plan
Revisions to action/ organisations/ timeline
Action complete
Action closed
Action moved to another theme
Action is ongoing/business as usual
Action with no current timeline
Community Resilience
Action No. 2019 | Action No. 2018 | Action No. 2017 | Original Ref No/Year | Original Action | Revised Action | Agreed Completion Date | Revised Completion Date | Lead Organisation | Revised Lead Orgnisations | Supporting Organisation | Revised Supporting Organisations | Summary of Changes
85 | 111 | 134 | 109/2016 | Link willing shops to the local flood hubs so they can be used in the event of a future flood, work to ensure coverage is robust and exploring provision of other local amenities. |  | Ongoing to March 2019 | Ongoing to December 2020 | Calderdale Metropolitan Borough Council |  | Banks and local business; NHS/ Health emergency planning Adult health and social care team Staying Well |  | Revised timeline
86 | 112 | 137 | 106/2016 | Improve communications with public transport operators to enable them to better plan adjustments to their services and to issue travel warnings. |  | March 2019 | 2016 Onwards | Calderdale Metropolitan Borough Council |  | Environment Agency West Yorkshire Combined Authority |  | Revised timeline
87 | 113 | 139 | 111/2016 | Work with schools across Calderdale to provide evacuation and invacuation training to support school emergency plans. |  | Ongoing to Summer 2019 |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  | No update to timeline
Appendix 2 and Appendix 3 | 114 and Appendix 2 | 146 | 114/2016 | Maintain a database of volunteers willing to offer support and help in response to flood events and ongoing public education and awareness of flooding. |  | Complete since June 2017 / Also ongoing |  | Calderdale Metropolitan Borough Council |  | Local Resilience Forum Community Resilience Operations Group Town Parish councils |  | Action archived - complete before September 2018 - see Appendix 3, also ongoing action Appendix 2
Appendix 2 and Appendix 3 | 115 and Appendix 2 | 150 | 117/2016 | Ongoing updates to key household information for households at risk of flooding, provided on laminated cards and fridge magnets, as and when contact information changes. |  | Complete since June 2017 / Also ongoing |  | Calderdale Metropolitan Borough Council |  | Community Resilience Operations Group Public Health Infection Prevention & Control Team |  | Action archived - complete before September 2018 - see Appendix 3, also ongoing action Appendix 2
88 | 116 | 151 | 118/2016 | Carry out a questionniare to find out how many properties are still without flood risk insurance cover and promote Flood Re insurance scheme to qualifying households. |  | End of September 2018 | Spring 2020 | Calderdale Metropolitan Borough Council |  | Relevant insurance companies |  | Revised timeline to enable promotion of FloodRe
Appendix 3 | 117 | 154 | 121/2016 | Issue and delivery of work through business' resilience grants to be completed; Business team also making linkages through business advice and practices for flood preparation. |  | Complete since June 2017 |  | Calderdale Metropolitan Borough Council |  |  |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 2 | 118 | 155 | 122/2016 | Establish and implement a communications and marketing plan around preparedness and behaviour change for the three target sectors of owner occupiers, private tenants and private landlords (and letting agents); with a specific focus on improving and updating content for the ‘Eye on Calderdale' website. Messages also required on maintenance, servicing and repair of flood resistance works such as pumps, flood doors, barriers, air vent covers etc |  | November 2018 | Ongoing | Calderdale Metropolitan Borough Council |  | Private landlords National Landlord Association |  | Action is now ongoing - see Appendix 2
89 | 119 | 159 | 126/2016 | Target schools at high risk to raise awareness of flooding with students and staff to develop knowledge and skills and to keep safe during flooding. |  | Ongoing to September 2020 |  | Environment Agency |  | Calderdale Metropolitan Borough Council Community Resilience Operations Group |  | No change
Appendix 3 | 120 | 161 | 128/2016 | Review initiatives carried out under the Joseph Rowntree Foundation Kindliness initiative locally and nationally, identify best practice and what would support community resilience in flooding. |  | Complete since June 2017 |  | Calderdale Metropolitan Borough Council |  | Community Resilience Operations Group |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 3 | 121 | 163 | 130/2016 | Completion of Level 2 work of Strategic Flood Risk Assessments, to inform the Local Plan policies and land allocation. |  | Complete since June 2017 |  | Calderdale Metropolitan Borough Council |  | Environment Agency |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 2 | 122 | 165 | 132/2016 | Develop and maintain a portfolio of case studies from owner occupiers, private landlords and private tenants linking in to social media and press releases to communicate key messages around flood reslience, resistance works and behavioural change. Use case studies in comms & marketing campaign across various channels of internet, social media, etc |  | To be confirmed | Ongoing | Calderdale Metropolitan Borough Council |  |  |  | Action is ongoing - see Appendix 2
90 | 123 | 168 | 168/2017 | Review delivery of Calderdale Metropolitan Borough Council actions resulting from the Council S19 report (lead local authority requirement following major flood event) on the winter 2015 floods; future S19 reviews will be incorporated into the learning and Council actions resulting from any other Calderdale floods. |  | Ongoing to March 2019 | Ongoing to May 2020 | Calderdale Metropolitan Borough Council |  |  |  | Revision to timeline
91 | 124 | 170 | 135/2016 | Work with Google to use Environment Agency data from the Environment Agency flood warning system to enable greater visibility of flood warnings and to alert those at flood risk based on their location. (National action) |  | Ongoing to end of 2018 | Complete since September 2018 | Environment Agency |  | Google |  | Action complete
| 125 | 172 | 137/2016 | Help communities at high risk of flash flooding to install their own methods of monitoring weather and river conditions and triggering alerting systems. |  | Ongoing to end of 2018 |  | Slow the Flow |  | Community Resilience Operations Group Environment Agency |  | Action closed, related action substantially revised and moved to NFM theme
92 and Appendix 2 | 126 | 174 | 140/2016 | Agreements being developed with mobile phone companies to enable recruitment of customers to the flood warning system through an opt-out approach. (National action) |  | Ongoing to Winter 2018/2019 | Complete since September 2018 and also ongoing | Environment Agency |  | Community Resilience Operations Group O2 Other mobile phone companies |  | Action complete and now ongoing - see Appendix 2
Appendix 3 | 127 | 175 | 141/2016 | Support and, where needed, provide training to professional partners, including flood groups, on using social media to raise awareness of the risk of flooding, flood warnings and how to be better prepared for flooding. |  | Complete since June 2017 |  | Environment Agency |  | Calderdale Metropolitan Borough Council |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 3 | 128 | 177 | 144/2016 | Provide more online forecasts, including communicating the probabilities of flooding and flash flooding, measuring river levels and showing forecast river level up to 36 hours in advance. |  | Complete since June 2017 |  | Environment Agency |  | Community Resilience Operations Group |  | Action archived - complete before September 2018 - see Appendix 3
Appendix 3 | 129 | 178 | 145/2016 | Investigate how we can integrate risks from groundwater flooding into our existing flood warning service, and help local councils reach those people at risk of flooding from local sources. |  | Complete since June 2017 |  | Environment Agency |  | Calderdale Metropolitan Borough Council Community Resilience Operations Group |  | Action archived - complete before September 2018 - see Appendix 3
93 | 130 | 180 | 147/2016 | Investigate producing maps (preferably in real time) that show roads affected by and impassable due to flood water and make them available including the use of social media. | Explore additional ways to communicate information about roads affected by and impassable due to flood water during incidents, such as real-time mapping. | Ongoing to March 2019 | Ongoing to end of 2020 | Calderdale Metropolitan Borough Council |  |  |  | Action revised and update to timeline.
94 and Appendix 2 | 131 | 181 | 106/2016 | Installation of variable message signing at key decision points across Calderdale’s major highway network to warn drivers of closures and incidents. |  | Spring 2019 and ongoing | Complete since September 2018 and also ongoing | Calderdale Metropolitan Borough Council |  |  |  | Action complete and now ongoing - see Appendix 2
95 | 132 | 184 | 149/2016 | Review and communicate how flood recovery grants were allocated in 2015 to 2016. Consider any policy modifications to promote take up. |  | September 2019 | Spring 2020 | Calderdale Metropolitan Borough Council |  |  |  | Update to timeline
96 | 133 | 190 | 190/2017 | Delivery of mental health support, information and advice to improve health and well-being of Todmorden residents. |  | Ongoing to May 2019 | Ongoing to 2020 | Healthy Minds |  | Community Foundation for Calderdale |  | Update to timeline
97 | 134 |  | 134/2018 | Development and delivery of mental health support, information and advice to improve health and well-being and resilience of Calder valley residents vulnerable to or affected by flooding |  | Ongoing to Spring 2021 |  | Community Foundation for Calderdale |  | Healthy Minds |  | No change