## Ongoing
Appendix 2 - Ongoing Actions - Business as Usual (2019)
Strengthening Defences
2018 Action No | 2017 Action No | Original Ref No/ Year | What we’re going to do | When we will do it by | Who’s leading | Who’s supporting
BAU | 1 | 7/2016 | Implement the Calderdale flood investment plan to secure match funding. | Ongoing | Calderdale Metropolitan Borough Council | Environment Agency
2/BAU | 2 | 8/2016 | The Environment Agency will submit a flood management programme on behalf of the Calderdale Flood Partnership for the endorsement of the Regional Flood and Coastal Committee. The programme will be based on evidence of risk and impact and include flood risk reduction schemes and capital maintenance projects. The programme will be refreshed annually. | Annual/Ongoing | Environment Agency | Calderdale Metropolitan Borough Council Yorkshire Water
BAU | 45 | 43/2016 | Investigate surface water flow routes and ponding, consider using sustainable drainage systems more widely across the catchment. | Ongoing | Calderdale Metropolitan Borough Council
BAU | 48 | 46/2016 | Continue to support community led projects that raise awareness of the benefits of sustainable drainage systems, as well as further promoting the Construction Industry Research and Information Association sustainable drainage systems manual. | Ongoing | Calderdale Metropolitan Borough Council | Yorkshire Water
BAU | 55 | 97/2016 | Cut grass three times a year at Environment Agency owned flood embankments and washlands in the Upper Calder Valley, allowing inspection of assets and maintenance of grass cover to protect banks from erosion. Also carry out vermin control to ensure that the banks are structurally sound. | Ongoing | Environment Agency
BAU | 56 | 98/2016 | Inspect and maintain assets and structures in the Upper Calder Valley that the Environment Agency owns, three times a year. | Ongoing | Environment Agency
BAU | 57 | 99/2016 | Carry out a programme of inspecting culverts to check that they are structurally sound and that water can flow freely through them. | Ongoing | Environment Agency
BAU | 58 | 100/2016 | Clear out trash screens and silt traps at Environment Agency assets in the Calder Valley on a weekly basis. | Ongoing | Environment Agency
BAU | New |  | Continue inspection of assets identified in the asset record and draft an inspection and maintenance plan for CMBC assets. Asset inspection and management will be ongoing work with time limited actions identified if refurbishment or replacement is required. | Ongoing | Calderdale Metropolitan Borough Council
3 | 3 | 9/2016 | Compile a detailed register of all flood risk assets, including all potential flood defences, high risk culverts, watercourses, highway drains and other drainage assets, structures and locations. | Ongoing | Calderdale Metropolitan Borough Council
29 | 30 | 167/2016 | Review and map past flood data and information to identify the most significant issues on the canal system, to inform and help prioritise alleviation or mitigation actions on the canal system where cost beneficial. | Ongoing | Canal & River Trust
55 | 60 | 60/2017 | Work with flood groups to support deploying temporary defences at key locations as part of the CMBC Emergency Procedures Plan | Ongoing | Calderdale Metropolitan Borough Council | Flood Protection Solutions Hebden Bridge Flood Group
57 | 102 | 87/2016 | Deliver a communications and engagement campaign to raise awareness amongst landowners and communities of the roles and responsibilities of managing and maintaining watercourses along with flood risk assets as riparian owners. | Ongoing | Calderdale Metropolitan Borough Council | Yorkshire Water Environment Agency
Natural Flood Management
2018 Action No | 2017 Action No | Original Ref No/ Year | What we’re going to do | When we will do it by | Who’s leading | Who’s supporting
BAU | 63 | 67/2016 | Identify places where creating woodland and changing the way woodland is managed will reduce the risk of flooding. | Ongoing | Forestry Services (Forestry Commission) | Yorkshire Water National Trust Other owners of woodland holdings Environment Agency White Rose Forest
BAU | 68 | 50/2016 | Ongoing investigation of new and existing funding sources identified by partners for potential collaborative bids, including Leeds City Region Local Growth Fund. | Ongoing | Natural Flood Management Operational Group | Calderdale Metropolitan Borough Council Environment Agency South Pennines Facilitation Fund Natural England Yorkshire Wildlife Trust Canal & River Trust Moors for the Future
BAU | 83 | 69/2016 | Use hydrological and land cover information to identify priority areas for grip blocking (blocking drainage ditches to hold water) within the Special Area of Conservation (SAC). Continue to block a further 110 kilometres of blanket bog grips across the Upper Calder Valley, including Walshaw Moor. | Ongoing | Natural England | Environment Agency Moors for the Future University of Leeds
BAU | 85 | 81/2016 | Carry out, where appropriate, parts of the South Pennine Moors Special Areas of Conservation / Special Protected Areas Site Improvement Plan to restore and stabilise peat, which could reduce run-off. | Ongoing | Natural England | Yorkshire Water Environment Agency Moors for the Future Landowners
BAU | 87 | 82/2016 | Build on past work to restore moorland on Yorkshire Water land by improving the habitat in target locations, for example by trialling the introduction of sphagnum moss. | Ongoing | Yorkshire Water | Natural England Moors for the Future Tenants and Commoners
BAU | 92 | 85/2016 | Support community-led channel maintenance and stewardship, including the development of further sources of sustainable funding and investment. | Ongoing | Environment Agency | Riparian owners Community organisations Calder Future Calder Valley Clean-up Team Treesponsibility River Stewardship Company
BAU | 94 | 101/2016 | In addition to our annual maintenance programme, where necessary, remove any debris and vegetation that is causing a blockage in rivers and channels that could increase the risk of flooding. | Reactive as required | Environment Agency
BAU | 95 | 53/2016 | Share good practice and provide guidance in drawing up maintenance agreements for natural flood management with landowners and land managers. | Ongoing | Calderdale Metropolitan Borough Council | Natural Flood Management Operational Group Pennine Prospects Slow the Flow
BAU | 100 | 61/2016 | Work with landowners and land managers to collate information on and improve existing drainage infrastructure where it will have flood risk benefits. | Ongoing | Calderdale Metropolitan Borough Council
BAU | 103 | 55/2016 | Facilitate and co-ordinate Calderdale Flood Partnership Board responses to government consultations on catchment management in relation to flood mitigation and alleviation. | Ongoing | Natural Flood Management Operational Group | Calderdale Flood Partnership Board
BAU | 104 | 55/2016 | Proactively raise policy issues related to catchment management and flood mitigation with government ministers and committees, and bodies representing land owners and land managers. | Ongoing | Natural Flood Management Operational Group
66 | 69 | 50/2016 | Delivery of funding strategy for the Calderdale Natural Flood Management programme, ensuring linkages are made to the Leeds City Region Green Infrastructure Investment Plan and other local, regional and national funding strategies. | Ongoing | Calderdale Metropolitan Borough Council Environment Agency | Natural Flood Management Operational Group
81 | 90 | 84/2016 | Delivery of the strategy for reducing INNS in Calderdale. | Ongoing | Yorkshire Wildlife Trust and Yorkshire Invasives Species Forum | Calderdale Metropolitan Borough Council Environment Agency Riparian owners Calder Future Calder Valley Clean-up Team Treesponsibility River Stewardship Company Yorkshire Water Canal & River Trus
87 | 97 | 57/2016 | Delivery of plan to coordinate the engagement of landowners and land managers, (across the Calderdale Flood Partnership), to support landowners and land managers in identifying and implementing a range of natural flood management measures; and publicise the extent of engagement. | Ongoing | Calderdale Metropolitan Borough Council | South Pennines Facilitation Fund, Moors for the Future Yorkshire Wildlife Trust Treesponsibility Slow the Flow Natural England Pennine Prospects Environment Agency Canal & River Trust
Resilient Infrastructure
2018 Action No | 2017 Action No | Original Ref No/ Year | What we’re going to do | When we will do it by | Who’s leading | Who’s supporting
BAU | 110 | 38/2016 | Maintain and improve the security of the gas network through generic actions across the network: Introducing syphon points as standard on replacement schemes; Adding new water extraction equipment; Investing more in managing pressure remotely to monitor changes in pressure and adjust them to avoid loss of supply; Investing in overcrossing, aiming in the long term to put vulnerable crossings underground. | Ongoing | Northern Gas Network | Calderdale Metropolitan Borough Council
BAU | 116 | 14/2016 | Identify sections of the towpath that can be hardened to improve resilience, developing an ongoing programme for improvements subject to funding. | Ongoing | Canal & River Trust
BAU | 129 | 95/2016 | Ongoing inspections of critical assets such as silt traps, gullies and screens to inform inspections and maintenance. | Ongoing | Calderdale Metropolitan Borough Council | Public to report blockages
108 | 130 | 86/2016 | Host an annual maintenance meeting to discuss and review the planned maintenance work of Calderdale Metropolitan Borough Council, Environment Agency and Canal & River Trust. Involve local community representatives to promote a joined up approach and increase community involvement. | Annual/Ongoing | Calderdale Metropolitan Borough Council | Local community representative Calder Future Calder Valley Clean-up Team Canal & River Trust
Community Resilience
2018 Action No | 2017 Action No | Original Ref No/ Year | What we’re going to do | When we will do it by | Who’s leading | Who’s supporting
BAU | 132 | 105/2016 | Review the resilience and business continuity of essential emergency and community services such as fire, police stations and community facilities, including schools. | Annual/ Ongoing | Calderdale Metropolitan Borough Council | Environment Agency West Yorkshire Local Resilience Forum
BAU | 135 | 135/2017 | Review business continuity plans on a regular basis, ensuring assets and people are protected and able to function in a flood, including emergency duty teams in place for adult and children’s services and children and older people’s homes. | Ongoing | Calderdale Metropolitan Borough Council
BAU | 136 | 152/2016 | Work with the Integrated Commissioning Board and Commissioning Plan to ensure that statutory and voluntary organisations have actions in existing plans to support vulnerable people during and after flood events. | Ongoing | Calderdale Metropolitan Borough Council | Integrated Commissioning Board Community and Voluntary Sector
BAU | 138 | 110/2016 | Hold an annual flood emergency practice day (scoped with partners) in each area throughout Calderdale to practice flood plans. | Annual/Ongoing | Calderdale Metropolitan Borough Council | Environment Agency Flood warden groups Yorkshire Water Community Resilience Operations Group Community Foundation for Calderdale
BAU | 140 | 111/2016 | Work with nurseries across Calderdale to provide evacuation and invacuation training to support nursery emergency plans. | Ongoing | Calderdale Metropolitan Borough Council
BAU | 141 | 111/2016 | Work with housing providers of vulnerable residents (care and nursing homes) across Calderdale to provide evacuation and invacuation training to support emergency plans. | Ongoing | Calderdale Metropolitan Borough Council
BAU | 141 | 111/2016 | Work with housing providers of vulnerable residents (Registered Providers) across Calderdale to provide evacuation and invacuation training to support emergency plans. | Ongoing | Calderdale Metropolitan Borough Council
BAU | 143 | 143/2017 | Ongoing regular communication, training, support and sharing of knowledge and experience across networks of flood wardens and flood groups. | Ongoing | Community Resilience Operations Group | Environment Agency Calderdale Metropolitan Borough Council
BAU | 145 | 145/2017 | Ongoing volunteer recruitment to attract additional flood warden volunteers to the existing groups and continue support and training for new flood wardens. | Ongoing | Environment Agency | Calderdale Metropolitan Borough Council Community Resilience Operations Group
BAU | 146 | 114/2016 | Maintain a database of volunteers willing to offer support and help in response to flood events and ongoing public education and awareness of flooding. | Ongoing | Calderdale Metropolitan Borough Council | Local Resilience Forum Community Resilience Operations Group Town Parish councils
BAU | 148 | 148/2017 | Ongoing maintenance of community support hub and training and support to volunteers running community hub. | Ongoing | Calderdale Metropolitan Borough Council
BAU | 149 | 116/2016 | Work with flood groups to produce community flood plans. | Ongoing | Environment Agency | Calderdale Metropolitan Borough Council Community Resilience Operations Group
BAU | 150 | 117/2016 | Ongoing updates to key household information for households at risk of flooding, provided on laminated cards and fridge magnets, as and when contact information changes. | Ongoing | Calderdale Metropolitan Borough Council | Community Resilience Operations Group Public Health Infection Prevention & Control Team
BAU | 153 | 120/2016 | Continue to support the development and promotion of Watermark for local flood fundraising. | Ongoing | Community Foundation For Calderdale | Calderdale Metropolitan Borough Council
BAU | 160 | 127/2016 | Work with the Health and Wellbeing Board of Calderdale Metropolitan Borough Council to plan for the effects of future flooding on people's health. | Ongoing | Calderdale Metropolitan Borough Council | Yorkshire Water Environment Agency
BAU | 162 | 129/2016 | Continue to develop the community led web portal ‘Eye on Calderdale', providing up to date information about flooding and resilience across Calderdale, including review of the current website. | Ongoing | Calderdale Metropolitan Borough Council | Environment Agency Community Resilience Operations Group
BAU | 164 | 131/2016 | Consult with planners and architects on CMBC’s Local Plan for proposed development sites and the Supplementary Planning Document offering guidance on reducing flood risk at new developments. | Ongoing | Calderdale Metropolitan Borough Council | Town and Country Planning Association Environment Agency Yorkshire Water
BAU | 166 | 133/2016 | Signpost homeowners who are renovating or constructing new property to advice on flood resilience and resistance works to minimise the impact of future floods. This will include information on any financial assistance, when it is available. | Ongoing | Calderdale Metropolitan Borough Council | Environment Agency
BAU | 167 | 167/2017 | Delivery of FloodSave - to encourage businesses and residents to save monthly for new flood events. Each £ saved is equally matched, savers can access up to £2000 in flood events. | Ongoing | Community Foundation For Calderdale | Calderdale Credit Union
BAU | 169 | 134/2016 | Assess and improve the performance of Environment Agency flood warnings (coverage and triggers) so that people know what to expect earlier and have more time to take effective action. | Ongoing | Environment Agency | Community Resilience Operations Group
BAU | 176 | 142/2016 | Investigate the potential use and introduction of automated alerts and warnings to residents (linked to river level monitoring), through telephone, text and email. (National Programme) | Ongoing | Environment Agency | Community Resilience Operations Group
BAU | 179 | 146/2016 | Investigate Improvement of existing flood warning measures by prioritised hydrometry: the network of rain gauges throughout Calderdale, using telemetry, the CCTV network and Flood Forecasting Centre. | Ongoing | Environment Agency | Calderdale Metropolitan Borough Council Community Resilience Operations Group
BAU | 182 | 90/2016 | Work with partners, charities and local groups to continue to produce a regular newsletter that shows the local community the actions on flood recovery and updates on resilience news from partners, charities and community groups. | Bi-monthly /Ongoing | Calderdale Metropolitan Borough Council | Environment Agency Canal & River Trust Yorkshire Water Calder Future Calder Valley Clean-up Team
BAU | 188 | 154/2016 | Provision of skips to support flood clean-ups as and when required. | Ongoing | Calderdale Metropolitan Borough Council Flood Hubs
BAU | New |  | Ensure counselling, welfare support and advice to people, to reduce the emotional and psychological effects of flooding, is embedded into the community recovery framework. | Ongoing | Calderdale Metropolitan Borough Council | Public Health
118 | 155 | 122/2016 | Implement a communications and marketing plan around preparedness and behaviour change for the three target sectors of owner occupiers, private tenants and private landlords (and letting agents); with a specific focus on improving and updating content for the ‘Eye on Calderdale' website. Messages also required on maintenance, servicing and repair of flood resistance works such as pumps, flood doors, barriers, air vent covers etc. | Ongoing | Calderdale Metropolitan Borough Council
122 | 165 | 132/2016 | Develop and maintain a portfolio of case studies from owner occupiers, private landlords and private tenants linking in to social media and press releases to communicate key messages around flood reslience, resistance works and behavioural change. Use case studies in comms & marketing campaign across various channels of internet, social media, etc | Ongoing | Calderdale Metropolitan Borough Council
126 | 174 | 140/2016 | Agreements being developed with mobile phone companies to enable recruitment of customers to the flood warning system through an opt-out approach. (National action) | Ongoing | Environment Agency | Community Resilience Operations Group O2 Other mobile phone companies
131 | 181 | 106/2016 | Installation of variable message signing at key decision points across Calderdale’s major highway network to warn drivers of closures and incidents. | Ongoing | Calderdale Metropolitan Borough Council