Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Prosperity Fund: Global Business Environment Programme
Programme Value: £30m		Review Date: November 2019
Programme Code: GB-GOV-50-PF-08-GBE (including GB-GOV-3-PF-GBE-911; GB-GOV-3-PF-GBE-913; GB-GOV-3-PF-GBE-921)	Start Date: November 2017	End Date: March 2021

Summary of Programme Performance
Year	2018/19	2019/20	2020/21	2021/22
Programme Score	B	A
Risk Rating	Moderate	Moderate

Summary of progress and lessons learnt since last review

Since the last review in December 2018 the programme has geographically diversified into 3 new countries: Philippines, Malaysia and Vietnam in January 2019. The diversification was originally agreed by the then SRO and JFU in late 2018 and change request papers were submitted and approved by the Portfolio Board in July 2019.

The Theory of Change for Country Engagements has been reviewed and a new Theory of Change for the Global Window Initiative was produced. This exercise in turn has produced both country and global window results frameworks, which in turn inform the programme scorecard that includes indicators. These were approved at the May 2019 Partnership Council meeting.

In March 2019 the programme held a peer to peer learning event in Johannesburg, which had a focus on gender and inclusion, and the project has made a concerted effort and good progress in integrating these themes at the global and country project levels. Given the diverse nature of the policy work under the country engagement window, teams have identified various channels to incorporate gender-informed and gender-targeted activities in the projects’ design, with scope to do more on wider aspects of inclusion.

The programme has achieved 8 reforms since the last annual review in Brazil, Nigeria, Philippines and South Africa. Validation of these reforms is now ongoing.

The 1st Cycle Evaluation report was submitted to the programme team on 14th November 2019 and is currently being reviewed by the programme team and SRO. The Evaluation included a deep dive into South Africa, including a country visit to meet key stakeholders. The programme has also been able to upload indictors, baseline and first year values onto the Prospero system.

List of recommendations for the next year

1. It is important that the programme measures the difference reforms make to the real economy and not just on paper. The World Bank should set a baseline for their impact indicators and a methodology should be put in place for tracking progress and validating reforms achieved after the programme closes. [Responsibility: World Bank]
2. Building on its environmental and social framework, the World Bank should ensure it has a mechanism in place for assessing and tracking its interventions to ensure they do no harm. [Responsibility: World Bank]
3. Consider whether there is scope to surpass business case expectations on inclusion, by supporting more reforms that benefit large numbers of poor and/or socially excluded women and men. For example, by targeting reforms in sectors where poor women and men or other excluded groups are most commonly employed. [Responsibility: World Bank]
4. FCO makes it part of the job description of its PF-funded staff at Post to share updates on the passage of reforms with DIT colleagues (where relevant to UK and international investors) and leverage soft power benefits for the programme [Responsibility: FCO programme team]
5. Agree on the approach to categorisation of outputs and indicators for the remainder of the programme in conjunction with the Prosperity Fund evaluation provider. The arrangement will continue to allow annual reviews to assess progress against the business case and avoid any deviation to reporting frameworks. Reporting from the World Bank should be aligned to this approach. [Responsibility: World Bank and FCO programme team]
6. Estimate how much each indicator in the programme scorecard will change, year-on-year. Projecting how much each indicator will change, year-on-year, will make it easier to track progress of the outputs and make decisions on how to adapt programming to ensure outcomes are met. [Responsibility: World Bank]
7. As many of the end of programme indicator targets have already been achieved or are exceeding expectations at this stage of the programme, the programme team and the World Bank should consider agreeing more stretching targets for the remainder of the programme (where appropriate) [Responsibility: World Bank and FCO programme team]
8. The World Bank should consider the scope for strengthening cross-learning between countries and with other HMG programmes, following the positive examples in this review period. [Responsibility: World Bank]
9. The FCO programme team should reinforce guidance on the roles and responsibilities of PF-funded HMG staff at Post [Responsibility: FCO programme team]
10. Proactively notify posts about opportunities for the UK to be visible in its support for World Bank-implemented GBEP activities, where this visibility will not unduly compromise the real and perceived independence and impartiality of World Bank advice. [Responsibility: World Bank]
11. Strengthen relationships with key government of Nigeria stakeholders around business environment reform. [Responsibility: World Bank]
12. The World Bank should increase its communication and dissemination of outputs from the global influence window. Publishing or linking programme outputs to the programme website might be one way of doing this. [Responsibility: World Bank]
13. FCO should agree with the World Bank when and where the UK Aid and Prosperity Fund logos should feature on Global Influence Initiative publications funded by GBEP to increase visibility of PF funding [Responsibility: FCO programme team]

1. The FCO programme team should establish value for money indicators and systematically monitor these and hold regular discussions with the World Bank to ensure value for money is being achieved. [Responsibility: FCO programme team]
2. Improve communication with Post before and after key meetings with the World Bank. For example, give Posts at least a week to comment on World Bank Progress Reports before the GBEP London programme team meets the World Bank to discuss the report. Posts only had two working days to provide comment on the Y2H1 Progress Report before FCO programme team met World Bank for progress meeting. Giving additional time would allow Posts to be able to fully feed in their views on the programme including the alignment of interventions to host government objectives. [Responsibility: World Bank and FCO programme team]
3. The World Bank should ensure it demonstrates the linkages between business community engagements (through workshops for example) in its development of linked outputs (e.g. new strategies or policies) across all markets, using the best practices adopted in Indonesia.

List of Acronyms

DIT – Department for International Trade
FCO – Foreign and Commonwealth Office
DFID – Department for International Development
FDI – Foreign Direct Investment
GBE/GBEP – Global Business Environment Programme
G&I – Gender and Inclusion
HMG – Her Majesty’s Government
IBEP – Improving Business Environment Programme (another name for GBEP)
JFU – Joint Funds Unit
MNC – Multinational Corporation
N/A – Not applicable
OECD – Organisation for Economic Co-Operation and Development
PF – Prosperity Fund
SMEs – Small and medium-sized enterprises
SRO – Senior Reporting Officer
VfM – Value for money
WBG – World Bank Group

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-50-PF-08-GBE
DevTracker Link to Log frame:	Not yet available

The Global Business Environment Programme is a partnership between the Prosperity Fund, delivered by the Foreign & Commonwealth Office (FCO) and the World Bank Group (WBG), delivered by the International Finance Corporation (IFC) through their Improving Business Environment Programme window (IBEP). Total funding allocated is £30million over a 4-year period, of which £28.5m is managed by the WBG via a single donor trust fund.

The programme aims to support the business environment through two main channels: global research and learning activities – the Global Influence Initiative (GII) – and through initially six country programmes, now expanded to nine country programmes. The primary impact envisaged is to support c. 20-25 major economic reforms, resulting in savings to business and additional investment across the countries concerned. Several of these reforms will also help host countries to attract foreign investment and spur economic growth and higher incomes. This in turn will generate secondary benefits for UK and international businesses, in the form of greater investment and export opportunities. Conservative estimates (set out in the business case) suggest that benefits to the UK alone could range from £50 to £170m over 10 years. Actions to realise secondary benefits are for HM Government (not the World Bank Group). Other shorter-term secondary benefits will include “soft power” benefits with host governments.

The core objectives of the global engagement work through the GII (22% of the total budget) are to use the World Bank’s global reach and analytical work to support the design and implementation of reforms in the focal countries:
1. Fill existing gaps in business environment data and research.
2. Advance thought leadership by shaping frontier business environment topics
3. Reinforce the analytical foundation of various business environment reform areas.
4. Strengthen the design and implementation of business environment reforms in MICs.
5. Foster peer to-peer learning across a wide cross-section of reforming countries.

At the country level, (66% of the budget) the objectives are to:
1. Strengthen business regulations and practices.
2. Enhance business competitiveness
3. Catalyse shared prosperity through support to subnational efforts and equity.

The major components include analytics and diagnostics, reform toolkits and adaptive evidence-based policy design. It covers both cross-sectoral and sector dimensions with main components around FDI linkages, quality infrastructure and standards, good regulatory practice, markets and competition. Key outputs from the Programme are the flagship Investment Competitiveness Reports, biennial forums, and technical support to investment entry, promotion, competition and Ease of Doing Business reforms.

The GBEP aims to demonstrate added value through alignment with the overall Prosperity Fund Theory of Change, as set out in the Business Case. The GBEP aims to contribute to 3 of the 5 intermediate outcomes identified for the Prosperity Fund – Trade; Financial and Economic Reform; and Ease of Doing Business. Programme activities are intended to contribute to overall impacts envisaged in the original business case: creation and growth of firms; more and better jobs (including for women and youth); greater aggregate productivity; higher investment and trade flows; increased international and UK exports and market access; and increased international and UK investments.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (Primary Purpose – inclusive growth, gender equality, women’s economic empowerment and poverty reduction)

The business case sets out that the programme is seeking to achieve 25 reforms over its lifetime. The majority of these are expected to take place during years 3 and 4 of the programme, but the programme has seen some early successes at outcome level with 8 reforms being reported so far in Brazil (4 reforms), Nigeria (1 reform), Philippines (2 reforms) and South Africa (1 reform). The nature of these reforms varies by context from reforms to business regulation, competition policy, public private dialogue and support to an investment ombudsman. One of the first reforms achieved by the programme was in April 2019 when the Brazilian state of Ceará drew upon the reform recommendations and action plan prepared by the programme to adopt new environmental licence legislation which streamlines procedures and reduces the number of licences required from 3 to 1. It is anticipated that this will result in compliance cost savings to the private sector and contribute to inclusive growth by encouraging investment in one of Brazil's least developed states. For each of the reforms achieved, the programme plans to validate that these have been implemented not just on paper and that the private sector is benefitting from it. The majority of this validation will take place after year 3 of the programme and beyond. The World Bank continually assess the likelihood of success of each reform targeted and has a process in place for adapting their approach to ensure the programme stays on track.

The programme has 4 impacts that it is seeking – improved business/investor perception, reduced costs/private sector savings, investment generated and more open and competitive markets – but currently has no indicators targets to monitor these against so it will be difficult to track progress going forwards. It is essential that the programme team works with the World Bank to set reasonable targets at impact level that are aligned with the objectives in the business case and can be used to assess whether the programme has successfully met these objectives and whether it is delivering value for money, with a clear methodology of how they will track this. Whilst the majority of reforms being targeted will have clear, tangible benefits for the private sector and therefore should support increased growth in partner countries, research suggests that some of the targeted reforms risk delivering only marginal benefits. This highlights the importance of the programme validating the actual impact of reforms, and where little impact is found, using findings to prioritise the pursuit of more impactful reforms in future. For example, in South Africa and Nigeria, reforms have been implemented that reduce the number of days to start a business and evidence has shown that these types of reforms have limited impact on business activities or growth.[1]
[1] Research drawing on World Bank Enterprise Surveys reveals however that the average time taken to register a business deviates substantially in many developing countries from estimates based on businesses completing all official requirements. The same research also indicates that streamlining official requirements does not lead to a reduction in the actual amount of time taken by businesses to register. Source: Hallward-Driemeier, Mary and Lant Pritchett (2015) ‘How Business is Done in the Developing World: Deals versus Rules’, Journal of Economic Perspectives—Volume 29, Number 3—Summer 2015—Pages 121–140.

The business case sets out that the reforms being targeted will lead to increased competitiveness and distribution of resources more widely which will support the programme to reduce poverty by creating jobs, improving access to capital and delivering inclusive growth. The programme does not currently have indicators in place to track impacts on growth or poverty reduction, so it is difficult to measure whether it is on track to meet these objectives; however, it is too early in the programme for these benefits to be realised in any case. The business case makes a number of commitments on gender and inclusion, which are discussed under output 4, and the programme has made good progress in integrating a gender lens across the span of interventions through establishing a gender and inclusion action plan. Under the global influence window, the programme has developed a number of tools for doing this and is implementing them alongside gender-focused activities in each country – for example, where it considered which sectors would benefit women most when recommending sectors for investment promotion to the Government of Pakistan. However, to address gender and inclusion more widely in line with the Prosperity Fund’s Gender and Inclusion Policy, it will need to more clearly reflect previous PF G&I advice, policy and guidance provided on addressing both gender and wider inclusion for more inclusive growth. It is not clear whether the Bank has a methodology for tracking or assessing that interventions do no harm, but there is no evidence to suggest that this is a present concern and if the ambitions in the G&I action plan are achieved then it is likely that positive benefits for women’s economic empowerment will be realised.

The business case made practical commitments on both gender and inclusion[2] and specifically mentioned positive impacts for women and youth. The revised G&I policy and guidance was subsequently shared and presented to the World Bank and country partners, with recommendations by the FCO’s social development adviser. However, the World Bank’s G&I action plan still has a narrow focus on gender, reflecting the earlier policy. The programme’s inclusion agenda focuses on geographical, organisational and nationality dimensions, and does not clearly address wider inclusion dimensions, beyond gender. The programme could do more to ensure socially excluded groups (other than women) benefit from its activities, for example through targeting sectors where the greatest number of poor people are employed or are consumers.
[2] The PF Gender Policy was updated to a Gender and Inclusion Policy in March 2018, after the business case was drafted so this is unsurprising

Recommendation: It is important that the programme measures the difference reforms make to the real economy and not just on paper. The World Bank should set a baseline for their impact indicators and a methodology should be put in place for tracking progress and validating reforms achieved after the programme closes.

Annual outcome assessment (Secondary Benefits)

Many of the reforms targeted by the programme would contribute to host country economic growth, if implemented.[3] All other things being equal, this growth will lead to higher incomes, a share of which consumers will spend on imports, some of which are UK exports. Meanwhile, many GBE-supported reforms would also make host countries more attractive to UK and international investors. The removal of certain restrictions on foreign direct investment in Indonesia, and improved efficiency and transparency of Brazil’s anti-dumping framework are good examples. As reforms like these are implemented, the programme plans to start estimating how much additional investment flows into host countries as a result.
[3] This view is supported by World Bank analysis, and by FCO and DIT staff interviewed at Posts.
For reforms to spur greater investment however, UK and international businesses need to be aware that a reform has taken place. The Department for International Trade (DIT), through its extensive ongoing communication with UK businesses, can play a valuable role in informing British investors about reforms. FCO staff at Post should make DIT colleagues aware when reforms happen, so that DIT can notify relevant UK firms. Many already do this and with little additional effort, it could and should become standard practice.

GBEP also generates secondary benefits by enhancing UK soft power. Interviewees told the review team how GBEP has enhanced the UK’s reputation in Indonesia and Pakistan for supporting economic reform.[4] In some other host countries however, Posts feel that host governments are insufficiently aware of the UK’s role in funding GBE, with opportunities for visibility missed. Greater soft power could also be garnered through more visibility of the FCO’s funding of business environment thought leadership through GBE’s global influence window. See section E (risk) for recommendations on these points.
[4] DFID also funds a business environment reform programme in Pakistan, and we assume HMG’s recognition owes to both programmes.
Recommendation: FCO makes it part of the job description of its PF-funded staff at Post to share updates on the passage of reforms with DIT colleagues (where relevant to UK and international investors) and leverage soft power benefits for the programme.
Overall output score and description

The World Bank monitors progress of the programme via a programme scorecard (equivalent to a logframe) at Global and Country engagement levels which has clear indicators included at output, outcome and impact levels and targets for achievement at the end of the programme. However, output categories had not been defined in line with the theory of change set out in the business case (due to the way output indicators are structured in the programme scorecard) and, through the annual review process, the review team worked with the World Bank and programme team to define outputs (and associated impact weighting) for the purpose of the review. The programme scorecard does not include targets to be met within each review period, which made it difficult for the review team to make an objective judgement if progress is on track. The programme team has taken a subjective view on whether outputs have been met, taking into account an assessment of whether indicators appear to be on track at this stage of the programme and other relevant information contained in the twice-annual progress reports.

The majority of output indicators appear to be either on track or have already been achieved two years into the programme, which is positive. Implementation for each output is going well, with every output scoring a strong A or above. Indicators are aggregated from each of the country scorecards and it will be important for the programme to monitor progress at this level as well as the aggregate to ensure that strong performance overall does not mask poor performance in any particular countries.

Recommendation: Agree on the approach to outputs for the remainder of the programme in conjunction with the Prosperity Fund evaluation provider. The arrangement will continue to allow annual reviews to assess progress against the business case and avoid any deviation to reporting frameworks. Reporting from the World Bank should be aligned to this approach.

Recommendation: Estimate how much each indicator in the programme scorecard will change, year-on-year. Projecting how much each indicator will change, year-on-year, will make it easier to track progress of the outputs and make decisions on how to adapt programming to ensure outcomes are met.

Key lessons

The multi-country nature of the programme supports value for money by allowing managers to reallocate resources from countries where changes in local context make results less likely, to countries where greater results are likely, helping to support achievement of the programmes overall objectives rather than a siloed approach to each individual country.

The multi-country approach also allows lessons to be learned from other countries in the programme. One example of doing this at the programme level is through the peer to peer learning event in March 2019. There has been good practice of this taking place at the country level – the programme facilitated a knowledge exchange mission between Vietnam and Malaysia to learn about the Vietnamese experience of partnering with multinational enterprises and the private sector to support SMEs and to develop local suppliers’ capabilities. This provided valuable insights on the importance and ‘how-to‘ of establishing a competitive industry ecosystem. The Philippines Anti-Red Tape Authority also participated in a study tour in Malaysia on better regulation. These are great examples of the benefit of a global programme, facilitating knowledge exchange to share best practice and drive greater value for money from the programme’s interventions.

Recommendation: The World Bank should consider the scope for strengthening cross-learning between countries and with other HMG programmes, following the positive examples in this review period.

Key actions

The FCO programme team should reinforce guidance on the roles and responsibilities of PF-funded HMG staff at Post. Specifically, this should include details on escalation routes where there are disagreements between the HMG advisor and the World Bank team in country. Posts play a valuable role in helping London to monitor the alignment of GBEP in country activity with PF/GBEP strategy and help the World Bank to ensure its activities complement other donor initiatives and avoid duplication. This function is working well. However, the role of, and importance given to, the country sounding board is not always clear. In some countries this is referred to as a ‘steering board’ and such terms imply that staff at Post can and should directly influence the World Bank’s GBEP in-country strategy and tactics, bypassing London and Washington, which could create some tension or confusion, which could be avoided through clarity from the FCO London team about what role HMG advisors at post play in shaping the programme.
Summary of changes to the logframe since the last annual review

The Country Engagement theory of change has been updated in line with development of the programme scorecards and is different to that set out in the business case, as identified in the first programme evaluation. A Global Initiative Window theory of change and scorecard has also been developed. The two new theory of changes were approved at the May 2019 Partnership Council Meeting.

Summary of responses to issues raised in previous annual reviews

The structure of outputs being used for this annual review does not replicate last year’s annual review and mapping of last year’s recommendations against these new outputs is not possible. A summary of progress against last year’s recommendations is provided in this section instead, rather than under output. Of 22 recommendations made in the 2018 Annual Review, 19 have been implemented. Two of the three not yet implemented are dealing with secondary benefits and the development of engagement plans to the realisation of secondary benefits. We make further recommendations in this review that supersedes last year recommendations.

The final recommendation from the 2018 annual review: “An update of the contribution of other donor activity linked to this programme should be completed to ensure that leverage is properly captured in the Value for Money calculation” was for implementation by the World Bank Group and will need to be followed up.

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Clients and stakeholders engaged in business environment reform
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Number of beneficiaries/entities that receive assistance	70	82 (117%)
Number of workshops, training events, seminars, conferences, etc.	90	71 (79%)
Number of participants in workshops, training events, seminars, conferences, etc.	1,800 (at least 35% women; at least 20% from private sector)	3,852 (214%) / 49% of attendees women; 18% from private sector

Key Points

The programme has assisted more host country government counterparts than targeted. The number of workshops, seminars and events organised by GBEP has also exceeded the programme’s end target. So has the cumulative number of participants attending these events, largely because more invitees are attending dialogue events than the World Bank expected. Women’s participation in programme events and workshops has also exceeded expectations. Only private sector participation, at 18% of attendees, is falling (slightly) short of expectations. This however is a consequence of higher than expected public sector participation; the actual number of private sector participants is higher than expected.

In general, the quality of relationships between World Bank staff and host country governments remains high. In Indonesia for example, the GBE-funded investment climate analysis has influenced thinking at the highest levels of government on the need for business environment reform. In Malaysia, meanwhile, the willingness of government counterparts to share data analysis demonstrates trust in the World Bank partnership. There have however been relationship challenges in Nigeria, which the World Bank is addressing.

Recommendations

- Strengthen relationships with key government of Nigeria stakeholders around business environment reform.
- As many of the end of programme indicator targets have already been achieved or are exceeding expectations at this stage of the programme, the programme team and the World Bank should consider agreeing more stretching targets for the remainder of the programme (where appropriate).[5]
  [5] For this output, this recommendation applies particularly to the ‘number of participants’ indicator

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Evidence collection, evidence informed analyses, strategies and policies
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Number of databases/surveys/diagnostics for policy (disaggregated by gender)	50	29 (58%)
Number of policy reports (e.g. assessments, manuals, policy notes) completed (disaggregated by gender)	70	46 (66%)
Number of new strategies/ policies drafted or contributed to the drafting	35	14 (40%)

Key Points

This output is well on track to achieve the set targets. The first two years have been well utilised to collect baseline evidence, which in turn has contributed to the implementation strategy going forward. Over 60% (75 of 120) of planned diagnostics and policy reports have been completed and this has largely been achieved through engagement of 80 government counterpart agencies across nine countries in substantive policy dialogue. These include databases, surveys, assessments, legal reviews, and policy notes, and form the substantive basis of inputs into institutional strategies, draft policies and recommendations to shape legal and regulatory changes.

Of the three indicators, two are well above the 50% mark at the end of Year 2 indicating sound progress. The third indicator is currently at 40% of the target. This, however, is a combination of several factors - the addition of 3 countries to the programme in Year 2, in lieu of an overall reduction of budget might have shifted focus. Despite this, the programme has achieved early wins in the new market of Vietnam. WBG built on the findings of an earlier project in Vietnam to complete Phase II of Pilot Supplier Development Programme.  This had two-fold benefits – on one hand it demonstrated continuity to Vietnam government securing their support of the programme through a good VfM proposition and, secondly, it improved performance score in key competitiveness areas of selected 45 firms by almost 20%, creating a strong primary benefit narrative.  This has been a positive move forward despite a relatively late start. In certain markets, e.g. Nigeria, on the other hand, work has been stalled owing to on-going challenges with local administration. Once resolved, the output will be well on track in Year 3 and 4 to achieve the set targets. WBG must ensure that there is a focus on delivering activities and interventions in each country as per the workplan so they each achieve their targets at the country level, as well as at the programme level. There is a risk that the programme becomes overly focused on programme level targets and that provides a disincentive to pursue activities in more challenging contexts. It is important for value for money in a global level programme that this is managed correctly by both the World Bank and FCO.

There is evidence of World Bank using their country projects to consult the business community on policy issues within this programme. Particularly in Indonesia, there was positive feedback from Post that inputs from business community have fed into the WBG diagnostics and in turn their recommendations. The feedback has been secured through bilateral meetings with law firms, industry associations and individual firms or through public consultation workshops, which is best practice. The depth and frequency of these engagements currently vary country to country, but the World Bank should make attempts to harmonise the approach as much as possible following successful models such as the one in Indonesia.
Recommendations

The World Bank should ensure it demonstrates the linkages between business community engagements (through workshops for example) in its development of linked outputs (e.g. new strategies or policies) across all markets, using the best practices adopted in Indonesia.
## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Legal, regulatory and administrative recommendations
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Recommendations to laws/regulations/amendments/codes or recommendations to improve regulatory and legal environment	25	14 (56%)
Recommendations on procedures to be improved or eliminated	15	9 (60%)
Recommendations on business-enabling standards	2	1 (50%)

Key Points

The programme is on a comfortable track against this output. Based on the diagnostic work and consultative workshops with policymakers, the programme has delivered a total of 40 recommendations so far on institutional, legal, and regulatory changes. As a result, all three indicators have achieved 50% or more of their assigned targets within Year 2. Recommendations have been made across several pillars of work across the nine countries: Business Regulation Reform, Competition Policy Advocacy and Reform, Opening Markets and Sector specific competitiveness. Early successes have been recorded in Brazil (3 reforms), Philippines (2 reforms) and Nigeria (1 reform). These wins are scheduled to be validated in Year 3 going forward. Feedback from posts at target countries suggested that World Bank has actively engaged business communities leveraging industry forums, industry associations such as British business groups and has worked with DIT in certain markets. The broad consensus is that the reforms targeted are in line with respective host governments’ objectives and in line with the Prosperity Fund narrative. World Bank themselves acknowledge this to be an ambitious target but remain committed to achieving it. This output should be closely monitored next year, as most targets are meant to be achieved in Year 3. There is a strong case for WBG to use learnings from countries covered so far and pilot similar projects quickly in the others (where applicable).

Particularly positive feedback was received from Brazil, South Africa, Vietnam and Pakistan on this output. Despite some success, concerns were expressed by markets such as Philippines and Nigeria. All countries broadly agreed with the identified pillars of intervention in their respective markets. They are comfortable with WBG’s methodology and proposed Theory of Change. Posts such as Brazil, where early output wins have been recorded, remain hugely enthusiastic about the effectiveness and potential impact of the programme in the long run. However, concern remain on areas ranging from inclusive growth to G&I narrative, and this needs to be addressed by each country. It is acknowledged by both WBG and FCO that most results will not be evident before Year 3 and 4. In markets where some output targets have already been achieved, there were questions on whether the right interventions were chosen if results are being generated ahead of schedule. These concerns can be addressed through active engagement between posts and programme team, working with WBG to draw out the programme objectives for all stakeholders.

Recommendations

As many of the end of programme indicator targets have already been achieved or are exceeding expectations at this stage of the programme, the programme team and the World Bank should consider agreeing more stretching targets for the remainder of the programme (where appropriate).

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	Activities informed by crosscutting themes or advocating them
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
Number of gender and inclusion related activities	9	20 (222%)

Key Points
The Business Case committed the programme to ‘tackle gender-specific barriers to business and support gender-sensitive business environment reforms, including: legal and regulatory reform of discriminatory laws, regulations, and their implementation.’ Advisory work has progressed on the first part of this, with two interventions seeking to tackle gender-specific barriers to business underway. A further two are in design.[6] Arguably, the most ambitious of these is in Pakistan, where the programme is supporting a large business membership organisation to develop a system through which companies disclose their performance on several measures of workplace gender equality. The programme expects this will motivate companies to adopt more gender equal practices.
[6] Other gender-related programme activities include: supporting two partner governments to disaggregate data about entrepreneurs by gender; funding training of women entrepreneurs; and road-shows on women's rights (planned).
GBE has so far conceived seven interventions pursuing gender-sensitive business environment reforms. GBE’s decision to support reforms to Filipino legislation, ending discrimination against women’s ownership of the movable property, is one. Three more, in Malaysia, Nigeria and Pakistan, support and encourage host country governments to consider which sectors hold the most potential to empower women, when deciding which sectors to promote to investors.[7] In total, all 9 countries are planning to address gender and inclusion constraints in some way The programme plans to use wider World Bank research (the Women, Business and the Law Report) to scope additional potential gender-sensitive reforms in GBEP target countries, which is encouraging. Where the political will exists for further such reforms, the programme has the analytical tools and flexibility to make a difference.
[7] GBEP has also analysed which sectors of the Pakistani economy contribute most to women's economic empowerment. If this analysis leads the Pakistani government to consider gender when prioritising which sectors to promote to investors, and this is a new and sustainable change in Pakistan's investment promotion policy, there is a case for counting it as a gender-sensitive business environment reform.
To promote other forms of inclusion, the Business Case stated that the programme would work at the subnational level in certain countries, supporting business environment reform in regions that lag behind in their economic development. The programme also set out to benefit SMEs, for example through reforms which reduce the time and cost to start a registered business, and to provide domestic investors access to services and market opportunities through strengthening linkages between local and global firms. So far, the programme meets expectations in all three areas. In Brazil’s Ceara region, the programme provides technical assistance to improve environmental licensing, while in Malaysia’s Sabah region GBEP has started to research a range of economic and business environment reforms. To support SMEs meanwhile, the programme has successfully supported improvements to business registration in Nigeria and South Africa, begun to build the capacity of SMEs in Vietnam, and started designing similar capacity building in Turkey.
Building on the programme’s solid start in this output, GBE’s adaptive approach and the World Bank’s analytical strengths, there may be opportunities to go beyond Business Case expectations in future.[8] For example, in 1-2 countries, the programme could explore the feasibility of business environment reforms specific to sectors that employ large numbers of women, poor people or excluded groups. The programme might find that such reforms benefit a) people who are poorer or more socially excluded than those expected to benefit from existing interventions; and b) larger numbers of these groups than would benefit through existing interventions alone.
[8] Recognising that PF guidance on inclusion was published after the business case was developed

Recommendations

- The World Bank should ensure application of its environmental and social framework and demonstrate it has a mechanism in place for assessing and tracking its interventions to ensure they do no harm
- Consider whether there is scope to surpass business case expectations on inclusion, by supporting more reforms that benefit large numbers of poor and/or socially excluded women and men. For example, by targeting reforms in sectors where poor women and men or other excluded groups are most commonly employed. [Responsibility: World Bank]

## C: DETAILED OUTPUT SCORING (1 page narrative per output)

Output Title	New knowledge, tools and guidance developed, contributing to global knowledge sharing and programme effectiveness (global level)
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by end of programme)	Progress (cumulative)
# of publications and other data- and policy-based outputs (datasets, scans, diagnostic tools, toolkits, case studies, policy notes, etc.)	300	167 (56%)
# of peer-to-peer learning and capacity building workshops, training events, seminars, conferences, etc.	60	46 (77%)
# of participants in workshops, training events, seminars, conferences	1,200	1,758 (147%)
% of female participants in workshops, training events, seminars, conferences	40%	51% (125%)

Key Points

Despite being a global component, the global influence window supports the country level engagements and its outputs are shaped by feedback from the country programmes. Through learning events, country teams provide feedback on research designs and share insights that inform global window publications and datasets. Additionally, if a group of country programmes require new data, research or guidance, the global window looks to develop these. Every 6 months new activities are included under the global window based on country programme demand.
The global influence programme is making strong progress towards achieving its output targets by the end of the programme and has already achieved two of them. It has published 167 analytical and policy outputs which support both the GBEP country programmes and wider WBG projects, with 68 countries benefitting from the programmes outputs.

The global influence window is developing a number of innovative new products and piloting new approaches to filling gaps in business environment data and research. Highlights include Country Private Sector Diagnostics; new methods for calculating investment generated and retained; understanding the welfare and distributional effects of competition and investment; and Systemic Investor Response Mechanism. While there have been over 9,900 downloads of the projects’ outputs so far (33% of end of programme target), only three publications account for two thirds of these.[9] This suggests that the remaining outputs receive a low number of downloads each and are not disseminated very widely. The World Bank have indicated that they plan on recruiting a communications expert to enhance the dissemination of the various outputs under the programme, which will help to extend the global influence of the programme and drive greater value for money.
[9] A blog on “Outward Foreign Direct Investment: A New Channel for Development” and Product Market Regulations datasets for Philippines and Ukraine being downloaded more than 2,200 times each.

The flagship report of the programme – the Global Investment Competitiveness Report – presents novel analytical insights and empirical evidence on FDI drivers and contributions to development. It is due to be published every 2 years, but is currently behind schedule, with the 2017/18 report published in October 2017 and the 2019/20 report due to be published in March 2020. The report team encountered multiple unanticipated challenges in data collection – many beyond their control – which led to this delay; however, this delay has to be balanced against a much scaled up report which will provide more rigorous data than its previous iteration. One of the core elements of the report is a survey of executives of global firms and this report will include responses from 2,500 executives of global firms in 10 large middle-income markets, versus 750 in the previous report.

Peer to-peer learning events for GBE country teams also fall under this output. During the review period, the first such event took place in Johannesburg. The three-day event gathered 78 participants including government counterparts and FCO, DFID and WBG colleagues to share reform experiences, global trends and best practices, and used the event to start to develop GBE’s Gender and Inclusion Action Plan. Feedback suggests the event was a success, with 88% of participants stating that its content was relevant, and 94% stating that they extracted lessons for their own project. In addition to this peer-to-peer event, the global window has held 45 other learning events with 1,758 event participants (exceeding the target for event participants by the end of the programme) and a 92% satisfaction rating by participants suggesting that these are useful for those attending.

Recommendations

- As many of the end of programme indicator targets have already been achieved or are exceeding expectations at this stage of the programme, the programme team and the World Bank should consider agreeing more stretching targets for the remainder of the programme (where appropriate)
- The World Bank should increase its communication and dissemination of outputs from the global influence window. Publishing or linking programme outputs to the programme website might be one way of doing this.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (2 pages)

Key cost drivers and performance

Total funding allocated is £30million over a 4-year period, of which £28.5m is managed by the WBG via a single donor trust fund. The remaining £1.5M covers FCO Administration costs (salaries, travel, training, platform costs) over the 4-year period. The largest area of spend by the World Bank is on staffing and consultant costs, followed by travel expenses, which is to be expected in a programme of a global nature and was anticipated in the business case. 5% of funding to the World Bank is allocated to trust fund fees.

Budgets for the programme are set at country level and for the global influence window. A review of the country and Global Window projects by the World Bank in December 2018 led to a re-allocation of budgets to reflect updated workplans and resulted in the reduction of envelopes for Pakistan and Turkey, as well as the global window. This reduction allowed the programme to fund additional projects in 3 new countries without the need to increase the original programme budget of £30M. The largest budget allocation goes towards the global influence window, with South Africa and Brazil having the highest budgets for country engagements. The smallest budget for June 2019 to July 2020 is for Vietnam as it is one of the new countries where work was already established.

VfM performance compared to the original VfM proposition in the business case

The business case sets out that the World Bank was identified as the best value for money delivery partner due to its global reach, expertise in investment climate reform and experience of assessing the ease of doing business, that the programme interventions can draw upon. Narrative progress reports demonstrate that this has been effective in practice, with the country interventions utilising the products developed under the global influence window, which may not have been available to the Prosperity Fund with a different delivery partner. Furthermore, the World Bank has established relationships with government counterparts which they could draw upon to get implementation up and running quickly, particularly in the 3 new countries which have been added this year. The business case also posits that working with the World Bank provides an opportunity to have greater influence on business environment reform in focal countries because it enables access to a pipeline lending contingent on regulatory reform – the evaluation found evidence of this happening in some countries, notably Pakistan.

Economy – analysis of economy is broadly covered by the above section on key cost drivers. Staffing accounts for 69% of costs, but it is usual for staffing costs to be the highest proportion of a programme of this type and these are comparable with other similar programmes across HMG. The IFC takes a 5% fee for administration of the trust fund, which is lower than the WBG standard rate of 17.5%, resulting in significant cost savings on the original admin budget. The World Bank have a proven track record of delivering inputs to a high quality and this has been evidenced on this programme. FCO admin costs account for around 5% of the programme budget, which is in line with the business case. This is expected to remain constant over the life of the programme.

Efficiency – performance at an efficiency level is strong. So far, delivery against output indicators are on track or have exceeded their targets for the end of the programme. Whilst it is possible that some of the targets may have been set too low (e.g. on number of event participants), it demonstrates ability of the World Bank to use their resources efficiently to deliver more within the same budget envelope. The programme is delivering a high volume of activity and has demonstrated its ability to flex resources efficiency to adapt to challenges in delivery and to pursue new opportunities. In particular, 3 new countries of focus have been added to the programme this year without an increase in the overall budget or significant reduction in activities in most of the original 6 countries, suggesting that cost savings may have been made in delivery of these activities. This is particularly evident given that the pound to dollar exchange rate has dropped considerably since the business case was developed, resulting in a drop of funding to the Bank of around 20%. Additional cost savings were made by downscaling activities which, in light of changing political economy, were less likely to contribute to outcomes.

Effectiveness – the primary outcome that the programme is seeking to achieve is reforms to the business environment in the 9 focus countries. The business case sets a target of 25 reforms, but the World Bank are working towards a more ambitious target of 73 reforms, with varying degrees of likelihood. WBG have set this ambitious target to diversify the portfolio and manage the risk that targeted reforms do not come to fruition. So far, the programme has recorded 8 reforms, which is very positive at this stage of the programme and suggests that the programme is likely to be successful in meeting the target. It is too early in the programme to assess other results which the programme expects to achieve, such as improved business or investor perception, amount of investment generated and more open and competitive markets. The programme is currently on a good track to achieving this, but there are delivery risks which need to be monitored (as set out in the risk section). Data on this should start to become available in year 4 and in the 1-2 years after the programme ends when reforms are validated and have had time to impact business decisions. The needs of businesses are built into the design of the programme, for example in Brazil where one of the reforms achieved has been the implementation of “mesas executivas” – a new model of public-private dialogue which allows for improved co-ordination between public and private sector in the country. The impact of such initiatives, through consultative process, will become more apparent in the coming years of implementation. While the same model of private sector consultation may not be possible in other markets, WBG team are in a position to deliver tailored models for other countries going forward.

Equity – as identified in the Gender & Inclusion scorecard, the OECD Gender Equality Marker score for this programme is 0, with gender not being specifically targeted within the programme. However, whilst the programme has committed to a minimum level of ambition on alignment with the PF G&I framework, there is evidence of this commitment being exceeded in some areas towards empowerment and transformative levels of ambition. The PF G&I scorecard was completed in April 2019 and updated recently as part of the programme evaluation. It recommended that the programme’s G&I plans should clearly outline time-bound plans and responsibilities and consider how the country programmes have adequate G&I-specific capacity and support. The programme has responded to recommendations in the previous annual review through successful delivery of the peer-to-peer learning event in South Africa in March 2019 organised by the World Bank with inputs from the FCO’s Social Development Adviser. This event provided training for Government counterparts, World Bank Group Task Team Leaders of the nine Country Programmes, and World Bank (IBEP) programme management, with facilitation for development of initial country-level G&I intervention plans. It effectively leveraged expertise across WBG departments and units (Global Practices, the Women, Business and the Law unit, and the Africa Gender Innovation Lab) and external partners (e.g. UN Women). One topic with promise for future engagement is further improvement and application of the Women, Business and Law (WBL) index, with potential benefits across a number of Prosperity Fund programmes. The programme has subsequently developed a G&I action plan which sets out activities in each country and has appointed a gender specialist in the central team to support these teams on how to design and implement gender sensitive business environment reforms. However, as the programme scales up its ambition on G&I, additional specialist resources may be required at country level to deliver the more detailed action plans, as well as in the London FCO team to ensure adequate scrutiny of these activities. There are a number of indicators specifically focussed on gender and inclusion and others disaggregated by gender and the World Bank is reporting against these, but further may be required to ensure adequate monitoring. This suggests that the programme broadly understands the distribution of benefits within the programme and has adequate processes in place to track these at output level, which will support it in assessing the equity dimension of value for money in the future. However, there is more the programme can be doing on inclusion, as set out in recommendations 2 and 3.

Assessment of whether the programme continues to represent value for money

As there has been no significant shift in the costs from the Business Case and delivery is on track, the programme still continues to represent value for money at this stage. Value for money performance is currently measured against the indicators in the programme scorecard (these are also used as KPIs), but the programme would benefit from developing specific value for money indicators in addition to these to enable the programme team to clearly track performance year on year. It would also be helpful for the programme to establish a baseline for these indicators to identify where savings are being made or costs are higher than anticipated. A recommendation on this was made in last year’s annual review with suggested indicators, but this has not been taken forward by the programme team. Reporting against value for money indicators would not require additional reporting from the World Bank, but a presentation of the information in a slightly different way to enable the programme team to make a robust assessment in both the annual review and the value for money scorecard.

Despite the programme overall delivering good value for money, there are some areas where there are opportunities to drive greater value for money. As discussed in the key lessons section of this report, greater collaboration and knowledge exchange between the various country programmes and with other HMG and Prosperity Fund programmes will help to share and learn lessons and increase the effectiveness of the programme’s interventions (see recommendation 8).

Recommendation: The FCO programme team should establish value for money indicators and systematically monitor these and hold regular discussions with the World Bank to ensure value for money is being achieved.

Quality of financial management

There is a general assumption that the day to day finances of the programme are managed to WBG standards and subject to internal VfM check and balances, which have been vetted and approved by this and previous programmes. The FCO team have access to high-level data regarding spend but cannot investigate individual spend items. The WBG team implement their own audit and financial management procedures. The WBG have developed a comparative advantage for delivering work in this area; continued monitoring will be required to ensure delivery achieves value for money.
The World Bank report on finances within a six-monthly Progress Report. The data is broken down by each of the 9 country and the Global Initiative Window projects. The World Bank have so far received 4 payments totalling £17.8M, of the £28.5M due to be paid to them. £10.3 million was been paid in 2017 and 2018 for World Bank expenditure from the start of the programme up to the end of June 2019 (Note: World Bank Financial Year is July-June). The remaining £7.5M (paid in July 2019) is for World Bank activities between July 19-June 20. World Bank expenditure up to June 2019 comes to £9.84M which is a utilisation rate of 95.53%. Surplus funding (£460K) will therefore be used for activities in 2019/20 World Bank financial year. The underspend was due to country engagements activities being completed, but not physically paid for by the World Bank by the end of June 2019. These payments will made be in the first half of the following year.

The previous annual review highlighted the payments issues at the start of the programme and the front loading of the trust fund. Payments to World Bank are now based on World Bank requirements for the upcoming WB financial year (July-June) and the activities that they expect to complete rather than the flat-line payment schedule within the Administrative Arrangement. Each payment requested is reviewed by the FCO Programme Team and discussed and approved at the Partnership Council meeting prior to the payment being made. The Programme Team also check expenditure against the progress report and what the World Bank stated that would be doing to ensure funding is being used for what was agreed.

FCO expenditure covers salaries and platform costs of the Programme Team in London and at Posts. It also covers Programme Team travel and training. The Programme Manager reports on FCO expenditure on a monthly basis.

The below table shows the FCO Funding and FCO World Bank Expenditure:

Project/Component	Year 0 (Nov 2017 - Mar 2018)	Year 1 (Apr 2018 - Mar 2019)	Year 2 (Apr 2019 – Mar 2020)
GBEP total budget	£6,800,000	£3,400,000	£7,906,700
FCO payments to World Bank	£6,500,000	£3,800,000	£7,500,000[1]
FCO admin budget	£300,000	£220,000	£406,700
WB Spend	£1,850,600	£6,230,000	£1,758,512[2]
Country Engagement Window	£1,005,600	£4,449,600	£1,209,112[2]
Global Engagement Window	£496,000	£1,463,200	£477,400[2]
Other Management Fees4	£24,000	£127,200	£72,000[2]
Trust Fund Admin Fee (5%)4	£325,000	£190,000	-
FCO Admin Spend	£85,053	£219,458	£262,038
FCO Admin Costs (Salaries/Travel/ Training)	£85,053	£219,458	£158,258
FCO Platform Charges	£0	£0	£103,7803
FCO Actual Total Spend (WB Funding Payment and FCO Admin)	£6,585,053	£4,019,458	£7,762,038
[1] £7.5M Payment to WB in July 19 is for activities between July 19-June 20. No figures available for WB spend yet between July 19-Present.
[2] World Bank Spend Figures for Y2 Q1 (highlighted) were funded by payments in Year 0 and Year 1.
[2] This includes a refund of £92,690 in respect of an overcharge of platform costs in June 2019 by FCO Finance Directorate. 4 Additional costs covering Annual Reviews, Evaluation and reporting required by the Programme

Date of last narrative financial report	Oct 2019
Date of last audited annual statement	n/a

E: RISK (1 page)

Overall risk rating: Moderate

Overview of programme risk
The programme team keeps a comprehensive risk register. The risk register for this programme was revised in March 2019, and again in October 2019. It comprises 25 risks: 2 green; 10 yellow; and 13 amber. The review did not uncover any major risks falling outside of the current risk register. The key risks are outlined below, along with comment on how the programme is managing them.
The key operational risk identified is the programme being inadequately staffed by the World Bank in target countries. The review team found nothing that suggested this risk has materialised so far.
Key delivery risks include a failure of activity to contribute significantly to inclusive growth and FCO being unable to leverage activity to enhance UK soft power. The stakeholders interviewed generally felt that the first risk is low or moderate, with many of the reforms targeted bringing significant anticipated benefits to inclusive growth in target countries. In terms of the second risk, Posts did raise concerns that opportunities will be missed to achieve recognition from host governments for the UK’s support to business environment reform through the programme.
Another important delivery risk is failure to maximise results and value for money in the event of early closure or in the event of budget changes. Whilst unlikely, were this risk to materialise it could also affect HMG’s relationship with the World Bank. To mitigate this risk, the FCO programme team frequently engages with those setting the Prosperity Fund’s overall budget, making the case for continued funding and clarity on future funding.
The FCO programme team in London also raised the small size of their team, relative to workload, as a concern. Whilst prosperity fund guidance on the proportion of programme spend that can be spent on administration makes a staff uplift unlikely, this review has taken into account workload pressures when formulating its recommendations.
A final delivery risk is that outputs or outcomes are delayed when host government ministers and senior officials change. The World Bank and FCO have managed this risk well in the year under review. Following elections in several host countries, programme staff moved quickly to help new administrations understand the benefits of GBEP continuing. New administrations have welcomed the programme. The programme has also seized opportunities for reform resulting from a change of administration.
A related contextual risk is that the political economy in each host country changes, making certain reforms less feasible over time. The programme’s ability to reallocate resources to reforms that remain feasible lowers its risk of failing to achieve the targeted number of reforms. So does the programme’s approach of targeting 73 reforms (significantly above the programme’s target of 25).
To manage fiduciary risk, the programme benefits from the World Bank’s internal controls and long-standing experience of trust fund management.
Outstanding actions and recommendations from risk assessment
- Proactively notify posts about opportunities for the UK to be visible in its support for World Bank-implemented GBEP activities, where this visibility will not unduly compromise the real and perceived independence and impartiality of World Bank advice
- FCO should agree with the World Bank when and where the UK Aid and Prosperity Fund logos should feature on Global Influence Initiative publications funded by GBEP to increase visibility of PF funding
F: COMMERCIAL CONSIDERATIONS (1 page)

Delivery against planned timeframe

The programme has largely been on track in Year 2 without any major delays. However, the nature of the programme means it is susceptible to political changes in target countries. Both FCO programme team and WBG are aware and have agreed on reasonable flexibility to protect against potential delays.

Performance of partnership(s)

The working relationship with the World Bank is progressing well. Both FCO and World Bank teams are comfortable in their interactions and expectations. Challenges remain, however, in co-ordination between FCO, World Bank and Posts (see recommendation 9). While this may not affect outcomes and impact of the programme itself, it might raise operational challenges which are best avoided.

Changes in the Delivery Plan

A review of the country and Global Window projects by the World Bank in December 2018 led to a re-allocation of budgets particularly for Pakistan and Turkey, allowing the programme to expand into 3 new countries. In line with adaptive nature of Prosperity fund, this has allowed greater flexibility in the programme and has potential to significantly improve the VfM aspect as evidenced by early wins in Vietnam. While the scope of work in Pakistan and Turkey has been re-calibrated, it does not deviate from the original pillars of work thus having no impact on the overall Theory of Change. It has allowed for more focused targeting in Pakistan and Turkey, while allowing to push for new areas of intervention in the additional 3 countries, enhancing the scope and reach of the programme. Combined together, the Global Window Influence stands to gain from direct feedback loops of a wider geography within the programme.

Asset monitoring and control

The Programme is not generating any assets nor is expected to going forward.

G: Business Environment (½ page)

How has the business community and business environment responded to the programme?

The business community across nine countries have been engaged by WBG team, often with the support of local posts. Where involved, the posts have confirmed feedback received from the British business community. Feedback has largely been positive from networks such as in-country business councils, British business groups and DIT. The Global Influence Window captures business opinions in its biannual MNC surveys and the Global Investment Competitiveness Reports. A more accurate feedback of the programme will, however, emerge towards Year 4 of the programme when the suggested interventions lead to substantial changes on the ground for business community to acknowledge.

Risk: It is difficult for businesses to differentiate between programmes run by HMG at post. The attribution/contribution of any success of this programme may not be recognised by the business community. This is a greater risk for country engagements rather than the Global Influence Window (see recommendations 4 and 10).

(Where relevant) What role has non-oda spending played in promoting programme objectives?

The Programme has received no non-ODA funding.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

As a requirement of the Prosperity Fund all programmes are subject to a regular evaluation conducted by the contracted Evaluation and Learning team. After approval of the Approach Paper the data collection period of the evaluation started in May 2019 and included in-depth visit to South Africa to meet key stakeholders. The 1st cycle evaluation report comes within the second year of the programme and was submitted to the Programme Team (in draft) on 14 November 2019. Main conclusion from the Evaluation report is:

GBEP has performed well since its launch in 2018. The country programmes are on track with activities and outputs and, when combined, they are well set to achieve a total of 25 reforms, as envisaged in the BC. Despite being global and highly centralised, the programme has also successfully followed an adaptive management approach, responding to changes in context and new opportunities. Efforts are nonetheless required to complement the recently launched G&I action plans to strengthen the country programmes’ alignment to GBEP primary purpose.

Lessons and recommendations from the evaluation will be followed up by the Programme Team.

Monitoring progress throughout the review period

The primary method of monitoring progress of the programme is via FCO/WBG six monthly technical discussions between the FCO and WBG program management teams, as well as the semi-annual Partnership Council Meetings which includes the production of a detailed Progress report on the Global Initiative Window and the 9 country projects of the programme. The progress report details progress of the previous 6 months and a forward plan for the following 6 months.

Following the implementation of the 2018 Annual review recommendations, the 9 focal countries of the programme now produce a quarterly report and in country Risk Registers. These feed directly into the programme quarterly reports produced by the London Programme Team. Monthly catch up meetings between FCO Post country teams and the London Based Programme team have been set up to allow the exchange of information. World Bank Progress Reports and minutes of the Partnership Council Meetings are published on the PFLearning platform as soon as they are finalised. All Post Programme Managers are members of the GBEP Peer Space on the PFLearning platform. Following development of the country and global widow scorecards the programme has been able to upload indicators, baseline and year 1 values onto the Prospero system.

It would be beneficial for future Annual Review teams to make 1 or 2 in-depth visits to the focal countries of the programme rather than just having video calls with Posts. The programme will be in its third year which is when many of the reforms are due to be achieved and visits would allow the AR team to fully understand the country projects and allow them to talk to key stakeholders involved. With the Evaluation Team visiting South Africa this year the AR Team did not feel it necessary to make such visits for this annual review.

Recommendation: Improve communication with Post before and after key meetings with the World Bank. For example, give Posts at least a week to comment on World Bank Progress Reports before the GBEP London programme team meets the World Bank to discuss the report. Posts only had two working days to provide comment on the Y2H1 Progress Report before FCO programme team met World Bank for progress meeting.