Annual Review - Summary Sheet

PROGRAMME TITLE: East Africa CSSF Regional Migration Programme
Country and Region:	Kenya, Sudan, Ethiopia, Somalia
IATI Unique ID:	CSSF-03-000020
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), National Crime Agency (NCA), Crown Prosecution Service (CPS)
Total Budget :	ODA: £5m			Non-ODA: 0
Budget this FY	ODA: £1.7m			Non-ODA: 0
Spend this FY	ODA: £0.8m			Non-ODA: 0
Original Programme Start Date: April 2018		Planned End Date: March 2020
Outputs					Score
Increased capacity in relation to Organised Immigration Crime (OIC) within the security and criminal justice system					B
An increase in available evidence of a) community perception and b) interventions which work.					C
Influence and leverage with key national and regional and international actors to adopt consistent and supportive and evidence-led measures to tackle OIC.					B
Systematic use of evidence uptake in programming and policy making by international actors.					B
Overall output score					B
Outcome assessment: In Sudan, there is emerging evidence that programme outputs have contributed to outcome level change: disruption of OIC in a human rights (HR) compliant manner and adoption of UK supported HR compliant actions and procedures for disruption of OIC. Beyond Sudan, more limited progress at output level has constrained the programme’s contribution to outcomes. There are strong foundations to build off and associated projects are supporting the UK Government’s access and influence with target stakeholders. However, the regional programme has not worked as intended and has subsequently been changed to a country-specific approach.
Outcome Score: B			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	B	A	C	B	B
Risk Rating - low/medium/high	N/A	Medium	High		High
*output/outcome scores

What support did the UK provide in FY 18/19?

The East Africa Regional Migration Programme was designed as a three-year programme (2018 – 2021). It built on prior experience of Migration project delivery which had begun in 2016, in response to the crisis in the Mediterranean in 2016.

- Pillar 1 aimed to strengthen the capacity of the regional security and criminal justice system to disrupt organised immigration crime (OIC) in the region.
- Pillar 2 aimed to support evidence-led measures to weaken the enabling environment for Organised Criminal Gangs (OCG), reducing their influence through engaging with communities along migratory routes that facilitate or enable the OCG activity.
- Pillar 3 was a cross cutting and enabling pillar that aimed at strategically increase the UK Government’s political access and influence (PAI) at regional and international fora to encourage and coordinate an international response.
Key results for FY 18/19:

- Human trafficking operations supported by the Migration Adviser based in Khartoum in coordination with INTERPOL have led to arrests.
- Memoranda of Understanding (MoUs) for NCA/CPS support in relation to Migration Human Trafficking Teams (MHTCT) in Ethiopia have been signed.

Summary of progress and lessons learnt/actions taken since last review

- This has been a transition year as elements of the new programme were a continuation of activity funded under the Migration Returns Fund (MRF) Upstream Programme.
- Significant efforts have been made to design a more coherent, strategic, and policy driven programme. The three-pillar approach and broad Theory of Change emerged from a range of consultation exercises and Stabilisation Unit (SU) scoping studies.
- A new governance structure was provided by a Migration Governance Board (MGB) with representation from the FCO, Home Office, DFID, NCA and CPS.
- Despite some promising results, overall progress and support for the programme during its first year of implementation was less than hoped.
- Many of the challenges the programme faced can be linked back to deficiencies and complexities in the programme governance arrangements. The most critical being a lack of clear policy steer, oversight and policy direction. There was an underestimation of the effort and drive needed to make a coherent UK Government regional programme of this type work effectively.
- It was against this background that, in November 2018, the MGB reviewed governance arrangements and decided that management, oversight and funding should be devolved back to country teams.
- Consequently, from April 2019 there will no longer be a regional programme. Funding for financial year 19/20 will be split between Ethiopia and Sudan.
Summary of recommendations for the next year

Under the new devolved arrangements, regional policy leads should play a role in building the ‘regionality’ and cross-government nature of CSSF Migration programming. However, to be effective it needs to be supported with clear direction, strong leadership and clear lines of accountability, reporting and incentives for different stakeholders to engage.