Annual Review - Summary Sheet

PROGRAMME TITLE: East Africa Security Programme
Country and Region:	East Africa
IATI Unique ID:	CSSF- 03 - 000021
HMG Partners / (LEAD in bold)	Ministry of Defence (MoD)
Total Budget :	ODA: £0.30m			Non-ODA: £6.90m
Budget this FY	ODA: £0.11m			Non-ODA: £2.36m
Spend this FY	ODA: £0.08m			Non-ODA: £2.26m
Original Programme Start Date: April 2015		Planned End Date: November 2020
Outputs					Score
1: Strengthen Kenyan led internal governance and management of the counter improvised explosive device (C-IED) capability.					A
2. C-IED training delivered by a more capable and functional UK mentored Kenyan and East African (EA) staffed training cadre.					A+
3: UK political and policy engagement in support of Kenyan, regional and international engagement in regional C-IED capability development					A
4. Increasingly regional and relevant force elements acquire the knowledge and skills to operate in a high threat IED environments through receiving training by the wing.					B

Overall output score					A
Outcome Assessment: There is good evidence to show that the achievements made in delivering Outcome one have been underpinned by significant bilateral engagement. In parallel, programme stakeholders have implemented and built on the recommendations from last year’s annual review concerning programme governance, co-ordination, C-IED training, management and sustainment. Although a Monitoring and Evaluation (M&E) plan for the programme has yet to be established, much effort is on-going to develop appropriate measures and processes.
Outcome Score: A			Risk: Low

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score		A/B	A/B	B	A	A
Risk Rating		Low	Low		Low
*output/outcome scores
How has the programme changed during this period? / There has been considerable progress taking forward the bilateral agreement with the Kenyan authorities to enhance and sustain the capabilities of the C-IED Wing. The Kenyans have provided the required trainers and support staff. UK-sponsored training has progressed towards a train-the-trainer/mentoring approach, tailored to the operational requirements. Partner nations such as the US and Germany are supporting the facility and the development of appropriate African Union (AU) C-IED doctrine. Measures to promote the regional reach of the C-IED Wing have resulted in training for other African Union Mission in Somalia (AMISOM) nations.

What support did the UK provide in FY 18/19?

- Political and defence engagement leading to the signing of a Kenyan C-IED Institutional Development Programme for the C-IED Wing Mandate’ with Kenya’s Ministry of Defence.
- Development of the capabilities of the Kenyan training personnel assigned to the C-IED Wing.
- Adjusted the C-IED training schedule to reflect operational requirements. In tandem, prioritised a train-the-trainer approach with the intent that UK instructors will shift to a mentoring and instructing role.

Key results for FY 18/19:
Positive and productive bilateral political engagement provided momentum and political underpinning to programme implementation by both countries.

- The establishment of bilateral governance structures to direct and oversee the implementation of the ‘Institutional Development Programme’.
- A greater focus on the transition from UK led C-IED training to Kenyan led (UK mentored) training, in parallel with measures to take forward the regional engagement with the C-IED Wing.
- Working with United States Africa Command (AFRICOM), United Nations Mine Action Service (UNMAS), AU and the AMISOM contributing nations to develop AU C-IED doctrine and training standards.

Summary of progress and lessons learnt/actions taken since last review:

- The Programme Results Framework and Risk Matrix were updated. They included greater definition of the programme Exit Strategy. They also included measures required to assist Kenyan processes to take responsibility for the C-IED Wing and C-IED capability development.
- More coherent programme governance established, as well as more structured and frequent co-ordination between the programme team and BPST (A).

Summary of recommendations for the next year:

Adopt a more holistic approach to M&E by developing a wider field of data to assess operational performance and training effect on AU/UN operations. The team should also make greater use of open sources to track and assess IED incidents in Kenya and measures to deal with them.
- Assess options for enhancing programme support to Kenyan police to tackle IEDs, building on the police training C-IED training now occurring in the C-IED Wing. Consider whether such an approach would contribute to decisions on the future of the programme and UK’s long term strategy for C-IED support in the region.
- Develop a communications plan to promote the programme at regional events. In conjunction with this, encourage Kenyan measures to alert their public to the dangers of IEDs.
  This work should be led by the programme team initially, to ensure coherence.
- Highlight the importance of regional governments aligning their IED capability to match their IED threat. It is important that regional partners achieve a better understanding of the value of comprehensive semi-remote and manual C-IED tactics and procedures.
- Programme stakeholders should address what UK’s C-IED strategy for the region following the end of the programme. CSSF stepping away entirely may have unforeseen consequences and second and third order effects upon other CSSF programmes.
- Transfer of CIED Wing responsibility by the end of financial year 2019/2020, so Kenyan counterparts are able to understand these costs. The programme should also end the procurement of training equipment. These changes will ensure UK support in the final months of the programme is tightly focused on where the UK support has significant value added.