# Programme Completion Review - Summary Sheet

PROGRAMME TITLE: CSSF Great Lakes
Country and Region:	Great Lakes (DRC & Burundi), Africa
IATI Unique ID:	CSSF-03-000003
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £4.10m			Non-ODA: £0.7 million
Total Spend:	£4.91m(ODA + Non-ODA combined)[1]
Original Programme Start Date: April 2015		End Date: March 2019
Outputs (scored for the last FY 18/19)					Score
Output 1: A better trained civil society, linked with national and international efforts, encourages increased engagement of the authorities in the human rights and political dialogue in Burundi					A
Output 2: A tested approach on how to increase trust between security forces and communities/citizens in the Democratic Republic of Congo(DRC) and Burundi					A
Output 3: Pathways for the UK Government to influence decision-making at national level in the DRC are identified					B
Output 4: Analysis and engagement strategies and programming opportunities for the United Nations Organization Stabilization Mission in the Democratic Republic of the Congo (MONUSCO) and the DRC cross-border conflict are generated					A
Overall output score					A
Outcome Assessment: During this FY the project scored an A against its stated outcomes. A new Results Framework with realistic indicators and targets for the outcome statements has contributed to this scoring. The A score reflects the fact that the targets set for April 2019 were met, even if the outcome statements reflect planning over what was meant to be a three-year 2018 – 2021 programme. Over the course of its 4-year duration, the programme has scored A, B, B and A at the outcome level.
Final Outcome Score: A			Risk: Medium
[1] The programme overspent by £107,984 over 4 years, according to a review of previous Annual Reports.

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A/B	A	B	A	A
Risk Rating	Med	Med	Med		Med
*output/outcome scores

How has the programme changed during this period?

The design of this programme has shifted across its four years of operation. At inception in April 2015, it was designed with two pillars: defence engagement/reform, and addressing regional (cross-border) peace building. During the course of FY15/16, the programme shifted to respond to rising stability in Burundi with an additional Burundi strand. In FY16/17, it retained these strands and added a fourth focus area on Prevention of Sexual Violence Interventions (PSVI). In FY 17/18, the strands on regional peace building and defence reform were retained, the Burundi strand was refocused on supporting the conditions for peaceful elections and the PSVI strand dropped. A new strand was added to focus on human rights in the context of elections in the DRC. In the final year, the human rights programme had three distinct strands. These covered strategic and operational engagement with security forces in DRC; gaining insights on the situation in Goma and the performance of MONUSCO (the other key actor in DRC stability alongside the FARDC); and securing institutional change on human rights in Burundi.

What support did the UK provide?

The programme has supported a variety of conflict mitigation and human rights interventions across DRC and Burundi during the last four years. It worked with thirteen implementing partners and two advisers, some over many years, others for shorter engagements. The programme has been able to respond pro-actively in Burundi following the 2015 crisis; provided support in the DRC during the 2018 elections; supported broader conflict mitigation and human rights initiatives and funded two advisory roles to strengthen the UK’s presence in DRC.

What results did the programme deliver? Will they be sustained?

The programme has achieved a number of results at the project level, particularly at the community level where most projects have been focused.
- The marking of 52,000 Small And Light Weapons(SALW) and establishment of a database for FARDC to manage SALW stocks
- Establishment of local human rights reporting/early warning network of 23 local organisations in Burundi, including the delivery of at least 140 reports on human rights violations.
- Key Sexual and Gender Based Violence cases supported through the DRC legal system now part of case law
- Progress towards the proof of concept of community-based approaches to building trust between communities and the FARDC in DRC, and between communities and police in Burundi, including the establishment of joint action plans between communities and local FARDC officials.
- Training of 3,000 FARDC personnel in English language skills.
- Great Lakes Conference on Private Sector Investment.
- 13 workshops between key leaders and communities in Eastern DRC hotspots that opened up space for dialogue and provided the UK Government with additional insights into Eastern DRC conflict dynamics
- Knowledge within the UK Government and networks within the Armed Forces of the Democratic Republic of the Congo (FARDC) and MONUSCO as a result of advisory support.

The sustainability varies across different projects and interventions. For example, community level projects see some sustainability through improvements in knowledge and contacts made through the project and training of beneficiaries. During its final year, the programme emphasised the piloting of approaches and ‘proof of concept’, but given the ending of the programme, there has been insufficient time to ensure broader uptake.

What lessons have been learned?

This Annual Review has identified several key lessons at an outcome and output level, summarised below.
- Progress in the security sector requires technical assistance but more importantly political will. To generate buy-in it is important to build relationships, but these remain fragile and subject to personnel changes. Contextual factors can also impact on political will. It is important to take this into account and to be realistic in framing expected results.
- CSSF programmes funding advisory roles should develop indicators that reflect the nature of the work undertaken and set up tools to capture the political access and influence the UK gains from such work.
- The approaches to increase trust between security forces and communities/citizens in DRC/Burundi have merit, but longer-term investment, including the building of key relationships, is required to provide evidence and results.
- Strategic engagement with the FARDC is possible, but will remain dependent on alignment of priorities and how politicised the issues the project is seeking to address are. Results frameworks should be realistic in how they aim to capture results in very fragile environments like the DRC security sector.
- Embedding linkages and activities between advisers and projects could strengthen the ability for the CSSF to achieve its overall targets. There seemed to be missed opportunities between advisers, whilst the collaboration between the Security Sector Adviser (SSA) and Mine Action Group (MAG) has added value.
- CSSF programmes should have a kick-start workshop with all implementers to ensure they are all on the same page. Project management teams should also invest in training all personnel in project management skills for them to be comfortable dealing with logical frameworks as well as setting SMART indicators in highly fragile settings.
- Existing CSSF risk management should be enhanced through the articulation of key conflict sensitivity risks and the addition of such risks to the programme risk matrix.
Attempts have been made to integrate gender throughout the programme. However the programme missed the opportunity to do this in a more systematic and strategic manner. A robust gender analysis, linked to CSSF’s overall goals in the region could have enabled stronger integration of gender sensitivity.