Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Nigeria CSSF Niger Delta & Maritime Security Programme
Country and Region:	Nigeria, West Africa
IATI Unique ID:	CSSF-03-000005
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD), National Crime Agency (NCA)
Total Budget:	ODA: £0.90m			Non-ODA: £0.60m
Total Spend:	ODA: £1.11m			Non-ODA: £0.65m
Original Programme Start Date: April 2018		End Date: March 201931/03/2019
Outputs					Score
1. Increased dialogue and common understanding between citizens in the Niger Delta, Federal and States Governments on realistic and achievable objectives for the region leading to greater stability					B
2. There are innovative, scalable and strategic alternative economic policy approaches that contribute to removing actors from conflict and criminal activities, or preventing those at risk of entering.					B
3. Better informed UK Government improves effectiveness of engagement with Federal and State Government, impact of programmes, and international collaboration on the Niger Delta.					A
4. Nigerian Navy deep water maritime capability can operate effectively and efficiently to protect its territorial waters and reduce security threats in accordance with Human Rights and due legal process, in coordination with other agencies and its regional neighbours / Continued Advisory role with Nigeria Federal Ministry of Justice (FMoJ) Department for Public prosecution (DPP) and MLE Agencies.					A
5. Nigerian Navy training institutions produce capable, knowledgeable, well trained students to tackle challenges of the Maritime Operating Environment on a sustainable basis. Maritime Security Strategy Committee (MSSC) created to facilitate Maritime Security Strategy implementation.					B
Overall output score					B
Outcome Assessment: / Recent staff changes and an incomplete logframe made it difficult for the Review Team to confidently assess the programme’s performance. Overall, NDMS outcomes were assessed as potentially on track, with some notable risks to achieving the programme’s outcomes, which the programme team should seek to respond to and remedy in FY19/20.
Final Outcome Score: B			Risk: Medium/High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	B	B (BMATT) / / A (Niger Delta Stabilisation - NDS)	B (BMATT) A (NDS)	B (BMATT) A (NDS)	B	B
Risk Rating - low/medium/high		Medium (BMATT) / Medium (NDS)	Medium (BMATT) / High (NDS)		Medium (BMATT) / Medium (NDS)
*output/outcome scores

What support did the UK provide?
- Funded the Stakeholder Democracy Network (SDN) to increase dialogue, understanding and transparency between citizens and government in the Niger Delta; implement, assess and seek funding for alternative livelihoods; provide up to date briefings for the UK Government on the Niger Delta.
- Funded British Military Advisory Training Team (BMATT) to train and provide non-combat materials to the Nigerian Navy to operate effectively and efficiently to protect its territorial waters; reduce security threats working with other agencies/regional neighbours, and train students to tackle the challenges of the Maritime Operating Environment.
- Funded United Nations Office of Drugs and Crime (UNODC) to train prosecutors at the Nigerian Ministry of Justice (MOJ) to effectively prosecute crimes in the maritime waters of Gulf of Guinea.
- Funded International Maritime Organisation (IMO) to facilitate the development of a Maritime Security Strategy Committee (MSSC) to enable Maritime Security Strategy implementation.

Key results for FY 18/19
- Potentially effective approaches to economic diversification, peace-building and government transparency in Delta states. 12 pilots (target 4) were delivered.
- Enhanced capacity of twelve federal prosecutors to prosecute crimes of piracy in the Gulf of Guinea. Anti-Piracy Bill presented to the National Assembly and in the process of being approved ahead of final Presidential sign off.
- Increased capacity of over 500 Nigerian Navy personnel in a variety of maritime activities and delivery of training. The Nigerian Navy demonstrated an improved ability performing relevant actions in security exercises such as Op Express.

Summary of progress of lessons learnt/actions taken since last review
- Embedding the legal advisor within the Ministry of Justice was instrumental to supporting the piracy legislation, training of Nigerian MoJ prosecutors and establishing a core maritime crime group.
- Sharing of lessons between the various components was almost non-existent and it is assumed with other CSSF programmes both within Nigeria and elsewhere. Partners should suggest NDMS lessons.

Recommendations for future programming
- BHC to lead on closer collaboration between international donors working on stability and security in the Niger Delta region, in order to seek additional donor funds in this area, raise awareness of this programme’s activities and look at the possibility of sharing costs and risks.
- CSSF team to look to learn from DFID expertise on community policing and community peacebuilding methods. In addition DFID and CSSF programme teams should look to collaborate and share research and data so the CSSF team can learn from their expertise in this region.
- All activity needs to consider gender equality and improve its analysis on how activity will impact women and girls, in line with CSSF policy on mainstreaming gender equality within all programmes.

Output 1 recommendations:
- SDN use a more random approach to sampling to avoid potential bias with their reports that comes from convenience sampling.
- SDN consider separate focus groups to ensure less powerful groups can voice their opinions – women, members of the public.
- SDN to consider conducting conflict sensitivity analysis on possible conflict risks that the SIWP platform could cause.

Output 2 recommendations:
SDN to do more outreach with local partners, and look more broadly at alternative economic policies and approaches. E.g. working with start-ups and entrepreneurs.

Output 4 recommendations:
- BHC should ensure closer collaboration, including information and data sharing, between the Nigerian MOJ and UNODC.-.
- MOJ should develop a meetings’ plan for the Core Maritime Group in preparation for when the
- BMATT to assess electronic means of theoretical training for divers, given the lack of in-house dive training equipment and capacity.
- BMATT to meet with UNODC to integrate the Nigerian MOJ Harmonised Standard Operating Procedures (HSOP) principles and practices into their ship boarding course. This will mainstream common practices for the key action of evidence handling throughout the prosecutorial pathway. The BMATT Joint Maritime Security and Training Centre (JMSTC) Quarter 3 19/20 course offers a good entry point for this initiative.