Annual Review - Summary Sheet

PROGRAMME TITLE: Sahel Strategy 2018-2021 Defence and Security
Country and Region:	Sahel: Mali and Senegal
IATI Unique ID:	CSSF-03-000023
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD), National Crime Agency (NCA)
Total Budget :	ODA: £9.4 m			Non-ODA: £10.9 m
Budget this FY	ODA: £2.4 m			Non-ODA: £2.7 m
Spend this FY	ODA: £2.7 m			Non-ODA: £2.7 m
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
High quality strategic advice, infantry, medical and international humanitarian law training provided to the European Union Training Mission (EUTM)					B
Selected officers from regional armed forces supported by the UK in professional development					B
G5 Sahel-Force Conjointe (G5S-FC) provided with high quality materiel and human rights support					B
Personnel in regional security forces trained to more effectively generate and act on intelligence					B
Overall output score					B
Outcome Assessment: The outcomes sought at this stage are assessed as being below where they should be at this stage in the programme cycle. A series of urgent recommendations are set out in this review.
Outcome Score: B			Risk: High

Summary of Programme Performance

Year	2015/16 **		2016/17 **		2017/18*		2018/19*
Programme Score	B	B	A	A	A	A	B	B
Risk Rating - low/medium/high	M (Multilaterals)	M (Security & Crime)	M (Multilaterals)	High (Security & Crime)	High (Multilaterals)	High (Security & Crime	High
*output/outcome scores
How has the programme changed during this period? / The Defence and Security programme is a new programme commencing in 2018. Prior to this, a ‘security’ component was included within the Borders, Security and Crime programme, and a ‘defence’ component was included within the Sahel Multilateral Programme.

What support did the UK provide in FY 18/19?

The UK provided strategically selected secondments to the European Union Training Mission (EUTM) in Mali. This included six military secondees, focused on infantry, medical and counter-IED training (four) and offering command-level strategic advice (two), as well as two civilian secondees, focused on providing international humanitarian law training and advisory support.

The UK provided support to send Sahel officers to both UK and regional defence-related courses, ranging from command and leadership training to operational and strategy courses. The UK also worked in partnership with other regional actors, such as the Ecole de Maintien de la Paix Alioune Blondin Beye (EMP), to develop their own capacity to develop and deliver training.

The UK provided direct financial support - using the EU’s coordination mechanism, though the Africa Peace Facility, with onward delivery by Expertise France - to the G5S-FC (Group of 5 Sahel States Joint Force). This was to be used for material support for the G5S-FC - personal protective equipment (body armour and helmets) and counter-IED equipment.

In Mali, the UK provided mentoring, training and other support to a dedicated team, staffed by the Direction Generale de la Securite Exterieure (DGSE), which conducts intelligence gathering on criminal groups and networks. The UK has also provided support to the Gendarmerie Nationale, in Bamako and Segou, to develop a dedicated intelligence cell to enable implementation of a future national intelligence collection pathway. In Senegal, the UK provided mentoring, training and other support to an anti-corruption unit (ACU), which acts as an intelligence capability designed to investigate corrupt officials.

Key results for FY 18/19:

Six military and two civilian secondees to the EUTM provided high-quality advice and training.

The UK supported 28 course places for Sahel officers on UK or regional defence-related courses, furthering the professional development of Sahelien officers.

Provision of material support, in the form of equipment and services, to the G5S-FC.

In Mali, construction of a new office complex for the NCA-mentored, intelligence team.

In Senegal, the NCA intelligence shared with regional partners by the NCA mentored team of the Anti-Corruption Unit led to the seizure of 789kg of cocaine in Guinea Bissau - the largest seizure recorded in the country. Post-seizure investigations uncovered links to a narco-terrorist crime group trafficking cocaine from South America to West Africa for distribution in Europe.

Summary of progress and lessons learnt/actions taken since last review

The Defence and Security programme is a new programme. Prior to this, a security component was included within the Borders, Security and Crime programme, and a defence component within the Sahel Multilateral Programme.

Summary of recommendations for the next year

The difficult external and internal operating environment for the team should be taken into account when reading the following recommendations. The team had only recently expanded from three to six people and were operating in an uncertain domestic and regional climate, along with ongoing Embassy platform constraints.

Fully complete the Results Framework: A results framework was prepared in January 2019, but remained incomplete at the time of the review. This is an urgent requirement without which there are value for money concerns.

Refresh the risk register and provide a risk rating for each output: There are NSC Sahel Strategy and Defence and Security programme risk registers but these need updating, particularly given the high-risk rating of the programme.

Integrate cross-cutting thematic considerations (conflict sensitivity, gender, and human rights): Whilst the new results framework incorporates conflict sensitivity and gender markers, all three cross-cutting themes should be incorporated and reviewed in accordance with HMG guidance. An Overseas Security and Justice Assessment (OSJA) should be completed for the UK support to the Gendarmerie.

Consider re-balancing defence-related support, including using other delivery models: It is recommended that other methods of support to the G5S-FC are explored, as well as exploring indeed if support should be continued. The G5 continues to present human rights concerns; this risk has been mitigated by delivering the equipment through Expertise France but their own performance remains patchy with spending delays and an unclear earmarking process.

Broader and deeper professional development support by the UK through other actors such as EUTM or the MoD should also be considered, as current projects demonstrate more positive results and enhanced UK influence.

As regional serious organised crime strategies and corresponding projects are developed, consider splitting out the defence and security elements, as well as moving them into the CSSF Sahel Stabilisation programme.

Re-consider support to the Gendarmerie, and re-focus security support in Mali: Support to the Gendarmerie should be modified to include putting in place risk mitigation measures and cooperation agreements with the Government of Mali. An improved delivery model and an updated contract were being negotiated at the time of the review, which will determine any future collaboration. It may also be worth considering prioritising support to the NCA DGSE project.

Align work with global and eventual regional Serious Organised Crime (SOC) strategies, and develop training delivery plans based on need: The SOC programmes in Mali and Senegal could align further with the HMG Global SOC Strategy when they are published. NCA’s work in Senegal, and particularly Mali, should benefit from the development of a regional SOC strategy, and the Mali office is encouraged to consider participating regularly in JSOC meetings. Both NCA offices would benefit from a clear training delivery plan, based on strategic needs, and developing an exit strategy for CSSF funding. Senegal should continue its work towards encouraging an operational, dedicated unit to action investigatory finds.