Annual Review - Summary Sheet

PROGRAMME TITLE: Sahel Stabilisation
Country and Region:	Sahel: Mali, Chad, Niger
IATI Unique ID:	CSSF-03-000024
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: £17.5m			Non-ODA: £0.1m
Budget this FY	ODA: £3.1m			Non-ODA: £0.1m
Spend this FY	ODA: £3.5m			Non-ODA: £0.1m
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
New knowledge & understanding about conflict dynamics and interventions generated, including on women's roles and experiences;					B
UK participates at strategic level in international efforts towards stabilisation in Mali;					A
UK contribution (through the MINUSMA (United Nations Multidimensional Integrated Stabilization Mission in Mali) Trust Fund) expedites the Malian Government’s central Mali stabilisation efforts under its strategy for the central regions (PSIRC);					B
Public awareness raising activities in support of peacebuilding in Mali and Niger;					A
Cooperation and trust increased between population and security forces in Mali & Niger.					A
Overall output score					A
Outcome Assessment: / In 2018/19 the newly-shaped Stabilisation programme aimed to a) increase UK knowledge and understanding of the Sahelian conflicts so that the UK is able to better influence international decision making on this region; and b) to help make selected parts of the Sahel region more secure. / The new programme’s first year has been hampered by an inadequate Monitoring, Evaluation & Learning (MEL) framework, a lack of capacity, some procurement challenges, and a lack of a clear positioning for the programme. / Real successes have been achieved nonetheless – not least the coordination role within the highly efficient MINUSMA Trust Fund, continued high-calibre media work, secondments with relevant institutions, and an ambitious research plan which should bear fruit in 2019/20 and bring political leverage for the UK within the international community.
Outcome Score: B			Risk: Medium

Summary of Programme Performance

Year	2015/16	2016/17	2017/18		2018/19*
Programme Score	N/A	N/A	A	B	A	B
Risk Rating - low/medium/high	N/A	N/A	Medium		Medium
*output/outcome scores
How the programme has changed during this period: Between 2017/18 and 2018/19 the programme was streamlined with elements of two separate programmes reformulated into one. The results of 17/18 are taken from the most similar “Conflict Reduction and Stabilisation Programme”.

What support did the UK provide in FY 18/19?

- Financial support to stabilisation efforts in Central Mali through a contribution to the MINUSMA Trust Fund and PSIRC (the Stabilisation plan of the Malian government (GoM));
- Commissioning of research into: (i) violent extremism, transnational organised crime and inter-community and intra-communal conflicts in the Liptako-Gourma region (ii) young women’s engagement in violent extremists’ groups in Mali and Niger (iii) support to the G5 Sahel Joint Force mediation efforts and decentralisation in support of the peace process and (iv) decentralisation;
- Local level peacebuilding support to independent media in Niger;
- Two secondments with strategic-level roles to the EU Delegation’s Art. 28 mission; one secondment to the AFD in Paris;
- One high profile workshop on SU 'Elite Bargains' study workshop;
- Scoping of opportunities for bespoke UK support to the peace process in Northern Mali and for stabilisation activities in Chad.

Key results for FY 18/19:

- Improvement in operating conditions for UN peacekeepers, including securitisation of 6 camps and deployment of 60 members of the Malian gendarmerie;
- Enhancement of UK relations with UN, donors, governments and security actors through stabilisation support;
- Increased level of donor coordination within MINUSMA TF as a result of CSSF coordination;
- Improved HMG capability to provide authoritative information on Sahel dynamics, and potentially to play mediation role, as a result of commissioned research;
- Improved relations between community members and security forces in targeted areas (In Mali the regions of Mopti and Gao, in Niger the communes of Abala, Ayorou, Banibangou, Bankilare, Sanam, and Tera);
- Exposure of peace and stabilisation-orientated messaging to a potential 65% of the Nigerien population (216 news bulletins and magazines and over 400 news items) and in Mali, through 8 partner radio stations, 51 ‘roundtables’, broadcast 478 times; and
- Increase in sophistication of French stabilisation work.

Summary of progress and lessons learnt/actions taken since last review
Revise the Results Framework: Last year’s annual review stated that ‘a significantly revised approach will be needed in 18/19 to ensure tangible and sustainable outcomes’. The team responded to this in two main ways. Firstly, it contracted an independent MEL provider and has worked with this firm since Q3 2018/19. The results framework was given significant attention by the team and new MEL provider (including an initial visit by the provider in January of 2019), but further improvements are needed.

Lessons: Last year’s report stated that ‘More effort should be placed on learning lessons on what works, and adapting projects as required’ This was addressed through the research to showcase the impact of elite bargains in peacebuilding as part of wider research and analysis conducted by the UK Stabilisation Unit.

Better coordination: Last year’s report stated that ‘… there is still a lack of coordination within the international community, and therefore a risk of duplication or gaps in programming. However, there is scope to improve this, and the UK can play a key role as it is seen as a collaborative, but more neutral player than others. … One external option would be to support the capacity of the MINUSMA Trust fund to lead this more consistently’. This is precisely what the team has done and to good effect.

Resources: Last year’s report stated that ‘While a strong programme team is now in post, there is a risk that they are at capacity and may not be able to support an uplift with the same diligence and scrutiny’ and that ‘A wider staffing uplift would also benefit the CSSF’. This report concludes that this area has remained something of a weakness.

Timelines: Last year’s report stated that ‘multi-year funding arrangements should be considered for the Sahel CSSF’. This year’s report draws the same conclusion, in response to appeals from partners for the same.

Summary of recommendations for the next year

Enhance Monitoring, Evaluation and Learning: A revamp of the Results Framework (RF) and Theory of Change (ToC) is still required. The new ToC must be adequately underpinned by evidence and show the assumptions embedded in it. More coherence should be achieved between the ToC and an enhanced RF that contains indicators which are more ‘SMART’ (Specific, Measurable, Achievable, Realistic and Time-Bound), are premised on quantitative baselines and associated with logical milestones and targets, with improvement especially in regards to outcomes. The team should maintain a running log of progress on each indicator, updated on a quarterly basis, and record case studies systematically.

Boost research and contextual understanding to amplify effort: The focus on the research programme should shift towards understanding the real fundamental drivers of conflict. The four-year gap since the most recent JACS risks an inadequate overall view of a highly dynamic context. A JACS, or ‘mini-JACS’ carried out jointly with other donors could provide a common platform of analysis that may lead to more opportunities for coordination and political leverage.

Consideration of clear positioning: Programmes may contain projects that are highly cohesive and relate to a clear positioning, or they may be diffuse in their nature, in order to touch a wider spectrum of issues. In a complex context such as the Sahel, and with relatively little funding still at its disposal, a clear positioning may plausibly yield more benefit. Two options already stand out. The first is one the CSSF has already considered – ‘stabilisation’. This is worth pursuing, perhaps by taking forward the Elite Bargains work with a Sahel-dedicated pilot. In addition, the UK may want to consider piggybacking on the highly successful work done by the UK with MINUSMA, and make ‘coordination’ its central tenet. Coordination could be extended for example into research and/or contextual analysis, as above. Ideally, the team would reflect on its preference for a clear positioning or not, and if yes, include this within in its work plans for quarter two and three 2019/20 research on the activities and focus of other actors, to underpin such a decision.

Capacity: While the Programme Document states that ‘the Sahel CSSF team now has all the requisite staff in place in order to effectively manage the CSSF programmes from an administrative and political perspective’, it is our observation that this is only partly true. The current team is performing to a high level, however it seems questionable that the team has capacity to meet the ambition of the UK Government in the year to come without further resources.

Geographic expansion: ‘The conflict has spread to bordering Niger and Burkina Faso’ and has put ‘communities in Burkina Faso under increasing pressure’. Yet there is no CSSF presence there. At the same time, there is political pressure to expand in a post-Brexit setting. Appreciating that this is much-discussed inside HMG and hugely complex, further consideration should be given to establishing CSSF programmes in Burkina Faso (even if this is only viable in a way that mirrors the small operation in Niger) for a genuine Sahel-wide portfolio to be as successful as possible.