Annual Review - Summary Sheet

PROGRAMME TITLE: Somaliland CSSF Programme
Country and Region:	Somalia, Africa
IATI Unique ID:	CSSF-03-000012
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: £11.10m			Non-ODA: £1. 60m
Budget this FY	ODA: £3.04m			Non-ODA: £0.45m
Spend this FY	ODA: £3.05m			Non-ODA: £0.46m
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Institutional capacity, accountability, transparency and security of Somaliland Justice institutions is strengthened					A
Sustainability of Counter Terrorism capacity of Somaliland Police (SLP) is strengthened [outdated but remains in the Results Framework]					B
Institutional capacity, accountability and democratic oversight of defence institutions (MOD, Army, coastguard) is strengthened					B
Somaliland's electoral authorities have increased technical capacity and credibility					B
Government of Somaliland communications capacity and relationship with media is enhanced					A
Overall output score					B
Outcome Assessment / The programme has made some good progress towards the outcome statement “Somaliland is increasingly secure and stable, with increasingly accountable and transparent institutions, and a constructive partner on HMG objectives”. The programme contributed to peaceful presidential elections in the previous FY, but delays in parliamentary elections during this FY meant that it could not provide further election support. Substantial progress has been made on accountability and transparency of the criminal justice system and the military, and improved planning, coordination and communication for maritime surveillance with the coastguard. The programme has exceptional access to key government officials. Despite an overall output score of B, partially due to poor indicators in the results framework, the programme shows good progress towards the outcome and therefore scores an A. However, there are substantial questions about sustainability of this progress, which will need to be demonstrated during the extension phase of programme.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	B	A	A	B	B	A
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium
*output/outcome scores
How has the programme changed during this period? / Security and justice component continues; Media component ended in March 2019; New elections registration support component with Interpeace added for this year.

What support did the UK provide in FY 18/19?
- Security and Justice Reform: UK support provided capacity-building training and mentoring, equipment and infrastructure for Somaliland Ministry of Defence, the army, the coast guard, the judiciary, and the police (Implemented by Axiom).
- Media: training and mentoring with the Ministry of Information (MOI) and individual media houses, and the University of Hargeisa journalism degree for communications professionals (implemented by Coffey International).
- Elections: updating voter registration system in advance of parliamentary elections due to take place in late 2019 (implemented by InterPeace).

Key results for FY 18/19:
- Somaliland Ministry of Defence is now more capable of providing oversight for the army and has made more use of human resource practices.
- The Somaliland Coast Guard is equipped with operational management software systems (ASAAS) which has improved planning, coordination and communication for maritime surveillance to counter piracy, organised crime and smuggling networks.
- Increased accountability in justice and defence sectors, and increased transparency in the justice sector as a result of the well-functioning Monitoring and Inspection Committee (MIC).
- A Media Law (providing protection to journalists working to an agreed code of conduct) is fully drafted and agreed with the Ministry of Information, awaiting approval by Parliament.

Summary of progress and lessons learnt/actions taken since last review
The programme has made some progress towards its outcome of Somaliland becoming increasingly secure and stable, with increasingly accountable and transparent institutions, and a constructive partner on UK Government objectives. As highlighted above, there have been real achievements towards the outcome, and there is a strong demonstration of partnership and UK political access and influence, particularly with the judiciary, Ministry of Defence and coastguard.

Progress against the recommendations from the last annual review has been somewhat limited, noting that some of these are feeding into a new programme design in slower time and transition year activities for FY 19/20. For example, there have been discussions with UK Government stakeholders about how the CSSF programme should fit with other UK funding, shaping design of a new programme (which is also drawing on the May 2018 conflict analysis). While this has led to development of a new theory of change, there does not appear to have been any amendment to the current one, or any (documented) consideration of what would be achievable across the overall programme outputs. Similarly, there does not seem to have been any attempt to make the political stability strand ‘more political’, or rebalance the portfolio between security and justice and wider political stability (again, this is planned for the new programme).

Some limited actions were taken around agreeing the results framework in conjunction with the implementing partners: a workshop was held with Axiom in June 2018 to share findings from the conflict analysis, and component-level results frameworks have been updated. However, planned steps to align these with the overall results framework and improve the breadth and sources of monitoring evidence did not go ahead.

Summary of recommendations for the next year
Develop a clear UK Government approach to Somaliland, identifying clear priorities for government departments and funding mechanisms (DFID, FCO, CSSF, Prosperity Fund, and CTPF) and maximising complementarity and alignment.

Consider which elements of the programme should really be delivered by DFID (particularly security and justice reform activities, which fit better under a DFID mandate), building on the foundations of the CSSF Security and Justice programme. This could free up CSSF resources for high risk, short term and/or catalytic activities.

The results framework should be updated to reflect current implementation of the programme and have realistic and achievable milestones for March 2020, as well as measurable indicators and clear plan for assessing them.

1. Reduce the breadth of the programme and match with sufficient policy/ advisory oversight and direction, and programme management support.
2. Develop a clear sustainability approach and exit or transition strategy, for all elements of the programme.