Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF South Sudan Conflict and Resilience Programme FY18/19
Country and Region:	South Sudan
IATI Unique ID:	CSSF-03-000029
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development DFID
Total Budget :	ODA: £14.60m			Non-ODA:
Budget this FY	ODA: £4.48m			Non-ODA:
Spend this FY	ODA: £4.26m			Non-ODA:
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
Coordination and coherence: UK engagement supports national, regional and international actors to employ increased coherent messaging and strategies promoting peace and stability.					A
Accountability: Actors directly or indirectly contributing to conflict and violence are increasingly held to account					A
Inclusivity: Marginalised voices and communities are increasingly included in peace process and decision-making					B
Capacities: Increased capacities of constituencies, communities and leaders to manage and resolve conflict					A
Evidence and learning: Conflict/gender sensitive UK Government and international responses informed and adapted on the basis of emerging evidence, via lesson learning					A
Overall output score: A
Outcome Assessment: Progress has been made in some areas. However, contextual realities have prevented full progress against an ambitious set of outcomes. In addition, there are some limitations to the linkages between projects, outputs and outcomes.
Outcome Score: B			Risk: Medium-High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score		B	A	B	A	B
Risk Rating - low/medium/high		High	Medium	Medium	Med-High
*output/outcome scores

What support did the UK provide in FY 18/19?
The CSSF has supported:

Two implementation and monitoring bodies under the revitalised peace process, the Joint Monitoring and Evaluation Commission (R-JMEC) and the Ceasefire and Transitional Security Arrangements Monitoring and Verification Mechanism (CTSAMVM);
The UK’s technical expertise to South Sudan, including through providing HMG staff;
The South Sudan Council of Churches (SSCC) to implement their Action Plan for Peace (APP) which supports inter-church peacebuilding and reconciliation;
The Conflict Early Warning and Response System (CEWARS), which alerts authorities to conflicts, supports responses and builds local conflict-management capacities in three sub-national areas;
The Preventing Violence and Building Safer Communities (BSC) project, which focuses on civilian protection and gender-based violence issues in Wau;
The Conflict Sensitivity Resource Facility (CSRF), a pilot programme that aims to ensure donors and their implementing partners in South Sudan are conflict sensitive; and
The creation of a Peacebuilding Opportunities Fund (POF), which will work at both national and sub-national levels.

Key results and progress for FY 18/19:

Through supporting UK diplomatic influence, the peace process architecture, and the SSCC, the CSSF programme has contributed to greater coordination and coherence amongst international, regional and national actors on the peace process. Some progress has been made in promoting greater inclusion in the process. Through the provision of experts, the programme has supported the functioning of two peace process implementation mechanisms which has had some impact on accountability, despite a challenging operating context.

Progress has been made in supporting more inclusive and better-coordinated peacebuilding architecture. Support for the CEWARS has made it more inclusive and, through capacity building, more coordinated. Tangible coordination architecture has been developed between the country’s main churches through support for the SSCC. The BSC project has led to the creation of structures such as Women Protection Teams in the area it works. Progress has also been made in supporting targeted communities to be more resilient and able to resolve conflicts. Both the CEWARS and BSC projects appear to have had a positive impact in the locations they work. While nascent, there is some evidence of SSCC structures delivering a positive impact.

There has been significant progress, through CSRF, in generating evidence and learning across HMG and amongst several other donors. That the CSRF has been successfully piloted and ported to DFID is a positive result. There has been some progress has been made towards establishing the POF.

Summary of key changes and actions taken since last review

In line with AR 17/18 AR recommendation, the programme has maintained its level of support for the peace process bodies and ensured that it continues to be flexible. The programme has combined its national and subnational streams into a single programme to ensure it is flexible and strategic. A new results framework has been developed. A decision has been made to end support for two projects, the BSC and CEWARS, in the next year. The CSRF has been successfully ported to DFID.

Summary of key recommendations for the next year

1. Maintain a flexible posture in the face of an uncertain context whilst being clear about what the CSSF can and cannot influence.
2. Build on past effort responding to the risks (and limitations) around the peace process, in the design of the programme. This should include a focus on how to keep the peace process on track; what to do if it collapses; when and how to work on the longer-term issues of inclusive and accountable governance, security and justice, social reconciliation; and how to respond to changes in Sudan.
3. Building off the progress made in consolidating two strands into one, strengthen the linkages between projects within the programme whilst considering future complementarity with DFID programming in the conflict, security and justice area.
4. Continue to implement the commitment to learning and an adaptive approach through creating dedicated structures, allowing more field visits and establishing a local advisory group.
5. Re-open the results framework to ensure that the outcomes, outputs and projects are effectively captured and linked, and that indicators and the reporting against them is meaningful.
6. Review governance arrangements to ensure that it is best suited to the shifting context in Sudan and South Sudan and the changed portfolio of projects.