Annual Review - Summary Sheet

PROGRAMME TITLE: Strengthening Security and Resilience in Sierra Leone and Neighbouring Countries
Country and Region:	Sierra Leone, Guinea and Liberia
IATI Unique ID:	CSSF-03-000010
HMG Partners / (LEAD in bold)	Ministry of Defence (MoD), Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: £5.24m			Non-ODA: £5.23m
Budget this FY	ODA: £1.20m			Non-ODA: £1.42m (including uplift)
Spend this FY	ODA: £1.26m			Non-ODA: £1.45m
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Improved and more inclusive security sector governance					A
Increased capability, effectiveness and responsiveness of targeted institutions					B
Horton Academy is capable and self-sustaining					A
International Security Advisory Team access, reputation, and influence in the Sierra Leonean security sector					A
Overall output score: A
Outcome Assessment: “A capable, accountable and responsive security architecture ensuring stability in Sierra Leone through a sub-regional approach”. Over the four-year programme until March 2020, there is a good chance that the outcome will have been progressed, but it is unlikely to have been achieved in full.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	B	A	A	A	A	B
Risk Rating - low/medium/high	N/A	High	Medium		Medium
*output/outcome scores
How has the programme changed during this period? / The programme has worked through training, mentoring, advising and influencing to increase the professionalism, coherence, accountability and sustainability of the Sierra Leonean (SL) security sector. However, the programme has adapted over the period. It has shifted to deal with changing external shocks and challenges (e.g. Ebola response, hotly contested 2018 elections), but also to mirror UK Government priorities, with a greater emphasis on accountability, resource management, partner ownership and sustainability, and more focus on conflict sensitivity, gender and human rights considerations. The programme has also become more effectively cross-sectoral, looking to address the structural weakness of the police and of civilian oversight. Cross-government working has deepened.

What support did the UK provide in FY 18/19?

Working to a refreshed HMG Strategy for Sierra Leone and Neighbouring Countries, the programme’s (ISAT) main effort was to strengthen security and resilience in Sierra Leone by enabling the development of “security and justice institutions that are increasingly accountable, coordinated and capable of coherent planning, delivery and resource management; regional defence cooperation; maintaining land and maritime border security; tackling transnational and organised crime; and contributing standby forces to support pan-continental peace support efforts.”

This was done through advisory input and mentoring and training across the Sierra Leonean security sector but focused mainly on the Republic of Sierra Leone Armed Forces (RSLAF), Ministry of Defence (MOD), Sierra Leone Police (SLP) and Office of National Security (ONS). To seek to address the relative weakness of the SLP compared to the RSLAF, the programme sought to rebalance activity towards the police, but to date funding has not been secured to the extent required for transformative effect.

ISAT also oversees the running of the Horton Academy (HA). This provides training to the RSLAF as well as to other agencies and bodies in the security sector, and increasingly to the Economic Community of West Africa States (ECOWAS) regional participants. Horton Academy has consolidated its reputation as a regional centre of excellence, with a view to building African peace and security capability. In 18/19, for the first time Horton Academy began to draw in some funding from participants.

Key results for FY 18/19:

- ISAT mentoring and influencing has strengthened the primacy of the ONS as the key civilian oversight and coordination mechanism for the security sector, as recognised by the new administration.
- ISAT advice resulted in the creation of a directorate in the SLP to investigate internal and external complaints about the police and deal with disciplinary investigations, and delivered investigative training, showing SLP acknowledges a need for greater accountability.
- ISAT-trained police trainers completed host nation-led training for their Formed Police Unit (FPU) mission in Somalia, contributing to Peace Support Operations (PSOs) and suggesting that ISAT training is becoming more institutionalised, e.g. in the Sierra Leone Peacekeeping and Law Enforcement Academy.
- ISAT enabled the recruitment and basic training of 328 women recruits for RSLAF, addressing its gender imbalance and contributing to PSO deployability.
- ISAT prompted RSLAF to begin planning and training for the disposal of over 22 tonnes of condemned ammunition.
- A total of 239 officers from ten ECOWAS partners and five SL security agencies were trained at Horton Academy at junior, intermediate, senior and commander level, building regional skills and PSO interoperability.
- ISAT enabled RSLAF to deploy Force Reconnaissance Unit (FRU) to the Guinean border.

Summary of progress and lessons learnt/actions taken since last review

- In response to a recommendation to review the strategic direction and delivery of the programme, the Head of ISAT submitted a paper on the future of ISAT in January 2019.
- The Local Strategy Board, working across HMG stakeholders, commissioned the much-needed analytical baseline for an understanding of dynamics and priorities. Analysis on conflict, security and justice, and accountability are being incorporated into future programme design.
- In order to enable an integrated approach on S&J, a working group was established between ISAT, DFID and FCO, to help inform DFID’s return to the sector.
- Strong engagement with the new administration, including a visit by the President and Vice President to ISAT to hear messages on prioritisation and local ownership, where he gave commitments, including on Horton Academy transition.
- ISAT shifted quickly to new priorities of national revenue generation and management, with a sharper focus on maritime and border security.

Summary of recommendations for the next year

1. Build on “future ISAT” work to date, articulate and drive a realistic multi-year plan for what the programme could achieve over a transition period, assuming likely flat allocations. Protect key investments so far and clearly articulate exit points, both to the Centre and more transactionally with partners.
2. Progressively transition interventions from the tactical towards the structural, to foster ownership and sustainable outcomes, rather than substituting capacity. The increasing effectiveness and primacy of the ONS should give this approach more traction than in the past, while in the SLP and RSLAF the senior leadership will need increased mentoring in strategic prioritisation and oversight.
3. Build on the recommendations of the police accountability and other studies to strengthen accountability structures and regulations both within and operating upon the SLP. This will be political, however, and must recognise that deficits may result from vested interests rather than a lack of training or capability, so this will need coherent UK Government messaging to encourage buy-in.
4. Work closely with DFID, helping to inform their agenda as they move back into security and justice programming, and looking for opportunities to utilise pilot funds as they come on stream, recognising that flat CSSF resources alone will not be sufficient to effect the scale of rebalancing required.

1. On the RSLAF, use full spectrum UK messaging to push for resource prioritisation for the security sector, focussed on areas that will build sustainability e.g. investing in realistic PSO readiness, and strengthening national revenues from maritime and border security, while helping to deter ill-considered and unfunded schemes.
2. Responsively review the balance of advisory support. The programme can respond to the very positive beneficiary feedback on the importance of the resource management role (currently gapped) which aligns well with government-wide interests in better revenue management. The programme can also similarly prioritise maritime security, using ISAT’s convening power to co-ordinate partners’ work on the issue.
3. In order to protect significant long-term UK Government investment in Horton Academy, and the regional influence it brings, develop clear progressive financial milestones on the way to transitioning the Academy sustainably. Do this by increasing the breadth of regional attendees, developing sponsorship possibilities (challenging, due to the UK’s perceived leadership in the sector), e.g. from the USA, and encouraging Sierra Leonean input. But also advance contingency planning for scenarios where adequate resources are not forthcoming.
4. Refresh programme documentation better to capture all significant qualitative and quantitative evidence of impact, access and influence, while presenting evidence more coherently to make it easier to track progress; work on a more comprehensive theory of change, with cross-government buy-in, using governance structures and working groups as regular sounding boards; include more independent reporting and feedback to assure evidence.
5. Review the risk register to remove contextual assumptions and constraints, and avoid over-classifying risk.
6. With the CSSF lead, build on the excellent work on tapping into Joint Funds Unit/ network expertise on conflict sensitivity (CS) to ensure a rolling programme of integrating best practise on cross-cutting issues like CS, but also gender and human rights, and ensure new designate offers receive appropriate pre-deployment training.