Annual Review - Summary Sheet

PROGRAMME TITLE: CARIBBEAN SERIOUS ORGANISED CRIME PROGRAMME
Country/Region:	Caribbean/Americas
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO); National Crime Agency (NCA); Crown Prosecution Service (CPS); Home Office (Immigration Enforcement International(IEI), ACRO)); Department for International Development (DFID) and Ministry of Defence(MoD)
IATI Unique ID	CSSF-04-000001
Total Budget:	ODA: £18.71m	Non-ODA: £1.58m
Budget this FY:	ODA: £3.83m	Non-ODA: £0.32m
Spend this FY:	ODA: £3.90m	Non-ODA: £0.31m
Original Start Date: April 2017		Planned End Date: March 2018
Revised Start Date: April 2017		Actual End Date: March 2019
Outputs					Score
Capacity within the Jamaican Justice System (Criminal Justice Advisor)				CPS	A
Support to Digitisation of Police Records (Jamaica)				ACRO	A
Support to SOC Operations (Jamaica)				NCA	C
Strategic Corrections Project (Jamaica)				DFID	A
Maritime Skills and Leadership Training (Regional)				MoD	C
Enhancement of Fusion Centre Capacity in Digital Forensics (Barbados)				NCA	-
Deployment to Joint Regional Communication Centre (JRCC) (Barbados)				HO/IEI	A
Support to Eastern Caribbean SOC Processes (Barbados)				CPS	A
Guyana Financial Mentor to Special Organised Crime Unit (Guyana)				NCA	C
Guyana Security Sector Reform				FCO	B
Support to SOC Operations (Dominican Republic)				NCA	C
Trinidad & Tobago Criminal Justice Reform				FCO	B
Overall output score B
Outcome Assessment:
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	B	C	B	C	B	B
Risk Rating	Unknown	Unknown	Unknown		Medium

*output/outcome scores

What support is the UK providing?
CSSF is providing funding to improve the ability of Caribbean governments, judiciaries and law enforcement agencies to prevent and disrupt serious organised crime (SOC), which impacts both the region and UK. This is done through the provision of expert advisors and technical assistance; UK Government-led project delivery; externally procured project delivery and; bilateral support to specific governments.

Summary of progress and lessons learnt/actions taken since last review
Since the last annual review, significant efforts have been made to improve the strategic direction of the CSSF Caribbean programme. An ambitious HMG Caribbean strategy has been drafted to articulate the UK Government’s interests and objectives in the region. This will be used to bring a greater coherence to CSSF programme activity from FY 19/20.

In line with best practice, a regionally-chaired Caribbean CSSF Management Board (CCMB) has now been set-up, with the first meeting taking place in March 2019. The CCMB meets on a quarterly basis. There have been changes in ways of working, driven largely by the arrival of a new Head of Programme Team, based in Kingston. Additional regional programme management resource is now in place. In FY19/20 two more local project roles will be reframed as regional roles, bolstering the core programme management team. A Home Office Serious and Organised Crime network lead will arrive in April 2019 to coordinate SOC policy across the region. Decisions have already been taken to move some funding to the FCO baseline (ACRO Jamaica), to ensure greater oversight of project spend and to aid agility in the fund.

Programme documentation has been revised to include the full scope of CSSF activity in the region, including an updated Theory of Change (ToC). Supporting documents on project activity have now been provided by all departments in receipt of CSSF funds.

There’s an improved focus on cross-cutting thematic issues, demonstrated by the January 2019 Gender Workshop held in Trinidad. However, the gender review, recommended in the last AR, has not yet been undertaken.

Summary of recommendations for the next year

The Caribbean SOC Programme is an evolving portfolio. There continues to be improved programme compliance and reporting, underpinned by a much needed increase in staff capacity. In this context the Annual Review (AR) team recommends:

Strategic Alignment and Direction: The Caribbean CSSF Management Board and Conflict Stability and Security Fund Team should ensure activity aligns with the new HMG Caribbean Strategy. The Annual Review Team thinks this will require the Caribbean CSSF Management Board and programme team to agree a process for reviewing and redesigning the current portfolio and prioritise activity that promotes coherence and end activity which doesn’t meet this threshold.

Complementarity: The CCMB and CSSF Team should consider how CSSF compliments other HMG efforts. The Annual Review team thinks there are opportunities for HMG departments to work together more effectively.

Programme Documentation: The results framework (RF) and ToC need further development to reflect the progress made in specific areas, and fit with overarching strategic objectives.

Political Access and Influence (PAI): Whilst some initial work on PAI is being undertaken shortly, using Guyana and Trinidad as examples, the team should establish a method to measure the PAI of programme activity.

Evidence: A focus on gathering evidence to support what works in the region in relation to SOC activity would be useful in the proposed inception phase in Q1 of FY19/20.

ODA Eligibility: We recommend the ODA eligibility of some project activity is reassessed. The distinction between funding for core ‘operational’ business and programme activity, raised in last year’s AR, still needs to be addressed.

Exit strategies: Sustainable exit planning across the team is inconsistent. A more structured focus is necessary for the team to maximise the value for money of investment to date. At some point, CSSF investment will end and this should be factored into development of each project.

Diversity of focus: The CCMB and CSSF Team should consider whether SOC, including upstream activity, should remain the focus of the CSSF Caribbean programme. It is key that any review understands the necessity to focus programme activity effectively and to develop a greater level of effect within tighter points of reference.