Annual Review - Summary Sheet

PROGRAMME TITLE: Colombia and Peru CSSF Serious and Organised Crime Programme (Incorporating part of Colombian CSSF Security and Justice Programme)
Country and Region:	Latin America, Colombia and Peru
IATI Unique ID:	CSSF-04-000003
HMG Partners / (LEAD in bold)	National Crime Agency (NCA), Foreign and Commonwealth Office, Crown Prosecution Service,
Total Budget :	ODA: £8.75m			Non-ODA: £0
Budget this FY	ODA: £2.78m			Non-ODA: £0
Spend this FY	ODA: £3.01m			Non-ODA: £0
Original Programme Start Date: 2015		Planned End Date: 2020
Outputs					Score
Cluster 1 – Cross CJS Coordination					B
Cluster 2 – Reformed Criminal Justice Institutions					B
Cluster 3 – Advanced Tactical and Technical Capacity in Tackling Priority Crimes (in key thematic areas)					B
Cluster 4 – Corruption - Enhanced Colombian and Peruvian anti-corruption capacity.					B

Overall output score					B
Outcome Assessment: There is potential for strategic impact within some elements of the programme (e.g. anti-corruption, intelligence, financial investigations, integrity work and criminal justice training). However, the different elements/projects are at times disconnected and are not always delivered in a regionally coherent manner.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A/B	A	A	B	B	B
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium
*output/outcome scores
How has the programme changed during this period? / The Programme is in the process of transition and managing changing departmental priorities of the delivering agencies. This requires thought as to what the Programme will focus on and how it is delivered with the Programme team confirming steps are already under way to complete this process through next financial year.

What support did the UK provide in FY 18/19?
The support provided via the CSSF allocation consisted of the following:
- Colombia – Mentoring, Facilitation, Expert Assistance, Training support for the Fiscalia in the respect of criminal justice and anti-corruption work.
- Peru – Mentoring, Facilitation, Expert Assistance across the Fiscalia, Police and Integrity Commission (the latter of which sits within the Presidencia del Cosejo de Ministros). Support to the Peruvian Police.

Key results and findings for FY 18/19:
Overall, and across the region, the programme team has developed a strong understanding of key stakeholders in both the Colombian and Peruvian Governments, and the way in which most of the projects are contributing towards higher-level outcomes. More consideration could be given about how activity is situated alongside wider international/donor contributions, including the much larger package of support provided by the United States.

- A few projects stood out as being particularly well designed and, according to partners, having a real-world impact at the outcome level. In Colombia, these included support to the Counter-Narcotics Directorate of the Fiscalia on countering illicit finances, which showed potential, especially if it can be more closely integrated with network analysis capabilities (see below).
- Opportunities exist to increase the overall impact of the various projects within both Colombia and Peru, including by supporting their strategic/network analysis capabilities and the development of clear narratives that articulate the SOC threat. In Colombia, the obvious docking-in point would be the Counter Narcotics Directorate within the Fiscalia. We recommend that a dedicated scoping is conducted to that effect. This would also offer a means of bringing together information coming from the various projects into one coherent set of products. In Peru, such an approach would offer the Peruvian government with an improved understanding of the ‘top ten’ organisations operating in the country (a necessary baseline for activity)
- In Peru, the value of facilitating the training of prosecutors and judges was assessed to be high and of clear value to the beneficiaries (although such training need not necessarily be coordinated by a criminal justice adviser). Judges and judicial trainers in Lima highlighted the value of assistance, particularly with respect to approaching complex organised crime cases. In Colombia – a country which has benefited from continuous external assistance on achieving SOC-related criminal justice outcomes for the past four decades, the value and strategic impact of this support was much less clear.
- In Peru, CSSF-enabled support was provided and contributions made within the context of the Peruvian National Police Leadership Policy – a ministerial commitment to improve anti-corruption and integrity training. Feedback from the Ministry of Interior was that the training was deemed of very high value and quality and focussed on one of the country’s most pressing issues. It would seem logical for this support to be continued, albeit augmented by ‘real world’ capabilities such as tools aimed at anti-corruption reporting (further detail below).

Summary of progress and lessons learnt/actions taken since last review
- Progress in some areas since the last review seemed notable. Building on the above results, key areas which seemed to have been advanced were: (a) support to judges and judicial trainers in Peru; (b) Financial investigation training in both Peru and Colombia (a central component of the new regional serious and organised crime strategy) and (c) operational training provided to the Peruvian Police.
- Since the last review, there have been attempts at improving the programme documentation, particularly with respect to clarifying the main outcomes and milestones of the different projects and providing quarterly updates. Some projects would still benefit from setting out objectives more clearly.
- There is currently a lack of clarity on the extent to which the different projects amount to a regional programme, rather than a series of Colombia and Peru-specific activities. There are opportunities to clarify such interrelationships and linkages within the programme documents.
- The programme has reflected a number of the recommendations and suggestions of the previous annual review, such as continuing high-performing programmes and engaging extensively with the judiciary in order to identify the best entry points for support (see 2017/18 Annual Review).

Summary of recommendations for the next year
- Overall, greater coherence needs to be provided on the overall strategic purpose of the SOC programme. This includes how the different projects are connected to one another and how these are situated within an overall regional programme as well as the recent SOC strategy. This will be important in order to ensure a wider impact rather than a series of isolated projects in Colombia and Peru. Ways of achieving this might include demonstrating how mentoring in Colombia and Peru might offer start points or leads for counter illicit finance activity in Panama or ensuring that tactical mentoring efforts are reflected in strategic assessments. It should be noted that important steps have been made towards this end in recent months, including by way of a clear theory of change that reflects the priorities of the regional SOC strategy.
- Some of the current projects are performing well and are clearly achieving both diplomatic and operational dividends. These are well received by partners and genuinely seem to be making a difference. Others however, seem to be bolted on to previous activity or tangential in nature. In turn, and given the above point about needing to demonstrate more of a regional approach, this review recommends that an exercise is undertaken aimed at clarifying the potential connections between the projects that are performing well, whilst discontinuing those that are not (some of these are in the process of being wound down).
- Opportunities should be explored to ensure that key partners in Peru and Colombia are able to feed into the products of different CSSF supported projects within wider-ranging all source assessment. Providing support on social network analysis and strategic threat reporting would offer a low cost and potentially high impact of bringing together these different lines of work. This would likely require a dedicated scoping within the Fiscalia’s Office of Strategic Analysis in Colombia and the Strategic Analysis Unit within the Prosecutor’s Office in Peru. Such an approach would assist both partners in the region and HMG in developing a better understanding of the main and most prolific organised crime networks operating in the region.
There are clear opportunities to augment and bolster the impact of integrity and anti-corruption focussed work in Peru by way of more innovative solutions. One such opportunity that was discussed with interlocutors during the course of the review (and is supported by behavioural science research) was to make better use of scalable and technology-based capabilities, in line with the some of the key principles of the CSSF.
- Consideration should also be given to reducing the number of projects and activity that focus solely on ‘one off’ training events (such as workshops or classes) as opposed to more ‘hands on’ mentoring work or more innovative approaches. These latter approaches offer a clearer means of measuring output and impact.
- In Colombia, efforts have been made to connect the SOC programme with the Peace Process programme. This is logical on a number of levels, including with respect to adding coherence and complementarity between programmes. There is, however, a risk that the SOC programme becomes focussed on local (illicit) economic drivers of violence rather than on transnational supply chains and illicit financial flows – including to the UK. The two aims needn’t be mutually exclusive but the linkages ought to be clearly articulated within the programme document.