Annual Review - Summary Sheet

PROGRAMME TITLE: Security and Access to Justice for Peace Programme
Country and Region:	Colombia, Latin America
IATI Unique ID:	CSSF-04-000002
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office
Total Budget:	ODA: £38.42m			Non-ODA: 0
Budget this FY	ODA: £10.28m			Non-ODA: 0
Spend this FY	ODA: £10.33m			Non-ODA: 0
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Support the rural development and reintegration programmes to create opportunities for sustainable economic transformation of post-conflict areas					A
State security and justice capacity strengthened					A
Contribute to effective Government of Colombia communications to encourage public support for peace					A
Overall output score					A
Outcome Assessment: Strong performing programme with a mix of strategic and pilot interventions supporting the Colombian peace process and security and justice objectives
Outcome Score: A+			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	A	A	A	A+
Risk Rating - low/medium/high	Medium	Medium	Medium		Medium
*output/outcome scores
How has the programme changed during this period? The programme has attempted to adapt to the changing political and security context in Colombia, responding to challenges and opportunities to support the implementation of the peace process.

What support did the UK provide in FY 18/19?
The Security and Access to Justice for Peace Programme, hereafter referred to as the Colombia Peace Process (CPP) Programme, aims to support the Government of Colombia (GoC) to address the causes and symptoms of violent conflict thereby sustaining trust in and progress towards implementation of the historic peace agreement of November 2016 between the GoC and the Fuerzas Armadas Revolucionarias de Colombia (FARC). During 18/19, the programme supported 19 projects to the value of £10m, aimed at delivering progress against three intended outputs:

- Output 1: Support the rural development and reintegration programs to create opportunities for sustainable economic transformation of post-conflict areas.
- Output 2: State security and justice capacity strengthened.
- Output 3: Contribute to effective GoC communications to encourage public support for peace.

The programme is managed by a small CSSF team and implemented by several different partners, including the United Nations and its associated agencies, the British Council, and local and international non-governmental organisations (NGOs).

Key results for FY 18/19:
- The main result during the year has been the ability of the UK, through its multi-faceted CSSF programme and wider diplomatic initiatives, to help the incoming Government of Colombia meet its commitment to the implementation of the peace process. The programme adapted its interventions and engagement to the changing context to lock in some initial key peace deliverables in conflict-affected areas.
- The team was also able to use small amounts of CSSF funding to leverage greater investments, both from other HMG funds, as well as the Government and other donors.

Summary of progress and lessons learnt/actions taken since last review

Based on this light-touch Annual Review process, it is evident that the projects funded by the programme are relevant, effective and strategic in their objective of contributing to the stated outcome. The programme has performed strongly in a challenging year that was marked by a change in Government and various related challenges to the implementation of the peace agreement. Nonetheless, the programme and the team ensured that the programme was used to full effect by adapting the projects and interventions to deliver peace dividends, build confidence and trust, and ensure continued commitment to the peace deal by the incoming Government. These were all key elements to continue to support and build the conditions for long-term peace and stability. By providing flexible, critical and strategic support at key moments the UK cemented its reputation as one of the most responsive and influential members of the international community. Unfortunately, the results framework does not lend itself to capturing these results and this type of qualitative impact, but it is the reason that the Outcome Score is an A+, whilst output scores based on the results framework scored three A’s.

Lessons
- Context continues to matter, and activities and risks need to be adapted accordingly. One key contextual risk has been the deteriorating security in “post-conflict” areas, which are marked by increases in illicit economic activities as other armed groups occupy areas vacated by FARC . To mitigate this, the UK has encouraged UN Trust Fund resources to be deployed to fund reintegration projects and to accelerate delivery of the peace deal.
- Peacebuilding and statebuilding is a long term challenge.
- ­­­­­­­­The programme consists of a significant number of projects and interventions, which has placed a considerable management burden on the programme team.

Summary of recommendations for the next year
1. From a monitoring and evaluation perspective, a fixed results framework does not seem the right fit for this type of strategic and outcome-oriented programme. It is therefore recommended that alternative options for tracking progress and achievements is explored. The programme should consider developing a more flexible and adaptive results framework to allow the programme to adjust to changing context and better capture impact and outcomes.[1]
  [1] Adaptive programmes are those which make systematic, planned and intentional use of emerging knowledge and evidence to drive decisions on programme content, form and/or strategy over time. They can be an effective response to many of the complex and difficult to predict environments in which HMG works, allowing programmes to systematically test a range of approaches and select those that work best. DFID Using the Logical Framework for adaptive programming, 2016; Andrews, M. SearchFrames for Adaptive Work (more logical than logframes). https://buildingstatecapability.com/2016/06/06/searchframes-for-adaptive-work-more-logical-than-logframes/
2. All projects and activities should be linked to a simplified results framework. The programme Theory of Change document can then act as the programme’s key monitoring tool
3. The team should develop an indicator or results-focused approach to measuring or capturing the importance of UK influence/engagement with stakeholders.
4. Ensure greater coherence between the illicit economies and Colombia CSSF programmes, including on design and implementation processes and requirements for consistency regarding concept notes and proposals to ensure that there is clarity on Theory of Change, risks/assumptions, Monitoring and Evaluation, gender and conflict sensitivity, and sustainability/exit strategy.
5. Make better systematic use of short case studies on successes (and possibly failures or trying/failing/adapting) to capture all the interesting, innovative and challenging things that are being achieved through CSSF funding.
6. Engage the Americas Board about options to develop CSSF programmes in Venezuela, which would need a separate rapid response envelope. There is currently a risk that future Venezuela work could disrupt funding streams and initiatives supported through the high-performing Colombia CSSF programme.
7. Consider visibility and attribution of GoC work in the Territorially-Focussed Development Plans (PDETs – Planes de Desarollo Enfoque Territorial). There is currently a risk that we’re missing an opportunity to support an improved level of trust between GoC and communities in affected areas.
8. Consider updating the risk register to include migration challenges driven by the Venezuelan crisis and risks around crop substitution work.
9. Consider consolidating some of the interventions and/or recruiting more programme staff.
10. Commission an independent review of the funding to MAPP to determine impact, value for money and whether same level of support is justified in future years.