Annual Review - Summary Sheet

PROGRAMME TITLE: Commonwealth 18-20 Fund – Fairness Programme
Country and Region:	Commonwealth
IATI Unique ID:	CSSF-01-000012
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department of Health and Social Care (DHSC)
Total Budget :	ODA: £19.61m			Non-ODA: n/a
Budget this FY	ODA: £7.78m			Non-ODA: n/a
Spend this FY	ODA: £7.33m			Non-ODA: n/a
Original Programme Start Date: April 2018		Planned End Date: March 2020
Outputs					Score
Member States’ capacity to deliver on their commitments to create a fairer, more sustainable, prosperous, and secure future for their citizens is strengthened					A
The Commonwealth increases practical solidarity and enhances cooperation between Member States					B
Overall output score					A
Outcome Assessment: Outcome Assessment: Member states take new political, operational or legislative actions to deliver on their Commonwealth Heads Of Government Meeting (CHOGM) 2018 commitments / There is good evidence from the first year of the programme that projects’ capacity building activities will enable member states to deliver on their commitments relating to fairness.
Outcome Score: Member state actions – A			Risk: Medium
Outcome Assessment (Member States increase mutual support and coordination in international and regional organisations): / More could be done at project and programme level to improve solidarity and cooperation between member states. However, there is evidence that the programme also contributes to this outcome at a Fund level by providing examples of delivery and progress that UK Government policy engagement draws upon.
Outcome Score: Member state coordination – B

Summary of Programme Performance

Year	2018/19*		2019/20*
Programme Score	A	B
Risk Rating - low/medium/high	Medium
*output/outcome scores

What support did the UK provide in FY 18/19?

The Fairness programme is a group of 10 projects. These were as follows:

- Building Fairer, More Equal and More Inclusive Commonwealth Societies (£2.32M)
- Commonwealth Partnership for Democracy (£1.7M)
- Improving Work Opportunities for Young People in the Commonwealth (£0.15M)
- Time to Change Global (£0.38M)
- Pacific Commonwealth Equality Project (£0.55M)
- Commonwealth Electoral Observations (£1.0M)
- Network of Women Mediators (£0.7M)
- Supporting Small States at the Commonwealth Small States Office (CSSO) – Human Rights (£0.14m)
- Supporting Small States at the CSSO – Trade (£0.18m)
- Commonwealth Forum of National Human Rights Institutions (£0.2m)

The support provided by these projects was varied in its theme (including democracy, anti-discrimination and stigma, peacebuilding, human rights, and the rule of law). Mechanism of delivery also varied (including capacity building for institutions and civil society groups, conducting research and delivering knowledge sharing platforms, and training and mentoring individuals). They were delivered in different geographies (most projects had specific activities in between five and ten target Commonwealth countries, but some interventions were Commonwealth wide, and others were focused on regions like the Pacific or Caribbean).

Key results for FY 18/19:

As would be expected from a programme of 10 diverse projects which have only recently started up, results from the first year have been variable. Some projects have mobilised slowly due to delays in contracting and recruitment, so have yet to deliver results. However, most projects were able to start up effectively and have started to deliver good progress against outputs, and some early indications of progress towards outcomes. Selected key results from the projects achieved in the first year include:

- The Network of Women Mediators recruited 37 members across 15 Commonwealth countries.
- Supporting Commonwealth Small States at the Commonwealth Small States Office (CSSO) on human rights delivered a successful event on violence against women.
- Commonwealth Forum of National Human Rights Institutions (NHRIs) project ran a series of side events at Global Alliance of NHRIs, addressing advancing rights of minority groups.
- The Building Fairer, More Equal and More Inclusive Commonwealth Societies project started technical assistance in Namibia, Saint Lucia, Mauritius and Belize on legal protection for women, girls and LGBT people, and reforming discriminatory laws.
- Commonwealth Partnership for Democracy project held three successful regional events to strengthen inclusive and accountable democracy.
- Experts convened through the Improving Work opportunities for Young People in the Commonwealth project and set up six clusters of educational institutions in four target Commonwealth countries.
- Time to Change Global delivered training to project coordinators/champions in India and Ghana.
- Pacific Commonwealth Equality Project ran a regional seminar on the UN Convention Against Torture (UNCAT), leading to Samoa depositing its instrument of ratification of UNCAT; a request for a ratification scoping mission has been received from the Solomon Islands; Kiribati have drafted a cabinet paper recommending ratification of the UNCAT.
- Commonwealth Electoral Observations conducted strategic advance missions to Solomon Islands, Maldives, and Belize, as well as a full election observation mission in Nigeria.

Summary of recommendations for the next year

- Dealing with Qualitative Indicators – where possible, qualitative indicators should be avoided in favour of quantitative indicators to provide more objectivity.
- Identify and build on areas of commonality – more could be done at programme or fund level to find areas of commonality between projects and encourage projects to work together, share knowledge, and pull towards common objectives.
- Monitoring and Evaluation (M&E) beyond March 2020 – given the long term nature of impacts for many projects, the programme team should consider how they will monitor results beyond the programme close date of March 2020 to determine the effectiveness of project interventions and capture learnings for future. It would also be good to understand if there are unexpected results related to the project (such as effects beyond the countries the projects work directly with).
- Active use of M&E documents – it is recommended that projects are required to report progress in their quarterly reports using newly updated M&E documents – in particular for value for money.
- Beyond March 2020 – it is strongly recommended that a decision on the potential continuation of funding for each project is achieved as soon as possible (by August 2019 at the very latest), to allow projects sufficient time to plan an effective close-down which ensures a sustainable legacy, or adapt their activities to make best use of any potential extension.
- Risk Management – Project level risks are monitored by the project teams in their risk registers, and reported to the programme team in their quarterly reports. While the programme team does review these and takes note of high project risks they have identified (incorporating these into general programme risks which are reported to the programme board), this is only done informally. It is therefore recommended that a formal mechanism is put in place to ensure all high risks are escalated to the programme board to allow them to review, monitor and mitigate them, such as listing high project risks specifically at the end of the list of general programme risks.