Annual Review - Summary Sheet

PROGRAMME TITLE: Commonwealth 18-20 Fund – Prosperity Programme
Country and Region:	Commonwealth
IATI Unique ID:	CSSF-01-000010
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), / Department For International Development (DFID), Department for Education (DfE), Her Majesty’s Revenue and Customs (HMRC)
Total Budget :	ODA: £19.33m			Non-ODA: n/a
Budget this FY	ODA: £12.5m			Non-ODA: n/a
Spend this FY	ODA: £12.03m			Non-ODA: n/a
Original Programme Start Date: April 2018		Planned End Date: March 2020
Outputs					Score
Member States’ capacity to deliver on their commitments to create a fairer, more sustainable, prosperous, and secure future for their citizens is strengthened					A
The Commonwealth increases practical solidarity and enhances cooperation between Member States					A
Overall output score					A
Outcome Assessment (Member states take new political, operational or legislative actions to deliver on their Commonwealth Heads Of Government Meeting 2018 commitments): / All projects are delivering well against their capacity building objectives and appear on track to meet their targets by the end of year two. It is too early to assess fully how the training translates into member states taking the intended actions. The theory behind the interventions to drive change is reasonable, although change may take place after March 2020 when this programme is currently scheduled to end. However, without follow-on funding beyond March 2020 the programme and projects (with the exception of the Queen Elizabeth Commonwealth Scholarships) are not sustainable and there is a major risk that the gains made by this initial two year investment will not last or will be eroded.
Outcome Score: A			Risk: Medium

Outcome Assessment (Member States increase mutual support and coordination in international and regional organisations): / The Commonwealth 18-20 Fund has an overall objective to increase mutual support and cooperation in international and regional organisations, although this was not articulated as a specific objective for the Prosperity programme. However, projects can still contribute to this objective through their capacity building work: either because that work itself builds linkages or because it directly and significantly demonstrates the value of the Commonwealth; there is evidence that the programme contributes to this outcome at a Fund level by providing examples of delivery and progress that UK Government policy engagement draws upon. / The assessment of this review is that all projects are contributing towards greater cross-Commonwealth cooperation, although that objective is often less explicit and could be demonstrated as part of quarterly reporting. Progress is good, but more could be done: the network, peer learning and cooperation element of the Commonwealth Standards Network would benefit from more support in year two; the Association of Commonwealth Universities (implementer for the Queen Elizabeth Commonwealth Scholarships project) could think more explicitly about graduate networks and communities of practice; and addressing the relationship-building and peacebuilding elements of trade across all three projects would mean the programme could contribute more to the cooperation objective.
Outcome score (Commonwealth Coordination): A

Summary of Programme Performance

Year	2018/19*		2019/20
Programme Score	A	A
Risk Rating - low/medium/high	Medium
*output/outcome scores

What support did the UK provide in FY 18/19?

- SheTrades (£4.05m) aims to build the competitiveness of women owned businesses, cooperatives and associations in Nigeria, Ghana, Kenya and Bangladesh and to provide a platform for lesson sharing across the Commonwealth.
- Commonwealth Standards Network (£1.5m) supports the increased use of international standards as a tool to stimulate domestic economic performance and export potential across the Commonwealth.
- Trade Facilitation Agreement (TFA) project (£1.48m), aims to address barriers to cross-border trade between Commonwealth countries.
- An endowment to fund the Queen Elizabeth Commonwealth Scholarships project (£5m) allowing an additional seven scholarships to be offered per year on top of the current 15.

Key results for FY 18/19:

This was the first year of the programme, and many projects did not start running until mid-way through the year. It is still too early to expect significant results, but the following are worth highlighting:
- Thirty-nine Business Support Organisations in Bangladesh, Ghana, Kenya and Nigeria have received support to provide better services for women entrepreneurs.
- Thirty-eight countries have signed up to be part of the Commonwealth Standards Network.
- Activity in 16 Commonwealth countries to support new Trade Facilitation Agreements.
- A major Trade Facilitation Agreement Conference with 250 participants and 44 African countries represented.
- Twenty-one new scholars studying under the Queen Elizabeth Commonwealth Scheme in 16 different Commonwealth countries.
- Training and support delivered to 1,147 women owned businesses, with tools and information to improve their competitiveness.

Summary of recommendations for the next year:

- The programme and projects within it all need clarity about their future beyond March 2020 as soon as possible in order to plan and to ensure that progress made to date is sustained. This includes understanding whether the Commonwealth 18-20 Fund and the Prosperity programme will continue to exist.
- Consider how Commonwealth cooperation might be enhanced through the programme and projects in year two, including through lesson learning and sharing with member states.
- Immediately start to plan to put in place a sustainability strategy for each project.
- Develop work to explore issues around conflict sensitivity and gender among the three trade projects. Capture the learning and share with Joint Funds Unit and Stabilisation Unit for broader dissemination across the UK Government.
- Develop a programme level results framework. This can be a light-touch exercise that builds on work already started and pulls together key project indicators. Although previously discounted as an option by the Commonwealth 18-20 Fund, the absence of even a basic programme results framework has made conducting a programme level review much more difficult.
- Consider how SheTrades work specifically supporting the Commonwealth can be highlighted more to external stakeholders and reflected in how the Global Outlook tool and data within it is developed and presented.
- Ensure that the networking and peer support elements of the Commonwealth Standards Network project receive sufficient support and attention during year two.
- Undertake stricter geographical prioritisation for the Trade Facilitation Agreement work, based on diagnostic assessments.
- For the Queen Elizabeth Commonwealth Scholarships, encourage some focus on particular academic areas which promote either global goods across the Commonwealth and / or Commonwealth prosperity.