Annual Review - Summary Sheet

PROGRAMME TITLE: Commonwealth 18-20 Fund - Sustainability Programme
Country and Region:	Commonwealth
IATI Unique ID:	CSSF-01-000013
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for Environment, Food and Rural Affairs (DEFRA), / Department for International Development (DFID)
Total Budget:	ODA: £29.21m			Non-ODA: n/a
Budget this FY	ODA: £16.58m			Non-ODA: n/a
Spend this FY	ODA: £15.89m			Non-ODA: n/a
Original Programme Start Date: April 2018		Planned End Date: March 2020
Outputs					Score
Member States’ capacity to deliver on their commitments to create a fairer, more sustainable, prosperous, and secure future for their citizens is strengthened					A
The Commonwealth increases practical solidarity and enhances cooperation between Member States					B
Overall output score					A
Outcome Assessment (Member states take new political, operational or legislative actions to deliver on their CHOGM commitments): / There is good evidence in the first year of the programme that demonstrates member states taking action to deliver on the commitments made at the 2018 Commonwealth Heads of Government Meeting (CHOGM).
Outcome Score (actions): A			Risk: Medium
Outcome Assessment (Member States increase mutual support and coordination in international and regional organisations): / There is little evidence of member states coordinating at project and programme levels. However, there is evidence that the programme contributes to this outcome at a Fund level by providing examples of delivery and progress that UK Government policy engagement draws upon.
Outcome Score (coordination): B

Summary of Programme Performance

Year	2018/19*		2019/20*
Programme Score	A	B
Risk Rating - low/medium/high	Medium
*output/outcome scores

What support did the UK provide in FY 18/19?

As part of the UK’s efforts to deliver a more sustainable future under the Commonwealth 18-20 Fund, the UK funded six projects, covering three broad categories: increased resilience and responsiveness to climate change; conservation and sustainable use of the Ocean; and supporting the integration and inclusion of vulnerable populations. They aimed to:

- Enable more cost-effective, rapid and reliable disaster recovery in the Caribbean by strengthening planning and enabling the use of financial instruments like insurance to build resilience, speed recovery and reconstruction (£1.0m).
- Support creation of a hub of technical excellence to help Pacific Island states to develop and implement plans to tackle climate change (Nationally Determined Contributions) (£0.27m).
- Develop national plans for sustainable maritime economies in Small Island Developing States (SIDS) through the provision of baseline data and advice on the impact of climate change, navigation and trade, marine protection and food security (£8.67m).
- Develop Marine Litter Reduction Action Plans for four Commonwealth members (£2.44m).
- Contribute to the elimination of blinding trachoma as a public health problem in the Commonwealth by implementing the World Health Organization (WHO) endorsed (Surgery for trachomatous trichiasis, Antibiotics to clear ocular C. trachomatis infection, Facial cleanliness to reduce transmission of ocular C. trachomatis, Environmental improvement particularly improved access to water and sanitation) SAFE strategy for trachoma elimination (£3.0m).
- Accelerate socioeconomic improvement for Commonwealth women by fostering engagement from the mobile industry and relevant actors to increase access to life-enhancing mobile services (£0.51m).

Key results for FY 18/19:

2018/19 is the first year of the programme and results were affected by the slow mobilisation of some projects. However, a good trajectory of progress was seen, both in terms of achievement of outputs as well as early evidence of outcome level change. Some of the key achievements during the year were:

- 125 individuals from Vanuatu and Solomon Islands have participated in waste management workshops, leading to Vanuatu adopting a National Marine Litter action plan and the Solomon Islands being on track to do so.
- Over 7,500 trachomatous trichiasis (TT)[1] cases managed in Tanzania, Nigeria and Pakistan.
  [1] Trichiasis is the sight-threatening consequence of conjunctival scarring in trachoma, the most common infectious cause of blindness worldwide.
- A strong commitment was received from Telenor (a mobile and digital services provider) in Pakistan to take actions for improving mobile access and usage through EasyPaisia. A few initiatives have already been taken for birth registration in Pakistan and other pilot initiatives are in progress.
- Centre for Global Disaster Protection’s technical assistance through the World Bank has agreed to conduct domestic markets diagnostic work for Caribbean and the training and capacity building support to insurance regulators has been agreed with A2ii (Access to Insurance Initiative).
- The Nationally Determined Contributions (NDC) Hub has been established to address identified needs and priorities of Pacific Island Countries (PICs) to enhance and successfully implement their NDCs.

Summary of recommendations for the next year:

- Standardised project output reporting linked to results framework - All project partners are reporting on a quarterly basis using a standard template. The template reports progress which is too broad and high-level. It is recommended that an output-based reporting template, linked to outputs and outcomes as structured in the log-frame, should be developed.
- More nuanced and regular risk management – All six project partners are monitoring and recording the risks, both internal and external, using the project risk register. The quarterly report records very broad, high level risks. It is recommended that project level risks are reviewed on a regular basis during the routine meetings with the project partners, as well as reported in a structured format in the monthly progress reports.
- Strategic steer from the programme board – The sustainability programme board meets every quarter to take stock of activities under the programme. The board discusses the high-level risks and issues affecting the programme. It is recommended that a project level discussion on critical risks, outputs and challenges is to be initiated at the programme board to take strategic steer from the board chair.
- Reporting on CSSF cross cutting themes – It is important for implementing partners to regularly report on conflict sensitivity, gender and social inclusion and human rights. The programme should factor this in the quarterly reporting and issue guidelines for partners to streamline reporting.
- Programming beyond March 2020 – Using the findings of annual review, the programme should conduct broad lessons exercise or a series of consultations, covering both programme and policy to advise on programming beyond the lifetime of this programme.
- Communication and liaison with country offices – Although the programme team is engaging with the country offices at a strategic level, the projects also need to liaise with the country offices at a more operational level to make use of HMG resources on the ground for improving programme performance and policy leveraging.
- Improving Value for Money (VFM) Reporting – The quality of VFM reporting varies significantly across projects. It is recommended that detailed guidelines should be shared with project partners to improve their understanding of the subject and drive an improved focus on VFM.