Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Central Asia Programme
Country and Region:	Central Asia (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan)
IATI Unique ID:	CSSF-05-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD), National Crime Agency (NCA)
Total Budget :	ODA: £11.53m		Non-ODA: £0.91m
Budget this FY	ODA: £3.50m		Non-ODA: £0.62m
Spend this FY	ODA: £3.47m		Non-ODA: £0.61m
Original Programme Start Date: April 2016		Planned End Date: March 2020

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	B	B (outcome)	A (output)	B (outcome)	A (output)
Risk Rating - low/medium/high	Low/medium	Low/medium	Low/medium		Low/medium
Outputs and Scores:
Capacity enhanced of Uzbek media sector to produce more balanced high-quality media content and have increased awareness of the roles and responsibilities of the media						A
Capacity built of selected journalists and local institutions in Kazakhstan, Kyrgyzstan and Tajikistan in skills needed to identify, challenge and undermine disinformation						A
Central Asian Republics (CARs) are more enabled to engage on defence alternatives such as UN peacekeeping mission						A
Formal cooperation agreements established between the UK and Central Asian Republics on policing and capacity built of national security providers on international police cooperation and countering serious organised crime						A
Improved institutional frameworks for the Government of Uzbekistan to manage public administration reform more effectively						A
Capacity needs identified and initial capacity built of senior and mid-level managers in the Ministry of Justice of Uzbekistan to deliver key reforms						A
Capacity needs identified and initial capacity built of the Uzbek Parliament on legislative and financial oversight						A
Capacity built of Tajik and Afghan government officials and border agencies on cross-border cooperation and conflict management, and capacity built of border communities to improve their livelihoods						A
Water and pasture infrastructure are rehabilitated in conflict-affected border communities in Kyrgyzstan and Tajikistan and capacity is built of government and communities on natural resources management						A
Capacity is built of government on inclusion of young people in local governance, children in conflict with the law are provided with a protective environment, and young people from vulnerable ethnic communities in Kyrgyzstan and Tajikistan are provided with peacebuilding opportunities aimed at promoting inter-ethnic accord						A
Comprehensive support services are provided to existing, returning and outgoing labour migrants in selected provinces of Uzbekistan and capacity is built of Uzbek civil servants on preventing radicalisation of labour migrants						A
Enhanced systems of countering radicalisation and violent extremism in selected prisons of Kazakhstan, Kyrgyzstan and Tajikistan						A
Law on prohibiting underage religious marriages is implemented and promoted by relevant State Authorities in Kyrgyzstan effectively, with the involvement of civil society, and religious institutions						A

What support did the UK provide in FY 18/19?
The Central Asia Programme spent approximately supported 13 projects across five Central Asia countries. These projects aimed to:
- Countering disinformation by building the capacity of independent media organisations and improving the media literacy of targeted news and information consumers;
- Supporting good governance reforms in Uzbekistan by providing capacity-building support to the Ministry of Justice and Parliament.
- Enhancing relationships with and building the capacity of the region’s security and law enforcement institutions including through their increased participation in international peacekeeping missions;
- Reducing the risks from marginalisation of vulnerable groups by strengthening the resilience of cross border communities through improved access to water and land resources and improving community integration; and supporting greater inclusion of the region’s youth into community based decision making organisations;
- Working with the region’s prison services to develop a human rights based approach to the management and rehabilitation of vulnerable prisoners;
- Providing advisory and capacity building support to improve the adherence of select Kyrgyz institutions on national gender equality legislation, based on international commitments.

Key results for FY 18/19:
- Media information literacy training rolled out to all journalism faculties in Kyrgyzstan and fact-checking introduced in some leading Central Asian media outlets;
- Domestic violence law in Uzbekistan and underage marriage law in Kyrgyzstan passed with significant project input;
- Preparations made for roll-out of digital public services in Uzbekistan;
- Vocational training courses were offered to 720 vulnerable Tajik community members, including (returning) migrants and their family members (371 females / 349 males), in order to improve their employment prospects;
- Five irrigation and three drinking water systems (with 30% local contribution) were renovated in vulnerable cross-border communities in Kyrgyzstan and Tajikistan. This provided drinking water to 7,537 citizens and irrigation water to 22,469 beneficiaries;
- 497 (46 female / 451 male) Kyrgyz and Tajik children in conflict/contact with law enforcement agencies benefited from more supportive environment. Innovative peacebuilding learning spaces were rolled out in Tajikistan. Youth and child Friendly Local Governance Initiative scaled up to 43 municipalities in Kyrgyzstan, whereas in Tajikistan, more than 2,000 children and adolescents from border areas received access to innovative learning spaces;
- Kazakhstan military international peacekeeping deployment;
- NCA delivered its first regional training on Mutual Legal Assistance and Asset Recovery for five Central Asia Republics, with the Kyrgyz and Uzbek General Prosecutor’s Offices now submitting international letters of request to the UK in line with international standards.
Summary of progress and lessons learnt/actions taken since last review
There has been progress against the recommendations from last year’s annual review in a number of areas. Perhaps most notably, the programme is now a portfolio with three thematic programmes, and it now has a consolidated results map detailing how activities, outputs, outcomes and National Security Council strategic objectives interrelate. This at a minimum makes it easier to explain the programme narrative, although outcome measurement is still a real challenge and the team are still hampered somewhat by the complex policy picture and competing draws on CSSF funds. In other areas there has been progress, for instance the development of a programme-level (and project-level) action plan has enabled a response to other recommendations around gender, conflict sensitivity and programme governance. That said, some recommendations remain unresolved, notably around technical advisory capability, but the team has made real efforts to bring in additional advisory resource to meet the needs left by a lack of dedicated capacity.

In general however, the CSSF team have made a real effort to respond to the many recommendations originating from the various reviews of the portfolio, including conflict sensitivity and gender audits, the CSSF-wide review and a Joint Analysis of Conflict and Stability 2018 refresh. DFID allocated an additional £1.4m from its bilateral budget to CSSF given the year-on-year CSSF Central Asia budget reduction, which helped the portfolio to deliver its planned results.

Summary of recommendations for the next year
The key portfolio-level recommendations for the next year include a recommendation to consider more technical resource, to prioritise donor coordination particularly in Uzbekistan and to revalidate the outcomes in particular to find more robust outcome indicators.