Annual Review - Summary Sheet

PROGRAMME TITLE: Good Governance Fund
Country and Region:		Serbia, North Macedonia, Bosnia-Herzegovina, Moldova, Ukraine, Armenia, Georgia
IATI Unique ID:		CSSF-05-000003
HMG Partners / (LEAD in bold)		Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Budget :		ODA: £180m		Non-ODA:n/a
Budget this FY		ODA: £35.60m		Non-ODA:n/a
Spend this FY		ODA: £37.05m		Non-ODA:n/a
Original Programme Start Date: April 2016			Planned End Date: March 2021
	Outputs					Score
International Financial Institution (IFI), Multilateral and other donor projects	Output 1.1 Interventions that support liberalisation and modernisation of key growth sectors in partner countries					B
	Output 1.2 Interventions that support reform of tax systems and improvements to the business environment in partner countries					A
	Output 1.3 Interventions that support rule of law and democratic accountability					A
	Output 1.4 Interventions that support public finance management reform and anti-corruption measures in partner countries					A
Managed Fund	Output 2.1 Well targeted, adaptive technical assistance provided by Managed Fund projects to support growth, governance and accountability. The Managed Fund employs an adaptive approach through sharing learning and knowledge from the programme on an ongoing basis and scaling up projects where traction is being gained.					A
Strategic Support Fund (SSF)	Output 3.3 Interventions that support rule of law and democratic accountability					A
	Output 3.4 Interventions that support public finance management reform and anti-corruption measures in partner countries					B
	Output 3.5 Interventions that support the strengthening independent media and strategic communications in partner countries					A
	Overall output score					A
	Outcome Assessment: Programme meeting expectations
	Outcome Score: A				Risk: Major

Note: some outputs not scored due to no projects being delivered through the relevant strand during the review period

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score		A	A	B	A	A
Risk Rating - low/medium/high		Major	Major		Major
*output/outcome scores
How has the programme changed during this period? / Principal change: extension of activities to Armenia and North Macedonia. Otherwise objectives and programme set-up substantially unchanged.

What support did the UK provide in FY 18/19?

Continued technical assistance (first initiated in 2015) in Bosnia-Herzegovina (BiH), Georgia, Moldova, Serbia and Ukraine, and technical assistance in Armenia and North Macedonia from April 2018 onwards. Assistance is in support of governance and economic reform in areas of: liberalisation and modernisation of key growth sectors; reform of tax systems and improvements to the business environment; strengthening rule of law and democratic accountability; public finance management reform and anti-corruption; strengthening independent media and strategic communications. Support was provided through three strands: supporting activities by international organisations; a demand-led Managed Fund, largely responding to needs identified by government counterparts; and a Strategic Support Fund, usually supporting small initiatives by non-governmental organisations.

Key results for FY 18/19:

The Good Governance Fund (GGF) delivers many projects. The following is a sample of key outcome results.

- Following Armenia’s 2018 “Velvet Revolution” the UK took a lead role in helping the Central Election Commission to organise parliamentary elections that were internationally recognised as free and fair.
- Ukraine: support to a major initiative to move transactions between citizens and the state online and improve their transparency is helping reduce the scope for public corruption.
- Help to reform Georgia’s VAT and corporate income tax models led to an increase in reinvestment rates, according to the Ministry of Finance, supporting inward investment as a sustainable source of external finance and build a more resilient Georgian economy through boosted investment rates more broadly.
- Moldova: GGF funding substantially improved facilities allowing people with disabilities to vote in elections, including through a voter’s guide in braille and on audio CD, simulations of elections, and a device to enable blind people to vote without assistance.
- The Local Investment-Friendly Environment programme in Bosnia-Herzegovina helped governmental organisations to reduce regulatory burdens, cut business costs and improve competitiveness.
- Several small GGF projects in North Macedonia leveraged substantial assistance from other international organisations in priority reform areas. For example, help to draft the national energy strategy unlocked a large package of USAID support for implementation of the new energy law plus substantial European Bank for Reconstruction and Development (EBRD) support for energy efficiency work.
- Serbia: support for developing a one-stop shop speeded property registration by citizens and helped to eliminate the practice by which, when property was purchased by a married man and woman, only the man would be registered.

The GGF continues to demonstrate good performance across all the countries in which it operates. This assistance is greatly appreciated by stakeholders and other donors. The available data indicates that many are doing considerable political and economic good and gaining considerable credit for the UK. Its principal achievement in this past year has been successful expansion to two new countries, Armenia and North Macedonia.

The operation of the GGF continues to be heavily influenced by individual countries’ political contexts, within the country strategic framework and the strategic objectives set by the National Security Council. Posts have shown commendable deftness in positioning GGF to best effect. This has involved a spectrum of approaches that range from swift and agile responses in Armenia and North Macedonia to their reformist governments’ needs for immediate assistance, to Bosnia-Herzegovina‘s careful positioning of GGF within the EU’s socio-economic “Reform Agenda”.

In operational delivery terms (i.e. delivery of outputs) GGF is a considerable success. Increasingly GGF (and CSSF) operations are working closely with political teams in embassies, with GGF programming both a reinforcement to and an integral part of policy work, while policy insights both shape programming and inform its development (e.g. through risk monitoring). Ambassadors clearly appreciate GGF as a flexible and highly useful tool supporting in-country diplomatic priorities and giving additional influence and access.

Across all seven countries operational mechanisms have continued to strengthen. Staffing has stabilised, weaker project results frameworks have been winnowed out, working relations between the Joint Unit in London and posts have continued to improve, risk escalation mechanisms are working well, value for money guidance has been issued and two professional networks of governance staff and economic staff have been created. Working relationships with implementing partners are generally good, despite some local issues usually around tailoring programmes to local realities. However, the long-awaited external monitoring, evaluation and learning contract has only come into operation late in the year; the prolonged uncertainty over the future of the Managed Fund has hampered long-term planning and adversely affected operations and value for money; and guidance to posts on gender and conflict sensitivity has not been issued.

Both outcome and output scores are A: programme meeting expectations.

Summary of recommendations for the next year

- All posts should move towards the model in which the work of GGF programming team, policy team and embassy leadership are closely integrated, as described in the full report.
- The balance of emphasis between support through international organisations and support through the Managed Fund should be reconsidered and reviewed annually and priority given to retaining significant funds in each country to be used to respond to government requests.
- Preference should not automatically be given to working with international financial institutions; other international organisations should be given equal consideration.
- The respective responsibilities of Joint Unit and country teams for managing Strand 1 projects should be clarified, possibly by updating the roles and responsibilities document covering all three Strands.
- Strand 1 projects should only be undertaken with institutions having an in-country presence; exceptions to this arrangement should only be agreed where the implementing partner can guarantee adequate alternative liaison arrangements.
- HMG must avoid a repetition of delays in letting contracts for running the Managed Fund, which adversely affected value for money.
- Joint Unit should undertake a light touch review of the implementation of the VFM guidance including support offered by the Monitoring, Evaluation and Learning (MEL) contractor after 12 months i.e. in February 2020 to gauge its effectiveness.
- Joint Unit should require all project implementers, but particularly those in Strand 1, to adopt systematic and effective risk management, possibly through contractual requirements.
- Joint Unit should issue country teams with guidance on gender issues (urgently) and a simple tool for screening conflict sensitivity issues at project evaluation stage.