Annual Review - Summary Sheet

PROGRAMME TITLE: Eastern Partnership Programme
Country and Region:	Armenia, Azerbaijan, Georgia, Moldova and Belarus. Eastern Europe and Central Asia.
IATI Unique ID:	CSSF-05-000002
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MoD)
Total Budget:	ODA: £14.5m		Non-ODA: £1.89m
Budget this FY	ODA: £4.17m		Non-ODA: £0.41m
Spend this FY	ODA: £4.17m		Non-ODA: £0.41m
Original Programme Start Date: 2015		Planned End Date: March 2020

Summary of Programme Performance

Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	A (outcome)	A / (output)	A (outcome)	A / (output)
Risk Rating - low/medium/high	High	Medium	Medium		Medium
Outputs					Score
Visible and active UK political and practical support to international reconciliation efforts.					B
Community actors, officials and civil society are supported to facilitate the development of space for peace-building and engage in dialogue, inter-community and confidence-building measures.					A
Removal of barriers for conflict-affected communities and vulnerable groups to participate in peace-building activities.					A
Technical and advisory assistance provided to governance actors to develop models of governance that improve rights of vulnerable groups and to advance gender-sensitive reforms in management and administration capabilities of government security sectors.					B/A
Empowerment of vulnerable groups and support for civil society working to reduce barriers of isolation and to overcome socio-political and economic challenges.					B
Expertise and training to governance and CSO / community actors in target regions to improve human rights adherence.					A
Delivery of innovative, gender sensitive media content through support to independent media outlets and capacity building of women journalists.					A+
The relatively small size of the programme and the range of smaller projects has remained constant over the last few years, enabling the programme to experiment and learn lessons. At the same time, the programme has consolidated best practice in programming through longer-running projects and has built trust and relationships with local partners. Over the year, the programme has built on recommendations from the Independent Commission on Aid Impact (ICAI) and a gender audit. The programme has also refreshed its conflict analysis. This experience is helping the programme team to prepare a stronger analytical foundation for 2020.

What support did the UK provide in FY 18/19?
The programme delivered projects in Georgia, Azerbaijan, Armenia, Moldova and Belarus. The portfolio included a regional British Council English language project and two multi-country media projects. The largest footprint is in Georgia, which also hosts the Programme Hub. The programme contributes to delivery of UK Government’s ‘Eastern Partnership’ (EaP) strategy by supporting stability, reform and resilience and is split across two strands and four priority themes (a third strand, focused on economic reform, is addressed by the Good Governance Fund (GGF)):

- Improve effectiveness, transparency and accountability of government and security sectors;
- Counter and reduce the effect of destabilising disinformation, mainly through support to independent media outlets;
- Increase the space for constructive dialogue on conflict resolution, through support to dialogue mechanisms, inter-community initiatives and confidence-building measures for officials and civil society; and
- Reduce the isolation and vulnerability of conflict-affected societies, including to address socio-political and economic challenges affecting communities in conflict-affected areas.

Key results for FY 18/19
Overall, the programme has delivered most of the expected results and achieved high-profile success at output level, consolidating a leading role for the UK in the region.

- In Georgia, the EU Monitoring Mission continued to play a vital strategic role in providing stability along the ABLs, with CSSF supporting 10 secondments of UK experts into key roles such as the Deputy Head of Mission and Gender Advisor and two secondments into the EU Special Representatives’ Office.  CSSF continues to facilitate the leading confidence-building Track 2 dialogue programme in Georgia led by Conciliation Resources (the “Limehouse Platform”). CSSF support for The Halo Trust contributed to the ongoing task of clearing unexploded ordnance across Abkhazia and enabled them to continue the clear-up of the explosion site at Primorsky following the 2017 accident at a weapons’ store. This restored land to support livelihoods as well as reducing the threat to life.
- In Moldova, CSSF supported a high-visibility project to encourage practical cooperation on fire safety between both sides of the Transnistria divide and conducted the first survey of women’s needs living along the dividing line. The survey has provided a series of recommendations backed up with evidence to support policy and project implementers to better integrate gender issues into future stabilisation work.
- In Armenia CSSF continued to support civil society peacebuilding organisations and facilitated an exchange of views between experts from Northern Ireland and Armenian stakeholders.
- Across the South Caucasus, new CSSF-funded English Learning Hubs delivered by the British Council were opened, benefiting thousands of young people and hundreds of teachers. The hubs are located in local communities that lack access to quality English language teaching, an enabler for economic and social development. CSSF also continued to support two independent, regional media outlets, Jam News and Chai Khana. The latter was awarded a number of international awards for their gender-sensitive reporting.
- All CSSF interventions met minimum standards on gender and are increasingly aligned to supporting the UK and regional National Action Plans on Women, Peace and Security.

Summary of progress and lessons learnt/actions taken since last review
The programme responded positively to the recommendations set out in the Independent Commission for Aid Impact (ICAI) review, a regional gender audit and last year’s annual review. Overall, the programme has strengthened its approach to gender, sustainability, and risk and conflict sensitivity and secured an improved evidence base.

- A Joint Analysis of Conflict and Stability (JACS) was commissioned during the 2018-19 financial year and finalised in April 2019. It will improve the evidence base and generate an understanding of gaps in programming.
- An Action Plan and a Gender Work Plan is in place to help address ICAI recommendations on risk, results reporting and gender and conflict sensitivity.
- There has been increased communication and a focus on visibility including the UK in South Caucasus Facebook page, diplomatic reporting and senior briefing.
- The review team found evidence of improved budget management processes that have helped manage risks, in particular the MoD budget.
- There is good coordination between the Programme Hub in Tbilisi and posts. There was significant evidence that the Hub provided advice, quality assurance and promoted best practice across the region.

Summary of recommendations for the next year
- There is still room for improvement on monitoring and evaluation. The programme should focus on measuring the political access and influence (PAI) that is gained through the programme and consider using the new PAI tool or other mechanisms, particularly to measure the impact of the embedded advisers and secondees.
- The programme is complex and harvesting evidence of outcomes remains a challenge given the broad scope of the portfolio. The Hub should consider adopting country level theories of change that could support a wider regional framework or streamline existing theories of change and results frameworks for ease of understanding.
- The Hub have made progress to refresh and update the results framework during the year but should now ensure it is updated more frequently and used as a tool to measure success throughout the year.
- Quarterly reporting from posts is still very much focused on activity and output level results. Posts should be further encouraged to report on the outcomes and impact of their interventions as they mature, linking these directly to the results framework.
- The Hub has made progress on financial management this year and could consider developing a value for money toolkit for the region to ensure a consistent approach.
- An updated UK Government Strategy is expected shortly. This provides an opportunity to refresh policy goals, making more strategic decisions on where to focus programming. The Hub should ensure that policy and programming thinking is joined up and any new strategic direction is reflected in any new programming.
- Individual posts should understand the recommendations made in the JACS and adapt their projects accordingly.
- The programme should identify how to strengthen the contribution to human rights and integrate this into the Results Framework.
- The programme should continue to build the evidence base to support gender sensitive interventions, both through harvesting data from existing interventions and by considering the value of external review.
- The programme should continue to build capacity and understanding of implementers to address conflict and gender sensitivity more robustly.