Annual Review - Summary Sheet

PROGRAMME TITLE: Border Force Cutters
Country and Region:	Aegean and Mediterranean
IATI Unique ID:	CSSF-01-000008
HMG Partners / (LEAD in bold)	Home Office (Border Force)
Total Budget:	ODA: £12.15m			Non-ODA: £0
Budget this FY	ODA: £7.12m			Non-ODA: Nil
Spend this FY	ODA: £6.88m			Non-ODA: Nil
Original Programme Start Date: April 2017		Planned End Date: March 2020
Outputs					Score
Deployment of Border Force (BF) cutter to Aegean Sea and Central Mediterranean to conduct search and rescue (SAR) operations in line with Frontex operational requirements.					A
Overall output score: A
Outcome Assessment: A
Outcome Score: A			Risk: Medium/ High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score			A	A	A	A
Risk Rating - low/medium/high			Medium/ High		Medium/ High
*output/outcome scores
How has the programme changed during this period? The performance of the programme remains high. External factors caused a reduction in the number of the Border Force (BF) cutters deployed in this financial year, however the relevance and importance of the programme remains the same.

What support did the UK provide in FY 18/19?
CSSF funding supported Search and Rescue (SAR) of 2,316 individuals through the deployment of two Border Force (BF) Cutters (as of April 2019). This is part of the EU’s Frontex humanitarian operations. However, loss of life at sea continues and current projections suggest demand for search and rescue will continue in 2019/20.

Key results for FY 18/19:
- The programme provided humanitarian support to and prevented the loss of life of 2316 individuals through SAR operations;
- There is significant evidence of the continued political goodwill generated by the programme, particularly with the Hellenic coastguard;
- Strengthening the Monitoring and Evaluation of the programme by working on the theory of change and results framework and working with a Monitoring and Evaluation Adviser.
- Programme activity is delivering against outcomes listed in the Results Framework (RF). However, the RF would benefit from being developed further to include milestones and monitoring across all outcomes and outputs. This will enable a more robust analysis of results.
Summary of progress and lessons learnt/actions taken since last review

Since last review Monitoring and Evaluation was strengthened by working on the theory of change and results framework and working with a Monitoring and Evaluation Adviser.
The previous review recommended the UK influence FRONTEX towards providing intelligence products which enable operational and tactical level activity. This was raised by the UK at FRONTEX review of operations in Warsaw on 20/21 November 2018. FRONTEX is now trialling satellite imagery, fixed-wing aircraft and drones to produce operational intelligence. The UK also sought opportunities to facilitate Turkish and Hellenic coast guard communication.

Summary of recommendations for the next year

- Continue to feed into and monitor strategic advice on the best humanitarian/ SAR need.
- Given the current situation of difficulties disembarking in Italy, the cutters should remain active, monitor the political situation and consider re-engaging in the central Mediterranean if the situation changes.
- Consider opportunities and feasibility for providing human slavery training to the Hellenic coastguard. This will add to the longer term capacity in the region by helping to identify vulnerable people earlier in the operation.
- Given that the current fleet of cutters are nearing the end of their working life, require more maintenance and are therefore out of action for longer periods, consideration should be given to long-term plans for the assets used in the programme.