Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Multilateral Strategy (MuSt) - Championing our Values
Country and Region:	Worldwide
IATI Unique ID:	CSSF-01-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Budget :	ODA: £21.85m (included CVE projects – FYs 16/17 and 17/18)			Non-ODA: N/A
Budget this FY	ODA: £4.14m			Non-ODA: N/A
Spend this FY	ODA: £4.39m			Non-ODA: N/A
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Initiation of Iraq work: funding to Civil Society Organisations (CSOs) on Iraq’s Women, Peace and Security (WPS) National Action Plan implementation and conflict prevention.					A
Improved early warning system on Conflict-Related Sexual Violence (CRSV) developed through key peacekeeping missions by strengthening their monitoring and reporting, and developing information sharing protocols and other tools.					A
Ensure development and implementation of mechanisms to address impunity for conflict-related sexual violence in place in countries affected it.					A
Department of Peacekeeping Operations (DPO) CRSV team identifies and disseminates best practices and lessons learnt from field missions.					B
Strengthened coordination between the all United Nations (UN) departments and agencies on response to victims of Sexual Exploitation and Abuse (SEA) and prevention of SEA.					A
Professionalised investigations of SEA affecting minors across UN common system					A
Survivors of SEA are offered adequate and effective local level assistance when reporting SEA to authorities/UN.					B
Progress in the implementation of action plans to end and prevent grave violations against children (Afghanistan, Democratic Republic of Congo (DRC), Myanmar, Philippines, and Sudan).					B
Non-state armed groups (NSAs) are engaged with Office of the Special Representative for Children and Armed Conflict (OSRSG CAAC) to strengthen the protection of children (Colombia, Central African Republic (CAR), Myanmar, Philippines, Sudan, South Sudan).					A
Strengthening of DPO/Peacekeeping mission’s awareness and practice of child protection mandate through development of policy, production of policy handbook and training to UN military and UN Police (UNPOL) focal points.					B
Office of High Commission for Human Rights (OHCHR) improves the way it manages and utilises human rights information through the development of specialised internal human rights information management capacity					B
Overall output score					A
Outcome Assessment: There is evidence that progress is being made across outcomes 1 – 5 but due to the nature of multilateral work it can be slow. In parallel, there has been progress building on the recommendations from the 17/18 Annual Review concerning policy engagement and support in ongoing monitoring of reporting and design. Most programme stakeholders have taken on the requirement for project frameworks and establishing Monitoring & Evaluation (M&E). Of the Outcomes, 2, 3 and 4 have achieved the greatest traction and seen the most progress in understanding and reporting.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	B	A	A	A	A
Risk Rating - low/medium/high	Medium	Medium	Medium	Medium	Medium	Medium
*output/outcome scores
How has the programme changed during this period?: In line with AR recommendations, over the last three years the programme has streamlined from over 20 projects to the current 11 focussed projects in line with UK policy priorities. Policy engagement in London, New York and Geneva has increased with detailed input into the design of the programme and ongoing Monitoring & Evaluation. Spend has increased with improved forecasting and holding implementers to account. Impact is communicated with Ministers and external audiences with more regularity and is a central plank of policy engagement at post.

What support did the UK provide in FY 18/19?
The Championing Our Values programme is designed to deliver sub-objective 2.6a of the NSC Strategy: ‘Multilaterals better able to promote a reduction in human rights violations, mass atrocities, recruitment and deployment of child soldiers, sexual violence in conflict, sexual exploitation and abuse, and better protection and participation of women and girls.’
The support given by the UK to achieve this sub-objective are as follows:
- Core funding for the key UN bodies responsible for specific issues (e.g. UN Offices on Children and Armed Conflict and the Department of Peacekeeping) - £3m
- Contributing to trust funds which deliver projects in a particular thematic area (e.g. Preventing Sexual Violence Initiative (PSVI)) in which the UK is seen as the lead - £1.39m
- Increased support to implementers on good CSSF project implementation, risk planning and Monitoring and Evaluation.
- Political and Defence engagement leading to consensus, and as a result some significant change. Specifically in Sexual Exploitation and Abuse (SEA), PSVI and Children Affected in Armed Conflict (CAAC), along with the ‘professionalisation of investigations in the UN’ – In kind

Key results for FY 18/19:
- Initiation of the UN’s professionalisation of national investigations into sexual exploitation and abuse where the victim is a child;
- Three countries (DR Congo, Somalia, South Sudan) actively engaged in implementing Prevention Plans and five agreements with non-state armed groups recruiting and employing armed children;
- Creative use of strategic communications to share good practice on preventing SEA, particularly in South Sudan;
- Development of methodology and processes to capture and disseminate mapping for the rights of victims;
- Sustained, if not enhanced, the perspective that the UK is a sought after and serious partner in the areas this programme covers;
- In the PSVI Team of Experts a small team is beginning to co-ordinate Agencies’ response in various missions, whilst developing a centre of knowledge;

Summary of progress and lessons learnt/actions taken since last review
Recommendations of 2017/18 Annual Review	Actions Taken
Policy leads to be more involved in guiding and explaining to implementers what impact level change they are seeking to progressively achieve through UK funding.	There has been a clear, evidenced increase in policy engagement and support in ongoing monitoring of reporting, and the design of related projects.
As per previous annual reviews: increased and effective scrutiny of projects and analysis of their efficiency is required and this suggests additional or reconfigured team resource in New York.	No additional resources for New York in FY18/19. / Additional scrutiny and development of most projects has been achieved throughout FY18/19.
Where funding is for staff positions, the programme team and policy leads need to ensure that implementers have exit strategies and plans to embed policy reforms.	We have encouraged all implementers to consider whether they can prioritise staff positions for regular budget considerations. However recognition that funding for staff positions on these thematic areas are difficult given the need for UN member state consensus. / In the case of WPHF we will be ending the agreement after FY19/20.
Stronger monitoring and quality control of key programme milestones should be pursued as consistent practice for all the projects but this may require additional resources.	Stronger monitoring and quality control of key milestones has occurred through engaging M&E experts, use of donor meetings to highlight requirements and stronger input from policy leads.
Establish joint outcome level indicators for each theme/value. This would enable programme and policy teams to easily track the contribution of specific projects achieving policy level results, in line with UK interest.	Results framework has been streamlined with projects delivering towards joint outcomes.
Log frames need to be updated to show progression with detailed and realistic targets for subsequent work plans, in particular: WPHF, Team of Experts, OSRSG CAAC, and OHCHR PSVI.	Project level logframes and reporting has improved through dedicated coaching; in particular OSRSG CAAC, OHCHR PSVI and Information Management, projects have greater transparency and clarity on achievements and/or areas unfulfilled.
The two interventions with OHCHR need to be reviewed to ensure that our funding is leading to tangible and long term institutional reforms in practice on human rights reporting given the large funding commitment. Policy leads need to strengthen their scrutiny of this work.	Detailed and regular discussions with OHCHR on ensuring long term reform and VfM. Policy leads engaged with monitoring project level results, but believe there are strong policy grounds to continue with these projects.
To assess whether direct monitoring of activities can be done in-country for certain projects .i.e. for WPHF we are doing this through the Baghdad National Steering Committee.	We are doing this: In-country monitoring of projects has been introduced through the WPHF. UK Embassy Baghdad colleagues sit on the local National Steering Committee and are assisting with developing M&E with the project staff.
Revise outcome indicators for DPKO CRSV project to assess how peacekeepers performance can be assessed.	DPO has submitted new logframe.

Summary of recommendations for the next year
1. Resourcing in NYC. To further strengthen the relationships between the CoV programme manager, implementers and policy leads, and increase scrutiny of the programme, the team should consider recruiting additional resource in NY, or rebalance the current structure to enhance the NYC footprint.
2. M&E. Despite considerable progress being made, there is still a requirement for stronger M&E and results frameworks at project level. Clearer indication of achievement of outputs and outcomes is required to better articulate what the UK funding is contributing to.
3. Development of the Political Access and Influence tool. Much of this programme is built on the ability of the UK to shape and steer the UN in areas it deems critical to its operating environment, and this is likely replicated in other programmes under MuSt. A tool to monitor and evaluate this is being experimented with in the wider CSSF and is essential for this programme to utilise and adapt this.
4. OSJA. As 3 programmes, and with a 4th to follow, are focused on the UN, it is recommended that an overarching OSJA is put in place as soon as possible, to ensure the right levels of assurance are in place for the programme team.
5. Sustainability. The programme needs to pay particular focus to addressing the issue of sustainability, especially in the case of funding UN Offices and individuals. As the programme enters the final year of CSSF funding it needs to consider an exit strategy for each project that will ensure sustainability of achieved results so far.
6. Anniversaries – WPS and PSVI. Suggestion that with the forthcoming anniversaries (PSVI – Nov 2019 (5 yrs.); WPS – Oct 2020 (20 yrs.)) and UK’s championing of these issues, Joint Funds Unit and programme team should consider how to balance robust M&E with the capacity of stretched but high performing implementers.