Annual Review - Summary Sheet

PROGRAMME TITLE: Migration - Eastern Route Programme
Country and Region:	Turkey, Greece and Serbia
IATI Unique ID:	CSSF-01-000006
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO) / Home Office (HO)
Total Budget:	ODA: £8.3m			Non-ODA: £0.13m
Budget this FY	ODA: £4m			Non-ODA: £0.13m
Spend this FY	ODA: £3.19m			Non-ODA: £0.06m
Original Programme Start Date: April 2017		Planned End Date: March 2019
Outputs					Score
Directorate General of Migration Management (DGMM) staff acquire knowledge on trafficking, asylum, regular & irregular migration issues					A
Turkey develops and implements an efficient asylum system with specialised caseworkers					A
Systems set up nationwide to increase returns of irregular migrants from Turkey					B
DGMM Removal Centre staff trained on international human-rights standards					A
DGMM staff understand better the enforced return procedures and implements them according to the guidelines					A
Cooperation mechanism between Turkey and Countries of Origin (COI)					A
Migrants and vulnerable migrants access the appropriate care and support services available to them in a shorter timescale that would otherwise be possible					A
Serbian Migration Systems					-
Overall output score					A
Outcome
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	Amber/Red	B	B	A	A
Risk Rating - low/medium/high	N/A	High	Medium		Medium
*output/outcome scores

What support did the UK provide in FY 18/19?

- In Turkey, the programme continued to direct its support in 18/19 towards strengthening the capacity of Turkey’s frontline migration institutions (principally the Directorate General of Migration Management (DGMM) and the Ministry of Labour & Social Policy (MoL&SA)), to improve asylum and returns processes, migrant integration and labour market inclusion, countering human trafficking and irregular migration.
- In Greece, support for the EU-Turkey Statement in 18/19 included provision of specialist deployments to the EU Commission and to the Greek Authorities, including seven interpreters to the Reception and Identification Services (RIS) on the Greek Island Hotspots. This helped RIS to function more effectively and facilitated much needed access to camp services for vulnerable migrants/asylum seekers. CSSF also funded an EU/Turkey Liaison Officer in the Embassy in Athens.
- In Serbia, the programme supported key Serbian institutions (Asylum Office, Asylum Commission, and Administrative Court) to gain knowledge and skills to implement the new Law on Asylum and Law on Foreigners, improving protection and asylum procedures. Further support was provided to service providers from reception centres to improve the protection of vulnerable groups of migrants in Serbia. Key strategic documents and training capacities of the Migration Training Centre were developed in cooperation with the Commissariat for Refugees.

Key results for FY 18/19:

This Eastern Route Programme is a high-profile and highly successful programme under CSSF Migration. Following the comprehensive, in-depth review of 2017/18, considerable progress has been made this year in monitoring project results, and in gender sensitivity. A recent conflict and stability audit of the Turkey programme has also made a number of further recommendations. There has been re-consideration of the programme elements, including through a revision of the Theory of Change and supporting documents, which means that the 19/20 programme looks very different.

Greece activity was also thoroughly reviewed in 2017/18 and examined again in the Home Office’s Strategic Review of Migration Support in Greece in February 2019, leading to the cessation of funding of the specialist deployments to the EU Commission and the EU-Turkey Statement Liaison Officer role.

Programme work in Serbia concluded in March 2019.

This review will prioritise assessment and recommendations for the Interpreters project in Greece, which is continuing in 19/20, and the four ongoing projects being implemented in Turkey this financial year, namely:
- Assisted Voluntary Return and Reintegration (AVRR), and Supporting the Directorate General of Migration Management (DGMM) efforts in enhancing the Capacity of Removal Centres on Turkey.
- Supporting the Asylum Decision Making Capacity of Turkey’s DGMM, and Strengthening the Operational and Strategic Capacity of DGMM.

Turkey: Outputs/Outcomes:
- Establishment of a National AVR Action/Mechanism – an important first step to national ownership/control of AVRR by the Government of Turkey as well as a more cost-effective solution than using long term detention.
- Development of the first national training curriculum on human rights principles and standards in immigration detention for Removal Centre (RC) staff. In 18/19, 788 staff were trained in national and international human-rights standards from 22 RCs (654M and 134F), of which, 567 were security personnel. This has led to a reported reduction by DGMM Headquarters in the number of complaints received from migrants of ill-treatment by RC staff and a commensurate decrease (circa 30%) in disciplinary procedures being brought against staff – indicating an improvement in staff comportment.
- Successful establishment of an International Protection Bureau (IPB) in Ankara (March 2018) – from which 8,000 plus asylum applications were processed in one-year (including applications where the interviews are completed but the final decisions are not yet issued). This success led to the opening of a second IPB in Istanbul in March 2019 and plans to establish a further 3 (one per region in Turkey) by 2021. This in turn promises significantly improved Refugee Status Determination (RSD) procedures and speed of asylum making decisions.
- 2,097 migrants were assisted to return to their country of origin (2017-19) through the Assisted Voluntary Return and Reintegration (AVRR) initiative - 21% higher than originally planned, which reflects the increasing demand in Turkey for AVRR. This also reflects the cost effectiveness and value for money of the AVR programme in Turkey.

Greece: Output/Outcomes:
- Vulnerable migrant groups assisted by the interpreters include unaccompanied minors, single-parent families and over 65s.
- In 5-months (since figures began to be recorded), interpreters have assisted in 2,801 medical assessments and 595 psycho-social assessments;
- During the reporting period it is estimated that the interpreters have indirectly facilitated 5,083 vulnerability assessments. This is an important outcome, since until vulnerability assessments are complete, migrants cannot have asylum claims progressed, or be returned to Turkey under the EU-Turkey Statement.

Summary of progress and lessons learnt/actions taken since last review

In Greece, a fundamental review took place in December 2018 to account for contextual changes along the Eastern Mediterranean Route since the height of the migration crisis in 2015. This resulted in key decisions not to continue expert deployments to the EU Commission after March 2019 and not to replace the EU/Turkey Liaison Officer. For 19/20, only the interpretation services were retained, with a further review planned for October 2019 to assess the capacity of Greek Authorities to provide interpretation services directly and the need for ongoing UK bilateral support of interpreters, post March 2020. Monitoring, Evaluation and Learning (MEL) systems and reporting have also been greatly improved for Greece (from a zero base in 17/18).

In Turkey, clear efforts have been made to further consolidate projects in the portfolio and there has been a noticeable shift since 2017 towards a more nuanced, strategically focussed programme that is finding its niche. In a context in which other larger donors are operating, there is recognition by Post that the Eastern Route Programme (Turkey) should be distinct and deconflicted with what others are doing. From 32 projects in 2016, there were eight projects in 18/19 and seven planned in 19/20. .

Key recommendations from AR17/18 for the Turkey programme to (i) strengthen in-house Monitoring, Evaluation and Learning (MEL) capacity, (ii) ensure policy and reform work in Turkey is gender sensitive and (iii) develop a clearer, more achievable Results Framework (RF) and Theory of Change (ToC), have all been acted on. Over the course of the year, the team have engaged an SU Gender Adviser and M&E Adviser to good effect, culminating in a ToC ‘refresh’ in May 2019. Furthermore, having commissioned an independent study on the effectiveness of the labour migration project in January 2019, findings have been used to shape how Post will engage in future on labour migration. The study also demonstrated the value and worth of external evaluation and acted as a springboard to strengthening MEL activities in 19/20. These include plans to commission further independent evaluation of projects, and to build the MEL capacity of government beneficiaries, DGMM and the MoI, via a bespoke project. These are excellent examples of strategically aligned MEL by Post. The Embassy in Ankara have recently been through an Audit on conflict sensitivity and have taken forward the results of this with JFU and the Secretariat.

In summary, 18/19 has been a year of internal review, critical reflection and consolidation for both Programmes in Turkey and Greece, which has set the Eastern Route Migration Programme up to be in a stronger position in 19/20.

Summary of recommendations for the next year

Greece:
- A full review of the interpretation services on the Hotspot Islands is already scheduled to take place in October 2019. Since the Greek Authorities’ Reception and Identification Services (RIS) began contracting an agency to provide interpretation services in March 2019, it will be a means of assessing whether UK Interpretation Services are still needed post March 2020. As part of this review, an analysis of interpretation needs from a gender perspective is strongly recommended, as gaps in this respect are anticipated that the UK could potentially meet (depending on findings).
- Further revision of the MEL systems and reporting in 19/20 is recommended, with a view to gathering quantitative data on interpretation services more accurately and efficiently, to avoid risks of double counting and potential conflation of numbers.
- External safeguarding mechanisms and procedures on the Hotspot Islands (e.g. as applied by the Camp Management Authorities) need to be clearly understood and accompanying internal safeguarding processes and procedures developed and applied (e.g. for reporting safeguarding concerns that the UK interpreters or visiting HMG staff may have).

Turkey:
- Ongoing consolidation of programme, with emphasis on embedding learning from 18/19 on gender, conflict sensitivity and MEL and holding Implementing Partners (IPs) to account.
- Greater impact reporting from Post - considering the groundwork in 18/19 and development of a far clearer ToC and RF for 19/20 that is aligned to demonstrating results and strengthening the evidence base, an increase in impact reporting from Post is recommended.