Annual Review - Summary Sheet

PROGRAMME TITLE: Organised Immigration Crime (OIC) Taskforce (Project INVIGOR)
Country and Region:	Various
IATI Unique ID:	CSSF-01-000007
HMG Partners / (LEAD in bold)	Home Office (HO) (including Office for Security and Counter-Terrorism, Crime Policing & Fire Group, Immigration Enforcement and Border Force), National Crime Agency (NCA), Crown Prosecution Service (CPS)
Total Budget :	£27.08m
Budget this FY	ODA: £4.38m			Non-ODA: £10m
Spend this FY	ODA: £4.14m			Non-ODA: £9.98m
Original Programme Start Date: This programme builds on the Organised Immigration Task Force Programme which ran in 2015/16 and 2016/17.		Planned End Date: March 2021
Outputs					Score
Ensure that all OIC Taskforce posts overseas and in the UK are appropriately staffed and that the location of the Taskforce remains appropriate and relevant as migratory routes and the OIC threat moves					A
Build and develop capacity and capability in source and transit countries to tackle OIC					B
Develop an enriched intelligence picture on OIC across source and transit countries and in the UK					A
Investigate and prosecute organised crime groups (OCGs) and facilitators profiting from OIC					A
Disrupt the use of enablers utilised by organised crime groups to facilitate OIC, including social media					B
Disrupt and recover the criminal finances associated with OIC					A
Overall output score					U
Outcome Assessment:
Outcome Score: U (unscored)			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score		A	A	U	U	U
Risk Rating - low/medium/high		Medium	Medium		Medium
*output/outcome scores

What support did the UK provide in FY 18/19?

The OIC Taskforce, or Project INVIGOR provides for staff time from the NCA, HO, CPS and Immigration Enforcement in the UK and in a number of overseas locations together with dedicated programme funding to focus exclusively on countering the OIC threat. Support is provided by mentoring and helping build the capability and capacity of overseas law enforcement partners, improving the intelligence picture overall and facilitating greater sharing with international partners where possible, and conducting and supporting investigations and prosecutions. INVIGOR has also developed focus on countering the enablers of OIC activity, in particular social media sites which advertise illegal services, and in disrupting and recovering associated criminal finance.

In FY 2018/19 the project continued along the same trajectory as previous years.

Key results for FY 18/19:

- The Taskforce inter-agency model for gathering, exchanging and acting on intelligence still proves very effective.
- Under one operation the programme moved swiftly to capture intelligence, mobilise resources and coordinate a response with partners to the increase in general maritime-facilitated migration in the Channel.
- The project has secured valuable relationships with EU and overseas partner countries to share intelligence in support of investigations (in the UK or overseas) and prosecutions.
- The number of disruptions reported this financial year is still relatively high, demonstrating the effect of INVIGOR’s multi-agency partnership. The review found evidence that intelligence procured under the project has directly contributed to arresting individuals convictions sentencing and freezing assets. Referrals and closures of social media accounts and websites facilitating OIC are still ongoing in the UK and Greece, which is the highest referring country in Europe.
- Through the programme, Greece’s operational capability has visibly augmented, to a point where both agencies supported through the project show levels of autonomy in performing key counter-OIC tasks. The programme has been involved in leading or supporting 19 operations over 2019/2019. In total, 12 OCGs were disrupted with Hellenic authorities and 40 arrests were made resulting from the NCA directly supplying intelligence. During the reporting period, assistance to Greece has been provided on 10 UK-linked cases ranging from extradition, European Investigation Order and investigatory support.
- Mentoring support to the Hellenic Police Intelligence Division and Hellenic Coast Guard led to
  - 63 reports which led to 36 cases in total, 77% of cases relating to migrant smuggling and 14% document forgery.
  - The delivery of Open Source Intelligence and Dark web training to relevant units
  - Referral of social media content promoting OIC to EUROPOL, following a national procedure created to ensure deconfliction of cases with all Hellenic agencies
  - Improved ability to collect information, analyse and identify trends and patterns of operation among OCGs, to profile facilitators, boats, migrants and connect information to ongoing cases.
  - There were 18 detections of suspect boats over a 9-month period.
- A Memorandum of Understanding was agreed with the Attorney General in Ethiopia, kicking off cooperation between the project and national prosecutors.

Summary of progress and lessons learnt/actions taken since last review

In terms of action taken, the last Annual Review (AR) produced two main recommendations, both of which were partly implemented during 2018/19.

While the INVIGOR team finds it challenging to attach milestones and targets to what they consider operational work, one must also recognise that CSSF tools are new concepts for agencies operating under the Taskforce and are not well understood. Beyond the requirement of compliance to CSSF standards, it is essential for the CSSF Joint Funds Unit and Migration programmes team to better communicate about the purpose of a theory of change to INVIGOR leadership and the benefits they would draw from it as well.

Summary of recommendations for the next year

Priority recommendations to embed programmatic requirements in the project, to start implementing within the next three months and follow-up by the CSSF Migration Board.

Gather key stakeholders from the Taskforce, the Stabilisation Unit’s transnational threat advisers and CSSF Migration programme representatives to embark on a theory of change design process, with a clear aim at specifying objectives of the project and from which to develop a mechanism for consistently reporting results. Draw from the Serious Organised Crime and Justice Assessments as a source for setting strategic direction.

Develop a framework for systematic monitoring and reporting against pre-defined indicators and collection of evidence to assess impact of the project. Consider hybrid models of frameworks if more appropriate to the project.

Set up mechanisms to capture and incorporate lessons learned early, regularly and consistently through regular reporting, and to disseminate these to partners but also more widely across HMG.

Recommendations for implementation during the course of the FY
Beyond listing activities undertaken by agencies under the Amplification Plans, develop theories of change against which to implement the plans, clearly articulating the contribution of each agency to a common, realistic and measurable objective. Assess results one year into implementation and identify how blockages can be mitigated.

Seek greater integration between PURSUE and PREVENT activities, some of which are funded by the CSSF Migration programmes such as strategic communications work undertaken under the Upstream strand of the CSSF Migration programmes, but also DfiD programming.