Annual Review – Summary Sheet

PROGRAMME TITLE: CSSF Multilateral Strategy (MuSt) - Peacebuilding
Country and Region:	Worldwide
IATI Unique ID:	CSSF-01-000002
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: £31.45m		Non-ODA: £0
Budget this FY	ODA: £8.4m		Non-ODA: £0
Spend this FY	ODA: £8.4m		Non-ODA: £0
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs				Score
Internal reform of UN to ensure efficient and conflict sensitive delivery				A
Gender mainstreamed in UN peacebuilding, mediation and conflict prevention efforts				A+
Strengthened national/in-country capacities through effective UN HQ support				A+
Overall output score A+
Outcome Assessment: The MuSt Peacebuilding Programme has scored well against all outcome statements, with the annual progress exceeding expectations for all of them.
Outcome Score: A+		Risk: Moderate

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	A	A+	A+	A+	A+
Risk Rating - low/medium/high	Medium	Medium	Moderate		Moderate

What support did the UK provide in FY 18/19?
The following is the overall budget spread under the programme that is channelled towards the UN’s extra-budgetary resources:

PROJECT/COMPONENT	LEAD DEPT	IMPLEMENTING ORGANISATION	BUDGET	FY 2018/19	START	END
Peacebuilding Fund (PBF)	DFID	PBSO	£14.3m	£4m	April 2016	March 2020
DPPA Multi-Year Appeal	DFID	DPPA (formerly DPA)	£11.2m	£3.1m	April 2016	March 2020
Joint UNDP - DPPA Building National Capacities for Conflict Prevention	DFID	UNDP, DPPA	£3.75m	£1m	April 2016	March 2020
UN Global Programme on Strengthening the Rule of Law and Human Rights to Sustain Peace and Foster Development	FCO	UNDP	£1.2m	£0.3m	April 2016	March 2020
Human Rights Up Front Light Team Deployment	FCO	OHCHR	£0.45m	£0	April 2016	March 2019

SUMMARY OF PROGRESS AND KEY RESULTS FOR FY 18/19:

Sustaining Peace Agenda: The CSSF Multilateral Strategy (MuSt) Peacebuilding programme directly leverages the momentum created by the UN’s ‘Sustaining Peace’ Agenda and further supports its implementation. The reform, which continues to be strongly backed by the Secretary General, focuses on securing improved political, financial and operational support from the member states for peace. It has already led to a reform process in the UN’s Peacebuilding Architecture. A key highlight of which is a successful merger of the Peacebuilding Support Office (PBSO) and Department for Political Affairs (DPA) into a new Department for Political and Peacebuilding Affairs (DPPA). DPPA are now positioning themselves as the key think-tank and policy unit within the UN system on the preventive diplomacy agenda and will be increasingly significant with the overall UN reform bedding down. The Secretary General’s report on Sustaining Peace proposed 42 recommendations of which 38 were reported to be on track in the recent interim progress review. Those not showing enough progress relate to financing and are the prerogative of the member states. That said, both the Peacebuilding Fund and the DPPA Multi-Year Appeal exceeded their financing target in the reporting year.

Peacebuilding Fund (PBF): In 2018, the PBF had a budget of $183m (£143.4m) across 96 projects in 40 countries – up from 14 last year. This is an increase of 16.5% in terms of funding compared to 2017, with the trajectory expected to continue in the next two years. In addition to MuSt £4m funding, DFID also contributed £12m (up from £4m last year), making UK the second largest donor. PBF work consisted of 50% post conflict, 40% prevention and 10% in active conflict settings. There are three priority windows for the projects: gender and youth promotion; facilitating transitions; and cross border peacebuilding. There are many country level examples of successful PBF interventions, such as the PBF Democratic Republic of the Congo stabilisation projects. In southern Irumu, dialogue platforms have provided space for security sector actors and communities to jointly develop local security plans that reflect communal priorities. Early reports indicate that this initiative has increased the accountability of security actors, fostered social cohesion and reduced violence as communities have begun turning to local mechanisms to peacefully resolve disputes. The process also revived negotiations between the Government and the armed group ‘Force de résistance patriotique de l’Ituri’, which had been a security threat in the area.

Department of Political Affairs and Peace Building Affairs (DPPA) - Multi Year Appeal (MYA): On 1 January 2019, DPA became the DPPA, following the implementation of the reforms under ‘sustaining peace agenda’, the MYA now being run by DPPA. In 2018 the DPPA’s MYA budget was $35.6m (£27.9m), the UK’s contribution through the MuSt was £3.1m, making the UK the fourth largest contributor to the MYA. The MYA has done much to diversify and expand its donor base, getting an 8% increase in its funding. In this reporting period the MYA has developed a new results framework and theory of change and now conducts three evaluations per year. DPPA Special Envoys have committed to championing gender. With UK funding, DPPA has recruited a position in its Gender Unit and conducted gender and conflict analysis training with mediators.

Joint UNDP- DPPA Building National Capacities for Conflict Prevention: The Joint Programme raised $12.5m (£10m) from donors, including £1m from the MuSt programme, making the UK the third largest donor. In December - the Joint Programme initiated a new five-year project phase up to 2023, the new phase - will further strengthen the analytical capacities of national stakeholders and the UN system in support of Member States efforts to advance policy and programmatic coherence on conflict prevention and support strategies for sustaining peace. The Joint Programme supports 49 PDAs across 60 countries. Deployed PDAs work for the Resident Coordinators (RCs) conducting conflict analysis and supporting peace-building interventions, especially through the PBF. The Joint-Programme is increasingly piloting regional PDAs working across several countries. PDAs have therefore not only emerged as an important technical cadre the equivalent of political councillors to the RCs, but also play a pivotal role in boosting the professional and intellectual capacity on the ground on peacebuilding policy and programming.

UN Global Programme on Strengthening the Rule of Law and Human Rights to Sustain Peace and Foster Development: The UK is the only donor who earmarks its contribution to support the Global Focal Point (GFP), largely responsible for the HQ costs of the Global Programme of £300,000. In 2018, GFP underwent an independent review to reflect implications of the restructuring of the UNDS and UN PSA to ensure better coordination and delivery of better results on rule of law in mission, non-mission and transition settings. Currently GFP is the key platform within the UN system to centrally coordinate on security and justice issues.

LESSONS LEARNT/ACTIONS TAKEN SINCE LAST REVIEW
The following actions have been taken in 2018 following the last annual review.
- The MuSt support to the Human Rights Up Front (HRUF) Light Team Deployments was suspended, until they can demonstrate that all previous funding has been spent.
- Work is still ongoing to refresh and update the UK’s strategy towards the UN’s ‘Sustaining Peace’ agenda.
- The MuSt programme document has since been updated. The programme team has begun work on updating individual results frameworks with each of the implementers, which will feed into overarching changes to the programme logframe and theory of change.
- In the interim DFID has been providing additional policy resources, but there remain gaps. Work is also ongoing, but not complete, to improve coherence between London and New York offices of HMG. Greater DFID and FCO coordination is also needed in reaching out to the country posts.
- There is strong cooperation on UN-WB partnership at HQ level as well as in several focus countries, including Niger, Tunisia, Zimbabwe and Jordan. More strategic governance framework for implementation on the ground has been agreed.

SUMMARY OF KEY RECOMMENDATIONS FOR THE NEXT YEAR
- DPPA should continue to boost the professionalisation of Peace and Development Advisers (PDAs) – who are a high impact investment of the programme and can contribute positively to the ongoing UN reform process. MuSt could also consider linking DPPA with HMG’s Governance and Conflict Cadres for targeted technical assistance.
- While both DPPA and PBF report to be working and coordinating well together, the risk of duplications remains, and MuSt should continue to monitor this closely.
- Global Focal Point are unique in the sense that they provide a central coordination point on security and justice issues in the UN system. MuSt should ensure that appropriate links are made with respective Security & Justice policy teams at DFID and FCO.
- M&E remains an area that will need long term focus. There are indications where the responsible UN departments are making efforts to boost staff capability by hiring more specialist staff, improving their results frameworks and an increased focus on evaluation. These are all good building blocks towards a robust M&E culture where concrete results and impacts are targeted, captured and reported.