Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Multilateral Strategy (MuSt) - Peacekeeping
Country and Region:	Worldwide
IATI Unique ID:	CSSF-01-000003
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Ministry of Defence (MOD), Stabilisation Unit (SU)
Total Budget :	ODA: £10.85m			Non-ODA: £8.18m
Budget this FY	ODA: £2.33m			Non-ODA: £1.98m
Spend this FY	ODA: £1.75m			Non-ODA: £1.75m
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
1.1 Executive Office of the Secretary General: assuring the delivery of strategic reviews and new transition planning process.					A
1.2 Peacekeeping planning: improve integrated strategic planning through operational support.					B
1.3 UN project coordination: strengthened UN planning capabilities for UN missions.					A
1.4 Staffing principles and parameters: strengthened UN planning capabilities for UN missions.					A
2 Fully operational peacekeeping capability readiness system.					A
3.1 Deployments: demonstrate contribution of UK experts to the performance of pre-deployment training and field missions.					A
3.2 Training: all newly appointed sector commanders and heads of mission trained on relevant courses					A
3.3 Leadership partnering initiative: newly appointed and existing senior personnel supporting the initiative.					B
4.1 Standard mission network capability: develop secure network architecture design for peacekeeping missions.					A
4.2 Peacekeeping intelligence policy: situational awareness in relevant operations is significantly enhanced through functioning intelligence systems.					B
5.1 Enhancing the protection of civilians mandate: selected field offices have a structured plan to engage communities to address local conflicts and threats					A
5.2 Structured community engagement: advisors receive operational support and guidance.					A
Overall output score					A
Outcome Assessment: While measuring organisational change within a highly complex political body such as the UN will always remain challenging, the programme has made good progress, and there is evidence that our interventions are helping support a wider cultural change in UN peacekeeping. / Following the last annual review, the level of ambition of the outputs and outcomes in the programme results framework indicators and milestones was reduced, with the result that the programme is more realistic.
Outcome Score: A			Risk: Low

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	B	A	B	A	A
Risk Rating - low/medium/high	Low	Low	Low	Low	Low	Low
*output/outcome scores
How has the programme changed during this period? There has been a high level of continuity through the life of the programme; the strands of activity (police and military deployments, support to extra-budgetary projects) have not changed, and funding has remained steady.

What support did the UK provide in FY 18/19?

	ODA	Non-ODA
Extra-budgetary funding to the UN Departments of Peace Operations and Field Support.	£1.75m	£1.16m
Support to the strategic analysis and planning unit in the Executive Office of the Secretary General	£0.08m	£0.12m
Deployment of UK military and police officers to HQ, field missions, and in support of pre-deployment training (17 military deployments, one police deployment to UN Police (UNPOL) in New York, and 3 police deployments to support training for Police Contributing Countries (PCCs))	£0.50m	£0.50m

Key results for FY 18/19:

Performance: The intensive orientation and senior commanders courses provide the only UN-provided training for senior military commanders serving or about to serve in UN peacekeeping missions. The courses cover how to integrate gender issues, and the preventative framework for preventing sexual exploitation and abuse. The course was also amended this year to include scenario exercises based on real peacekeeping situations, to support the recommendations from the Santos Cruz report.

Planning: Support to the comprehensive performance assessment system increased the effectiveness of its initial implementation. By soliciting a wider range of views from the field, a successful roll-out of what is a key deliverable for the UN, and a critical tool in measuring and improving mission performance, is more likely.

Pledges: The strategic force generation cell has been widely judged a success, and, from initially only receiving UK funding, from next year will be wholly funded by other donors. By assessing the quality of Troop Contributing Countries (TCCs) commitments before they deploy, using the peacekeeping capability readiness system, and offering support in filling gaps, the cell provides an effective, less politically charged, method of addressing the performance issues of UN peacekeeping missions.

Summary of progress and lessons learnt/actions taken since last review

Strategic alignment. Over the three-year life of the programme, activity has continued to be more focused. Projects have, in line with last year’s recommendations, continued to be focused on planning, pledging and performance.

Field/HQ links. Contact between deployees and the programme team have been improved, with a more systematic approach to debriefs and pre-briefs, and monthly reporting from UK military deployees structured around planning and performance.

Monitoring and evaluation. The 2018/19 results framework has been substantially amended since last year’s annual review. The programme continues to use the planning performance and pledges structure, but within this, outcome indicators are mostly now more specific and measurable. Indicators map onto the individual extra-budgetary projects, and reflect but summarise the more detailed UN project logframes.

Summary of recommendations for the next year

The peacekeeping programme is now in its final year, and projects for 2019/20 have been selected. Over the past three years, the programme has made progress on monitoring and evaluation, strategic alignment and focus, and developing better policy/programme links. Given this, both the scope and requirement for significant change in financial year 19/20 is limited, and largely focused on building on the areas identified in earlier reviews.

Monitoring and evaluation. The programme is using different frameworks and strategies to articulate and measure its results: the NSC strategy, the programme results framework, and the UN-owned logframe. Efforts have been made to align these; but there are still mismatches and omissions in what needs to be the overall means to measure results, the programme results framework.
Field/HQ links. There is still scope to better understand how the UN reform agenda is implemented in the field. Our UK deployees provide a useful perspective through their improved reporting, but their insights will always be anecdotal, and their reporting always focused on their main, military functions in the missions. The programme team should continue to identify opportunities to visit the field, to talk to those on the front line of peacekeeping on UN reform initiatives. But given the difficulties of arranging visits, they could also think more creatively about how to gather in-country views, drawing on colleagues at post, particularly those working on other CSSF programmes.
Coordination. New UK funding streams have created some confusion within the Department of Peace Operations on what funding is available, and in support of what priorities. Untangling this has created additional work and damaged the UK’s reputation at the working level as a cooperative and efficient donor. There needs to be better communication between programme and policy leads working on UN reform within the UK Mission to the UN New York to avoid a repeat of this issue. Greater coordination would also support the development of a longer-term strategy and programme.