Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Multilateral Strategy (MuSt) - Security Capacity Building
Country and Region:	Worldwide
IATI Unique ID:	CSSF-01-000004
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: £5.18m			Non-ODA: £6.31m
Budget this FY	ODA: £2.53m			Non-ODA: £1.21m
Spend this FY	ODA: £2.46m			Non-ODA: £1.14m
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Hybrid Threat:
1: Strategic Communications: NATO adopts a more integrated, campaign-focused approach					A
2: Strategic Communications (Western Balkans), developing a framework for implementation and coordinating with stakeholders enhancing NATO’s strategic communications engagement					A
3: Cyber (NATO Voluntary National Contributions)					A
4. Baltics Resilience: NATO advises and implements potential improvements to resilience planning across the Baltic States					A
5: EU-NATO Resilience: joint commitments on coordinated or joint exercises (PACE18)					A
6: Hybrid threats (NATO – European Centre of Excellence)					A
Capacity Building/Civilian Resilience:
7: Defence Capacity Building (DCB) – demonstrable progress in establishing DCB architecture in NATO					A
8: Civilian Planning & Conduct Capability: Common Security and Defence Policy (CSDP) missions function better, and more effective					A
9: Security for Development – strengthened implementation capacity of EU Delegations and contracting partners, including effective indicators for all EU Counter Terrorism (CT)/Countering Violent Extremism (CVE)/Serious Organised Crime (SOC) projects					B
10: European External Action Service Serious & Organised Crime: CSDP missions/operations and wider EU security activity (SOC/CT/CVE) fully reflects UK interests including by strengthening internal & external security					B
11: CT Capacity Building/Stakeholder Mapping, Jordan – improvements in quality of advice on how to progress NATO’s DCB objectives in Jordan, including on CT					A
Human Rights/Freedoms:
12: Chairmanship of the Human Dimension Committee (OSCE)					A
13: Senior Adviser to the Office of the Special Representative on Freedom of the Media (OSCE)					A
14: OSCE Chairmanship Taskforce – Italian Ministry of Foreign Affairs					A
Counter Proliferation:
15: IAEA carry out activities necessary for the verification and monitoring of Iran’s nuclear-related commitments under the Joint Comprehensive Plan of Action (JCPoA)					A
16: – not in RF
17: provide technical advice and institutional support for OSCE participating States to supplement OSCE Small Arms and Light Weapons/Stockpiles of Conventional Ammunition normative base and improve implementation of its practical assistance					A
Countering Violent Extremism
CVE 1: Strategic Communications: to develop capacity of Member States and UN entities in the utilisation of strategic communications in Preventing/CVE					B
CVE 2: UNDP: Coordinated UN Development Programme and partner support to the formulation, implementation and monitoring of regional and national PVE Plans of Action					B
CVE 3: Commonwealth Secretariat initiates projects in support of target country P/CVE National Action Plans					A
Overall output score					A
Outcome Assessment: Institutional change and capacity-building are challenging in a national environment, and even more so in established, multilateral institutions (securing members’ consensus to commit to transform, courses of action and implementation), but the SCB programme has achieved strong results across a broad range of interventions.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	Not Applicable	B	A	A	A	A
Risk Rating - low/medium/high		Medium	Medium	Medium	Medium	Medium
*output/outcome scores

What support did the UK provide in FY 2018/19?
- UK civil servants and Deployable Civilian Experts deployed in multilateral institutions - £1.5m
- Funding to multilateral institutions to recruit staff - £100,000
- Funding for multilateral monitoring and verification exercises – £270,000
- Funding for multilateral CT and CVE projects - £1.7m

Key results for FY 2018/19: an illustrative example from each “strand”:
Hybrid: strategic communication campaign #WeAreNATO showcasing Alliance’s role. The campaign (UK led) was initiated as part of the Alliance’s 2016-2017 NATO Communications Strategy, which identified the need for a campaign to increase awareness and understanding of NATO and its role in global security.
- Capacity Building: EU-NATO joint commitments for Exercise (PACE18). Drafting a more ambitious PACE concept seeking to enhance engagement between NATO Allies and EU Member States.
- Human Rights: Ministerial Council approval of texts under the OSCE Second Dimension - Declaration on Digitalisation and Security, and a Decision on the role of Human Capital Development in managing the impact of digitalisation on Security. Both decisions closely aligned to UK thinking on digital issues.
- Counter Proliferation: Verification and monitoring by the International Atomic Energy Agency of Iran’s nuclear-related commitments as set out in the JCPOA.
- Countering Violent Extremism: Commonwealth Secretariat implementing its strategy including activities with four priority countries – Trinidad and Tobago, Tanzania, Cameroon and Bangladesh.

Summary of progress and lessons learnt/actions taken since last review

The Senior Responsible Officer endorsed the Annual Review FY2017/18 recommendations commenting they “provide a strong platform to continue to improve the programme in 2018/19” with a tracker to record implementation. For FY 2018/19 the programme continued to progress, adding new strands (counter proliferation and CVE) with additional institutions (UN, IAEA and the Commonwealth Secretariat). The programme management is to be commended for continuing to seek improvements through project development, project monitoring and sharing lessons.

Summary of recommendations for the next year

1. Require reporting to focus on output and outcomes, rather than activity and input.
2. Enhance awareness and understanding of the Theory of Change with partners and adapt to reflect additions (counter proliferation and CVE), plus the effects of Brexit.
3. Strengthen with policy leads and deployees the criticality of the Results Framework to inform and assess performance towards achieving outputs and outcomes.
4. Promote with policy leads and deployees the CSSF purpose and key components, in particular the cross-cutting themes (conflict sensitivity, gender and human rights) for interventions.
5. Ensure deployees understand their intervention fit within the National Security Council strategy and share this intent with their multilateral principal to develop mutually beneficial work streams.
6. Consider, with the expansion to five strands, programme coherence, strategic effect and fit of projects within strands and across strands, bringing the desired political access and influence.