Annual Review - Summary Sheet

PROGRAMME TITLE: Anguilla Programme (AP)
Country and Region:	Anguilla, Caribbean
IATI Unique ID:	CSSF-07-000005
HMG Partners	Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: N/A			Non-ODA: £60m
Budget this FY	ODA: N/A			Non-ODA: originally £20m (then agreed to be £8.27m at the supplementary estimates stage).
Spend this FY	ODA: N/A			Non-ODA: £8.29m
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
Output 1 - Education infrastructure restored to pre-Hurricane Irma level and built back better.					B
Output 2 - Health facilities restored to pre-Hurricane Irma levels of functionality but with greater hurricane resilience.					B
Output 3 - The majority of Government of Anguilla (GoA) officials to be located in appropriate, safe and hurricane resilient accommodation realising financial savings by co-locating and reducing of amount of rented accommodation.					B
Output 4 - Prioritised elements of National Infrastructure returned to full functionality but built back stronger.					B
Output 5 – Information Technology systems underpinning Inland Revenue strengthening, General Service Tax (GST) and Lands Information					A
Overall output score					B
Outcome Assessment: B
Outcome Score: B			Risk: High Risk

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	N/A	N/A	N/A	B	B
Risk Rating - low/medium/high	N/A	N/A	N/A	N/A	High	High
*output/outcome scores
How has the programme changed during this period?: The breadth of coverage has been reduced from an initial circa 30 programme strands to focus on fewer strands in order to continue to fit within the overall budget package.

What support did the UK provide in FY 18/19?
- The UK has provided funding for a focused range of projects towards helping to rebuild Anguilla’s critical national infrastructure with enhanced resilience, as an enabler for progress towards sustainable economic development and self-sufficiency.
- The UK has provided advice to the AP and project managers on governance requirements, deliverability, procurement, legal, project management, Mechanical & Engineering and financial management.

Key results for FY 18/19:
- Completion of a clear reprioritisation exercise to fit within the funding envelope removing lower priority projects – these have either been removed from the programme, or pushed back such that they would only start if further funding is identified (or efficiencies or favourable exchange rate movements mean that more can be completed with the existing funds).
- Most project strands have progressed to design stage of the project lifecycle.
- Significant improvement to the quality and completeness of business cases for the multiple project strands – rendering the projects more likely to meet the wider objectives of the programme and helping to protect Value for Money (VfM) considerations.
- Increased familiarisation for key stakeholders with CSSF and FCO Pay 2 Purchase processes and procedures in order to facilitate future delivery.
- Education:
  - Primary schools - business cases for all primary schools completed. One school completed. Tender process for refurbishment to one school completed – along with tender for a second.
  - Secondary School – progression of the business case including options analysis. Stakeholder events held. Identification of several risks involved and involvement of expert advice.
- Health:
  - Hospital – significant strengthening of core building to hurricane secure standard; concept designs for the Accident & Emergency, theatre expansion and garage and storage unit progressed. The hospital perimeter wall built following an emergency re-tender resulting in essential equipment being more secure, including dialysis pumps.
  - Three clinics - designs and works to all three clinics delayed till early Quarter 1, Financial Year 19/20.
- Access:
  - Combined (Fire and Air Traffic Control) Services Building – fire trucks procured and in use. Building close to being operational by August 2019.
- Taxation and Land Registry systems:
  - IT systems integral to the revenue strengthening projects, and wider public financial management reform, have been procured and implementation of these project strands is on track.

Summary of progress and lessons learnt/actions taken since last review

- Early activity was affected by a conditionality clause which (with other factors) will likely result in the need consider extending the timeframe for parts of the programme.
- Capacity constraints within critical parts of the GoA - implementing partner – slowed down preparation of business plans.
- Lessons regarding the importance of early and comprehensive communication with key stakeholders.
- There have been some challenges integrating foreign contractors to backfill capacity/capability.

Summary of recommendations for the next year

1. In order to continue to maintain the VfM of the programme we recommend that timeframes for the programme be reviewed and revised where possible. Striking a balance so that the envisaged timeframe remains stretching and does not delay the benefits for the intended recipients unnecessarily, but also sets a realistic time horizon and does not force the acceptance of sub-optimal decisions nor the tolerance of reduced quality.
2. Seek further funding including for the renewable energy aspects of the building projects (potentially from alternative funding sources) which will not be possible to complete within the current programme envelope (and are outside of the current remit).
3. Add qualitative measures to the results framework to increase the ease of assessing progress. Recommended rewording of the sections relating to the IT systems underpinning the GST and Land Registry to reflect that it is the implementation of the systems rather than the regulatory changes which are the objective of the programme.
4. The programme seek the advice of the CSSF Advisory Team with regards to documentation of decisions relating to Gender and Social Inclusion.
5. Governor’s Office to seek small recurrent capital budget following the completion of the programme to support where appropriate for aspects of the whole-life cost of the assets procured or built by the programme and noting that rights and obligations of ownership will sit with the GoA.