Annual Review - Summary Sheet

PROGRAMME TITLE: British Virgin Islands Territory Programme (BVITP)
Country and Region:	British Virgin Islands (BVI), Overseas Territories
IATI Unique ID:	CSSF-07-000007
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO)
Total Budget :	ODA: n/a			Non-ODA: £10.00m
Budget this FY	ODA: n/a			Non-ODA: £4.08m
Spend this FY	ODA: n/a			Non-ODA: £4.10m
Original Programme Start Date: April 2018		Planned End Date: March 2021
Outputs					Score
Recovery and Development Agency (RDA) established & delivering					B
British Virgin Islands Government (BVIG) supported to stabilise security					B
Transitioned UK early recovery support to BVI-led long-term recovery					B
Overall output score					B
Outcome Assessment: The pace of BVITP delivery has been slower than expected, due in large part to the initial challenges achieving a consensus for recovery, agreeing the Recovery to Development Plan (RDP) and establishing the RDA, followed by the February 2019 general election. The situation was further complicated by a subsequent change of BVIG. The new Government, elected with a mandate to speed up the recovery process and deliver good governance, has initially decided to take stock of the previous Government’s recovery planning. The impact of this on programme delivery timescales has been more profound than anticipated, leading to delays across the programme. In some of these cases, delaying activity to secure appropriate local buy-in and ownership is appropriate.
Outcome Score: B			Risk: Medium-High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score					B	B
Risk Rating - low/medium/high					Medium/High
*output/outcome scores

What support did the UK provide in FY 18/19?
- Financial support (operating costs) for the establishment of the RDA, which will deliver public infrastructure projects in line with BVIG’s priorities as set out in the five- to seven-year RDP.
- Funding for recovery projects that are identified as critical priorities to the resumption of normal security & justice activities or in disaster preparedness (the constitutional responsibility of the Governor of the British Virgin Islands).
- Funding for the continuation and completion of early recovery projects and plans for the restructuring of critical BVIG public works departments and agencies.

Key results for FY 18/19:
- The RDA has been established with full staff complement and functioning independent board and is now overseeing the delivery of a small portfolio of projects with potential to take forward a comprehensive portfolio of complex recovery to development projects in line with BVIG’s priorities.
- The repair of the Jost Van Dyke admin complex (including police, customs and immigration) and Virgin Gorda Police Barracks are almost complete, with (gender sensitive) improvements made in line with BVIG ambitions.
- Early recovery projects have been completed. While the Memorandum of Understanding formally transferring ownership and maintenance of project outputs is yet to be signed by BVIG, the programme team are confident that the MoU will be signed early in the new financial year.

Summary of progress and lessons learnt/actions taken since last review

While BVITP is new this year, key stakeholders (UK Government, BVIG and the RDA) have learned lessons from the immediate response and early recovery programmes of support following Irma and Maria. These lessons include:

- The importance of docking into locally driven lines of communication early on in a crisis;
- Supporting BVIG to keep a tight focus on the scope of immediate response and early recovery interventions to meet the basic needs of as many vulnerable people as possible, as soon as possible
- Understanding the limits of participatory approaches to project delivery when engaging with vulnerable beneficiaries

During the year the Programme Team have continuously adapted their plans, in response to lessons learned and assessments of the complex political context. In particular, the team have reflected on the importance of investing time and effort to secure early stakeholder buy-in to, and ownership of, strategic delivery through embedded technical advice where appropriate. This collaborative approach should help to ensure the sustainability of programme investments in the medium to long term.

It will be important for the Programme Team and the RDA to continue to check in on the realism of expectations regarding the pace of delivery, contingent on the expressed priorities and absorptive capacity of a new BVIG administration.

Summary of recommendations for the next year

The Programme Team need to refresh its Theory of Change, looking beyond the immediate results chain to consider wider assumptions and dependencies and their effects on the programme. Once completed, any changes need to be incorporated into a Results Framework that better accounts for the challenges present in the programme’s operating context.

With the programme approaching the mid-way mark, it is important for the Programme Team, in collaboration with the RDA and BVIG counterparts, to set out a viable exit strategy, the feasibility of which can be monitored over the coming year in order to inform any required adaptations to current plans.

The RDA should continue to develop its rigorous monitoring and evaluation to inform strategic decision-making and portfolio adaptation, including by gathering end user and beneficiary feedback at project level to learn lessons. The RDA should also take forward plans to focus senior contributions at the strategic level (e.g. through the use of Concept Notes for programme approval), and focus even more on its capacity building, fundraising and strategic communications efforts, given their importance to the RDA’s overarching Theory of Change and BVITP’s current timeframe.