Annual Review - Summary Sheet

PROGRAMME TITLE: Justice, Security and Governance Programme
Country/Region:		Overseas Territories
IATI Unique ID:		CSSF-07-000004
HMG Partners / (LEAD in bold)		Foreign and Commonwealth Office (FCO), National Crime Agency (NCA), Ministry of Defence (MoD), Home Office (HO), Children and Family Court Advisory Support Service/Ministry of Justice (CAFCASS/MoJ), Department of Health and Social Care/Public Health England (DHSC/PHE), Crown Prosecution Service (CPS), Commonwealth Parliamentary Association UK (CPA UK), National Audit Office (NAO), HM Treasury
Total Budget :	ODA: £2.83m			Non-ODA: £24.36m
Budget this FY	ODA: £1.41m			Non-ODA: £15.36m
Spend this FY	ODA: £1.27m			Non-ODA: £13.16m
Original Programme Start Date: July 2016			Planned End Date: March 2020

Outputs		Score
1.1 Overseas Territory (OT) security and justice actors are supported to increase capacity, capability and competency.		B
1.2 Inter-agency collaboration to address crime and safeguard vulnerable and minority groups is enabled and enhanced through technical equipment and advice.		B
2.1 Public sector standards and public service delivery brought in line with international standards and obligations, particularly in relation to child safeguarding and health.		A
2.2 Capability and accountability in public financial management lead to greater confidence in international investors.		A
3.1 OT preparedness to respond to 'all hazards' is supported and sustained through organisational development and capacity building in security, justice and related sectors.		B
3.2 Long-term risks, including in respect of public health and economic security, are mitigated through UK support.		A
Overall output score		B
Outcome Assessment: B / Although there have been a number of successes, including bolstering the capacity to support child safeguarding and public health in the OTs and increased public financial management capability, there are still some key areas the programme needs to address going forward.
Outcome Score: B	Risk: Medium
Summary of Programme Performance / Year 2015/16 2016/17 2017/18* 2018/19* / Programme Score N/A A (SGGDM) Security, Good Governance and Disaster Management / A (SDIO) Sovereignty, Defence and International Obligations A A B / Risk Rating - low/medium/high N/A Medium (SGGDM) / Low (SDIO) Medium Medium Medium / *output/outcome scores
How has the programme changed during this period? The Programme is highly ambitious both in scope and geographical remit since integration of two programme components following recommendations from the last Annual Review period.

What support did the UK provide in FY 18/19?

The Justice, Security and Governance (JSG) Programme provides support to ensure the UK Overseas Territories (OTs) are protected from and resilient to a range of security threats including natural and manmade disasters, economic insecurity, crime, and public health threats. It aims to ensure the OTs are governed by effective and transparent government agencies and institutions who are compliant with key, identified international conventions.

Key results for FY 18/19

Establishment of Integrated Ballistic Identification System (IBIS), allowing identification and matching of bullet casings and other evidence from firearms-related crimes across Caribbean OTs, is a promising achievement, and has already contributed high quality evidence that secured convictions.

Repairs and reconstruction work following Hurricane Irma has been progressing well and restoring much needed security of prison infrastructure.

Multi Agency Safeguarding Hubs opened in two OTs with social workers, medical professionals and social workers co-locating to support victims of abuse. The UK has worked with OT Governments to develop an online digital forensic Hub to tackle online child abuse and cyber-crime in the OTs.

Improved resilience and preparedness for the 2019 hurricane season. The CSSF part-funded a twin-engine light utility helicopter operated by the Royal Cayman Islands Police Service which is now available to support Caribbean OTs in disaster response and law enforcement operations.

Summary of progress and lessons learnt/actions taken since last review

The results framework has been streamlined with programme components now sharing collective responsibility for delivering joint outcomes and outputs, strengthening coherence between components and opportunities for improved collaboration between projects. Urgent equipment procurement was completed under Disaster Resilience Programme in August 2018 to support disaster preparedness. Emergency deployment protocols have been agreed for UK Police with the Home Office/National Police Coordination Centre (NPoCC) and for Prisons with Her Majesty’s Prison and Probation Service (HMPPS). A call-down contract with the private sector has been agreed to provide support from prison officers. To enhance the operability of the Montserrat Patrol Vessel (MPV), a specialist contractor was engaged to increase capability of crew and engineers, and improve offshore/onshore management. This provided technical expertise needed by the crew and the FCO to ensure effective management of the vessel and provided recommendations that are still being used to obtain best value for money. Key lessons learned have been shared with other programmes on speed of delivery and the absorption capacity of the OTs. Public Health support has been re-shaped to complement the wider programme and disaster resilience more closely, including support to counter mosquito-borne diseases after a disaster. The Law Enforcement, Criminal Justice and Prisons components have been reviewed to make sure that urgent projects around post-hurricane repair and immediate security needs could be delivered while starting a more ambitious strategic programme supporting the entire justice cycle, with Ministry of Justice expertise.

Summary of recommendations for the next year

Recommendations focused on programme governance such as the need for the Programme Team to develop a Gender policy and integrate it into programme activities and disseminate among delivery partners; recommendations on refining the programme results framework; applying more robust budget forecasting that avoided underspends; and strengthening the monitoring and evaluation of the activities and outputs. Additionally, there was a policy recommendation to consider widening the Public Health component of the programme to complement and support other areas of the programme.