Annual Review - Summary Sheet

PROGRAMME TITLE: Maritime Governance and Environment (MGE)
Country and Region:	Overseas Territories (OTs)
IATI Unique ID:	CSSF-07-000008
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office(FCO), Department for the Environment, Food and Rural Affairs (DEFRA), Maritime and Coastguard Agency (MCA), Department for Transport (DfT), UK Hydrographic (UKHO), Ministry of Defence (MoD), Marine Management Organisation (MMO), The Centre for Environment, Fisheries and Aquaculture Science (CEFAS), Animal and Plant Health Agency (APHA),
Total Budget:	ODA: £7.53m			Non-ODA: £17.53m
Budget this FY	ODA: £3.16m			Non-ODA: £9.70m
Spend this FY	ODA: £3.91m			Non-ODA: £10.04m
Original Programme Start Date: April 2018		Planned End Date: March 2020
Outputs					Score
Maritime Obligations					A
Search And Rescue (SAR) Capability					A
Pollution Response					A
4 & 5. Hydrography & Seabed Mapping (including, Output 5, boundary delimitations)					A
6. Natural Capital					A
7. Biosecurity & Invasive Species					A
8. Blue Belt					A
Overall output score					A
Outcome Assessment: A
Outcome Score: A			Risk: Med

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	N/A	A	A	A	A
Risk Rating - low/medium/high	N/A	N/A	Med		Med
*output/outcome scores

How has the programme changed during this period?

This has been a productive year for the MGE programme, now in its third year (though first year with this programme structure) and benefiting from the amalgamation of elements from the previous Sustainable Economic Development programme and the Sovereignty, Defence and International Obligations programme. MGE comprises two principal elements: the ‘Blue Belt’, and the UK’s responsibility to ensure that the OTs are capable of complying with their international obligations as flag, port and costal states. Projects set up to deliver the latter have now been successfully completed and links between these projects and Ministerial commitments (such as the DEFRA 25-year Environment Plan) have been established to assist OTs in sustaining the capability into the future.

Financially, there were several changes in the programme. The original allocation of £12.87m was revised in year to £13.51m. Underspends against the original budget in areas such as MCA and UKHO caused by delays in legislation or by factors such as the weather, were compensated for by additional spending on other projects within the programme, such as the Blue Belt.

What support did the UK provide in FY 18/19?

The programme is split into three areas of focus:
- Delivering the UK Government’s ‘Blue Belt ‘commitment to provide long term protection to over four million Km2 of marine environment.
- Meeting the UK’s responsibility to ensure the OTs are capable of complying with their international obligations as flag, port and costal states (International Maritime Organisation’s audit (III Code), Security Needs Assessment, Search and Rescue (SAR), seabed mapping, Hydrographic charting).
- Increasing environmental resilience across the OTs.

Key results for FY 18/19:

Maritime Obligations and SAR: Legislative scoping studies and capability reviews have identified gaps and individual programme plans are being developed to address the issues. SAR Central Alerting Post (single point of contact for all regional SAR related matters) equipment has been delivered to Anguilla, British Virgin Islands (BVI), Cayman Islands, Montserrat and St Helena.

Pollution Response: The majority of pollution response capability reviews have been undertaken and reports are in draft; pollution response equipment has been procured for BVI and Montserrat.

Seabed Mapping: Seabed mapping completed in Turks and Caicos Islands (TCI), BVI, Anguilla and St Helena, with 10 OTs completing a seabed governance capacity building course. This allows for the production of new navigational charts, improved governance and leads to improved conformance with international obligations.

Natural Capital: This programme was completed in March 2019, with significant progress made in building OT understanding in the value of the natural environment in enhancing economic security and disaster resilience in the OTs.

Biosecurity and Invasive Species: workshops and analysis of how to tackle invasive species have been completed for all OTs with support being given for the development of action plans. Continued preparation towards the RSPB-led project to eradicate the large population of non-native invasive mice on Gough Island, a dependency of Tristan da Cunha.

Blue Belt: Surveys of krill population and seafloor environment around South Georgia & the South Sandwich Islands by research ship RRS Discovery. Surveys conducted around Tristan da Cunha and St Helena, providing valuable data for management of fisheries and other activities.

Summary of progress and lessons learnt/actions taken since last review

The recommendations from the 2017/18 review observed that it was difficult to ‘piece together the totality of the programme effort contributing to NSC Strategy objectives’. The programme has been rationalised with the corresponding Results Framework, Results Tracker and Risk Register. This makes it a lot easier to assess the progress of the programme and has assisted co-ordination at project level. The overarching documentation is now clear, and so activity is easy to map and evaluate. This has also played positively into the recommendation that communication across all stakeholders needed to be strengthened. Efforts to seek greater buy-in from OT governments are ongoing and the programme team have worked on and improved their internal collaboration creating a more streamlined programme team.

Summary of recommendations for the next year

Recommendations centre on working with OT governments to ensure their continued commitment so that key components of the programme are taken forward and that practice follows policy; that OT decisions on implementation (e.g. of marine conservation areas and fishing regulations) can be delivered, the resources are there; and that the OTs are able to pass and support the legislation to deliver new capabilities in a timely manner. Aside from the OTs’ governance, there are recommendations for the programme team (e.g. to review the Theory of Change and assumptions) to include the ecological and economic benefits of the programmes in UK Government and OT policy planning and communications products; and to plan for the longer-term.