Annual Review - Summary Sheet

PROGRAMME TITLE: CSSF Myanmar Programme
Country and Region:	Myanmar
IATI Unique ID:	CSSF-09-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID)
Total Budget :	ODA: £14.7m			Non-ODA: £103,418
Budget this FY	ODA: £3m			Non-ODA:n/a
Spend this FY	ODA: £2.87m			Non-ODA:n/a
Original Programme Start Date: April 2015		Planned End Date: March 2020
Outputs					Score
High quality research and technical advice made available to all the main parties to the peace process.					B
Formal and informal conflict management mechanisms are strengthened to amicably resolve and/or prevent conflict.					B
Elected government officials, safety and security-related agencies and the public together reshape community security approaches, including for the prevention of violence against women and girls.					A
Spaces and key community figures promote community engagement in Rakhine, building our analysis of potential security risks and supporting the accountability process.					U
Overall output score					B
Outcome Assessment: The stalling of the formal peace process has impacted progress towards outcome one significantly this year, although steps forward at both the state and sub-national level remain possible. Most progress has been made under outcome two (community security) and a strong start made to developing a Rakhine strand of work. The outcome score reflects the likelihood of the current outcomes being achieved by the projected end date of the CSSF Myanmar programme.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19
Programme Score	A	B	B	C	B	B
Risk Rating - low/medium/high	M/H	Medium	Medium		Medium

*output/outcome scores

What support did the UK provide in FY 18/19?
The CSSF Myanmar programme is a multi-year programme seeking to support Myanmar’s evolving political settlement. A primary objective is to support the nationwide formal peace process between the government, ethnic armed organisations (EAOs), and the military (Tatmadaw). There are three pillars to the programme:

i) Peace process: Technical and financial support to the process, including high-level advice to the parties.
ii) Community Security: Improving how Myanmar and EAO authorities (including security services) and communities work together to understand local security and safety needs, with a particular focus on women and girls’ safety and security.
iii) Rakhine: Promoting capacities for tolerance and resilience to inter-communal tensions in mixed communities.

Key results for FY 18/19:
Despite the stalling of the peace process the programme has delivered informal dialogue between high level stakeholders to move the peace process forward.

- A wide range of activity around the peace process, including research products to inform negotiation positions, public dialogues to increase participation in the process, coordination meetings amongst stakeholders and informal meetings between them are supported.
- The National Crime Prevention Strategy was launched in May 2019.
- Organised national and sub-national events for public interaction with security actors on public safety issues.
- Engaged with government officials at township and ward level to raise awareness of gender-based violence (GBV), and gathered evidence of women’s safety issues.
- Supported the construction of learning centres for shared use by Muslim and Buddhist community members for a range of communal activities and trained young people in these communities on conflict prevention and managing inter-communal tensions in Rakhine.

Summary of progress and lessons learnt/actions taken since last review
Significant work has been done since last year’s review, in particular to improve the results framework. This now recognises access and influence as a key output and seeks to measure the resulting effect.

This review covers the period from June 2018 to June 2019, to align with the period covered under last year’s CSSF Myanmar Annual Review towards the annual milestone of June 2019 in the Results Based Framework. This year, the Rakhine crisis and the stalling of the formal peace process has had the most immediate impact on the CSSF programme’s ability to make progress towards its outputs and outcomes. CSSF-funded work in Rakhine on community cohesion and resilience is in its inception phase.

Summary of recommendations for the next year

Update and revise the programme Results Framework and Theory of Change
The programme Results Framework (RF) needs to be up to date, logical and reflective of the actual funding of projects. The theory of change (ToC) underpinning the RF requires some fundamental improvements to meet good practice standards. A revision of the ToC provides an opportunity to review whether all projects under the community security pillar should continue to be funded.

Continue supporting the peace process
UK funding of the Joint Peace Fund (JPF) signals the UK’s continuing commitment to the peace process. As well as continuing funding, British Embassy Yangon (BEY) should remain active in pushing for improvements to JPF as needed.

Review external risk factors and mitigation
BEY should revisit its assessment of external context risks (or explain why this is not necessary) and conduct a thorough reassessment of possible context risks and potential mitigation.

Increase monitoring of the programme’s conflict sensitivity
The CSSF programme team should be systematically monitoring conflict sensitivity at the programme level. Whether or not the programme requires dedicated conflict advisory support, beyond what support may be available from the new DFID conflict adviser, should be considered.

Improve monitoring of technical support to the peace process
Progress should be supported by a clear theory of change explaining the logic behind interventions leading to the intended results via intermediate outcomes.

More actively promote learning and collaboration between projects
BEY should increase its efforts to bring the implementing partners for the peace process, community security and Rakhine pillars together on a regular basis as a means to improve the sharing of learning across projects.