Annual Review - Summary Sheet

PROGRAMME TITLE: Nepal Conflict, Stability and Security Fund (CSSF) Peacebuilding Programme
Country and Region:	Nepal, South Asia
IATI Unique ID:	CSSF-09-000002
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID), Ministry of Defence (MoD)
Total Budget :	ODA: £3.2m			Non-ODA: N/A
Budget this FY	ODA: £1.16m			Non-ODA: N/A
Spend this FY	ODA: £1.16m			Non-ODA: N/A
Original Programme Start Date: / April 2017		Planned End Date: / March 2020
Outputs					Score
Targeted marginalised communities understand the new federal structures, are supported to articulate their needs and engage with political representatives.					A
Political party representatives increasingly understand and reflect the interests of their constituents.					A
Nepal's objective, independent and non-partisan political research capacity improves, and creates safe spaces for policy debate.					A
Overall output score					A
Outcome Assessment: The (revised) Theory of Change is robust, evidence-based, and adaptable, using mechanisms for regular review. This allows implementing partners to prioritise outputs and outcomes rather than inputs. We assess that the outputs align strongly with the programme’s stated outcomes, although we may need to further probe the contribution of the media work.
Outcome Score: A			Risk: High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	N/A	B	B	A	A
Risk Rating - low/medium/high			High	High	High	High
*output/outcome scores
How has the programme changed during this period? / The programme was redesigned following recommendations made in last year’s annual review. At the outcome level, the programme now uses progress on federalism as a means to interpret inclusion of certain marginalised communities (the Government of Nepal introduced federalism shortly after the programme document’s completion in 2017.) This increased focus at the outcome level has led to the following delivery changes: / The programme focused more narrowly on three Provinces in Nepal. This improves depth and quality of delivery and flexibility, drawing on comprehensive and integrated learning and research. / A shift from a demand-led, rights based approach to a collaborative approach to help foster trust and confidence between communities and elected officials. / An explicit focus on the most marginalised groups and identity/caste discrimination to prevent widespread discontent, and consolidate initial peace dividends offered by federalism. / A new observational research project with a new partner. This focuses on building national research capacity, improving the evidence base for policy, and opening up the space for a policy debate around federalism.

What support did the UK provide in FY 18/19?

The programme supports the delivery of the UK’s cross-government strategy on Pillar 1: De-facto devolution of formal power from federal to sub-national governance. Specifically, it contributes to the effective functioning of three new spheres of government, and protects democratic space. In Pillar 3: Reduced culture of impunity, it protects rights for minorities, invests in the protection for the poorest, and supports resilience to shocks and natural hazards. Collectively, these reduce the risk of a return to sub-national conflict (stability and inclusion)[1]. The programme works directly with affected communities in the Terai to address the trust deficit, and supports confidence-building measures between ethnic minority groups and the political establishment, using federalism as the entry point.
[1] The One HMG strategy was updated in 2018 explaining the change in language around the HMG objective(s) that the programme supports the delivery of.

In 2018/19, two projects were supported by the UK in order to deliver the programme’s outcomes and outputs:

  1. A Consortium of international and national NGOs, led by International Alert, and implemented with Sundar Santha Nepal. The purpose of the project is to demonstrate how sub-national conflict drivers can be addressed by reducing causes of marginalisation. The Consortium has been supported since the programme’s outset in September 2017, but went through a redesign process in 2018.

  1. Observation of Nepal’s Post Constitution Politics and Governance (OPPG) is a research project run by the Democracy Resource Centre Nepal (DRCN). The purpose of the project is to ensure that law and policy-making at national and subnational level is informed by reliable, accurate and timely evidence gathered locally in order to create an enabling environment for the consolidation of federal democratic governance and a corresponding reduction in the risk of conflict and related violence.

Summary of progress and lessons learnt/actions taken since last review

The CSSF programme team and implementing partners have made significant progress since the last review. They have comprehensively addressed the vast majority of the recommendations from the last annual review, and all those of greatest strategic importance. The programme, as a result, is in a strong place to deliver some good results into the next financial year, having already demonstrated that the activities and approach are well targeted to deliver a clearer and more focussed output and outcome.

Summary of recommendations for the next year

Support through CSSF should continue beyond March 2020. Potentially to include targeted support for the Consortium given its ability to remain flexible, and its focus on risks, context and drivers of conflict. It is recommended that the UK Government team consider looking at grievances that have remained unaddressed in the constitution, including: human rights; transitional justice; and early warning, retaining some flexibility to respond to opportunities should they arise.

DFID should create more explicit departmental ownership for the programme and its outcomes. The CSSF governance board should think about broadening representation of DFID to include someone from the “leave no one behind” pillar.

The UK Government should discuss whether there are opportunities to champion any of the policy areas as part of the new political governance programming and space should be created in a tender process for this to be explored in more detail.

The Consortium to produce a learning and evidence strategy and dissemination plan. Support from Consortium headquarters or external support funded by the UK Government is recommended and should be prioritised. Capture collaboration and complementarity in reporting.

The CSSF team, with DFID, to consider how they support the learning and knowledge sharing effort. The CSSF team needs to think about how to address resource constraints on their side that might undermine effectiveness of delivering this.