## Annual Review - Summary Sheet

PROGRAMME TITLE: Consolidating Democracy Programme in Pakistan (CDIP)
Country/Region:	Pakistan/South Asia
HMG Partners / (LEAD in bold)	Department for International Development (DFID), Foreign and Commonwealth Office (FCO)
Unique IATI number:	CSSF-08-000001
Total Budget:	ODA: £ 26.40m			Non-ODA: N/A
Budget this FY (post Supps)	ODA: £ 9.37m			Non-ODA: N/A
Spend this FY:	ODA: £ 9.35m			Non-ODA: N/A
Start Date: July 2016		End Date: March 2020
Outputs					Score
Election management and election oversight processes are more credible, transparent and inclusive.					A
Parliamentary processes are more inclusive, and Parliamentarians are more effective in holding government to account.					B
Political parties across the mainstream political spectrum better represent, respond to and deliver for their constituents.					A
Expanded democratic space allows improved policy dialogue, political debate and public discourse.					A
Overall output score: A
Outcome Assessment: Progress at outcome level is mixed. General progress in voter registration, turnout and in the operational aspects of election management, as well as in support to democratic institutions including parliaments and political parties. However, with shrinking civil space, challenges to media freedom and growing economic disparity, significant challenges remain. While these external factors are not in the control of the programme, the programme will explore including more nuanced outcome level indicators to gauge Programme Completion Review.
Outcome Score: A			Risk: Medium

Summary of Programme Performance
Year	2016/17	2017/18	2018/19
Programme Score (Output)	A	A	A
Programme Score (Outcome)		n/a	A
Risk Rating	Medium	Medium	Medium

What support is the UK providing?
The expected impact of the Pakistan CSSF “Consolidating Democracy in Pakistan (CDIP)” Programme is to contribute to the British High Commission Pakistan’s Integrated Delivery Plan (IDP). These objectives aim to support Pakistan’s democratic institutions to be more inclusive and effective.

The programme is managed by DFID and the FCO at post. It exists within a broader framework of the UK’s cross-departmental programming, bilateral political engagement and interventions from other development partners and diplomatic missions. The CDIP programme has a budget of up to £31.5m and is implemented by the United Nations Development Programme and Development Alternatives International (DAI).

Key results for FY 18/19:

Elections:
The programme’s main achievements this past year have centred on the 2018 General Election. Strategic support has been provided to an increasingly effective Election Commission Pakistan (ECP). Civic and voter education outreach was also crucial, though the impact is yet to be measured. Key results include:
- Approximately 200 mid & senior level ECP officials trained in BRIDGE ‘Electoral Management’ Course including, various modules, e.g. on delimitation enabling the ECP to conduct a credible, smooth and robust delimitation exercise by ECP
- Approximately 850,000 elections officials trained.
- Election Observation Database developed of approximately 37,000 observers (international and domestic) participating in the General Election 2018 developed.
- 85,000 polling stations across Pakistan mapped using Geographic Information System (GIS) to finalise the polling scheme for elections.
  - Software for monitoring and evaluation of training developed, including a database of trained officials for duty in future by-elections and elections.
- Because of our support to ECP’s Gender Strategy:
  - 405,000 women facilitated to register to vote; the National Database & Registration Authority (NADRA) and ECP confirm that an additional 1.4 million women have obtained computerised national identity cards (CNICs) since October 2017 (required for voter registration)
  - ECP’s main logo for the election campaign period is a woman’s hand casting a vote. The ECP has also produced voter education material that is inclusive and contains graphics of women, persons with disabilities and other marginalised groups.
  - Supported ECP’s dialogue with political parties and their role in encouraging women’s voter registration and turn out
- Supported ECP’s efforts to encourage and facilitate the participation of Persons with Disabilities (PWDs) including awareness videos on the new facility of a postal ballot.
- Supported monthly meetings for the ECP’s Gender and Disability Electoral Working Group (GDEWG) in Islamabad and in the provinces – a coordination platform for civil society, donors and ECP

Parliament:
The post-election phase of implementation slowed considerably and, with a new Parliament, relationships and strategies needed to be reset.
- Establishing National Legislative Archive (NLA) for research and legislative scrutiny.
- Punjab Assembly - Supporting the development of its Strategic Plan and Communications and Outreach Strategy
- Orientation session of 150 incoming members of KP and Balochistan assemblies.
- Provided technical support to Women Parliamentary Caucus to improve the legislative effectiveness of women parliamentarians. Supporting an enabling environment for women parliamentarians so that they can better perform their legislative, oversight and representation roles. Briefed over 35 members of the National Assembly, senators and relevant parliamentary staff in undertaking the next generation of parliamentary reforms. Suggestions included introducing Prime Minister Question Hour and backbench member hours, and further empowering committees.

Political Parties:
Despite an election year, significant progress was made under this output including:
- Enhanced capacity of 166 mid- and senior-level officials/ candidates / campaign managers from 13 political parties, on relevant aspects of the Elections Act, 2017, for greater understanding and compliance with its obligations. As a result, nine political parties were better able to comply with the Elections Act, 2017.
- Enhanced understanding of 110 mid-senior political party officials on Pakistan’s international commitments through five briefing sessions on Sustainable Development Goals (SDGs).
- Conducted two research studies providing recommendations on improving gender and social inclusion in political parties; and setting up policy wings within party structures.
- Launched two innovative initiatives to enhance the meaningful participation of women and youth in political parties:
  - i) the Women in Politics Support Group – where women politicians from 10 political parties attended the inaugural meeting of the Women in Politics Support Group and unanimously adopted the charter, aims and objectives.; and,
  - ii) The Young Politicians Fellowship Programme was launched with the selection of the first cohort of 29 young political workers from 10 parties through a highly competitive process.

Democratic Space:
Despite having a relatively smaller resource allocation, this output delivered a range of tangible results:
- Radio messages developed on voting rights; how to cast a vote; issue-based voting; and leaving no one behind in 3 popular languages to air on 20 radio stations across Pakistan
- Election-related content developed for morning and late-night talk shows, including collaborating with various celebrities to communicate importance of voting.
2 million posters and brochures developed to encourage turn out and for use at polling stations
- Through [1]Agahi Centres, 434 persons trained to conduct voter education sessions targeting 64,500 women – especially for marginalised groups – women, persons with disabilities, transgenders, minorities – including mock polling stations
  [1] DFID Pakistan’s Voice and Accountability Programme.
- Supported 14,000 display centres nationwide to kick-off ECP’s voter registration campaign and finalise electoral rolls.
- Engaged approximately 30,000 people on civic and voter education, in communities and universities in Lasbela, Mansehra, Jamshoro/Hyderabad and Multan through UNDP/United Nations Youth Volunteers (UNVs)
- Elections Guide for 2018 General Election (with a website and app) published for easy to access elections related information.

Summary of recommendations for the next year

- Deepening democracy is a long-term process. The frame of any subsequent programming should be clearly defined as soon as possible, to enable this last year of implementation to contribute to feasibility studies, establishing baselines and even piloting in proposed priority areas with a key objective of doing less but at scale.
- Focus on the key outputs/interventions which are likely to gain traction/have an impact in the years ahead, for instance political parties, parliament and democratic space, and de-prioritise areas that carry a higher level of delivery risk.
- CDIP’s contribution to creating and promoting space for women and young politicians is highly valued and should continue to expand its support to other traditionally marginalised groups. The programme should consider addressing exclusionary politics more broadly, by also focussing on the under-representation of lower and middle classes within political parties. In the final year of the programme, the focus should be on inclusion through structures, and performance through standing committees and responsiveness through the interaction of parliamentarians with their constituents.
- Both UNDP and DAI should continue to support ECP. However, this requires improved coherence between the two delivery partners, with shared responsibility for delivery and lessons learned. This would benefit the programme in terms of economies of scale and help to close the gaps in results between the provinces.
- The programme’s ongoing political economy analysis was a useful tool in helping the programme prioritise and achieve delivery goals. This tool should be further refined to address upcoming challenges with support to local government elections.
- Update the log-frame.