Programme Completion Review - Summary Sheet

PROGRAMME TITLE: Professionalise the Bangladeshi Armed Forces
Country and Region:	Bangladesh, South Asia
IATI Unique ID:	CSSF-09-000004
HMG Partners / (LEAD in bold)	Ministry of Defence
Total Budget:	ODA: £0			Non-ODA: £1.01m
Total Spend:	ODA: £0			Non-ODA: £0.26m
Original Programme Start Date: April 2015		End Date: March 2019
Outputs					Score
Bangladeshi Armed Forces completing UK-based courses					A
Bangladeshi Armed Forces completing in-country UK run courses					A
Bangladeshi Armed Forces value relationship with UK Defence					A+
Overall output score					A
Outcome Assessment: Officers continue to be trained and understand professional values and the military’s place in the democratic system. Officers who have been trained have not supported any attempts to undermine or overthrow the democratically elected government. The UK continues to maintain a high level of access and insight within the Bangladesh system.
Final Outcome Score: A			Risk: LOW/MED

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19
Programme Score	A	A	A	A
Risk Rating - low/medium/high	LOW - MED	LOW - MED	LOW - MED	LOW - MED
*output/outcome scores

What support did the UK provide?

The UK provides professional education, mentoring and advice to all three branches of the Bangladesh Armed Forces, to assist with their development programme and to highlight governance, transparency and oversight of relevant activities. Historically the Armed Forces have intervened in domestic politics on a number of occasions and the UK is keen to ensure the new generation of Senior Officers are better informed of the usual role in a democracy.

Alongside this education the UK assists with the development of professional competencies in niche areas where we have expertise (Economic Exclusion Zone management as an example) as well as focusing on the Integration of Military and Civilian capabilities in Humanitarian Assistance to Disaster Response (HADR). By resourcing coordination exercises and seminars, the UK enhances domestic and regional HADR capability, reducing the reliance on the wider international community. The Bangladeshi military employs both men and women across all ranks with the exception of the combat arms.

What results did the programme deliver? Will they be sustained?:
- The programme continues to deliver courses both in Bangladesh and in the UK. These are for senior military officers across all services and continue to increase how influential the UK is in relation to Bangladeshi military strategy and policy.
- These courses continue to provide valuable insight and influence from the UK to Bangladesh and the UK continues to be highly regarded in respect of the courses it has delivered and continues to deliver.

What lessons have been learned?
The defence section continues to take account of feedback from course attendees and as a result tailors what is being delivered to meet the course objectives and be useful/relevant to the students taking part.