Annual Review - Summary Sheet

PROGRAMME TITLE: Sri Lanka CSSF: Delivering increased stability and reducing the risk of a return to conflict
Country and Region:	Sri Lanka
IATI Unique ID:	CSSF-09-000003
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO) and Ministry of Defence (MoD)
Total Budget :	ODA: £17.4m			Non-ODA: £1.2m
Budget this FY	ODA: £3.3m			Non-ODA: £0.185m
Spend this FY	ODA: £3.3m			Non-ODA: £0.162m
Start Date: April 2016		End Date: March 2022
Outputs					Score
Police Reform: strategic and technical assistance					A
Defence Engagement: non-kinetic training and engagement on defence reform					A
Anti-bribery and Corruption: Investigation, prosecution and witness protection training					A
Demining: clearance of 700,000 sq. m of unsafe land					A
Interfaith relations: Training for District Inter Religious Committees (DIRCs) in conflict mediation and reconciliation					A
Reconciliation and Transitional Justice					A
Overall output score					A
Outcome Assessment: Progress was made towards outcomes and good results achieved but changes in the external context limited full achievement of the milestones set.
Outcome Score: B			Risk: Medium

Summary of Programme Performance
Year	2016/17	2017/18*		2018/19
Programme Score	A	A	B	A	B
Risk Rating - low/medium/high	M	M		M
*output/outcome scores
How has the programme changed during this period?: The programme has become more streamlined and focused over the three year period, acting on annual review recommendations and adapting to a changing context.

What support did the UK provide in FY 18/19?

The CSSF programme in Sri Lanka in FY 18/19 was designed to support reconciliation and to strengthen democracy and the rule of law, to ensure long-term stability through targeted project activity in six key areas:

- Peacebuilding: supporting the government’s commitment to establishing credible and effective transitional justice mechanisms as part of Sri Lanka’s reconciliation process and sustainable resettlement of Internally Displaced Persons (IDPs);
- De-mining: clearing high density mine contaminated land and delivering mine risk education in the North and East, enabling the resettlement of IDPs;
- Inter-faith dispute mediation: support to community-level mediation of ethno-religious tensions in the Eastern Province;
- Policing: support to police reform and training based on a community policing approach that is gender sensitive and respects human rights;
- Defence: strengthening the defence relationship through targeted non-kinetic training and high level dialogue which will support security sector reform and foster greater awareness of the importance of accountability and reconciliation, and;
- Anti-corruption: sharing UK expertise to strengthen government capability to tackle bribery and corruption.

The majority of this work was ODA eligible under the Organisation for Economic Co-operation and Development (OECD) Development Assistance Committee's revised directive on peace and security.

Key results for FY 18/19:
- Cleared 533,922 square kilometres of high-density minefield, and provided mine risk education to approximately 40,000 people, contributing towards the Government of Sri Lanka’s (GoSL) ambition to be the next mine impact free country, and enabling the return of IDPs.
- 1,984 IDPs resettled on newly released land in the North and East provided with immediate resettlement support, better livelihood opportunities and improved living conditions.
- Targeted anti-bribery and corruption capacity building with civil society and the judiciary, including support to build civic awareness, in witness protection, case management, legislative reform and asset forfeiture.
- Technical support provided on security sector reform including the development of the Police Reform Action Plan and also to strengthen community policing and police response to gender and human rights.

Summary of progress and lessons learnt/actions taken since last review

The Sri Lanka CSSF programme continues to deliver across UK conflict and security objectives in Sri Lanka and is a core component of the UK Government’s integrated policy delivery. The activities in 2018/19 were designed to align with the wider international approach to supporting the GoSL’s reconciliation and stability agenda.

The programme is well managed and demonstrates a continuous ability to learn and adapt. During the reporting period, there were numerous changes in the political context and conflict dynamics. The programme continued to achieve impressive results at project level, including successfully absorbing additional funds in the second quarter of the year for resettlement and demining projects. The team have used the flexible nature of the CSSF to help partners respond to contextual challenges in a quick and appropriate way.

The programme has acted upon the recommendations of the previous annual review by, for example, better focusing anti-corruption work, increasing demining activity to assist the GoSL in its target of being the next mine impact free country globally. The results framework has also been revised whilst remaining true to the programme’s existing, ambitious goals.

Progress towards outcomes has been more difficult due to shifts in context, including a constitutional crisis in 2018, the terrorist attacks on Easter Sunday in 2019.

In a political and security context which continues to shift and evolve, the programme will need to remain agile and continue to adapt. Strategic thinking, analysis, and engagement with the new government will be critical, alongside project delivery. This work has already started, providing a strong foundation for the CSSF to continue to be an effective tool in preventing a return to conflict.

Summary of recommendations for the next year

Ensure that conflict analysis is up to date, identify and fill other gaps in analysis. Draw upon global good practice, particularly in policing and anti-corruption, when designing new activities.

Invest time in strategic thinking and discussion to be clear on what the programme can achieve after 2019 Presidential elections and following 2020 parliamentary elections. Revise the theory of change once the priorities of the new government become clear.

Supplement the programme board with strategic meetings to review and adapt programme activity in light of a changing context and ensure linkages between CSSF and other activity.

Formalise and document existing cooperation between the FCO and MoD to ensure better measurement of how defence engagement complements and supports CSSF and High Commission objectives,

Use personnel changes as an opportunity to lightly review the staffing model for CSSF oversight and ensure that it still works for the High Commission.

Strengthen the results framework so that outcome indicators, whilst still ambitious, are more realistic and adapt it more quickly if the context changes.