Annual Review - Summary Sheet

PROGRAMME TITLE: Algeria CSSF Programme
Country and Region:	Algeria, Middle East and North Africa
IATI Unique ID:	CSSF-06-000001
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Department for International Development (DFID, Home Office (HO), Ministry of Defence (MoD)
Total Budget:	ODA: £13.2m			Non-ODA: £0
Budget this FY	ODA: £6.4m			Non-ODA: £0
Spend this FY	ODA: £6.5m			Non-ODA: £0
Original Programme Start Date: April 2017			Planned End Date: March 2019
Outputs					Score
Increased support for political access and influencing by the UK Government (including with and through implementing partners).					A
Young Algerian women and men in target groups are supported to increase their capacity to access employment opportunities.					A
Political actors and media are trained to increase outreach to citizens and inclusiveness.					A
Increased capability of rule of law agencies, Prison Directorate, Parliament and the newly established Algerian Child Protection Commission in complying with international human rights standards and commitments.					A+
Overall output score					A
Outcome Assessment: A
Outcome Score: B		Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	N/A	B	A	B	A	B
Risk Rating - low/medium/high	N/A	Medium	Medium		Medium
*output/outcome scores
How has the programme changed during this period? Not significantly over period covered by the review. This was shortly before presidential elections were postponed in May and July 2019.

What support did the UK provide in FY 18/19?

The £6.5m Algeria CSSF programme sought to support the Government of Algeria (GoA) and the Algerian people through 11 projects focused on: economic reform and youth access to employment; political participation and inclusivity; and good governance and human rights.

The Algeria programme decided early in its development that it should focus on two strands: economic and political stability. This decision was supported by the Joint Analysis of Conflict and Stability (JACS) carried out in 2018. The programme used the Technical Assistance Fund (TAF) to prepare economic reports which reinforce the decision on focus areas and provide baseline information for the programme.

Key results for FY 18/19:
Mainstreamed new teaching methods in the national education sector and improved the performance of Algerian pupils in pilot schools supported by the British Council.
Trained over 6,000 young Algerians on job search techniques, employability and entrepreneurship skills.
Supported the creation of the Human Rights Department within the national police.
Achieved significant progress in relaunching the UK-Algeria All-Party Parliamentary Group (APPG) as a means to strengthen bilateral relations and the parliamentary process in Algeria.
Supported the six main political parties to improve citizen outreach and better reflect citizens’ needs.
Provided support to media services in creating and producing targeted, public service-oriented content.
Improved understanding of the evidence base of labour markets in the southern regions of Algeria.
Strengthened donor coordination, reducing risk of duplication and improving focus.
Strengthened UK Government access and influence with both donors (e.g. the UK chairs the new Youth Economic Empowerment Coordination Working Group) and Algerian stakeholders (e.g. improved access for the Consular team).

Summary of progress and lessons learnt/actions taken since last review

The Annual Review of 17/18 produced a number of recommendations which were considered and taken forward appropriately.

The programme started well in 2018/19 as the team worked hard to ensure a number of the contracts were in place before the financial year began for the first time ever. This resulted in implementers being able to start activities in April rather than waiting until Q2 or Q3. The spend throughout the year was very regular, with excellent forecasting and financial management, resulting in a 101% spend.

There was significant effort by the team to strengthen Monitoring and Evaluation (M&E). The programme team was supported by the North Africa Monitoring and Evaluation and Learning (NAMEL) team. Theories of Change were refreshed, and Results Frameworks sharpened. Case studies on the progress of some projects helped inform decisions on which projects to continue.

Summary of recommendations for the next year

The programme needs to adapt to the changing political context and personnel. The team should ensure they have the flexibility to turn things off, ramp things up and be able to scope new work, test previous assumptions of which partners they can work with. Key decision points for proceeding with activities will help manage this change. At the time of the annual review, the focus on economic rather than political objectives look right, but this should be kept under close review.

Ensure outcomes and outputs are sufficiently ambitious. Test assumptions in the Theory of Change. Work with partners on more use of qualitative indicators. Ensure outcomes focus on the specific change we want to see, rather than providing support. Embed M&E in projects from the start - this is already starting to happen, and the team should work with NAMEL to build on this.

Strengthen conflict sensitivity, developing programme team and implementer understanding of what this means in Algeria and build on work to mainstream gender into all activity. Decide when to refresh the JACS.

Further deepen integration with the other sections of the Embassy, to ensure a strong UK understanding of a complex context and informed decision-making on programming, with interventions particularly at this time of political flux, targeting the right beneficiaries.

Consider how to communicate impact of the programme (especially on political access and influencing) to non-programme audiences in a straightforward way. Work with NAMEL should support this.

Explore whether implementers could do more together to coordinate and maximise effectiveness within and across strands of work to have more impact and identify opportunities for maximum impact.

Build on and continue existing donor engagement, sharing analysis. Project managers to maintain awareness of other donor activity in their sectors. Explore if regional efficiencies can be achieved in programming across the region with other CSSF teams. Multilateral organisations such as IFIs are working across the region.