## Annual Review - Summary Sheet

PROGRAMME TITLE: Jordan CSSF: Defence and Borders Programme
Country and Region:	Jordan, Middle East and North Africa
IATI Unique ID:	CSSF-06-000019
HMG Partners / (LEAD in bold)	Ministry of Defence (MoD), Foreign and Commonwealth Office (FCO)
Total Budget:	ODA: £0		Non-ODA: £8m
Budget this FY	ODA: £0		Non-ODA: £2.6m
Spend this FY	ODA: £0		Non-ODA: £2.4m
Original Programme Start Date: April 2016		Planned End Date: March 2019

Outputs		Score
Quick Reaction Force (QRF) has the appropriate infrastructure, equipment and training (for men and women in QRF) to support 3 Battalions and a Brigade HQ		B
QRF is organised to support effective operations		A
The Jordanian Armed Forces (JAF) Border Guard Force (BGF) is better able to monitor, identify and report external threats to protect the Jordan-Syria border.		B
JAF has modernised training facilities (ranges) in the four commands		C
Increased number of JAF Officers complete UK Defence Education courses		C
Overall output score: C		C
Outcome Assessment: C
Outcome Score: C	Risk: Medium

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19
Programme Score	A/B	A	A	B	C	C
Risk Rating	Medium	Medium	Medium		Medium

*output/outcome scores

What support is the UK providing?

The Jordan Defence and Borders Programme (JDBP) is a non-ODA programme comprising five projects aimed at enabling the Jordanian Armed Forces (JAF) to become more effective and better able to protect the country from internal and external threats. One project was closed in July 2018 leaving four extant at the time of the Annual Review (AR). The projects entail the provision of equipment and infrastructure, funded through the CSSF, together with training, the majority of which is provided through MoD core funding.

Summary of progress and lessons learnt/actions taken since last review

The top headline from the previous AR was the programme was well regarded by Jordanian counterparts and was playing a very useful role in strengthening the UK’s reputation as an ally and valued partner. Although the programme was facing some unresolved procurement challenges, the overall message in May 2018 was positive. Disappointingly, the impact of the JDBP during FY 18/19 has been adversely affected by a significant inability to deliver activity due to the delays arising from introducing standard MoD infrastructure and equipment procurement procedures. As a result, the final allocation was reduced to an amount lower than the initial allocation. Training and mentoring interventions have been largely both on schedule and successful except when impacted adversely by procurement delays.

No military equipment procurements were progressed, and no new infrastructure projects were started: these two aspects of the programme effectively stalled. The reputational impact was, to some extent, mitigated by the reallocation of equipment which had been originally earmarked for CSSF activity in Syria, but was no longer required.

Whilst the MoD identified the need to use standard procurement procedures, internal systems and processes within MoD proved not well suited to conducting small-scale, local procurements on behalf of another nation. The MoD commercial delivery organisations responsible for procuring infrastructure (Defence Infrastructure Organisation (DIO)) and equipment (Defence Equipment and Support) are more typically tasked with delivering much larger value core MoD programmes entailing complex processes with relatively long lead times. More permanent and sustaining solutions are being sought to overcome these issues to support and meet procurement requirements for MoD-led CSSF projects in future years.

It is encouraging that the CSSF Programme Team and Defence Section at Post have taken steps to re-prioritise work in an effort to maintain the relationship with JAF counterparts. This has included getting special delegated authority to finish infrastructure contracts where these were already advanced and bringing in an independent engineer to ensure that the statement of requirements was technically correct. Without exception, all UK stakeholders interviewed were of the view that the relationship with the JAF can be maintained once a viable and enduring procurement process for infrastructure, equipment and (commercial) training is in place. It is also of note that the Defence Senior Advisor Middle East (DSAME), in his most recent report, also formed this judgement.

There remains a strong case for continuing to draw on CSSF resource to contribute to the UK Government’s efforts in supporting the stability of Jordan. The rationale for continuing investment comprises a number of reasons: the fact that the DBP has been well received in the past by the Government of Jordan and JAF Command; that it has met JAF needs; that Jordan needs ongoing support due to regional instability. It is however recommended that the results framework is updated to take account of the delivery challenges and that expectations are also revised appropriately. Overall however the AR team concluded that the programme has potential to contribute to HMG goals providing an appropriate delivery solution is found as matter of urgency.

Summary of recommendations for the next year

Every effort must be expended to swiftly produce both interim and enduring solutions to MoD procurement issues that will allow the relationship with the JAF to be rebuilt and strengthened.

The results framework (RF) should be revised to reflect the current level of Embassy ambition aligned with what can be achieved. The RF should focus on the contribution of CSSF activity and not cover DE work that is MoD funded.

The establishment of a MoD Portfolio Management Office in London is essential to enable MoD to deliver CSSF programmes in a technically and commercially compliant manner; in Jordan and other regions where there are MoD equipment and/or infrastructure CSSF aspirations. This office should serve as a MoD tasking authority to direct Front Line Commands and their associated DE&S procurement chains to fulfil CSSF procurements, assisting programme managers to navigate MoD processes in a timely and effective manner.

There are a number of useful lessons that can be drawn from the DBP thus far. These should be collated, and a lesson log created both for the benefit of the country team but for the Joint Finds Unit as well.

A record of assets (including disposal or transfer) should be maintained for the course of the programme.

MoD planning timelines for both equipment and infrastructure delivery projects are available to MoD programme staff. These must be communicated clearly and immediately to CSSF programme staff to enable accurate forecasting during the FY 19/20. If the MoD cannot deliver within this year, then funds should be returned to the central CSSF at the earliest opportunity for reallocation.

Recognising the DIO’s systematic approach to infrastructure projects, the programme should produce a prioritised Infrastructure Development Programme in conjunction with the nominated Principal Support Provider (PSP), once appointed. This will give DIO better visibility of the programme’s aspirations, allowing appropriate technical and commercial support to be allocated where possible.

As it is highly likely that delivery will again be limited in 19/20, early discussion should take place about how the return of funds will be planned / organised.