Annual Review - Summary Sheet

PROGRAMME TITLE: Jordan CSSF: Internal Security Programme (ISP)
Country and Region:	Jordan, Middle East and North Africa
IATI Unique ID:	CSSF-06-000018
HMG Partners / (LEAD in bold)	Foreign and Commonwealth Office (FCO), Home Office (HO)
Total Budget:	ODA: £16.2m			Non-ODA: £0.8m
Budget this FY	ODA: £8.2m			Non-ODA: £0.8m
Spend this FY	ODA: £8.1m			Non-ODA: £0.8m
Original Programme Start Date: April 2016		Planned End Date: March 2020
Outputs					Score
Public Security Directorate staff (PSD) trained in, and provided with, relevant skills/tools for use in counter terrorism (CT) and other investigations					A
Multi-agency command training for critical incident management delivered					B
Gendarmerie specialist units trained to respond to critical incidents					A
Gendarmerie and PSD specialist trained to deploy an intelligence-led approach					A
At risk youth within vulnerable communities equipped with tools to cope with stress, make better decisions, build constructive relationships and strengthen their local communities					A
Community Police specialists trained and equipped in pilot communities, and public access to stations increased					A
First response to major incidents and cooperation between local police, businesses, and the wider community improved					A
How change is enacted in Security Forces is better understood & their priorities (current & future) understood.					B
A recruits’ training curriculum with a greater emphasis on community policing approaches and positive interaction between police officers and the public is piloted with new entrants at the King Abdullah II Training City.					A
Overall output score					A
Outcome Assessment:
Outcome Score: B			Risk: Medium / High

Summary of Programme Performance
Year	2015/16	2016/17	2017/18*		2018/19*
Programme Score	A	B	B	B	B	A
Risk Rating - low/medium/high	Medium	Medium / High	Medium / High	Medium / High	Medium / High
*output/outcome scores
How has the programme changed during this period? In FY 18/19, the original security project entered its final year, a new Home Office project commenced, a youth, peace and security pilot project was completed and a new four year MOU signed with UN Women.

What support did the UK provide in FY 18/19?

The programme is designed to reduce the likelihood and impact of internal security incidents. It will do this by strengthening the capability of the civilian security services, boosting the resilience of young people to negative and anti-social influences, and improving gender equality through supporting implementation of the Government of Jordan’s (GoJ’s) National Action Plan on Women, Peace and Security.

In FY18/19, the programme built on the UK Government’s previous investment in the security field by contributing to the Jordan NSC Strategy (2017) objectives, especially the Security Pillar. It did this by helping Jordan’s capability to grow to enhance both the country’s own security and its ability to act as a key ally in tackling internal and regional threats in a manner compliant with human rights. The programme was delivered through activity in three projects and a new MoU:

- Jordan Security Sector Project (JSSP) - Supporting capacity building for the internal security sector.
- Police Professionalisation Project (P3) - A Home Office (HO) led project focused on broader reform issues in the police.
- Supporting Resilient Youth and Communities in Jordan Project (SRYJ) - A short term accountable grant pilot aimed at boosting the resilience of vulnerable youth to negative and anti-social influences.
- Supporting the Jordanian National Action Plan on Women, Peace and Security (JONAP MoU) - Over four years this project aims to support the GoJ through UN Women, as it integrates a gender-based approach to increasing female participation in conflict prevention and maintaining stability.

Key results for FY 18/19:

The Programme has made considerable progress throughout FY 18/19 across all its projects.

- Police Professionalism Project (P3): The PSD re-evaluated their training portfolio, resulting in curriculum amendments, financial and staff abstraction savings. A pilot project demonstrated to senior officers that public security could be provided in combination with greater engagement with citizens. As a result, the PSD decided to expand the new approach to Aqaba.
- JSSP: The PSD mainstreamed community policing approaches into recruit training, embedded an intelligence led approach in specialist Gendarmerie units responsible for the protection of critical infrastructure, and improved an Automatic Number Plate Recognition (ANPR) system for multi-agency use in support of Counter Terrorism (CT) investigations.

SRYJ: The pilot project worked with young men, women and parents in three priority communities (Russeifa, Salt and Ma’an). Achieved through mentoring, self-expression workshops and parental support. It provided an evidenced output and opportunities for further youth resilience activities. Targets for psychosocial wellbeing were exceeded through strong attendance and quality of activity. Training of mentors, coaches, and case managers together with a “tool kit” did provide some evidence of a sustainable approach.

JONAP: A launch conference for JONAP was delivered in February 2019 to demonstrate GoJ and donor commitments to the implementation of the National Action Plan; and provide an opportunity to share experiences from across the MENA region in drafting and implementing action plans that promote Women, Peace and Security. UN Women and the Jordanian National Commission for Women (JNCW) have created a number of MoUs with security related organisations, which will be signed in FY 19/20.

Summary of progress and lessons learnt/actions taken since last review

A sound action plan was put in place to address previous year’s recommendations resulting in:
- Improved programme Results Frameworks (RFs) following feedback to implementers to ensure respective project RFs were more measureable which clearly linked towards the programme RF.
- The team drawing on and benefitting from advice provided by a Home Office Strategic Policing Adviser (SPA); a Senior Police Adviser embedded in PSD HQ; and adhoc support from Stabilisation Unit’s Senior Rule of Law Adviser. P3 was able to draw on Home Office and serving police assets to inform the programme and respond quickly to PSD interest in new areas of activity.
- Relationship mapping enabling the programme and UK Counter Terrorism and Extremism Network (CTEN) to support each other’s cases for new projects. CTEN convened several meetings of Embassy interested parties to provide a clearer sense of relationship leads and with whom to engage. The programme team briefed colleagues, and held a number of discussions with other donors to share positions.
- An external Monitoring & Evaluation (M&E) adviser supporting the programme in mid-2018 to improve the programme level Theory of Change (ToC) and RF.
- An M&E specialist employed by JSSP and Ark-Siren to improve how trainings/outputs contribute to the overall impact of the project, leading to a reworked JSSP project level RF.
- Increased female participation in training opportunities, and gender needs considered throughout the programme. Ark-Siren were challenged to improve gender sensitivity of the JSSP, and P3 were briefed to look out for entry points in PSD interactions. While increased participation is important, it is not meaningful if male/female participants are not matched in terms of duties/ skills required/opportunities.

Summary of recommendations for the next year

The “Blended delivery approach” to programme management involving separate UK Government and private sector implementing partners needs to be carefully calibrated to ensure that all the ISP components are working as collaboratively as possible especially the HO, P3 and the new commercial supplier to the Police Reform and Capacity Building project (PRCB), once the latter is tendered in FY 19/20.
Review of the overall ISP strategy with consideration of how the projects P3, JONAP and JSSP’s replacement can be more complementary.
- The programme RF should be revised as should the P3 RF. Both should be expressed in language that can be understood by non-police readers. The targets as currently written are difficult to assess and thus the ISP may not get proper credit for the effort invested. Revisions should include baseline data, including VFM indicators where possible and for the P3 project, moving from narrative to quantitative indicators. JONAP should be included in the RF.
- The external policing evaluation (covering JSSP and P3) made a number of recommendations that the CSSF team will consider. The AR team endorses the recommendations to ensure that the new supplier has a theory of change that adequately reflects outcome level change; that M&E systems should be incorporated into the project from the outset; and for the CSSF team to continue exploring how the demand for policing development can be supported whether e.g. coming from the GoJ, the security agencies or from the public.
- Consideration to be given to adopting a lesson log so as to capture all the information currently known by the CSSF team as the programme has matured.
- The CSSF team should monitor how the HO manages the P3 project in 19/20 especially in relation to a) deploying /contracting personnel and b) future recruitment processes. .
- The next AR that covers FY 19/20 should have the opportunity of seeing beneficiaries directly to assess progress.
- The CSSF team should continue to draw on external expertise for institutional reform and other specialist advice.